## L2 Status
Sprint | R812
Row Labels | Count of Object
L2 Not required | 88
Grand Total | 88
we skip L2 for this sprint

## Status R812
Sprint | R812
Count of Object | Column Labels
Row Labels | Baxter Code Review Complete | Development Complete | L3 Pass | (blank) | L3 In Progress | Grand Total
ARO | 2 |  | 4 |  | 8 | 14
eCommerce |  | 8 |  |  |  | 8
Finance | 5 | 1 |  |  |  | 6
Logistics | 4 | 45 |  | 1 |  | 50
Order Management |  | 10 |  |  |  | 10
Grand Total | 11 | 64 | 4 | 1 | 8 | 88

## query
Object | GxP critical flag | Object Type | FS Doc Nbr | TS Doc Nbr | Sprint | Testing Sprint | Phase | Description | Status | L3 Defect Number | L3 Defect Status | Deployed to UT | Critical for go-live (L, M, H) | Deployed to PPD | Functional Area | Main Function | Baxter Functional Owner Name | L2 Status | L2 testing KPIT testing comments | App Created By | App Modified By | Baxter Tech Lead Name | Code Review Comments | Code Reviewer | Compliance Asset Id | Content Type | Country | Created | Created By | Estimated Dev End Date | Estimated Dev Start Date | FSTS Name/ Number | ID | Interface Type | Item Child Count | KPIT Technical Lead | Label applied by | Label setting | Modified | Modified By | OMW Project | Purpose | Ready for Baxter Tech Review | Ready for EUUT promotion | Retention label | Retention label Applied | Retrofit Comments | Sprint Track | Test Script ID 9.2 | Test Script Name | Version Projects | Global | Global needed in PRODUCTION | Number | Item Type | Path
R55FRGL40 | No | UBE | BXU545344 (6133) | BXU545485 (6133) | 1 |  | CRP | UK VAT Partial Exemption report | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/7/2019 | 6/7/2019 |  | 1 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-09 05:57 | Singh, Sunil Kumar | 56-F-EU-V-190527-S1FI056 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190527-S1FIV056A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56COD01 | No | UBE | BXU546845 (6772) | BXU545487 (6772) | 3 |  | CRP | Concur - Upload full account details file | L3 Pass | 218 | Ready for Testing | TRUE | HNE2E |  | Finance AP | Finance | Eileen Paula | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/1/2019 | 7/1/2019 |  | 2 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-09 05:56 | Singh, Sunil Kumar | 56-F-EU-V-190628-S3FI040 | Upload | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56CTASQL | No | UBE | BXU549987 | BXU547391 | 5 |  | CRP | UBE to Replace Month End SQL | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/12/2019 | 8/12/2019 |  | 3 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-09 06:00 | Singh, Sunil Kumar | 56-F-EU-V-190812-S5FI003 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56R9006 | No | APPL | BXU547244 | BXU547038 | 6 |  |  | Maintain Russian Correspondence Offset Accounts | L3 Not Required |  |  | TRUE | LNE2E |  | Localization | Finance | Keith Haxton | L2 Not required | No KT, test in E2E |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 9/13/2019 | 9/13/2019 |  | 4 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-09 06:01 | Singh, Sunil Kumar | 56-F-EU-V-190829-S6FI094 | Maintenance | Yes |  |  |  |  | No KT |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5674003 | No | UBE | BXU545315 (4712) | BXU545468 (4712) | 3 |  | CRP | Update SEPA Bank Account Setup F740001 | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT , CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/1/2019 | 6/30/2019 |  | 5 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-09 06:06 | Singh, Sunil Kumar | 56- F-EU-V-190701-S3FI060 | Setup | Yes | Y | [6 empty] | 56- F-EU-V-190701-S3FIV60A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641040 | No | UBE | BXU545319 | BXU545515 | 3 |  | CRP | Item Cost Integrity Report | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/1/2019 | 6/28/2019 |  | 6 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-09 06:07 | Singh, Sunil Kumar | 56-F-EU-V-190701-S3FI073 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3FIV73A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56COD04 | No | UBE | BXU546845 (6772) | BXU545487 (6772) | 3 |  | CRP | Concur Lite - send details to countries not on full Concur | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Eileen Paula | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/1/2019 | 6/30/2019 |  | 7 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-09 06:08 | Singh, Sunil Kumar | 56-F-EU-V-190701-S3FI052 |  | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3FIV052A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P74LI408 | No | APPL | 1266483 (6924) | BXU545374 (6924) | 3 |  |  | Tax Rate/Area Additional Information - POR - 74L - IORGA | L3 Not Required |  |  | FALSE | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/8/2019 | 7/5/2019 |  | 8 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-09 06:19 | Singh, Sunil Kumar | 56- F-EU-V-190702-S3FI086 |  | Yes |  |  |  | Retrofit not required | No KT |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5674LI01A | No | UBE | 1266483 (6924) | BXU545374 (6924) | 1 |  |  | Date Range for Finance SAFT generation | L3 Not Required |  |  | TRUE | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/7/2019 | 6/7/2019 |  | 9 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-09 06:42 | Singh, Sunil Kumar | 56-F-EU-V-190530-S1FI185 |  | Yes | Y |  |  |  | No KT |  |  | 56-F-EU-V-190530-S1FIV185A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74LI01A | No | UBE | 1266483 (6924) | BXU545374 (6924) | 3 |  |  | Get SAF-T Data Header | L3 Not Required |  |  | FALSE | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/12/2019 | 7/11/2019 |  | 10 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-09 06:44 | Singh, Sunil Kumar | NA |  | Yes |  |  |  |  | No KT |  |  | 56-F-EU-V-190712-BV1063A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74LI01G1 | No | UBE | 1266483 (6924) | BXU545374 (6924) | 3 |  |  | Get SAF-T Data - General Ledger Entries | L3 Not Required |  |  | FALSE | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/8/2019 | 7/8/2019 |  | 11 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-09 06:44 | Singh, Sunil Kumar | 56-F-EU-V-190701-S3FI003 |  | Yes |  |  |  |  | No KT |  |  | 56-F-EU-V-190701-S3FIV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56EUV00 | No | APPL | BXU547481 (10806) | BXU545535 (10806) | 1 |  | CRP | Maintain VAT - Tax code mapping Table (F56EUV00) | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/6/2019 | 6/5/2019 |  | 12 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-09 06:47 | Singh, Sunil Kumar | 56-F-EU-V-190523-S1FI050 | Maintenance | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P560411R | No | APPL | BXU545337 (10328) | BXU545516 (10328) | 5 |  | CRP | Suspected Duplicate Payments Review | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/12/2019 | 8/12/2019 |  | 13 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-09 06:48 | Singh, Sunil Kumar | 56-F-EU-V-190812-S5FI014 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV014A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56EUV01 | No | APPL | BXU546529 |  | 1 |  | CRP | Maintain VAT Drive shipping or Interbranch Cycle (Table 4) | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/6/2019 | 6/6/2019 |  | 14 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 23:42 | Joshi, Abhishek N | 56-F-EU-V-190522-S1FI045 | Maintenance | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56EUV02 | No | APPL | BXU546529 |  | 1 |  | CRP | Maintain VAT Exception Table (Table 1) | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/6/2019 | 6/6/2019 |  | 15 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 23:44 | Joshi, Abhishek N | 56-F-EU-V-190527-S1FI059 | Maintenance | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56EUV03 | No | APPL | BXU546529 |  | 1 |  | CRP | Maintain VAT Table of Related Documents (Table 3) | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete | Check use of UDC 56/VN used by this application. |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/6/2019 | 6/6/2019 |  | 16 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 23:47 | Joshi, Abhishek N | 56-F-EU-V-190513-S1FI003 | Maintenance | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56EUV04 | No | APPL | BXU546529 |  | 1 |  | CRP | Maintain VAT Intercompany General Rule (Table 2) | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/6/2019 | 6/6/2019 |  | 17 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 23:49 | Joshi, Abhishek N | 56-F-EU-V-190603-S1FI023 | Maintenance | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56EUV00 | No | UBE | BXU546529 |  | 1 |  | CRP | AR VAT Preprocesser | L3 Pass |  |  | TRUE | HE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/7/2019 | 6/7/2019 |  | 18 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 08:26 | Joshi, Abhishek N | 56-F-EU-V-190530-S1FI181 |  | Yes | Y | [6 empty] | 56-F-EU-V-190530-S1FIV181A , 56-F-EU-V-190530-S1FIV181B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56EUV05 | No | APPL | BXU547481 |  | 1 |  | CRP | Maintain VAT - Exception Table A/P (Table 5) | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/6/2019 | 6/6/2019 |  | 19 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 23:51 | Joshi, Abhishek N | 56-F-EU-V-190603-S1FI196 | Maintenance | Yes | Y | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56EUV06 | No | APPL |  |  | 1 |  | CRP | Maintain VAT Vendor by Line of Business (Table 6) | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/6/2019 | 6/6/2019 |  | 20 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-09 02:33 | Rasselet, Cedric | 56-F-EU-V-190530-S1FI186 | Maintenance | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56ECACM | No | APPL | BXU545607 |  | 5 |  | CRP | ECEMEA GL Account Mapping Maintenance | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/12/2019 | 8/9/2019 |  | 21 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 04:17 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI010 | Maintenance | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560911TB | No | UBE | BXU545607 (10883) | BXU545638 (10883) | 5 |  | CRP | Trial balance with source a/c F0911 | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/12/2019 | 8/9/2019 |  | 22 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-09 06:50 | Singh, Sunil Kumar | 56-F-EU-V-190812-S5FI031 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV031A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56AR100 | No | UBE | BXU545317 |  | 3 |  | CRP | AR by Division - BLACKHAWK | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 1/7/2019 | 1/7/2019 |  | 23 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 03:47 | Joshi, Abhishek N | 56-F-EU-V-190628-S3FI041 |  | Yes | Y | [6 empty] | 56-F-EU-V-190628-S3FIV041A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56ECGL2 | No | UBE | BXU545607 |  | 5 |  | CRP | Z file fill in ECEMEA A/c balances from F0902TMP to F0911Z1 | L3 Pass | 270 | Closed | TRUE | HNE2E |  | Finance GL | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/12/2019 | 8/09/2019 |  | 24 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 08:20 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI007 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV007A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56CIPR1 | No | UBE | BXU545324 |  | 3 |  | CRP | Create Commisionnaire Invoices in Principal Books | L3 Pass |  |  | TRUE | HE2E |  | Finance GL | Finance | Lokesh Reddy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/28/2019 | 6/27/2019 |  | 25 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 08:16 | Joshi, Abhishek N | 56-F-EU-V-190701-S3FI063 |  | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3FIV63A,56-F-EU-V-190701-S3FIV63B,56-F-EU-V-190701-S3FIV63C,56-F-EU-V-190701-S3FIV63D,56-F-EU-V-190701-S3FIV63E,56-F-EU-V-190701-S3FIV63F | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600007 | No | UBE | BXU545348 |  | 5 |  | CRP | Create Deemed Move Bookings and Documents | L3 Pass | 217 | WIP | TRUE | HE2E |  | Finance GL | Finance | Lokesh Reddy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 06/28/2019 | 06/27/2019 |  | 26 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 03:41 | Joshi, Abhishek N | 56-F-EU-V-190624-S3FI005 |  | Yes | Y | [6 empty] | 56-F-EU-V-190624-S3FIV005A,56-F-EU-V-190624-S3FIV005B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5503B01E | No | UBE | BXU545341 |  | 3 |  | CRP | Italian Monthly details | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/1/2019 | 7/1/2019 |  | 27 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 06:06 | Joshi, Abhishek N | 56-F-EU-V-190701-S3FI007 |  | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3FIV007A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5603B01 | No | APPL | BXU545336 |  | 3 |  | CRP | Work with Cash Sweep Inquiry | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/3/2019 | 6/27/2019 |  | 28 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 23:18 | Joshi, Abhishek N | 56-F-EU-V-190702-S3FI090 | Inquiry | Yes | Y | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5600001 | No | APPL | BXU545608 |  | 1 |  | CRP | Maintenance Application for VAT Document Next Number | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/6/2019 | 6/4/2019 |  | 29 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 09:26 | Joshi, Abhishek N | 56-F-EU-V-190531-S1FI071 | Maintenance | Yes | Y | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5600002 | No | APPL | BXU545608 |  | 1 |  | CRP | Maintenance Application for VAT Document Number Cross Ref. | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/4/2019 | 6/4/2019 |  | 30 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 09:34 | Joshi, Abhishek N | 56-F-EU-V-190603-S1FI193 | Cross Ref / Maintenance | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P03B202 | No | APPL | BXU547654 |  | 4 |  | CRP | Work With Statements | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete | 7/8/2019-PD: L2 pass as per the discussion and Mail from Abdul |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/24/2019 | 07/22/2019 |  | 31 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 08:50 | Joshi, Abhishek N | 56-F-EU-V-190722-S4FI001 |  | Yes | Y | [6 empty] | 56-F-EU-V-190722-S4FIV01A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P12115 | No | APPL | BXU547419 |  | 2 |  | CRP | Location Transfer | L3 Pass |  |  | TRUE | HNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/20/2019 | 6/19/2019 |  | 32 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 02:54 | Joshi, Abhishek N | 56-F-EU-V-190611-S2FI032 |  | Yes | Y | [6 empty] | 56-F-EU-V-190611-S2FIV32A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R03B551 | No | UBE | BXU548273 |  | 2 |  | CRP | Update Receipts Header | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/18/2019 | 6/17/2019 |  | 33 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-05 06:19 | Joshi, Abhishek N | 56-F-EU-V-190617-S2FI045 |  | Yes | Y |  |  | Retrofitted |  |  |  | 56-F-EU-V-190617-S2FIV45A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P590909 | No | APPL | BXU545339 |  | 3 |  | CRP | Work With Special Exchange Rate Mapping | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 06/28/2019 | 06/27/2019 |  | 34 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 05:11 | Joshi, Abhishek N | 56-F-EU-V-190625-S3FI022 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R11414A | no | UBE | BXU547045 |  | 5 |  |  | Currency Restatement Compute and Print | L3 Pass | 174 | Closed | TRUE | HNE2E |  | Finance GL | Finance | Joanne Byrne | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | JB 19/07:&nbsp; Retest ongoing with prior year F0902 data copied in VV-29/07 moved to Sprint 4 as per request from Joanne | Bargavi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/19/2019 | 6/17/2019 |  | 35 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-05 06:22 | Joshi, Abhishek N | 56-F-EU-V-190617-S2FI048 | Printer | Yes | Y |  |  | Retrofitted. Passed in R3 |  |  |  | 56-F-EU-V-190617-S2FIV48A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56EUV10 | No | UBE | BXU545330 |  | 3 |  | CRP | Deemed Moves/Invoices VAT posting to F0018 | L3 Pass |  |  | TRUE | HE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/28/2019 | 6/27/2019 |  | 36 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 08:30 | Joshi, Abhishek N | 56-F-EU-V-190628-S3FI036 |  | Yes | Y | [6 empty] | 56-F-EU-V-190628-S3FIV36A, 56-F-EU-V-190628-S3FIV36B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56CIPI1 | No | UBE |  |  | 3 |  | CRP | Intercompany AP Voucher Creation (CIPI) | L3 Pass |  |  | TRUE | HE2E |  | Finance AP | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/28/2019 | 6/27/2019 |  | 37 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-28 13:33 | Haxton, Keith | 56-F-EU-V-190701-S3FI066 |  | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3FIV66A,56-F-EU-V-190701-S3FIV66B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56404H | No | APPL | BXU545609 |  | 1 |  | CRP | Toscanini Interface Header File Inquiry | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/4/2019 | 6/3/2019 |  | 38 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 23:29 | Joshi, Abhishek N | 56-F-EU-V-190531-S1FI069 | Inquiry / Interface | Yes | Y | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5839120 | No | UBE | BXU545360 |  | 4 |  | CRP | Period Build - Russia | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/22/2019 | 7/22/2019 |  | 39 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 08:44 | Joshi, Abhishek N | 56-F-EU-V-190722-S4FI005 |  | Yes | Y | [6 empty] | 56-F-EU-V-190722-S4FIV005A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600046 | No | UBE | BXU545612 |  | 3 |  | CRP | Principal Commissionaire Related Documents Inquiry | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/05/2019 | 06/28/2019 |  | 40 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 03:57 | Joshi, Abhishek N |  | Inquiry | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3FIV082A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564211I | No | UBE | BXU545617 |  | 3 |  | CRP | Deemed Transactions - F0018 to GL Integrity | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/01/2019 | 07/01/2019 |  | 41 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 00:32 | Joshi, Abhishek N | 56- F-EU-V-190701-S3FI057 |  | Yes | Y | [6 empty] | 56- F-EU-V-190701-S3FIV057A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5603B01 | No | UBE | BXU550591 |  | 3 |  | CRP | Realised and unrealised F/X Gains/Losses in Pricipal's Books | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/26/2019 | 6/26/2019 |  | 42 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 00:43 | Joshi, Abhishek N | 56-F-EU-V-190624-S3FI008 |  | Yes | Y | [6 empty] | 56-F-EU-V-190624-S3FIV008A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564572FOI | No | UBE |  |  | 5 |  | CRP | Deutche Bank - Foreign Print Program + IBAN | L3 Pass | 234 | WIP | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/1/2019 | 6/28/2019 |  | 43 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-31 10:30 | Gilthorpe, Peter | 56-F-EU-V-190628-S3FI033 | Printer | Yes | Y | [6 empty] | 56-F-EU-V-190628-S3FIV33A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564572M2I | No | UBE |  |  | 3 |  | CRP | Deutche Bank - Foreign Pmnt Pgm Malta + IBAN | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/1/2019 | 7/1/2019 |  | 44 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-31 10:30 | Gilthorpe, Peter | 56-F-EU-V-190701-S3FI051 |  | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3FIV051A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R57032002 | No | UBE | BXU545684 |  | 2 |  | CRP | MT940 Receipts Upload to F03B13Z1 Deutshe Bank - Modified | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 06/11/2019 | 06/10/2019 |  | 45 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 04:57 | Joshi, Abhishek N | 56-F-EU-V-190625-S2FI058 | Upload | Yes | Y |  |  | Dependent on DSI Business Function |  |  |  | 56-F-EU-V-190625-S2FIV58A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P570030G | No | APPL | BXU547228 |  | 3 |  | CRP | Bank Account Information | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/9/2019 | 7/8/2019 |  | 46 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 00:46 | Joshi, Abhishek N | 56-F-EU-V-190702-S3FI084 |  | Yes | Y |  |  | VV-02/07 - Moved to Sprint 3 as per the request from Abhishek Deshmukh |  |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600038 | No | UBE | BXU548844 |  | 3 |  | CRP | Extract from F590113 Grants File into a CSV File. | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Eileen Paula | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 03/07/2019 | 03/07/2019 |  | 47 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 06:26 | Joshi, Abhishek N | 56- F-EU-V-190628-S3FI035 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5839130 | No | UBE | BXU548335 |  | 4 |  | CRP | Stock Valuation GL Update - Russia | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/22/2019 | 7/19/2019 |  | 48 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 03:47 | Joshi, Abhishek N | 56-F-EU-V-190722-S4FI006 |  | Yes | Y | [6 empty] | 56-F-EU-V-190722-S4FIV006A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5839600 | No | UBE | BXU548336 |  | 4 |  | CRP | Stock Valuation Extraction - Russia | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/22/2019 | 7/19/2019 |  | 49 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 03:49 | Joshi, Abhishek N | 56-F-EU-V-190722-S4FI012 |  | Yes | [7 empty] | 56-F-EU-V-190722-S4FIV012A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600043 | No | UBE | BXU547511 |  | 3 |  | CRP | Grant Code to write CSV file | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Eileen Paula | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/5/2019 | 7/5/2019 |  | 50 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 06:27 | Joshi, Abhishek N | 56-F-EU-V-190624-S3FI006 |  | Yes | Y | [6 empty] | 56-F-EU-V-190624-S3FIV006A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56R0113 | No | UBE |  |  | 3 |  | CRP | Grants Concur Extraction - EMEA Region | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Eileen Paula | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/2/2019 | 7/2/2019 |  | 51 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-25 02:36 | Gilthorpe, Peter | 56-F-EU-V-190628-S3FI046 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5841021E | No | UBE |  |  | 1 |  | CRP | F41021/F4105 extract to csv | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Ravi Thapa | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 52 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-13 03:55 | Thapa, Ravi Pratap | 56-F-EU-V-190515-S1FI011 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190515-S1FIV11A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P042002 | No | APPL | BXU547655 |  | 2 |  | CRP | A/P Voucher Journal Entry Redistribution | L3 Pass | 135 | Closed | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/19/2019 | 6/17/2019 |  | 53 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 09:00 | Joshi, Abhishek N | 56-F-EU-V-190613-S2FI032 |  | Yes | Y | [6 empty] | 56-F-EU-V-190613-S2FIV32A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4314 | No | APPL |  |  | 5 |  |  | Voucher Match | Moved to 64bit | 215 |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | VV-29/07, Moved to Sprint 4 as per reqeust from Peter | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 54 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-10 08:48 | Bodin, Fatiha | 56-F-EU-V-190508-S2FI001 |  | Yes | Y |  |  | PG: Retest pending following changes to Business Function |  |  |  | 56-F-EU-V-190508-S2FIV01A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P0411Z1 | No | APPL | BXU547418 |  | 2 |  | CRP | A/P Batch Voucher Entry | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 06/13/2019 | 06/10/2019 |  | 55 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 08:58 | Joshi, Abhishek N | 56-F-EU-V-190610-S2FI005 |  | Yes | Y | [6 empty] | 56-F-EU-V-190610-S2FIV05A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P03B102 | No | APPL | BXU547057 |  | 2 |  | CRP | Standard Receipt Entry | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/12/2019 | 6/11/2019 |  | 56 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 08:47 | Joshi, Abhishek N | 56-F-EU-V-190612-S2FI001 |  | Yes | Y | [6 empty] | 56-F-EU-V-190612-S2FI001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600033 | No | UBE | BXU547237 |  | 3 |  | CRP | Populate GL Date on Routing Ledger | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Ravi Thapa | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/28/2019 | 6/27/2019 |  | 57 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 06:19 | Joshi, Abhishek N | 56-F-EU-V-190628-S3FI032 |  | Yes | Y |  |  | Retrofit not required |  |  |  | 56-F-EU-V-190628-S3FIV032A, 56-F-EU-V-190628-S3FIV032B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600029 | No | UBE | BXU547117 |  | 3 |  | CRP | Deemed Invoices - Revenues Commissions Split | L3 Pass |  |  | TRUE | HE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 19/06/28 | 19/06/27 |  | 58 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 03:50 | Joshi, Abhishek N | 56-F-EU-V-190625-S3FI013 |  | Yes | Y | [6 empty] | 56-F-EU-V-190625-S3FIV013A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600060 | No | UBE | BXU544659 |  | 4 |  | CRP | Set RCND to F0911 | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/22/2019 | 7/19/2019 |  | 59 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-05 06:39 | Joshi, Abhishek N | 56-F-EU-V-190722-S4FI003 |  | Yes | Y | [6 empty] | 56-F-EU-V-190722-S4FIV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P1204 | No | APPL | BXU547223 |  | 2 |  | CRP | Work With Assets | L3 Pass |  |  | TRUE | HNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/14/2019 | 6/13/2019 |  | 60 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-05 05:45 | Joshi, Abhishek N | 56-F-EU-V-190610-S2FI010 |  | Yes | Y | [6 empty] | 56-F-EU-V-190610-S2FIV010A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600062 | No | UBE | BXU544659 |  | 4 |  | CRP | GL Account Reconciliation Report | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/22/2019 | 7/19/2019 |  | 61 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-05 06:43 | Joshi, Abhishek N | 56-F-EU-V-190723-S3FI024 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190723-S3FIV024A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600921 | No | UBE | BXU544659 |  | 4 |  | CRP | Automatch on Common Key | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/22/2019 | 7/19/2019 |  | 62 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 01:13 | Joshi, Abhishek N | 56-F-EU-V-190722-S4FI013 |  | Yes | Y | [6 empty] | 56-F-EU-V-190722-S4FIV013A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560911A | No | UBE | BXU544659 |  | 4 |  | CRP | Extract General Ledger to Work File | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/22/2019 | 7/19/2019 |  | 63 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 03:28 | Joshi, Abhishek N | 56-F-EU-V-190722-S4FI002 |  | Yes |  |  |  | Retrofit not required |  |  |  | 56-F-EU-V-190722-S4FIV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560922P | No | UBE | BXU544659 |  | 4 |  | CRP | Fetch Purchase Receipt Detail | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/22/2019 | 07/22/2019 |  | 64 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 00:16 | Joshi, Abhishek N | 56-F-EU-V-190722-S4FI007 |  | Yes | Y | [6 empty] | 56-F-EU-V-190722-S4FIV007A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R04423B | No | UBE | BXU548621 | BXU555769 | 2 |  | CRP | Open A/P Details with Aging | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Nithya Ramachandran | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | After Rework, Code reviewed by Vikas | Devi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/11/2019 | 6/11/2019 |  | 65 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-07-24 03:48 | Singh, Sunil Kumar | 56-F-EU-V-190611-S2FI026 |  | Yes | Y | [6 empty] | 56-F-EU-V-190611-S2FIV026A, 56-F-EU-V-190611-S2FIV026B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R04431 | No | UBE | BXU548620 |  | 2 |  | CRP | Cash Requirements Report | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Vijey Sesha | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 06/14/2019 | 06/14/2019 |  | 66 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 05:45 | Joshi, Abhishek N | 56-F-EU-V-190613-S2FI035 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190613-S2FIV035A, 56-F-EU-V-190613-S2FIV035B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R04431A | No | UBE | BXU548619 |  | 2 |  | CRP | Cash Requirements Report with Currency Aging | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Vijey Sesha | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/12/2019 | 6/11/2019 |  | 67 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 05:49 | Joshi, Abhishek N | 56-F-EU-V-190611-S2FI011 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190611-S2FIV011A,56-F-EU-V-190611-S2FIV011B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R04570 | No | UBE | BXU547238 |  | 3 |  | CRP | Create Payment Control Groups | L3 Pass | 199 | Closed | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/02/2019 | 06/27/2019 |  | 68 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 05:52 | Joshi, Abhishek N | 56-F-EU-V-190624-S3FI004 |  | Yes | Y |  |  | 236 versions missing from UT |  |  |  | 56-F-EU-V-190624-S3FIV04A,56-F-EU-V-190624-S3FIV04B,56-F-EU-V-190624-S3FIV04C,56-F-EU-V-190624-S3FIV04D,56-F-EU-V-190624-S3FIV04E | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560922C | No | UBE | BXU544659 |  | 4 |  | CRP | Fetch Cardex Details | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/23/2019 | 7/22/2019 |  | 69 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 04:14 | Joshi, Abhishek N | 56-F-EU-V-190722-S4FI008 |  | Yes | Y | [6 empty] | 56-F-EU-V-190722-S4FIV008A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560922F | No | UBE | BXU544659 |  | 4 |  | CRP | Fetch FINMOV Details | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/23/2019 | 7/22/2019 |  | 70 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 04:14 | Joshi, Abhishek N | 56-F-EU-V-190722-S4FI015 |  | Yes | Y | [6 empty] | 56-F-EU-V-190722-S4FIV015A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560922G | No | UBE | BXU544659 |  | 4 |  | CRP | Fetch GL Details | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/23/2019 | 7/22/2019 |  | 71 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 04:28 | Joshi, Abhishek N | 56-F-EU-V-190723-S4FI019 |  | Yes | Y | [6 empty] | 56-F-EU-V-190723-S4FIV019A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560922S | No | UBE | BXU544659 |  | 4 |  | CRP | Fetch Sales Order Detail | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/23/2019 | 7/23/2019 |  | 72 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 04:29 | Joshi, Abhishek N | 56-F-EU-V-190723-S4FI017 |  | Yes | [7 empty] | 56-F-EU-V-190723-S4FIV017A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56TOSC2 | No | UBE | BXU545881 |  | 1 |  | CRP | Toscanini Interface Analysis Report | L3 Pass |  |  | TRUE | HE2E |  | Finance GL | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/06/2019 | 07/06/2019 |  | 73 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 04:48 | Joshi, Abhishek N | 56-F-EU-V-190528-S1FI036 | Interface / Report | Yes | Y | [6 empty] | 56-F-EU-V-190528-S1FIV36A,56-F-EU-V-190528-S1FIV36B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5600024 | No | APPL | BXU547237 |  | 1 |  | CRP | Maintain GL Date on Routing Ledger | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Ravi Thapa | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/04/2019 | 6/03/2019 |  | 74 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-05 09:03 | Joshi, Abhishek N | 56-F-EU-V-190529-S1FI037 | Maintenance | Yes | Y |  |  | Retrofit not required |  |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRAP146 | No | UBE | BXU546853 |  | 5 |  | CRP | KPI for p2P non-comliant vouchers | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Saurabh Gupta | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/12/2019 | 8/12/2019 |  | 75 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 03:57 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI040 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV040A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R550411P | No | UBE | BXU547501 |  | 5 |  | CRP | Pega Reconciliation Report | L3 Pass | 305 | Open | TRUE | HNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/12/2019 | 8/12/2019 |  | 76 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 03:08 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI016 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV016A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564211CR | No | UBE | BXU549984 |  | 3 |  | CRP | Commission Calculation Reconciliation Extract | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/2/2019 | 7/1/2019 |  | 77 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 00:31 | Joshi, Abhishek N | 56-F-EU-V-190628-S3FI030 |  | Yes | Y | [6 empty] | 56-F-EU-V-190628-S3FIV30A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL100 | No | UBE | BXU547582 |  | 1 |  | CRP | Data Analysis CSV - F0901/F0000/F0902 | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Nithya Ramachandran | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/7/2019 | 6/7/2019 |  | 78 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 10:47 | Joshi, Abhishek N | 56-F-EU-V-190521-S1FI041 |  | Yes | Y | [6 empty] | 56-F-EU-V-190521-S1FIV041A,56-F-EU-V-190521-S1FIV041B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649010 | No | APPL |  |  | 1 |  |  | Work With Custom AAIs Table | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 19/06/04 | 19/06/04 |  | 79 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:50 | Chiau, Liesbet | 56-F-EU-V-190603-S1LO139 |  | Yes | Y |  |  | No Retrofit Required | FCA OUT |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564211ME | No | UBE | BXU545938 |  | 4 |  | CRP | ME Sales Report CSV Report | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/23/2019 | 7/22/2019 |  | 80 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 03:40 | Joshi, Abhishek N | 56-F-EU-V-190723-S3FI025 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190723-S3FIV025A , 56-F-EU-V-190723-S3FIV025B , 56-F-EU-V-190723-S3FIV025C | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5612LHW | No | APPL | BXU545949 |  | 2 |  | CRP | View Leased Hardware Moves in F5612LHW | L3 Pass |  |  | TRUE | HNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/14/2019 | 6/14/2019 |  | 81 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 02:25 | Joshi, Abhishek N | 56-F-EU-V-190611-S2FI003 |  | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRFA21 | No | UBE | BXU544915 |  | 2 |  | CRP | Fixed Asset Batch Update F1202 | L3 Pass |  |  | TRUE | HNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 14/06/19 | 14/06/19 |  | 82 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 04:21 | Joshi, Abhishek N | 56-F-EU-V-190610-S2F1011 |  | Yes | Y | [6 empty] | 56-F-EU-V-190610-S2F1V11A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56GETPD51 | No | UBE | BXU545890 |  | 1 |  | CRP | GetPaid ARCUST build programs (F56ARCUS) Portugal | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Vijey Sesha | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/4/2019 | 6/4/2019 |  | 83 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 04:33 | Joshi, Abhishek N | 56-F-EU-V-190527-S1FI053 |  | Yes | Y | [6 empty] | 56-F-EU-V-190527-S1FIV053A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600036 | No | UBE | BXU547126 |  | 4 |  | CRP | Populate Remark Field on F43121 for Pega Interface | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete | PDF Output not came Blank in one step and this is informed to Baxter SME |  |  | Terry Greenard / Vikas Verma |  | TANKUT CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/23/2019 | 7/22/2019 |  | 84 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 03:53 | Joshi, Abhishek N | 56-F-EU-V-190722-S4FI014 | Interface | Yes | Y | [6 empty] | 56-F-EU-V-190722-S4FIV014A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600058 | No | UBE | BXU547127 |  | 5 |  | CRP | Valorised On hand Report | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 08/20/2019 | 08/19/2019 |  | 85 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 04:07 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI034 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190812-S5FIV034A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5600021 | No | APPL |  |  | 1 |  |  | Maintain Next Tracker Number Table | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 86 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:50 | Chiau, Liesbet | 56-F-EU-V-190515-S1LO020 | Maintenance | Yes | Yes |  |  |  | KTT1 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56FINM1 | No | APPL | BXU547434 |  | 4 |  |  | Maintenance application for F56FINMV | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/23/2019 | 7/22/2019 |  | 87 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 00:27 | Joshi, Abhishek N | 56-F-EU-V-190722-S4FI004 | Maintenance | Yes | Y | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600035 | No | UBE | BXU547502 |  | 3 |  | CRP | Intransit Report | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Ravi Thapa | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/28/2019 | 07/15/2019 |  | 88 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 03:52 | Joshi, Abhishek N | 56- F-EU-V-190628-S3FI033 | Report | Yes | Y | [6 empty] | 56- F-EU-V-190628-S3FIV033A,56- F-EU-V-190628-S3FIV033B,56- F-EU-V-190628-S3FIV033C | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5712411B | No | UBE | BXU544974 |  | 4 |  | CRP | Depreciation Schedule, incl. Send Method 00 | L3 Pass |  |  | TRUE | HNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/24/2019 | 07/22/2019 |  | 89 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 03:36 | Joshi, Abhishek N | 56-F-EU-V-190722-S4FI011 |  | Yes | [7 empty] | 56-F-EU-V-190722-S4FIV011A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642801 | No | UBE | BXU545939 |  | 2 |  | CRP | Cardex Shipped Not Invoiced Report | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Vijey Sesha | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 90 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 03:41 | Joshi, Abhishek N | 56-F-EU-V-190614-S2FI043 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190614-S2FIV043A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600055 | No | UBE | BXU547674 |  | 4 |  | CRP | Customer Returns - Reclass COGS350 Suspense Account | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/24/2019 | 7/23/2019 |  | 91 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 04:03 | Joshi, Abhishek N | 56-F-EU-V-190722-S4FI009 |  | Yes | Y | [6 empty] | 56-F-EU-V-190722-S4FIV009A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600080 | No | UBE | BXU544638 |  | 4 |  | CRP | Customer Returns - Reclass COGS350 Suspense Account | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/24/2019 | 7/23/2019 |  | 92 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 00:57 | Joshi, Abhishek N | 56-F-EU-V-190722-S4FI016 |  | Yes | Y | [6 empty] | 56-F-EU-V-190722-S4FIV016A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P55B100 | No | APPL | BXU545685 |  | 5 |  | CRP | Monthly VAT Table European Localisations | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/12/2019 | 8/12/2019 |  | 93 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-05 05:52 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI001 |  | Yes | Yes | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRAR120 | No | UBE | BXU545685 |  | 5 |  | CRP | Sweden VAT Reporting - Accounts Receivable | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/12/2019 | 8/9/2019 |  | 94 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 09:19 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI018 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV018A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRDSOX1 | No | UBE | BXU547672 |  | 6 |  | CRP | DSO DRIVER REPORT | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete | Passing after confirmation from SME |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 9/3/2019 | 9/3/2019 |  | 95 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 05:00 | Joshi, Abhishek N | 56-F-EU-V-190828-S6FI068 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190828-S6FIV068A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FREX64 | No | UBE | BXU545807 |  | 6 |  | CRP | AR AsOf Reconciliation Report | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete | Passing after confirmation from SME |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/28/2019 | 6/27/2019 |  | 96 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-19 03:15 | Joshi, Abhishek N | 56-F-EU-V-190628-S3FI029 | Report | Yes | Y |  |  | Retrofit not required |  |  |  | 56-F-EU-V-190628-S3FIV029A, 56-F-EU-V-190628-S3FIV029B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRAR121 | No | UBE | BXU545685 |  | 5 |  | CRP | Denmark VAT Reporting - Accounts Receivable | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/12/2019 | 8/12/2019 |  | 97 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 09:21 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI013 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV013A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRAR122 | No | UBE | BXU545685 |  | 5 |  | CRP | Finland VAT Reporting - Accounts Receivable | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/12/2019 | 8/09/2019 |  | 98 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 09:22 | Joshi, Abhishek N | 56-F-EU-V-190807-S5FI001 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190807-S5FIV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRAR123 | No | UBE | BXU545685 |  | 5 |  | CRP | Norway VAT Reporting - Accounts Receivable | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/12/2019 | 8/9/2019 |  | 99 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 09:22 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI009 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV009A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRAP120 | No | UBE | BXU544763 |  | 5 |  | CRP | Sweden VAT Reporting - Accounts Payable | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/12/2019 | 8/12/2019 |  | 100 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 08:34 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI011 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV011A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRAP121 | No | UBE | BXU544763 |  | 5 |  | CRP | Denmark VAT Reporting - Accounts Payable | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/13/2019 | 8/13/2019 |  | 101 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 09:06 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI004 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV004A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRAP122 | No | UBE | BXU544763 |  | 5 |  | CRP | Finland VAT Reporting - Accounts Payable | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete | As discussed in scrum call today, going ahead by adding note to script for the field which is not in PO in JDE in both 812DV and 9.2DV |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/13/2019 | 8/12/2019 |  | 102 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 09:06 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI019 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV019A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRAP123 | No | UBE | BXU544763 |  | 5 |  | CRP | Norway VAT Reporting - Accounts Payable | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/13/19 | 8/12/19 |  | 103 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 09:07 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI012 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV012A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600074 | No | UBE | BXU547134 |  | 3 |  | CRP | F4211 Adjust Sales Line UBE | L3 Pass |  |  | TRUE | HE2E |  | Finance GL | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 19/06/28 | 19/06/27 |  | 104 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-05 06:44 | Joshi, Abhishek N | 56- F-EU-V-190625-S3FI025 |  | Yes | Y | [6 empty] | 56- F-EU-V-190625-S3FIV025A,56- F-EU-V-190625-S3FIV025B,56- F-EU-V-190625-S3FIV025C,56- F-EU-V-190625-S3FIV025D | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600075 | No | UBE | BXU547134 |  | 3 |  | CRP | Generate IC Orders from Drop Shipments UBE Object depends on P4210 object, waiting for it. | L3 Pass |  |  | TRUE | HE2E |  | Finance GL | Finance | Ayse Bayindir | L2 Pass / Complete | AB 19/07 On Hold pending completion of P4210 test which is also in Sprint 3 |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/28/2019 | 6/27/2019 |  | 105 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-05 06:47 | Joshi, Abhishek N | 56-F-EU-V-190701-S3FI069 |  | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3FIV69A,56-F-EU-V-190701-S3FIV69B,56-F-EU-V-190701-S3FIV69C | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600050 | No | UBE | BXU547128 |  | 5 |  | CRP | Spain VAT Reporting - CSV Extract | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/13/2019 | 8/12/2019 |  | 106 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 04:00 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI044 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV044A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL026 | No | UBE | BXU546833 |  | 5 |  | CRP | QA Quarterly Reports | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/13/2019 | 8/12/2019 |  | 107 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 03:01 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI008 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV008A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564112 | No | UBE | BXU546724 |  | 4 |  | CRP | PII Validation report | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/24/2019 | 7/23/2019 |  | 108 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 00:22 | Joshi, Abhishek N | 56-F-EU-V-190723-S4FI018 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190723-S4FIV018A,56-F-EU-V-190723-S4FIV018B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R57RECIC | No | UBE |  |  | 999 |  |  | RECIC/F0911 Reconciliation | Obsolete | [5 empty] | Finance GL | Finance | Joanne Byrne |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 109 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:12 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56R9005 | No | APPL | BXU547236 |  | 6 |  |  | Maintain Russian Correspondence Detail Posting Rules Table | L3 Not Required |  |  | TRUE | LNE2E |  | Localization | Finance | Keith Haxton | L2 Not required | No KT, test in E2E |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 9/13/2019 | 9/12/2019 |  | 110 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 04:21 | Joshi, Abhishek N | 56-F-EU-V-190910-S6FI150 | Maintenance | Yes | Yes |  |  |  | No KT |  |  | N/A |  |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56R9011 | No | APPL | BXU547236 |  | 6 |  |  | Maintain Detail Corresponce Table | L3 Not Required |  |  | TRUE | LNE2E |  | Localization | Finance | Keith Haxton | L2 Not required | No KT, test in E2E |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 9/13/2019 | 9/12/2019 |  | 111 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 04:23 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI067 | Maintenance | Yes | Yes |  |  |  | No KT |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R57004051 | No | UBE | BXU546189 |  | 4 |  | CRP | A/R - A/P IVA Tax Report - Italy - Cust | L3 Pass | 253 | Closed | TRUE | HNE2E |  | Finance GL | Finance | Lokesh Reddy | L2 Pass / Complete | Run the report with version confirmed over email |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/24/2019 | 7/23/2019 |  | 112 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 04:54 | Joshi, Abhishek N | 56-F-EU-V-190723-S4FI020 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190723-S4FIV020A,56-F-EU-V-190723-S4FIV020B,56-F-EU-V-190723-S4FIV020C,56-F-EU-V-190723-S4FIV020D | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5674P0410 | No | UBE | BXU545950 |  | 3 |  | CRP | VAT Purchase Domestic Register | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Nithya Ramachandran | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/2/2019 | 7/1/2019 |  | 113 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 03:36 | Joshi, Abhishek N | 56-F-EU-V-190701-S3FI057 |  | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3FIV057A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRAR128 | No | UBE | BXU546186 |  | 5 |  | CRP | Dutch VAT Reporting - Accounts Recieveable | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/13/2019 | 8/13/2019 |  | 114 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 09:27 | Joshi, Abhishek N | 56-F-EU-V-190814-S5FI076 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190814-S5FIV076A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5804002 | No | UBE | BXU548334 |  | 5 |  | CRP | Customer / Supplier Balance Report - Russia | L3 Pass | 284 |  | TRUE | LNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete | Check OCM settings required for this report to get proper BI & CSV outputs. |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/13/2019 | 8/12/2019 |  | 115 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 03:43 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI017 | Report | Yes | Yes |  |  | Special character “№” Removed |  |  |  | 56-F-EU-V-190812-S5FIV017A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600077 | No | UBE | BXU544658 |  | 3 |  | CRP | Concur Product Code Extract | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Eileen Paula | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | There is no other than XBX version. | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/28/2019 | 6/27/2019 |  | 116 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 06:35 | Joshi, Abhishek N | 56-F-EU-V-190626-S3FI001 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600078 | No | UBE |  |  | 3 |  | CRP | Concur Activity Code Extract | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Eileen Paula | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 117 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-25 02:36 | Gilthorpe, Peter | 56-F-EU-V-190626-S3FN003 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600079 | No | UBE |  |  | 3 |  | CRP | Concur Vendor Extract | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Eileen Paula | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/26/2019 | 6/26/2019 |  | 118 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-25 02:36 | Gilthorpe, Peter | 56-F-EU-V-190624-S3FI007 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600081 | No | UBE |  |  | 3 |  | CRP | Concur Employee Extract | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Eileen Paula | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/28/2019 | 6/27/2019 |  | 119 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-25 02:36 | Gilthorpe, Peter | 56-F-EU-V-190628-S3FI038 |  | Yes | Y | [6 empty] | 56-F-EU-V-190628-S3FIV038A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560401 | No | UBE |  |  | 3 |  | CRP | CONCUR GLAP Interface - EMEA Region | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Eileen Paula | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 06/28/19 | 06/28/19 |  | 120 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-25 02:36 | Gilthorpe, Peter | 56-F-EU-V-190624-S3FI010 | Interface | Yes | Y | [6 empty] | 56-F-EU-V-190624-S3FIV010A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560401P | No | UBE |  |  | 3 |  | CRP | Create F74P411H records from Concur upload | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Eileen Paula | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/24/2019 | 6/24/2019 |  | 121 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-25 02:36 | Gilthorpe, Peter | 56-F-EU-V-190624-S3FI009 | Upload | Yes | Y | [6 empty] | 56-F-EU-V-190624-S3FIV09A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56032005 | No | UBE | BXU544716 |  | 2 |  | CRP | Extract DB Confirmation Number to Text Attachment | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 06/19/2019 | 06/18/2019 |  | 122 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 01:48 | Joshi, Abhishek N | 56-F-EU-V-190612-S2F1034 | Text | Yes | Y | [6 empty] | 56-F-EU-V-190612-S2F1V34A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56032006 | No | UBE |  |  | 2 |  | CRP | Attach IXOS PDF file to Receipt using URL | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 123 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-04 10:21 | Frade Dolesor, Constanza | 56-F-EU-V-190612-S2FI002 |  | Yes | Y | [6 empty] | 56-F-EU-V-190612-S2FIV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5600092 | No | APPL |  |  | 1 |  | CRP | Cost Security Application | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Ravi Thapa | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/4/2019 | 6/4/2019 |  | 124 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-08 03:46 | Thapa, Ravi Pratap | 56-F-EU-V-190521-S1FI035 |  | Yes | Y | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5674LI02A | No | UBE |  |  | 1 |  |  | SAF-T Generate XML File | L3 Not Required |  |  | TRUE | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/7/2019 | 6/6/2019 |  | 125 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:50 | Chiau, Liesbet | 56-F-EU-V-190428-S1FI064 | XML | Yes | Y |  |  |  | No KT |  |  | 56-F-EU-V-190428-S1FIV064A |  |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564105 | No | APPL | BXU547242 |  | 1 |  | CRP | Cost Revisions - Secured | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Ravi Thapa | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/4/2019 | 6/4/2019 |  | 126 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 03:35 | Joshi, Abhishek N | 56-F-EU-V-190527-S1FI179 | Revision | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R57AR004 | No | UBE | BXU545807 |  | 3 |  | CRP | Cash Discount Calculation | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 127 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 00:54 | Joshi, Abhishek N | 56-F-EU-V-190628-S3FI001 |  | Yes | Y | [6 empty] | 56-F-EU-V-190628-S3FIV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRAP5 | No | UBE | BXU546825 |  | 1 |  | CRP | LIFO extract - Items Average Costs | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/7/2019 | 6/7/2019 |  | 128 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 09:17 | Joshi, Abhishek N | 56-F-EU-V-190522-S1FI047 |  | Yes | Y | [6 empty] | 56-F-EU-V-190522-S1FIV47A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641031 | No | UBE | BXU545952 |  | 1 |  | CRP | LIFO Inventory csv download | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/06/2019 | 6/06/2019 |  | 129 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-08 01:06 | Joshi, Abhishek N | 56-F-EU-V-190530-S1FI189 | Download | Yes | Y |  |  | Retrofit not required |  |  |  | 56-F-EU-V-190530-S1FIV189A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5512G51 | No | APPL | BXU547451 |  | 5 |  | CRP | Job Status Inquiry-Basic | L3 Pass |  |  | TRUE | HNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 08/13/2019 | 08/12/2019 |  | 130 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-05 05:47 | Joshi, Abhishek N | 56-F-EU-V-190813-S5FI065 | Inquiry | Yes | Yes | [6 empty] | 56-F-EU-V-190813-S5FIV065A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5512G52 | No | APPL | BXU547451 |  | 5 |  | CRP | Job Capitalisation | L3 Pass |  |  | TRUE | HNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/13/2019 | 8/12/2019 |  | 131 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-05 09:03 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI002 |  | Yes | Y | [6 empty] | 56-F-EU-V-190812-S5FIV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641032 | No | UBE |  |  | 1 |  | CRP | LIFO report on Item Master and Cost | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 19\06\06 | 19\06\06 |  | 132 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-18 04:35 | Rasselet, Cedric | 56-F-EU-V-190530-S1FI017 | Report | Yes | Y |  |  | No retrofit required |  |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5704ITLC | No | UBE | BXU545362 |  | 4 |  | CRP | Italian Statutory Reporting - Upload to F0911Z1 (SRP1 SRP4) | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/24/2019 | 7/23/2019 |  | 133 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 05:23 | Joshi, Abhishek N | 56-F-EU-V-190723-S4FI023 | Upload / Report | Yes | Yes | [6 empty] | 56-F-EU-V-190723-S4FIV023A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5704ITL | No | APPL | BXU547415 |  | 4 |  | CRP | Italian Statutory Inventory Materials Maintenance | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/24/2019 | 7/23/2019 |  | 134 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 00:48 | Joshi, Abhishek N | 56-F-EU-V-190723-S4FI021 | Maintenance | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R57093 | No | UBE | BXU546190 |  | 5 |  | CRP | Print IVA Summary Error Report - Italy | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Ravi Thapa | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/13/2019 | 8/12/2019 |  | 135 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 05:24 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI029 | Error / Printer / Report | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV029A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5603004 | No | UBE | BXU546906 |  | 5 |  | CRP | Sales Journal DACH Report 2 | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete | Change GL date range to 01/01/19 -31/01/19 as data is not there for range given in test script |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/13/2019 | 8/12/2019 |  | 136 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 01:29 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI015 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV015A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRAP31 | No | UBE | BXU547449 |  | 5 |  | CRP | Germany VAT Reporting - Accounts Receivable | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/13/2019 | 8/12/2019 |  | 137 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-05 06:27 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI047 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV047A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRAP33 | No | UBE | BXU547449 |  | 5 |  | CRP | Germany VAT Reporting - Accounts Payable | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/13/2019 | 8/12/2019 |  | 138 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-05 06:30 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI032 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV032A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRAP34 | No | UBE | BXU547449 |  | 5 |  | CRP | Austria VAT Reporting - Accounts Payable | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/13/2019 | 8/12/2019 |  | 139 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-05 06:32 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI033 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV033A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRAR23 | No | UBE | BXU547449 |  | 5 |  | CRP | Austrian VAT Reporting - Accounts Receivable | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/14/2019 | 8/14/2019 |  | 140 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-05 06:33 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI005 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV005A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R60A4011 | No | UBE |  |  | 6 |  |  | Commission Details Print | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Francisco Alvargonzalez | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 141 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-11 06:04 | Sharma, Nikit |  | Printer | [12 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R60A4100 | No | UBE |  |  | 6 |  | CRP | Commission Maturation | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Izaskun Ajuria | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 142 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-06 05:33 | Ajuria, Izaskun | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R60A4110 | No | UBE |  |  | 6 |  | CRP | Commission Liquidation | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Izaskun Ajuria | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 143 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-06 05:33 | Ajuria, Izaskun | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R60A4120 | No | UBE |  |  | 6 |  |  | ENASARCO Calculation | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Francisco Alvargonzalez | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 144 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-11 06:04 | Sharma, Nikit | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R60A4130 | No | UBE |  |  | 6 |  |  | FIRR Calculation | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Francisco Alvargonzalez | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 145 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-11 06:05 | Sharma, Nikit | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R60A4140 | No | UBE |  |  | 6 |  |  | ENASARCO Liquidation | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Francisco Alvargonzalez | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 146 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-11 06:05 | Sharma, Nikit | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R60A4150 | No | UBE |  |  | 6 |  |  | Year-end Declaration | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Francisco Alvargonzalez | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 147 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-11 06:05 | Sharma, Nikit | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R60A4170 | No | UBE |  |  | 6 |  |  | Calculate Indennità Suppletiva | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Francisco Alvargonzalez | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 148 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-11 06:05 | Sharma, Nikit | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R60A41Z1E | No | UBE |  |  | 6 |  | CRP | Input Batch from SOP - Sales Commissions | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Izaskun Ajuria | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 149 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-06 05:32 | Ajuria, Izaskun | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56CRNFY2 | No | UBE |  |  | 3 |  | CRP | Concur Interface - Payment Notification | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Eileen Paula | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/02/2019 | 06/28/2019 |  | 150 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-25 02:36 | Gilthorpe, Peter | 56- F-EU-V-190628-S3FI032 | Interface | Yes | Y | [6 empty] | 56- F-EU-V-190628-S3FIV032A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R57004050 | No | UBE | BXU546655 |  | 5 |  | CRP | AR Re-numbering UBE - Principal VAT | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Lokesh Reddy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/14/2019 | 8/13/2019 |  | 151 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 04:52 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI020 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV020A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59056 | No | UBE | BXU546671 |  | 4 |  |  | ECC:Budget Rollover#2:Copy Budget in Cost & Clear draft cost | L3 Pass |  |  | TRUE |  |  | ECC | ARO | Ravi / Cosmin | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/25/2019 | 7/24/2019 |  | 152 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:36 | Joshi, Abhishek N | 56-F-EU-V-190722-S4AR004 |  | Yes | Y | [6 empty] | 56-F-EU-V-190722-S4ARV004A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600005 | No | UBE | BXU548835 |  | 3 |  | CRP | Create Deemed Invoice Bookings and Documents | L3 Pass |  |  | TRUE | HE2E |  | Finance GL | Finance | Lokesh Reddy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/28/2019 | 6/28/2019 |  | 153 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 06:16 | Joshi, Abhishek N | 56-F-EU-V-190624-S3FI002 |  | Yes | Y | [6 empty] | 56-F-EU-V-190624-S3FIV002A , 56-F-EU-V-190624-S3FIV002B , 56-F-EU-V-190624-S3FIV002C , 56-F-EU-V-190624-S3FIV002D | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600006 | No | UBE | BXU548835 |  | 3 |  | CRP | Create Deemed Commission Bookings and Documents | L3 Pass |  |  | TRUE | HE2E |  | Finance GL | Finance | Lokesh Reddy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/28/2019 | 6/28/2019 |  | 154 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-05 06:36 | Joshi, Abhishek N | 56-F-EU-V-190624-S3FI003 |  | Yes | Y | [6 empty] | 56-F-EU-V-190624-S3FIV003A , 56-F-EU-V-190624-S3FIV003B , 56-F-EU-V-190624-S3FIV003C , 56-F-EU-V-190624-S3FIV003D | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FF101 | No | UBE | BXU546066 |  | 3 |  | CRP | Batch to transmit Invoices to F56FF11 | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/2/2019 | 7/2/2019 |  | 155 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 03:54 | Joshi, Abhishek N | 56-F-EU-V-190628-S3FI049 |  | Yes | Y | [6 empty] | 56-F-EU-V-190628-S3FIV049A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5674412 | No | UBE | BXU546064 |  | 5 |  | CRP | Italian Withholding Tax with BAR Code | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/14/19 | 8/13/19 |  | 156 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-08 04:13 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI022 |  | Yes | Y | [6 empty] | 56-F-EU-V-190812-S5FIV022A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564572FII | No | UBE |  |  | 999 |  |  | Deutche Bank - Foreign Pmnt Pgm ITALY + IBAN | Obsolete |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/2/2019 | 7/1/2019 |  | 157 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-22 08:00 | Gilthorpe, Peter | 56- F-EU-V-190701-S3FI059 |  | Yes | Y |  |  | PG: 220819 Confirmation from eSSC object is no longer used |  |  |  | 56- F-EU-V-190701-S3FIV59A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564572FJI | No | UBE |  |  | 999 |  |  | Deutche Bank - Frgn Pmnt Pgm ITALY Bieffe + IBAN | Obsolete |  |  | FALSE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 158 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:12 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRAP60 | No | UBE | BXU547448 |  | 5 |  | CRP | France VAT Reporting - Accounts Payable | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/14/2019 | 8/13/2019 |  | 159 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 07:10 | Joshi, Abhishek N | 56-F-EU-V-190813-S5FI067 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190813-S5FIV067A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5603003 | No | UBE | BXU546906 |  | 1 |  | CRP | Sales Journal DACH Report 1 | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 160 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 01:27 | Joshi, Abhishek N | 56-F-EU-V-190515-S1FI008 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190515-S1FIV08A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRAP61 | No | UBE | BXU547448 |  | 5 |  | CRP | France VAT AP Report for Payments | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/14/2019 | 8/13/2019 |  | 161 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 06:14 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI035 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV035A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5603002 | No | UBE | BXU545710 |  | 1 |  | CRP | Report Summarizing the number of customer set up per payment | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 04/06/2019 | 04/06/2019 |  | 162 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 01:25 | Joshi, Abhishek N | 56-F-EU-V-190521-S1FI033 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190521-S1FIV33A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRAR60 | No | UBE |  |  | 5 |  | CRP | France VAT Reporting - Accounts Receivable | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete | L2 Test Defect 293 is closed now.Report gets executed in 5 min now. |  |  | Terry Greenard / Vikas Verma | VV-04/09 - As requested from Payal and suggested by Joanne, changes L2 status to blank from L2 not required. | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/29/2019 | 8/29/2019 |  | 163 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-04 04:59 | Felitto, Gregory | 56-F-EU-V-190819-S5FI106 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190819-S5FIV106A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600003 | No | UBE | BXU545346 |  | 3 |  | CRP | JDE Numbering for Entites with Multiple VAT Registrations | L3 Pass |  |  | TRUE | HE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/28/2019 | 6/28/2019 |  | 164 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 03:37 | Joshi, Abhishek N | 56-F-EU-V-190624-S3FI001 |  | Yes | Y | [6 empty] | 56-F-EU-V-190624-S3FIV001A , 56-F-EU-V-190624-S3FIV001B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5941002 | No | UBE | BXU546389 |  | 4 |  | CRP | F4102 Copy LINE to CDCD Program | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/24/2019 | 7/24/2019 |  | 165 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 09:58 | Joshi, Abhishek N | 56-F-EU-V-190724-S4FI001 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190724-S4FIV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL89 | No | UBE | BXU546584 |  | 5 |  | CRP | IR & UK VAT Reports A/R Detail and Summary | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/14/2019 | 8/14/2019 |  | 166 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-05 06:34 | Joshi, Abhishek N | 56-F-EU-V-190814-S5FI085 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190814-S5FIV085A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRGL73 | No | UBE | BXU546584 |  | 5 |  | CRP | IR & UK VAT Reports A/P Detail and Summary v2 | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete | Object is tested successfully with another version. Defect will be raised from Jaonne for corrupted versions associated with this object and retested in CRP/UAT once it is fixed by BSL tech team(as per email confirmation ) |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/14/2019 | 8/13/2019 |  | 167 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 09:49 | Joshi, Abhishek N | 56-F-EU-V-190813-S5FI056 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190813-S5FIV056A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641038 | No | UBE | BXU546532 |  | 1 |  | CRP | Cost and GL Class Discrepancies Report | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 168 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-08 01:09 | Joshi, Abhishek N | 56-F-EU-V-190527-S1FI055 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190527-S1FIV055A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600134 | No | UBE | BXU544712 |  | 5 |  | CRP | Exempt Sales Report | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 08/14/2019 | 08/13/2019 |  | 169 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 01:04 | Joshi, Abhishek N | 56-F-EU-V-190813-S5FI070 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190813-S5FIV070A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600135 | No | UBE | BXU544712 |  | 5 |  | CRP | Intercompany Sales Report | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/14/2019 | 8/13/2019 |  | 170 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 01:06 | Joshi, Abhishek N | 56-F-EU-V-190813-S5FI058 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190813-S5FIV058A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P007101 | No | APPL |  |  | 999 |  |  | Text File Processor | Obsolete | [5 empty] | Finance AR | Finance | Francisco Alvargonzalez |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 171 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:12 | Chiau, Liesbet |  | Text | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600136 | No | UBE | BXU544712 |  | 5 |  | CRP | Dublin Moves Report | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/14/2019 | 8/13/2019 |  | 172 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 01:06 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI038 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV038A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600138 | No | UBE | BXU544641 |  | 5 |  | CRP | Dispatch Summary Report | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/14/2019 | 8/13/2019 |  | 173 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 01:07 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI030 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV030A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRAP13 | No | UBE | BXU547599 |  | 5 |  | CRP | Open Receipts by Company - CSV extract | L3 Pass | 446 |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/14/2019 | 8/13/2019 |  | 174 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 10:21 | Joshi, Abhishek N | 56-F-EU-V-190813-S5FI048 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190813-S5FIV048A,56-F-EU-V-190813-S5FIV048B, 56-F-EU-V-190813-S5FIV048C | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5703B221 | No | UBE | BXU546014 |  | 5 |  |  | Late Payment Delinquency Fees | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/25/2019 | 7/24/2019 |  | 175 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 05:02 | Joshi, Abhishek N | 56-F-EU-V-190723-S4FI024 |  | Yes | [7 empty] | 56-F-EU-V-190723-S4FIV024A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R9310 | No | UBE | BXU546499 |  | 4 |  | CRP | Generate Hyperion Account Ledger File | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/25/2019 | 7/24/2019 |  | 176 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 05:57 | Joshi, Abhishek N | 56-F-EU-V-190724-S4FI033 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190724-S4FIV033A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P74R9001 | No | APPL | BXU547236 |  | 3 |  |  | Correspondence Account Setup - RUS -09 - 74R | L3 Not Required |  |  | TRUE | LNE2E |  | Localization | Finance | Keith Haxton | L2 Not required | No KT, will be tested in E2E |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/4/2019 | 7/4/2019 |  | 177 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 05:28 | Joshi, Abhishek N | NA | Setup | Yes | Y |  |  | No retrofit required | No KT |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P74R9011 | No | APPL | BXU547236 |  | 3 |  |  | Review Correspondence - RUS - 09 - 74R | L3 Not Required |  |  | TRUE | LNE2E |  | Localization | Finance | Keith Haxton | L2 Not required | No KT, will be tested in E2E |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/5/2019 | 7/4/2019 |  | 178 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 05:30 | Joshi, Abhishek N | 56-F-EU-V-190705-S3FI116 |  | Yes | Y |  |  | Associated PO is T74R9001 | No KT |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5774076C | No | UBE | BXU545355 |  | 5 |  | CRP | Suspended IVA - Receipts/Rebate Control Reports (Customised) | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 08/14/2019 | 08/13/2019 |  | 179 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 08:35 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI036 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV036A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R9311 | No | UBE | BXU546501 |  | 4 |  | CRP | Post Hyperion Account Balance File | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/25/2019 | 7/24/2019 |  | 180 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 06:07 | Joshi, Abhishek N | 56-F-EU-V-190724-S4FI028 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190724-S4FIV028A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5609004 | No | UBE | BXU545729 |  | 5 |  | CRP |  | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/14/2019 | 8/12/2019 |  | 181 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 03:08 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI043 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190812-S5FIV043A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5839120W | No | UBE | BXU549974 |  | 1 |  | CRP | Write Additional Costs to F39120W for Advanced Stock Evaluat | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/7/2019 | 6/7/2019 |  | 182 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 03:45 | Joshi, Abhishek N | 56-F-EU-V-190527-S1FI060 |  | Yes | Y | [6 empty] | 56-F-EU-V-190527-S1FIV60A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5603B03 | No | UBE | BXU545715 |  | 1 |  | CRP | Update F03B11 | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/4/2019 | 6/4/2019 |  | 183 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 02:42 | Joshi, Abhishek N | 56-F-EU-V-190521-S1FI042 |  | Yes | Y | [6 empty] | 56-F-EU-V-190521-S1FIV042A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600206 | No | UBE | BXU544714 |  | 5 |  | CRP | Polish VAT Report for Pay when Paid | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/16/2019 | 8/16/2019 |  | 184 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 01:09 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI006 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV006A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600207 | No | UBE | BXU544714 |  | 5 |  | CRP | Principal Output VAT | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Nithya Ramachandran | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/16/2019 | 8/15/2019 |  | 185 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 01:11 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI021 |  | Yes | Y | [6 empty] | 56-F-EU-V-190812-S5FIV021A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5703B571 | No | UBE | BXU546015 |  | 4 |  |  | Create Automatic Debit Batch - EMEA SEPA | L3 Pass | 177 | Open | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete | L2 test performed after Rework |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/19/2019 | 6/19/2019 |  | 186 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 05:04 | Joshi, Abhishek N | 56-F-EU-V-190619-S2FI001 |  | Yes | Y | [6 empty] | 56-F-EU-V-190619-S2FI001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P03B571 | No | APPL | BXU547417 |  | 5 |  |  | Automatic Debit Batches | L3 Not Required | 178 | Closed | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete | L2 Test Performed after rework |  |  | Terry Greenard / Vikas Verma | VV-12/07 - Code reviewed by Vikas after rework | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/18/2019 | 6/17/2019 |  | 187 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 08:52 | Joshi, Abhishek N | 56-F-EU-V-190617-S2FI046 |  | Yes | Y |  |  | To be tested in CRP |  |  |  | 56-F-EU-V-190617-S2FIV046A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74LI41XML | No | UBE |  |  | 3 |  |  | Comunicação do Inventário de Existências à AT | L3 Not Required |  |  | TRUE | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/8/2019 | 7/5/2019 |  | 188 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-11 01:01 | Verma, Vikas | 56-F-EU-V-190704-S3FI109 |  | Yes | Y |  |  |  | No KT |  |  | 56-F-EU-V-190705-S3FIV109A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56743005 | No | UBE | BXU546530 |  | 4 |  |  | SEPA Direct Debit Extractor - EU - 03B - EMEA | L3 Pass | 177 | Open | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete | Tested after rework |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/20/2019 | 6/19/2019 |  | 189 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-08 03:58 | Joshi, Abhishek N | 56-F-EU-V-190619-S2FI050 |  | Yes | Y |  |  | Deffect 177 - Replace old business view V743005A with new business view V5603B57 in UBE R56743005. |  |  |  | 56-F-EU-V-190619-S2FIV050A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56032012 | No | UBE | BXU548347 |  | 2 |  | CRP | BESR Receipts Upload to F03B13Z1 UBS - CH | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 06/20/2019 | 06/20/2019 |  | 190 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 02:02 | Joshi, Abhishek N | 56-F-EU-V-190613-S2FI037 | Upload | Yes | Y |  |  | Report Did not validate due to DSI BSFN-BD3N070 |  |  |  | 56-F-EU-V-190613-S2FIV037A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600208 | No | UBE | BXU544714 |  | 5 |  | CRP | Commissionaire Output VAT | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Nithya Ramachandran | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/14/19 | 8/16/19 |  | 191 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 01:12 | Joshi, Abhishek N | 56-F-EU-V-190611-S2FI020 |  | Yes | Y | [6 empty] | 56-F-EU-V-190611-S2FIV020A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL76 | No | UBE | BXU547600 |  | 1 |  | CRP | Update B.U.'s with Model of Accounts | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/6/2019 | 6/6/2019 |  | 192 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 07:43 | Joshi, Abhishek N | 56-F-EU-V-190521-S1FI037 |  | Yes | Y | [6 empty] | 56-F-EU-V-190521-S1FIV37A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRGL119 | No | UBE | BXU546707 |  | 1 |  | CRP | Data Analysis CSV - F0901/F0000/F0902 - 14 Periods | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Nithya Ramachandran | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/6/2019 | 6/6/2019 |  | 193 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 09:34 | Joshi, Abhishek N | 56-F-EU-V-190530-S1FI180 |  | Yes | Y | [6 empty] | 56-F-EU-V-190530-S1FIV180A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56744002 | No | UBE |  |  | 6 |  | CRP | SEPA XML Credit Transfer - COMM - 04 - EMEA | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT , CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/2/2019 | 7/1/2019 |  | 194 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-01 05:47 | Gilthorpe, Peter | 56-F-EU-V-190701-S3FI076 | XML | Yes | Y |  |  | Error when trying to validate the report as the PO cReplaceChar mapping was missing against DSTR cReplaceSpecialChars in N7090010.D709001B. Hence Retrofitted the report |  |  |  | 56-F-EU-V-190701-S3FIV76A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P743002 | No | APPL | BXU546531 |  | 2 |  | CRP | SEPA Direct Debit Mandate | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/20/2019 | 6/19/2019 |  | 195 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-05 06:17 | Joshi, Abhishek N | 56-F-EU-V-190619-S2FI052 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56743002 | No | UBE | BXU546531 |  | 2 |  | CRP | SEPA Direct Debit Mandate Approval Form | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/20/2019 | 6/19/2019 |  | 196 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-08 03:45 | Joshi, Abhishek N | 56-F-EU-V-190617-S2FI098 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190617-S2FI098A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5604570 | No | UBE | BXU549998 |  | 3 |  | CRP | Create Payment Control Groups - Custom | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/24/2019 | 6/24/2019 |  | 197 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 03:38 | Joshi, Abhishek N | 56-F-EU-V-190624-S3FI011 |  | Yes | Y | [6 empty] | 56-F-EU-V-190624-S3FIV11A, 56-F-EU-V-190624-S3FIV11B, 56-F-EU-V-190624-S3FIV11C, 56-F-EU-V-190624-S3FIV11D,56-F-EU-V-190624-S3FIV11E | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600125 | No | UBE |  |  | 4 |  | CRP | Close Open Receipts for non Invoiced Transactions | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT , CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/25/2019 | 7/24/2019 |  | 198 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-10 02:41 | GOLGE, SERAY | 56-F-EU-V-190724-S4FI032 |  | Yes | Y | [6 empty] | 56-F-EU-V-190724-S4FIV032A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56SGJ0 | No | UBE | BXU546497 |  | 4 |  | CRP | Submit Group Job - Selection_NT Server | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT , CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/30/2019 | 7/24/2019 |  | 199 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 04:46 | Joshi, Abhishek N | 56-F-EU-V-190724-S4FI031 |  | Yes | Y | [6 empty] | 56-F-EU-V-190724-S4FIV031A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R57SGJ0 | No | UBE | BXU546497 |  | 4 |  | CRP | Submit Group Job - Selection | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/25/2019 | 7/25/2019 |  | 200 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 03:38 | Joshi, Abhishek N | 56-F-EU-V-190725-S4FI001 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190725-S4FIV001A,56-F-EU-V-190725-S4FIV001B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5603B1Z | No | UBE | BXU545717 |  | 3 |  | CRP | Split Payment VAT Processing ITA | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 06/28/19 | 06/28/19 |  | 201 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 02:42 | Joshi, Abhishek N | 56-F-EU-V-190624-S3FIV009 |  | Yes | Y | [6 empty] | 56-F-EU-V-190624-S3FIV009A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PYRGL11 | No | UBE | BXU546944 |  | 1 |  | CRP | ADP Payroll GL F0911Z1 record creation | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Lokesh Reddy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 202 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 03:17 | Joshi, Abhishek N | 56-F-EU-V-190515-S1FI010 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190515-S1FIV10A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5603002 | No | APPL | BXU544716 |  | 2 |  | CRP | Maintenance DB Payment Confirmation | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/21/2019 | 6/21/2019 |  | 203 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 02:19 | Joshi, Abhishek N | 56-F-EU-V-200619-S2FI053 | Maintenance | Yes | Yes | [6 empty] | 56-F-EU-V-200619-S2FIV053A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PYRGL12 | No | UBE | BXU546944 |  | 1 |  | CRP | Interface ADP Payroll to JDE | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Lokesh Reddy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/5/2019 | 6/6/2019 |  | 204 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 03:18 | Joshi, Abhishek N | 56-F-EU-V-190528-S1FI035 | Interface | Yes | Y |  |  | On hold because of DSI Business Function |  |  |  | 56-F-EU-V-190528-S1FIV035A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PYRGL13 | No | UBE | BXU546944 |  | 1 |  | CRP | ADP - Payroll text import | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Lokesh Reddy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | UBE excuted from R56PYRGL12 and its on Hold due to dependent DSI object. | Nikit |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/6/2019 | 6/6/2019 |  | 205 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 03:18 | Joshi, Abhishek N | 56-F-EU-V-190521-S1FI043 | Text | Yes | Y | [6 empty] | 56-F-EU-V-190521-S1FIV043A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5703B21F | No | UBE | BXU546012 |  | 4 |  | CRP | A/R Client Statement France | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/25/2019 | 7/24/2019 |  | 206 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 05:01 | Joshi, Abhishek N | 56-F-EU-V-190723-S4FI022 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190723-S4FIV022A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRAP100 | No | UBE | BXU547730 |  | 5 |  | CRP | DADS Reporting - France CSV Report | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/16/2019 | 8/15/2019 |  | 207 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 06:53 | Joshi, Abhishek N | 56-F-EU-V-190814-S5FI095 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190814-S5FIV095A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL84A | No | UBE | BXU547596 |  | 1 |  | CRP | Expense by Responsibility-Transaction Listing CSV (Address) | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Nithya Ramachandran | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/6/2019 | 6/5/2019 |  | 208 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 10:05 | Joshi, Abhishek N | 56-F-EU-V-190428-S1FI065 |  | Yes | Y | [6 empty] | 56-F-EU-V-190428-S1FIV065A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56414B | No | UBE | BXU546734 |  | 3 |  | CRP | Generate Profit Allocation Journal - RMF | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/28/2019 | 6/27/2019 |  | 209 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 00:25 | Joshi, Abhishek N | 56-F-EU-V-190701-S3FI072 |  | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3FIV72A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56414 | No | APPL | BXU546734 |  | 3 |  | CRP | Profit allocation data interfaced from RMF – JDE view | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/24/2019 | 6/24/2019 |  | 210 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 04:06 | Joshi, Abhishek N | 56-F-EU-V-190628-S3FI044 | Interface | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRGL117 | No | UBE | BXU546492 |  | 1 |  | CRP | Data Analysis CSV - F0901/F0000/F0902 - 14 Periods | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Nithya Ramachandran | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/6/2019 | 6/6/2019 |  | 211 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 09:31 | Joshi, Abhishek N | 56-F-EU-V-190522-S1FI046 |  | Yes | Y | [6 empty] | 56-F-EU-V-190522-S1FIV46A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5703B20S | No | UBE | BXU546011 |  | 999 |  |  | A/R Delinquency Notices Print | Obsolete |  |  |  | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 212 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 04:59 | Joshi, Abhishek N |  | Printer | [12 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R563B5002 | No | UBE | BXU545951 |  | 6 |  | CRP | Localized Statement Print - As Of GEMINI (56) | L3 Pass | 248 |  | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete | Defect 248 |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/26/2019 | 7/25/2019 |  | 213 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-08 00:39 | Joshi, Abhishek N | 56-F-EU-V-190722-S4FI010 | Printer | Yes | Y | [6 empty] | 56-F-EU-V-190722-S4FIV010A, B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R563B500X | No | UBE | BXU545951 |  | 5 |  | CRP | Statement Notification Refresh - As Of GEMINI (56) | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete | Calling object R563B5002/Defect 248 |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/26/2019 | 7/25/2019 |  | 214 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-08 00:51 | Joshi, Abhishek N | 56-F-EU-V-190723-S4FI025 |  | Yes | Y | [6 empty] | 56-F-EU-V-190723-S4FIV025A, 56-F-EU-V-190723-S4FIV025B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRGL84F | No | UBE | BXU546585 |  | 1 |  | CRP | Expense by Responsibility - Transaction Listing CSV - French | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Ravi Thapa | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/6/2019 | 6/6/2019 |  | 215 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 10:51 | Joshi, Abhishek N | 56-F-EU-V-190527-S1FI061 |  | Yes | Y | [6 empty] | 56-F-EU-V-190527-S1FIV61A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560359D | No | UBE | BXU545714 |  | 5 |  | CRP | F56902EC currency conversion and integrity report | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 06/28//2019 | 06/27//2019 |  | 216 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 02:12 | Joshi, Abhishek N | 56-F-EU-V-190628-S3FI039 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190628-S3FIV039A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56E0001 | No | UBE | BXU516652 (109164) | 109164 | 3 |  |  | GLAB - Update E1 to E1 ASN information | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 1/7/2019 | 1/7/2019 |  | 217 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 05:20 | Singh, Sunil Kumar | 56-F-EU-V-190628-S3LO004 |  | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190628-S3LOV004A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R573B672AI | No | UBE | BXU546017 |  | 3 |  | CRP | Draft Remittance for DB + IBAN | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/2/2019 | 7/1/2019 |  | 218 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 05:34 | Joshi, Abhishek N | 56-F-EU-V-190701-S3FI055 |  | Yes | [7 empty] | 56-F-EU-V-190701-S3FIV055A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5604601 | No | UBE |  |  | 5 |  | CRP | Duplicate Payments by Country | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | CIZMECI,TANKUT |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/16/2019 | 8/16/2019 |  | 219 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-19 05:00 | Gilthorpe, Peter | 56-F-EU-V-190816-S5FI102 |  | Yes | Y | [6 empty] | 56-F-EU-V-190816-S5FIV102A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56R0191 | No | UBE | BXU546495 |  | 3 |  | CRP | Cost Component - Inbound Processor R59R0191 optimized | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 2/7/2019 | 2/7/2019 |  | 220 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 03:20 | Joshi, Abhishek N | 56-F-EU-V-190628-S3FI042 | Inbound | Yes | Y | [6 empty] | 56-F-EU-V-190628-S3FIV042A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56R0193 | No | UBE | BXU546588 |  | 3 |  | CRP | Cost Component - Data Extraction UBE - optimized | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/3/2019 | 7/3/2019 |  | 221 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 04:44 | Joshi, Abhishek N | 56-F-EU-V-190703-S3FI001 |  | Yes | Y | [6 empty] | 56-F-EU-V-190703-S3FIV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5609100 | No | UBE | BXU545731 |  | 3 |  | CRP | Leased Hardware Profit Allocations | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/3/2019 | 6/28/2019 |  | 222 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 03:24 | Joshi, Abhishek N | 56-F-EU-V-190702-S3FI140 |  | Yes | Y | [6 empty] | 56-F-EU-V-190702-S3FIV140A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P74ZS038 | no | APPL | BXU545393 |  | 2 |  | CRP | Maintain VAT Sequencing Table | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 06/26/2019 | 06/25/2019 |  | 223 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 05:33 | Joshi, Abhishek N | 56-F-EU-V-190624-S2FI054 | Maintenance | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74ZS048 | No | UBE | BXU545393 |  | 3 |  | CRP | Localization CZ - Tax Detail Report | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Vijey sesha | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/9/2019 | 7/8/2019 |  | 224 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 08:01 | Joshi, Abhishek N | 56-F-EU-V-190704-S3FI107 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190704-S3FIV107A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R553B4201B | No | UBE |  |  | 1 |  | CRP | A/R Details with Aging | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/4/2019 | 6/3/2019 |  | 225 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-11 10:43 | Alvargonzalez, Francisco | 56-F-EU-V-190428-S1FI066 |  | Yes | Y | [6 empty] | 56-F-EU-V-190428-S1FIV066A,56-F-EU-V-190428-S1FIV066B,56-F-EU-V-190428-S1FIV066C,56-F-EU-V-190428-S1FIV066D,56-F-EU-V-190428-S1FIV066E,56-F-EU-V-190428-S1FIV066F | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRAP18 | No | UBE |  |  | 5 |  | CRP | AS OF Open AP - Summary Doc level | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Saurabh Gupta | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/16/2019 | 8/14/2019 |  | 226 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-18 09:49 | Gilthorpe, Peter | 56-F-EU-V-190813-S5FI057 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190813-S5FIV057A,B,C,D | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564572DOI | No | UBE |  |  | 3 |  | CRP | Deutche Bank - Swiss Domestic + IBAN | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/09/2019 | 07/02/2019 |  | 227 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-06 08:20 | Gilthorpe, Peter | 56-F-EU-V-190708-S3FI0102 |  | Yes | Y | [6 empty] | 56-F-EU-V-190708-S3FIV0102A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564572FBI | No | UBE |  |  | 3 |  | CRP | Deutche Bank - Foreign Print Pgm - Diff Bank Charges + IBAN | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/03/2019 | 07/03/2019 |  | 228 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-06 08:21 | Gilthorpe, Peter | 56- F-EU-V-190701-S3FI058 | Printer | Yes | Y | [6 empty] | 56- F-EU-V-190701-S3FIV058A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564572FRI | No | UBE |  |  | 3 |  | CRP | Deutche Bank - French Domestic Payments + IBAN | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/12/2019 | 7/3/2019 |  | 229 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-31 10:30 | Gilthorpe, Peter | 56-F-EU-V-190702-S3FI087 |  | Yes | Y | [6 empty] | 56-F-EU-V-190702-S3FIV87A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564572SPI | No | UBE |  |  | 3 |  | CRP | Deutche Bank - Spain Domestic Print Pgm + IBAN | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/01/2019 | 07/01/2019 |  | 230 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-31 10:30 | Gilthorpe, Peter | 56-F-EU-V-190701-S3FI065 | Printer | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3FIV065A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5609101 | No | APPL | BXU550998 |  | 3 |  | CRP | Leased Hardware Profit Allocations - Inquiry | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/28/2019 | 6/27/2019 |  | 231 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-04-02 06:06 | Joshi, Abhishek N | 56-F-EU-V-190626-S2FI062 | Inquiry | Yes | Y | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRAP15 | No | UBE | BXU547729 |  | 4 |  | CRP | PPV (F57PPVD) - CSV Extract - Matched | L3 Pass |  |  | TRUE | HNE2E | FALSE | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/26/2019 | 7/25/2019 |  | 232 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 07:00 | Joshi, Abhishek N | 56-F-EU-V-190724-S4FI034 |  | Yes | Y | [6 empty] | 56-F-EU-V-190724-S4FIV034A,56-F-EU-V-190724-S4FIV034B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PPVB | No | UBE |  |  | 4 |  | CRP | Generate PPV IRV Postings on Material Transactions | L3 Pass |  |  | TRUE | HNE2E | FALSE | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/26/2019 | 7/25/2019 |  | 233 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-28 05:58 | GOLGE, SERAY | 56-F-EU-V-190724-S4FI030 |  | Yes | Y | [6 empty] | 56-F-EU-V-190724-S4FIV030A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560902T | No | UBE | BXU545730 |  | 4 |  | CRP | Populate F0902TMP from SAP Text File | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Lokesh Reddy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/26/2019 | 7/25/2019 |  | 234 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 03:21 | Joshi, Abhishek N | 56-F-EU-V-190731-S4FI063 | Text | Yes | Y | [6 empty] | 56-F-EU-V-190731-S4FIV063A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564803C | No | UBE | BXU544718 |  | 3 |  | CRP | Project Actvity Report | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/3/2019 | 7/2/2019 |  | 235 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 04:39 | Joshi, Abhishek N | 56-F-EU-V-190628-S3FI031 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190628-S3FIV31A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55470412 | No | UBE |  |  | 5 |  | CRP | EDI Inbound Invoice/Match to P.O. - Target II | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete | L2 tested after Rework complete |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/26/2019 | 7/26/2019 |  | 236 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-19 05:00 | Gilthorpe, Peter | 56-F-EU-V-190726-S4FI001 | Inbound | Yes | Y |  |  | Awaiting source system data for L2 testing PG 2108 Test script added |  |  |  | 56-F-EU-V-190726-S4FIV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5603B421D | No | UBE |  |  | 1 |  | CRP | A/R Details with Aging - Country and Region | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/4/2019 | 6/4/2019 |  | 237 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-10 06:41 | BAYINDIR, AYSE | 56-F-EU-V-190522-S1FI040 |  | Yes | Y | [6 empty] | 56-F-EU-V-190522-S1FIV40A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5874R3032 | No | UBE |  |  | 4 |  |  | Stock Delivery Note - Russia - SOP - 74R | L3 Pass | 227 | Close | TRUE | HE2E |  | Transportation | Logistics | Puneet Sharma | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/23/2019 | 7/22/2019 |  | 238 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-14 08:27 | Sharma, Puneet | 56-F-EU-V-190722-S4LO003 |  | Yes |  |  |  |  | various2 |  |  | 56-F-EU-V-190722-S4LOV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRAP140 | No | UBE |  |  | 999 |  |  | DPO Report - Weighted Average Payment Terms | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 239 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:12 | Chiau, Liesbet |  | Report | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56R0047B | No | UBE |  |  | 999 |  |  | Coupa Account Master Extract - EMEA | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 240 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:12 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56R0048T | No | UBE |  |  | 4 |  | CRP | Coupa: Update Address Books Tag File | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/26/2019 | 7/25/2019 |  | 241 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-12 04:22 | Touyaa, Manuel | 56-F-EU-V-190724-S4FI021 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190724-S4FIV021A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0014 | No | UBE |  |  | 999 |  |  | Ariba Payment Terms Extract | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 242 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:12 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R561243 | No | UBE | BXU545946 |  | 4 |  | CRP | Acc Rec- All Companies | L3 Pass |  |  | TRUE | HNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/26/2019 | 07/25/2019 |  | 243 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 05:00 | Joshi, Abhishek N | 56-F-EU-V-190724-S4FI018 |  | Yes | Y | [6 empty] | 56-F-EU-V-190724-S4FIV018A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600178 | No | UBE |  |  | 4 |  | CRP | Fixed Asset Reprot | L3 Pass |  |  | TRUE | HNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT , CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/29/2019 | 7/26/2019 |  | 244 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-10 08:09 | Slaby, Libor | 56-F-EU-V-190725-S4FI037 |  | Yes | Y | [6 empty] | 56-F-EU-V-190725-S4FIV037A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564891 | No | UBE | BXU544718 |  | 3 |  | CRP | Populate project master (F564801) from Fixed Assets (F1201) | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/3/2019 | 7/2/2019 |  | 245 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 04:41 | Joshi, Abhishek N | 56-F-EU-V-190701-S3FI062 |  | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3FIV062A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P560411B | No | APPL | BXU550734 |  | 2 |  | CRP | A/P Standard Voucher Entry - B1 Rtft | L3 Pass | 168 | Closed | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | VV-19/07 - Code Reviewed by Vikas after Rework | Bargavi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/21/2019 | 6/21/2019 |  | 246 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-23 02:38 | Joshi, Abhishek N | 56-F-EU-V-190613-S2FI038 |  | Yes | Y |  |  | VV-18/07 - Rework is neded PG: 22/7 Email to Brilasoft to check if L2 completed again Seray: 23/07 missing related object, P55GL01S Seray 24/07 Track taxes error is not solved in Journal Entry Prompt form |  |  |  | 56-F-EU-V-190613-S2FIV038A,56-F-EU-V-190613-S2FIV038B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56P2P03 | No | APPL |  |  | 2 |  | CRP | A/P Voucher Journal Entry Redistribution - P2P - B1 | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 247 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-10 07:17 | Gilthorpe, Peter | 56-F-EU-V-190611-S2FI022A |  | Yes | Yes | [6 empty] | 56-F-EU-V-190611-S2FIV22A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56P2P04 | No | APPL |  |  | 5 |  | CRP | Voucher Match - BAX - P2P | L3 Pass | 158 | Ready for Testing | TRUE | HNE2E | FALSE | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | VV-29/07, Moved to Sprint 4 as per reqeust from Peter | Bargavi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 06/21/2019 | 06/20/2019 |  | 248 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-27 05:27 | Gilthorpe, Peter | 56-F-EU-V-190620-S2FI119 |  | Yes |  |  |  | PG: On hold pending fix to business function defect 215 |  |  |  | 56-F-EU-V-190620-S2FI119A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564892 | No | UBE | BXU544718 |  | 3 |  | CRP | Populate Project Master (F564801) from Work Orders (F4801) | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 249 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-08 03:41 | Joshi, Abhishek N | 56-F-EU-V-190701-S3FI001 |  | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3FIV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564893 | No | UBE | BXU544718 |  | 3 |  | CRP | Populate Project Master (F564801) from Grants (F55GL001) | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/03/2019 | 07/02/2019 |  | 250 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 04:43 | Joshi, Abhishek N | 56- F-EU-V-190701-S3FI056 |  | Yes | Y | [6 empty] | 56- F-EU-V-190701-S3FIV056A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564894 | No | UBE | BXU544718 |  | 3 |  | CRP | Populate Project Master (F564801) from BU Master (F0006) | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/4/2019 | 7/4/2019 |  | 251 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 04:43 | Joshi, Abhishek N | 56-F-EU-V-190701-S3FI074 |  | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3FIV074A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55JDRCP1 | No | UBE | BXU547856 |  | 4 |  | CRP | MILD - Receipts to JDE - JDRCPT/POJDE to Z files | L3 Pass | 249 |  | TRUE | HE2E |  | Finance AP | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT , CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/29/2019 | 7/28/2019 |  | 252 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 03:02 | Joshi, Abhishek N | 56-F-EU-V-190723-S4FI026 |  | Yes | Y | [6 empty] | 56-F-EU-V-190723-S4FIV026A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0197 | No | UBE | BXU546699 |  | 3 |  | CRP | Transfer Price Data-Inbound Processor UBE | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/4/2019 | 7/4/2019 |  | 253 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 07:31 | Joshi, Abhishek N | 56-F-EU-V-190701-S3FI078 | Inbound | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3FIV78A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0193 | No | UBE | BXU546701 |  | 3 |  | CRP | Cost Component - Data Extraction UBE | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/4/2019 | 7/3/2019 |  | 254 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 00:59 | Joshi, Abhishek N | 56-F-EU-V-190704-S3FI101 |  | Yes | Y | [6 empty] | 56-F-EU-V-190704-S3FIV101A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0981 | No | UBE | BXU548338 |  | 3 |  | CRP | FASTR PDF Format | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Robbin/Florencia | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/4/2019 | 7/3/2019 |  | 255 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 06:00 | Joshi, Abhishek N | 56-F-EU-V-190703-S3FI095 |  | Yes | Y | [6 empty] | 56-F-EU-V-190703-S3FIV095A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5603B421J | No | UBE | BXU545721 |  | 1 |  | CRP | A/R Details with Aging - Country and Region | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/4/2019 | 6/4/2019 |  | 256 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 02:58 | Joshi, Abhishek N | 56-F-EU-V-190527-S1FI062 |  | Yes | Y | [6 empty] | 56-F-EU-V-190527-S1FIV62A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900301 | No | APPL |  |  | 3 |  |  | FCA YTD Application | L3 Not Required |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/1/2019 | 7/1/2019 |  | 257 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-09 04:01 | Destrebecq, Eric | 56-F-EU-V-190701-S3LO004 |  | Yes | Y |  |  | On Hold N/A for EMEA | na |  |  | NA | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5603LBD | No | APPL | BXU545712 |  | 6 |  | CRP | EDI Cash Receipts File LBD Exceptions | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete | Can be tested indipendantly scrum 25/09 |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 9/3/2019 | 8/30/2019 |  | 258 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 02:23 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI019 |  | Yes | Yes |  |  | Waiting to have integration before testing |  |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5603067 | No | UBE | BXU545712 |  | 6 |  |  | 3PL Cash Receipts Pre Processor | L3 Not Required |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Not required | Waiting to have integration before testing |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 9/3/2019 | 9/2/2019 |  | 259 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 01:43 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI053 |  | Yes | Yes |  |  | to be tested in CRP |  |  |  | 56-F-EU-V-190827-S6FIV053A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56912A | No | UBE | BXU544752 |  | 4 |  | CRP | Indexed Allocation computation Update | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/29/2019 | 7/26/2019 |  | 260 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 04:44 | Joshi, Abhishek N | 56-F-EU-V-190724-S4FI035 |  | Yes | Y | [6 empty] | 56-F-EU-V-190724-S4FIV035A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56912B | No | UBE | BXU544752 |  | 4 |  | CRP | Variable Allocations Update/Split Out | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/29/2019 | 7/26/2019 |  | 261 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 08:15 | Joshi, Abhishek N | 56-F-EU-V-190725-S4FI036 |  | Yes | Y | [6 empty] | 56-F-EU-V-190725-S4FIV036A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5612701 | No | UBE | BXU545947 |  | 2 |  | CRP | Integrity Report - FA to GL/ GL to FA for AA and D1 ledgers | L3 Pass |  |  | TRUE | HNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/26/2019 | 6/25/2019 |  | 262 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 23:43 | Joshi, Abhishek N | 56-F-EU-V-190625-S2FI139 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190625-S2FIV139A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560311A | No | UBE | BXU549993 |  | 1 |  | CRP | Extraction Program for Netting | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/4/2019 | 6/4/2019 |  | 263 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 04:53 | Joshi, Abhishek N | 56-F-EU-V-190531-S1FI072 |  | Yes | Y | [6 empty] | 56-F-EU-V-190531-S1FI072A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5604425R | No | UBE | BXU549997 |  | 5 |  | CRP | AP FX Realised - Russia | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 08/16/2019 | 08/14/2019 |  | 264 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 05:49 | Joshi, Abhishek N | 56-F-EU-V-190816-S5FI103 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190816-S5FIV103A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641046 | No | UBE | 1230484 |  | 4 |  | CRP | Restamp Item Branch Finance data - Non B4ONE | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/29/2019 | 7/28/2019 |  | 265 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 08:24 | Joshi, Abhishek N | 56-F-EU-V-190731-S4FI064 |  | Yes | Y | [6 empty] | 56-F-EU-V-190731-S4FIV064A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P55JDRCS | No | APPL | BXU545606 |  | 3 |  | CRP | Set-up info for Interfaces to JDE PO & Receipts | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/2/2019 | 6/28/2019 |  | 266 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-23 02:42 | Joshi, Abhishek N | 56-F-EU-V-190624-S3FI014 | Interface | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5643FG1 | No | APPL |  |  | 5 |  | CRP | Fieldglass to JDE Revision | L3 Pass | 261 | WIP | TRUE | HNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete | L2 Testing is completed after rework |  |  | Terry Greenard / Vikas Verma |  | TANKUT , CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/29/2019 | 7/26/2019 |  | 267 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-07 05:14 | GOLGE, SERAY | 56-F-EU-V-190729-S4FI001 | Revision | Yes | Y | [6 empty] | 56-F-EU-V-190729-S4FIV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5643FG2 | No | APPL |  |  | 4 |  | CRP | Fieldglass to JDE Account Configuration | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/29/2019 | 7/26/2019 |  | 268 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-23 08:51 | GOLGE, SERAY | 56-F-EU-V-190725-S4FI034 |  | Yes | Y | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5643FGC | No | APPL | BXU547429 |  | 4 |  | CRP | Fieldglass COA Upload | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/29/2019 | 07/28/2019 |  | 269 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 23:33 | Joshi, Abhishek N | 56-F-EU-V-190726-S4FI018 | Upload | Yes | Y | [6 empty] | 56-F-EU-V-190726-S4FIV018A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5603B11 | No | APPL | BXU547424 |  | 6 |  | CRP | Standard Invoice Entry - Iframe Depends on Defect #528: Siebel is successfully opening the JDE i-frames but it is opening JDE 8.12 instead of JDE PPD 9.2. | L3 Pass | 528 | Depends on Defect #528: Siebel is successfully opening the JDE i-frames but it is opening JDE 8.12 instead of JDE PPD 9.2. | TRUE | HNE2E | FALSE | Finance AR | Finance | Ayse Bayindir | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 09/03/2019 | 09/02/2019 |  | 270 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 23:20 | Joshi, Abhishek N | 56-F-EU-V-190813-S5FI059 |  | Yes | [7 empty] | 56-F-EU-V-190813-S5FIV059A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56R0030 | No | UBE |  |  | 3 |  |  | Process Vendor Bank Accounts Requests - EMEA | L3 Pass |  |  | TRUE | L |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/1/2019 | 7/1/2019 |  | 271 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-15 03:22 | Barrera Perez, Carlos Manuel | 56-F-EU-V-190628-S3MD004 |  | Yes | Y | [6 empty] | 56-F-EU-V-190628-S3MDV004A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0030 | No | UBE |  |  | 3 |  |  | Process Vendor Bank Accounts Requests | L3 Not Required |  |  | FALSE | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/1/2019 | 7/1/2019 |  | 272 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:13 | Chiau, Liesbet | 56-F-EU-V-190628-S3MD008 | SECURE | Yes | [7 empty] | 56-F-EU-V-190628-S3MDV08A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5600019 | No | APPL | BXU545335 |  | 3 |  | CRP | Principal Commissionaire Related Doc Inquiry | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/4/2019 | 7/4/2019 |  | 273 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 23:17 | Joshi, Abhishek N | 56-F-EU-V-190702-S3FI083 | Inquiry | Yes | Y | [6 empty] | 56-F-EU-V-190702-S3FIV083A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5604100 | No | UBE |  |  | 1 |  | CRP | UK Payment Practices and Performance Report | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/3/2019 | 6/3/2019 |  | 274 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-16 05:55 | Touyaa, Manuel | 56-F-EU-V-190527-S1FI052 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190527-S1FIV052A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R57AR003 | No | UBE | BXU545819 |  | 3 |  | CRP | Receipt Sweep Commisionaire to Principal | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/4/2019 | 7/4/2019 |  | 275 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 08:37 | Joshi, Abhishek N | 56-F-EU-V-190704-S3FI001 |  | Yes | [7 empty] | 56-F-EU-V-190704-S3FIV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRGL111 | No | UBE | BXU545331 |  | 2 |  | CRP | European Sales/Purchase Listing | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Vijey Sesha | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/25/2019 | 6/25/2019 |  | 276 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 09:30 | Joshi, Abhishek N | 56-F-EU-V-190625-S2FI001 |  | Yes | [7 empty] | 56-F-EU-V-190625-S2FIV01A,56-F-EU-V-190625-S2FIV01B,56-F-EU-V-190625-S2FIV01C | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRCB14D | No | UBE | BXU545331 |  | 5 |  | CRP | Manual GL Entry Report - S-OX requirement (Enhanced) | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | CIZMECI,TANKUT |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/16/2019 | 8/14/2019 |  | 277 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 09:29 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI045 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190812-S5FIV045A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58P03B1 | No | UBE | BXU545763 |  | 5 |  | CRP | VAT Sales Register - POL - 58 | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Lokesh Reddy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | CIZMECI,TANKUT |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/16/2019 | 8/14/2019 |  | 278 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 09:01 | Joshi, Abhishek N | 56-F-EU-V-190814-S5FI093 |  | Yes | Y | [6 empty] | 56-F-EU-V-190814-S5FIV093A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56P03B1 | No | UBE | BXU545762 |  | 5 |  | CRP | VAT Sales Register - POL - 56 | L3 Pass | 307 |  | TRUE | HNE2E |  | Finance GL | Finance | Ravi Thapa | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/16/2019 | 8/14/2019 |  | 279 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 11:01 | Joshi, Abhishek N | 56-F-EU-V-190813-S5FI050 |  | Yes | Y | [6 empty] | 56-F-EU-V-190813-S5FIV050A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R57042002 | No | UBE | BXU549972 |  | 5 |  | CRP | Automatically match logged vouchers to open GRN's | L3 Pass | 215 | Ready for Testing | TRUE | HE2E |  | Finance AP | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/28/2019 | 6/27/2019 |  | 280 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 06:40 | Joshi, Abhishek N | 56-F-EU-V-190701-S3FI064 |  | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3FIV64A, 56-F-EU-V-190701-S3FIV64B, 56-F-EU-V-190701-S3FIV64C. 56-F-EU-V-190701-S3FIV64D, 56-F-EU-V-190701-S3FIV64E, 56-F-EU-V-190701-S3FIV64F, 56-F-EU-V-190701-S3FIV64G, 56-F-EU-V-190701-S3FIV64H | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900090 | No | APPL | BXU547240 |  | 4 |  | CRP | Override Currency Rules | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Francisco Alvargonzalez | L2 Pass / Complete | We mark this as L2 pass as per revised UTS and will re- verify changes done after cut off date in R1 and R2 |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/30/2019 | 7/29/2019 |  | 281 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 05:05 | Joshi, Abhishek N | 56-F-EU-V-190725-S4FI038 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5503B01D | No | UBE | BXU545340 |  | 1 |  | CRP | Receipt Stats by invoice year | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/4/2019 | 6/4/2019 |  | 282 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 06:04 | Joshi, Abhishek N | 56-F-EU-V-190603-S1FI022 |  | Yes | Y | [6 empty] | 56-F-EU-V-190603-S1FIV022A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRAP12 | No | UBE |  |  | 4 |  | CRP | PPV Actuals | L3 Pass |  |  | TRUE | HNE2E | FALSE | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/30/2019 | 7/29/2019 |  | 283 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-28 05:58 | GOLGE, SERAY | 56-F-EU-V-190723-S4FI027 |  | Yes | Y | [6 empty] | 56-F-EU-V-190723-S4FIV027A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5909303 | No | APPL | BXU548275 |  | 4 |  | CRP | Correct Hyperion Aplication Rounding Issue | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Manuel Touyaa | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT , CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/30/2019 | 7/29/2019 |  | 284 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 05:14 | Joshi, Abhishek N | 56-F-EU-V-190729-S4FI048 |  | Yes | Y | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5909300 | No | APPL | BXU550726 |  | 4 |  | CRP | Work With Hyperion Interface Constants | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Manuel Touyaa | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT , CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/30/2019 | 7/29/2019 |  | 285 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-23 02:07 | Joshi, Abhishek N | 56-F-EU-V-190729-S4FI049 | Constant | Yes | Y | [6 empty] | 56-F-EU-V-190729-S4FIV049A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5909301 | No | APPL | BXU550727 |  | 4 |  | CRP | New Ledger Type Mapping Revision | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Manuel Touyaa | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/30/2019 | 7/29/2019 |  | 286 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-23 02:26 | Joshi, Abhishek N |  | Revision | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5909211 | No | APPL | BXU550725 |  | 4 |  | CRP | Work With Hyperion Account Ledger | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Manuel Touyaa | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT , CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/30/2019 | 7/30/2019 |  | 287 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-23 02:00 | Joshi, Abhishek N | 56-F-EU-V-190730-S4FI001 |  | Yes | Y | [6 empty] | 56-F-EU-V-190730-S4FIV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5909212 | No | APPL | BXU548277 |  | 4 |  | CRP | Work With Hyperion Account Balance | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT , CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/30/2019 | 7/29/2019 |  | 288 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-20 06:16 | Joshi, Abhishek N | 56-F-EU-V-190729-S4FI056 |  | Yes | Y | [6 empty] | 56-F-EU-V-190729-S4FIV056A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600012 | No | UBE | BXU545611 |  | 4 | 4 | CRP | Validatiing Records in F0030 & F570030 | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/30/2019 | 07/29/2019 |  | 289 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 03:47 | Joshi, Abhishek N | 56-F-EU-V-190729-S4FI019 |  | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FREX63N | No | UBE | BXU547226 |  | 5 |  | CRP | AR to GL Integrity by GL Class and Account ID | L3 Pass | 306 | Confirmed that it is data issue. Closed | TRUE | LNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/16/2019 | 8/15/2019 |  | 290 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 07:28 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI037 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV037A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55R1001 | No | UBE | BXU547598 |  | 5 |  | CRP | F0902 Records with Subledger Consolidation | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/16/2019 | 8/15/2019 |  | 291 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 03:35 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI039 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV039A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0421 | No | UBE |  |  | 5 |  | CRP | JDE to Genpact ESM - Duplicate Audit Tool Report | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/19/2019 | 8/19/2019 |  | 292 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-31 12:00 | Touyaa, Manuel | 56-F-EU-V-190814-S5FI071 | Audit / Report | Yes | Yes | [6 empty] | 56-F-EU-V-190814-S5FIV071A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRCB14D | No | UBE | BXU545342 |  | 1 |  | CRP | Manual GL Entry Report - S-OX requirement | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/6/2019 | 6/6/2019 |  | 293 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 10:44 | Joshi, Abhishek N | 56-F-EU-V-190603-S1FI075 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190603-S1FI075A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0191 | No | UBE | BXU546937 |  | 3 |  | CRP | Cost Component - Inbound Processor | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/10/2019 | 07/03/2019 |  | 294 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 10:06 | Joshi, Abhishek N | 56- F-EU-V-190703-S3FI001 | Inbound | Yes | Y | [6 empty] | 56- F-EU-V-190703-S3FIV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0980 | No | UBE | BXU546937, BXU548725 |  | 3 |  | CRP | FASTR Row/Column Template | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Robbin/Florencia | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/02/2019 | 07/02/2019 |  | 295 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 01:04 | Joshi, Abhishek N | 56-F-EU-V-190702-S3FI085 |  | Yes | Y | [6 empty] | 56-F-EU-V-190702-S3FIV085A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P590980 | No | APPL | BXU546937 |  | 3 |  | CRP | Work With FASTR Report Configuration | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Robbin/Florencia | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/4/2019 | 7/4/2019 |  | 296 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 05:17 | Joshi, Abhishek N | 56-F-EU-V-190702-S3FI088 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190702-S3FIV88A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P590981 | No | APPL | BXU546937 |  | 3 |  | CRP | Select/Search Formula Name | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Robbin/Florencia | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/04/2019 | 07/03/2019 |  | 297 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 04:21 | Joshi, Abhishek N | 56-F-EU-V-190701-S3FI067 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P590982 | No | APPL | BXU546937 |  | 3 |  | CRP | FASTR Format Name Search and Select | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Robbin/Florencia | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/5/2019 | 7/5/2019 |  | 298 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 04:22 | Joshi, Abhishek N | 56-F-EU-V-190703-S3FI097 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5704572CH | No | UBE |  |  | 3 |  | CRP | Deutche Bank - Swiss Domestic - ESRN | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/5/2019 | 7/4/2019 |  | 299 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-06 08:20 | Gilthorpe, Peter | 56-F-EU-V-190628-S3FI035 |  | Yes | Y | [6 empty] | 56-F-EU-V-190628-S3FIV35A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5804001 | No | UBE |  |  | 5 |  | CRP | Generate Supplier Balance A/P - Russia | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/19/2019 | 8/18/2019 |  | 300 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-07 05:15 | GOLGE, SERAY | 56-F-EU-V-190814-S5FI078 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190814-S5FIV078A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58IC300 | No | UBE | BXU545523 |  | 4 |  | CRP | PII report IC300 - Load from JDE to hyperion | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Libor Slaby | L2 Pass / Complete | Executed with change in FYfrom 17 to 18 to get expected data |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/31/2019 | 7/30/2019 |  | 301 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 04:02 | Joshi, Abhishek N | 56-F-EU-V-190725-S4FI039 | Report | Yes | Y |  |  | R1 re-test will be needed. |  |  |  | 56-F-EU-V-190725-S4FIV039A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56R4501 | No | UBE | BXU549971 |  | 3 |  | CRP | Automatic Payments RUS - Load F74R4500 from F04572 | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/4/2019 | 7/5/2019 |  | 302 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 03:30 | Joshi, Abhishek N | 56-F-EU-V-190704-S3FI105 |  | Yes | Y | [6 empty] | 56-F-EU-V-190704-S3FIV105A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58R911RV | No | UBE | BXU545364 |  | 5 |  | CRP | Russian CBR Revaluation | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/19/2019 | 8/18/2019 |  | 303 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 09:09 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI024 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV024A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P560922R | No | APPL | BXU547427 |  | 4 |  | CRP | Maintain Inventory to GL Integrity Reconciled Items | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/1/2019 | 7/31/2019 |  | 304 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 23:25 | Joshi, Abhishek N | 56-F-EU-V-190725-S4FI042 | Maintenance | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56GMECP | No | UBE | BXU546938 |  | 999 |  | N/A | CPA & Project Information Transfer to GME | Obsolete |  |  | TRUE | LNE2E |  | Finance GL | Finance | Sriram Krithivasan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | VV-01/08 - Sprint chagned to 999, as object is obsoleted | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/5/2019 | 7/5/2019 |  | 305 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 10:55 | Joshi, Abhishek N | 56-F-EU-V-190701-S3FI002 |  | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3FIV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R555110 | No | UBE | BXU547224 |  | 4 |  | CRP | Fixed Assets Act of Acceptance - OC-1 | L3 Pass |  |  | TRUE | HNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT , CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/31/2019 | 7/30/2019 |  | 306 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 05:17 | Joshi, Abhishek N | 56-F-EU-V-190729-S4FI050 |  | Yes | Y | [6 empty] | 56-F-EU-V-190729-S4FIV050A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5603B426 | No | UBE |  |  | 2 |  | CRP | A/R Unrealized Gain/Loss Report | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/25/2019 | 6/24/2019 |  | 307 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-05 11:08 | Frade Dolesor, Constanza | 56-F-EU-V-190617-S2FI044 | Report | Yes |  |  |  | Retrofit not required |  |  |  | 56-F-EU-V-190617-S2FIV044A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5603B426R | No | UBE | BXU549992 |  | 2 |  | CRP | AR FX Realised - Russia | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/26/2019 | 6/25/2019 |  | 308 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 05:41 | Joshi, Abhishek N | 56-F-EU-V-190611-S2FI027 |  | Yes | [7 empty] | 56-F-EU-V-190611-S2FIV27A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL105 | No | UBE | BXU547570 |  | 5 |  | CRP | GRANT/PROJECT SPENT BY RESPONSIBLE | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/19/2019 | 8/16/2019 |  | 309 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 07:34 | Joshi, Abhishek N | 56-F-EU-V-190814-S5FI096 |  | Yes | Y | [6 empty] | 56-F-EU-V-190814-S5FIV096A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FREX19A | No | UBE | BXU547225 |  | 5 |  | CRP | AP Logging Report Reconciled to GL - MO | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | CIZMECI,TANKUT |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/19/2019 | 8/16/2019 |  | 310 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 07:24 | Joshi, Abhishek N | 56-F-EU-V-190814-S5FI091 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190814-S5FIV091A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R57042P2P | No | UBE | BXU548332 |  | 3 |  | CRP | AVMP Mixed Invoices | L3 Pass | 158 | Ready for Testing | TRUE | HE2E |  | Finance AP | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/28/2019 | 6/27/2019 |  | 311 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 05:18 | Joshi, Abhishek N | 56-F-EU-V-190701-S3FI071 |  | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3FIV71A, 56-F-EU-V-190701-S3FIV71B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56GL001 | No | APPL | BXU547435 |  | 4 |  | CRP | Maintenance of Grants and Projects | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/31/2019 | 7/30/2019 |  | 312 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 00:29 | Joshi, Abhishek N | 56-F-EU-V-190730-S4FI058 | Maintenance | Yes | Y | [6 empty] | 56-F-EU-V-190730-S4FIV058A, 56-F-EU-V-190730-S4FIV058B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL0032 | No | UBE | BXU546928 |  | 999 |  |  | Polish Statutory Profit and Loss Statement User confirmed that this object is not used. So updated as obselete | Obsolete |  |  | FALSE | LNE2E |  | Finance GL | Finance | Lokesh Reddy |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 313 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 11:05 | Joshi, Abhishek N | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL0043 | No | UBE | BXU546946 |  | 5 |  | CRP | Polish Balance Sheet | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | CIZMECI,TANKUT |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/19/2019 | 8/16/2019 |  | 314 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 11:14 | Joshi, Abhishek N | 56-F-EU-V-190814-S5FI086 |  | Yes | Y | [6 empty] | 56-F-EU-V-190814-S5FIV086A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5774291 | No | APPL | BXU547414 |  | 1 |  | CRP | Landed Cost Selection - COMM - 43 - Baxter | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/7/2019 | 6/7/2019 |  | 315 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 00:56 | Joshi, Abhishek N | 56-F-EU-V-190515-S1FI005 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190515-S1FI005A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564572RU | No | UBE | BXU549995 |  | 6 | 5 | CRP | Deutche Bank - Russian Payment Print Program (Frgn/Dmst) | L3 Pass | 225 | Closed | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT , CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/05/2019 | 07/04/2019 |  | 316 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 05:51 | Joshi, Abhishek N | 56- F-EU-V-190701-S3FI061 | Printer | Yes | Y |  |  | Missing object R564572RUC which is called in the event of missing data in the payment data |  |  |  | 56- F-EU-V-190701-S3FI061 | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5512G80 | No | UBE | BXU550369 |  | 2 |  | CRP | Automatic Creation of Assets | L3 Pass | 169 | Closed | TRUE | HNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/26/2019 | 6/25/2019 |  | 317 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 05:15 | Joshi, Abhishek N | 56-F-EU-V-190617-S2FI047 |  | Yes | Y |  |  | Retrofit not required |  |  |  | 56-F-EU-V-190617-S2FIV047A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL0044 | No | UBE | BXU546946 |  | 5 |  | CRP | Profit and Loss Statement | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/19/2019 | 8/16/2019 |  | 318 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 11:16 | Joshi, Abhishek N | 56-F-EU-V-190813-S5FI060 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190813-S5FIV060A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R573B500X | No | UBE | BXU545541 |  | 4 |  | CRP | Statement Notification Refresh - Customized | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/31/2019 | 07/30/2019 |  | 319 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 05:32 | Joshi, Abhishek N | 56-F-EU-V-190731-S4FI067 |  | Yes | Y | [6 empty] | 56-F-EU-V-190731-S4FIV067A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74R5120 | No | UBE | BXU544969 |  | 3 |  | CRP | Fixed Assets Cards - RUS - 12 - 74R | L3 Pass |  |  | TRUE | HNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/8/2019 | 7/7/2019 |  | 320 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 06:16 | Joshi, Abhishek N | 56-F-EU-V-190704-S3FI103 |  | Yes | Y | [6 empty] | 56-F-EU-V-190704-S3FIV103A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5594121 | No | UBE | BXU547061 |  | 5 |  | CRP | AP Account Balance Report | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/19/2019 | 8/16/2019 |  | 321 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 06:44 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI046 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV046A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74R0330 | No | UBE | BXU545455 |  | 3 |  | CRP | VAT Sales Book - RUS - 03B - 74R | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/08/2019 | 07/04/2019 |  | 322 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 08:05 | Joshi, Abhishek N | 56-F-EU-V-190701-S3FI060 |  | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3FIV60A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL0055 | No | UBE | BXU546947 |  | 5 |  | CRP | OPEX Report Poland | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/19/2019 | 8/16/2019 |  | 323 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 02:59 | Joshi, Abhishek N | 56-F-EU-V-190813-S5FI049 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190813-S5FIV049A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRAP180 | No | UBE | BXU547229 |  | 5 |  | CRP | As of AP Logging | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Saurabh Gupta | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/19/2019 | 8/16/2019 |  | 324 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 07:09 | Joshi, Abhishek N | 56-F-EU-V-190813-S5FI051 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190813-S5FIV051A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74P4120 | No | UBE | BXU545373 |  | 3 |  | CRP | Inventory Transaction Journal | L3 Pass |  |  | TRUE | LNE2E |  | Localization | Finance | Vijey sesha | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/9/2019 | 7/8/2019 |  | 325 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 08:03 | Joshi, Abhishek N | 56-F-EU-V-190705-S3FI119 |  | Yes | Y | [6 empty] | 56-F-EU-V-190705-S3FIV119A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5842092 | No | UBE | BXU546823 |  | 5 |  | CRP | GIT - In-Transit Extract -Work File Build | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/19/2019 | 8/18/2019 |  | 326 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 03:58 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI041 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV041A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL0001 | No | UBE | BXU545887 |  | 4 |  | CRP | Integrity Report Sales - A/R (From F4211) | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/31/2019 | 7/31/2019 |  | 327 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 04:40 | Joshi, Abhishek N | 56-F-EU-V-190731-S4FI001 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190731-S4FIV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL0002 | No | UBE | BXU545884 |  | 4 |  | CRP | Integrity Report Sales - A/R (From F03B11) | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/31/2019 | 7/30/2019 |  | 328 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 04:42 | Joshi, Abhishek N | 56-F-EU-V-190730-S4FI059 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190730-S4FIV059A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5842093 | No | UBE | BXU546823 |  | 5 |  | CRP | GIT - In-Transit Extract - for PII | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/19/2019 | 8/13/2019 |  | 329 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 08:11 | Joshi, Abhishek N | 56-F-EU-V-190813-S5FI053 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190813-S5FIV053A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R580018RV | No | UBE | BXU546822 |  | 5 |  | CRP | Czech VAT Report @ CBR Rate | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Lokesh Reddy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/20/2019 | 8/20/2019 |  | 330 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 03:42 | Joshi, Abhishek N | 56-F-EU-V-190814-S5FI072 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190814-S5FIV072A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74B100 | No | UBE | BXU545369 |  | 3 |  | CRP | Monthly VAT Payable report - Belgium | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Vijey Sesha | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/05/2019 | 07/03/2019 |  | 331 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 06:09 | Joshi, Abhishek N | 56-F-EU-V-190628-S3FI047 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190628-S3FIV047A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74B110 | No | UBE | BXU545369 |  | 3 |  | CRP | Monthly VAT Recoverable report - Belgium | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Vijey Sesha | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/5/2019 | 7/4/2019 |  | 332 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 06:11 | Joshi, Abhishek N | 56-F-EU-V-190703-S3FI096 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190703-S3FIV096A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5674B110 | No | UBE | BXU546726 |  | 3 |  | CRP | Monthly VAT Recoverable report - Belgium - Custom | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Nithya Ramachandran | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/4/2019 | 7/5/2019 |  | 333 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 03:34 | Joshi, Abhishek N | 56-F-EU-V-190701-S3FI080 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3FIV080A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P560901 | No | APPL | BXU544659 |  | 4 |  |  | Account Reconciliation | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/31/2019 | 07/30/2019 |  | 334 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-05 05:57 | Joshi, Abhishek N | 56-F-EU-V-190731-S4FI061 |  | Yes | Y | [6 empty] | 56-F-EU-V-190731-S4FIV061A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5874P0410 | No | UBE | BXU545461 |  | 3 |  | CRP | VAT Purchase Domestic Register - POL - 04 - 58 | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Nithya Ramachandran | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/5/2019 | 7/4/2019 |  | 335 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 08:45 | Joshi, Abhishek N | 56-F-EU-V-190705-S3FI117 |  | Yes | Y |  |  | Std PO has attached T74P0410 and there will be net changes in PO T74P0410 from Pd812 to Dv920 as The PO values are being used in UBE coding,So created copy of std T74P0410 in DV812 and brougt PAR and restored in DV920 |  |  |  | 56-F-EU-V-190705-S3FIV117A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564072EX | No | UBE | BXU546033 |  | 4 |  | CRP | Extract Pricing Data to CSV | L3 Pass | 238 | Closed | TRUE | LNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/1/2019 | 7/31/2019 |  | 336 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-08 01:01 | Joshi, Abhishek N | 56-F-EU-V-190725-S4FI040 |  | Yes | Y | [6 empty] | 56-F-EU-V-190725-S4FIV040A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R555130 | No | UBE | BXU547233 |  | 4 |  | CRP | Fixed Assets Act of Disposal - OC-4a | L3 Pass |  |  | TRUE | HNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/1/2019 | 8/1/2019 |  | 337 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 05:20 | Joshi, Abhishek N | 56-F-EU-V-190725-S4FI043 |  | Yes | Y | [6 empty] | 56-F-EU-V-190725-S4FIV043A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5704601 | No | UBE | BXU549973 |  | 5 |  | CRP | Suspected Duplicate Payments | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/20/2019 | 8/19/2019 |  | 338 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 06:45 | Joshi, Abhishek N | 56-F-EU-V-190814-S5FI079 |  | Yes | Y | [6 empty] | 56-F-EU-V-190814-S5FIV079A,B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRAP09 | No | UBE | BXU547235 |  | 5 |  | CRP | Goods Received not Vouchered | L3 Pass | 304 |  | TRUE | LNE2E |  | Finance AP | Finance | Saurabh Gupta | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/20/19 | 8/19/19 |  | 339 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 06:51 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI025 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5FIV025A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74ZS049 | no | UBE | BXU545393 |  | 3 |  | CRP | Localizace CZ - Tax Summary Report | L3 Pass |  | 56-F-EU-V-190703-S3FIV098A | TRUE | HNE2E |  | Localization | Finance | Nithya Ramachandran | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/9/2019 | 7/8/2019 |  | 340 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 08:03 | Joshi, Abhishek N | 56-F-EU-V-190703-S3FI098 | Report | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5800411 | No | UBE | BXU545020 |  | 5 |  | CRP | Voucher/Credit Notes | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/20/2019 | 8/19/2019 |  | 341 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 08:39 | Joshi, Abhishek N | 56-F-EU-V-190814-S5FI097 |  | Yes | Y | [6 empty] | 56-F-EU-V-190814-S5FIV097A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641026 | No | UBE |  |  | 4 |  | CRP | Restamp Item Branch Finance data | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/1/2019 | 7/31/2019 |  | 342 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-25 07:33 | Slaby, Libor | 56-F-EU-V-190729-S4FI051 |  | Yes | Y | [6 empty] | 56-F-EU-V-190729-S4FIV051A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRAP19 | No | UBE | BXU550728 |  | 5 |  | CRP | Open AP - Summary Doc level | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Saurabh Gupta | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/20/2019 | 8/19/2019 |  | 343 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-23 02:28 | Joshi, Abhishek N | 56-F-EU-V-190819-S5FI110 |  | Yes | Y | [6 empty] | 56-F-EU-V-190819-S5FIV110A, 56-F-EU-V-190819-S5FIV110B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5603B50NR | No | UBE |  |  | 999 |  |  | CZ Natural Rebates Autocash F03B13Z1 adjust | Obsolete | [5 empty] | Finance AR | Finance | Francisco Alvargonzalez |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 344 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:12 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PYRGL02 | No | UBE | BXU546690 |  | 1 |  | CRP | Interface Arinso Payroll to JDE | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Lokesh Reddy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/6/2019 | 6/6/2019 |  | 345 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 03:12 | Joshi, Abhishek N | 56-F-EU-V-190530-S1FI015 | Interface | Yes | Y | [6 empty] | 56-F-EU-V-190530-S1FIV015A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PYRGL01 | No | UBE | BXU546690 |  | 1 |  | CRP | Arinso Payroll GL F0911Z1 record creation | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Lokesh Reddy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/6/2019 | 6/6/2019 |  | 346 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 03:08 | Joshi, Abhishek N | 56-F-EU-V-190531-S1FI192 |  | Yes | Y | [6 empty] | 56-F-EU-V-190531-S1FIV192A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PYRGL03 | No | UBE | BXU546690 |  | 1 |  | CRP | ARINSO Payroll text import | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Lokesh Reddy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/6/2019 | 6/6/2019 |  | 347 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 03:15 | Joshi, Abhishek N | 56-F-EU-V-190530-S1FI182 | Text | Yes | Y | [6 empty] | 56-F-EU-V-190530-S1FIV182A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642S01 | No | APPL | BXU547490, BXU547491 |  | 3 |  | CRP | Maintain Deemed Generation Flag SO01 | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/5/2019 | 7/4/2019 |  | 348 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 00:40 | Joshi, Abhishek N | 56-F-EU-V-190701-S3FI075 | Maintenance | Yes | Y | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRGL125 | No | UBE | BXU546188 |  | 5 |  | CRP | VAT Report A/P & A/R Details | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/20/2019 | 8/20/2019 |  | 349 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 09:45 | Joshi, Abhishek N | 56-F-EU-V-190820-S5FI125 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190820-S5FIV125A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564801 | No | APPL | BXU544718 |  | 3 |  | CRP | Maintain Project Master Table | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/25/19 | 6/25/19 |  | 350 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 04:11 | Joshi, Abhishek N | 56-F-EU-V-190628-S3FI045 | Maintenance | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564802 | No | APPL | BXU544718 |  | 3 |  | CRP | Maintain Engineering Rates | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/28/2019 | 6/28/2019 |  | 351 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 04:15 | Joshi, Abhishek N | 56-F-EU-V-190628-S3FI043 | Maintenance | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564803 | No | APPL | BXU544718 |  | 3 |  | CRP | Maintain Project Activity Details | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/28/2019 | 6/27/2019 |  | 352 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 04:16 | Joshi, Abhishek N | 56-F-EU-V-260619-S3FI018 | Maintenance | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564801EX | No | UBE | BXU544718 |  | 3 |  | CRP | Export Project Master to CSV | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/5/2019 | 7/4/2019 |  | 353 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 04:35 | Joshi, Abhishek N | 56-F-EU-V-190704-S3FI102 | Export | Yes | Y | [6 empty] | 56-F-EU-V-190704-S3FIV102A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5612LHW1 | No | UBE | BXU545944, BXU545949 |  | 2 |  | CRP | Extract F4211 Leased Hardware Moves | L3 Pass |  |  | TRUE | HE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 06/26/2019 | 06/27/2019 |  | 354 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 23:50 | Joshi, Abhishek N | 56- F-EU-V-190618-S2FI049 |  | Yes | Yes |  |  | Object dependant on R561201Z1I for which a defect was raised |  |  |  | 56- F-EU-V-190618-S2FIV49A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5612LHW2 | No | UBE | BXU545949 |  | 2 |  | CRP | Extract F4111 Leased Hardware returns into F5612LHW | L3 Pass |  |  | TRUE | HE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 355 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 23:57 | Joshi, Abhishek N | 56-F-EU-V-190612-S2FI003 |  | Yes | Y |  |  | Object dependant on R561201Z1I for which a defect was raised |  |  |  | 56-F-EU-V-190612-S2FIV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564803 | No | UBE | BXU544718 |  | 3 |  | CRP | Import Project Activity Details | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/5/2019 | 7/5/2019 |  | 356 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 04:39 | Joshi, Abhishek N | 56-F-EU-V-190703-S3FI094 |  | Yes | Y | [6 empty] | 56-F-EU-V-190703-S3FIV094A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564803R | No | UBE | BXU544718 |  | 3 |  | CRP | Revalidate Project Activity Details | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/5/2019 | 7/8/2019 |  | 357 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 05:53 | Joshi, Abhishek N | 56-F-EU-V-190708-S3FI001 |  | Yes | Y | [6 empty] | 56-F-EU-V-190708-S3FIV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R57FRAP12 | No | UBE |  |  | 4 |  | CRP | PPV Driver Report - Populate WorkTable | L3 Pass |  |  | TRUE | HNE2E | FALSE | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/1/2019 | 7/31/2019 |  | 358 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-28 05:58 | GOLGE, SERAY | 56-F-EU-V-190731-S4FI068 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190731-S4FIV068A, 56-F-EU-V-190731-S4FIV068B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564810 | No | UBE | BXU544718 |  | 3 |  | CRP | Generate G/L Journals for Project Activity | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/08/2019 | 07/05/2019 |  | 359 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 04:40 | Joshi, Abhishek N | 56-F-EU-V-190705-S3FI122 |  | Yes | Y | [6 empty] | 56-F-EU-V-190705-S3FIV122A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564209 | No | UBE | BXU546729 |  | 4 |  | CRP | Held Order Report | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/31/2019 | 7/30/2019 |  | 360 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-08 01:26 | Joshi, Abhishek N | 56-F-EU-V-190731-S4FI072 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190731-S4FI072A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5712411A | No | UBE | BXU544971 |  | 4 |  | CRP | Depreciation Schedule | L3 Pass |  |  | TRUE | HNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 08/01/19 | 08/01/19 |  | 361 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 05:26 | Joshi, Abhishek N | 56-F-EU-V-190801-S4FI001 |  | Yes | [7 empty] | 56-F-EU-V-190801-S4FIV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5603001 | No | UBE | BXU545705 |  | 4 |  | CRP | Annual Customer Credit Review Report | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/01/2019 | 7/31/2019 |  | 362 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 01:17 | Joshi, Abhishek N | 56-F-EU-V-190731-S4FI060 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190731-S4FIV060A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5617251 | No | UBE | BXU545948 |  | 4 |  | CRP | Report for cycle count variance of Fixed Assets | L3 Pass |  |  | TRUE | HNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  | 07/31/2019 | 08/01/2019 | 363 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-08 04:06 | Joshi, Abhishek N | 56-F-EU-V-190801-S4FI008 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190801-S4FIV008A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564202 | no | UBE | BXU547103, BXU547104 |  | 5 |  | CRP | VAT Sequential Numbering Integrity | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/20/2019 | 8/20/2019 |  | 364 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 08:11 | Joshi, Abhishek N | 56-F-EU-V-190814-S5FI092 |  | Yes | Y | [6 empty] | 56-F-EU-V-190814-S5FIV092A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5547041 | No | UBE | BXU547732, BXU547733 |  | 6 |  | CRP | Inbound EDI Voucher Edit/Create - Custom <>AD - 26 July<> Defect 212 is raised for R5547041 change | L3 Pass | 325 | Closed | TRUE | HE2E |  | Finance AP | Finance | Keith Haxton | L2 Pass / Complete | Defect 212 is raised for R5547041 change and issue is fixed |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/28/2019 | 6/27/2019 |  | 365 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 05:35 | Joshi, Abhishek N | 56-F-EU-V-190626-S3FI024 | Inbound | Yes | Y |  |  | VV-26/07, As per request from Keith and approval from BSL and Baxter moved from Sprint 3 to Sprint 4 |  |  |  | 56-F-EU-V-190626-S3FIV024A,56-F-EU-V-190626-S3FIV024B,56-F-EU-V-190626-S3FIV024C,56-F-EU-V-190626-S3FIV024D,56-F-EU-V-190626-S3FIV024E | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74L09CC | No | UBE |  |  | 3 |  |  | Populate Portuguese Accounts - New | L3 Not Required |  |  | TRUE | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/2/2019 | 7/1/2019 |  | 366 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-09 07:29 | Byrne, Joanne Aileen | 56-F-EU-V-190701-S3FI054 |  | Yes | Y |  |  |  | No KT |  |  | 56-F-EU-V-190701-S3FIV054A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642023 | No | UBE | BXU545937 |  | 6 |  | CRP | SOX Pricing Exception Report | L3 Pass | 354 | Closed | TRUE | HNE2E |  | Finance GL | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/2/2019 | 8/1/2019 |  | 367 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-08 01:23 | Joshi, Abhishek N | 56-F-EU-V-190725-S4FI041 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190725-S4FIV041A,B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5803B001 | No | UBE | BXU545811 |  | 4 |  | CRP | Generate Customer Balance A/R - Russia | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/2/2019 | 8/1/2019 |  | 368 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 08:42 | Joshi, Abhishek N | 56-F-EU-V-190725-S4FI044 |  | Yes | [7 empty] | 56-F-EU-V-190725-S4FIV044A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600084 | No | UBE | BXU544629 |  | 5 |  | CRP | Supplier Ledger Extract - CSV | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Saurabh Gupta | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 08/20/2019 | 08/19/2019 |  | 369 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 00:59 | Joshi, Abhishek N | 56-F-EU-V-190819-S5FI200 |  | Yes | Y | [6 empty] | 56-F-EU-V-190819-S5FIV200A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5641051 | No | APPL | BXU547242 |  | 1 |  | CRP | Speed Cost Maintenance - Secured | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/4/2019 | 6/4/2019 |  | 370 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 03:38 | Joshi, Abhishek N | 56-F-EU-V-190603-S1FI076 | Maintenance | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74P4110 | No | UBE | BXU546385, BXU546384 |  | 5 |  | CRP | Inventory Trial Balance | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Vijey Sesha | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/10/19 | 7/08/19 |  | 371 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 06:13 | Joshi, Abhishek N | 56-F-EU-V-190704-S3FI114 |  | Yes | Y | [6 empty] | 56-F-EU-V-190704-S3FIV114A, 56-F-EU-V-190704-S3FIV114B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FREX63 | No | UBE |  |  | 999 |  |  | AR to GL Integrity by GL Class and Account ID | Obsolete | [5 empty] | Finance AR | Finance | Francisco Alvargonzalez |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 372 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:12 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRGL20 | No | UBE | BXU545882 |  | 5 |  | CRP | Grants - Link Subledger to Payments - Extract | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/20/2019 | 8/19/2019 |  | 373 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 09:47 | Joshi, Abhishek N | 56-F-EU-V-190814-S5FI083 |  | Yes | Y | [6 empty] | 56-F-EU-V-190814-S5FIV083A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642013 | No | UBE | BXU546062 |  | 1 |  | CRP | Valorised FOC Sales | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/4/2019 | 6/4/2019 |  | 374 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-08 01:19 | Joshi, Abhishek N | 56-F-EU-V-190603-S1FI194 |  | Yes | Y | [6 empty] | 56-F-EU-V-190603-S1FIV194A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56EDIMX | No | APPL | BXU547431 |  | 3 |  | CRP | EDI Invoices FINTRNEDI - Matrix table Maintenance | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/08/2019 | 07/08/2019 |  | 375 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 23:37 | Joshi, Abhishek N | 56-F-EU-V-190704-S3FI104 | Maintenance | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FB0040 | No | UBE | BXU545815, BXU547011 |  | 1 |  | CRP | SOX Manual Invoicing Report | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/4/2019 | 6/3/2019 |  | 376 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 03:50 | Joshi, Abhishek N | 56-F-EU-V-190531-S1FI070 | Report | Yes | Y |  |  | There is File path value Diff b/w PD812 and DV920 in few versions. However did not modify and moved for build as is(Confirmed by Robert) |  |  |  | 56-F-EU-V-190531-S1FIV70A , 56-F-EU-V-190531-S1FIV70B, 56-F-EU-V-190531-S1FIV70C, 56-F-EU-V-190531-S1FIV70D | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56EUV09 | No | APPL | BXU547487 |  | 1 |  | CRP | VAT - Invoice PrintMsgs by Company Header Branch Plant EMCU | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/04/2019 | 6/03/2019 |  | 377 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 00:24 | Joshi, Abhishek N | 56-F-EU-V-190529-S1FI038 | Printer | Yes | Y |  |  | Retrofit not required |  |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R57040005 | No | UBE | BXU546694 |  | 3 |  | CRP | VAT Renumbering for BOC | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/8/2019 | 7/5/2019 |  | 378 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 05:07 | Joshi, Abhishek N | 56-F-EU-V-190704-S3FI111 |  | Yes | Y | [6 empty] | 56-F-EU-V-190704-S3FIV111A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5509AR | No | UBE |  |  | 999 |  |  | FX Forecast Reporting A/R | Obsolete | [5 empty] | Finance AR | Finance | Francisco Alvargonzalez |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 379 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:12 | Chiau, Liesbet |  | Report | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRAP128 | No | UBE | BXU546067 |  | 5 |  | CRP | Dutch VAT Reporting | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/20/2019 | 8/19/2019 |  | 380 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 09:11 | Joshi, Abhishek N | 56-F-EU-V-190813-S5FI054 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190813-S5FIV054A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5623996A | No | UBE | BXU546025 |  | 4 |  | CRP | Extract I5 doc type | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/2/2019 | 8/1/2019 |  | 381 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-08 00:24 | Joshi, Abhishek N | 56-F-EU-V-190725-S4FI045 |  | Yes | [7 empty] | 56-F-EU-V-190725-S4FIV045A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5623996B | No | UBE | BXU546026 |  | 3 |  | CRP | Extract OV doc type | L3 Pass |  |  | TRUE | LNE2E |  | Finance Cost | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/08/2019 | 07/05/2019 |  | 382 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-08 00:28 | Joshi, Abhishek N | 56-F-EU-V-190701-S3FI068 |  | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3FIV068A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R60A401C | No | UBE |  |  | 6 |  |  | Sales Commissions - Close Records | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Francisco Alvargonzalez | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 383 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-11 06:04 | Sharma, Nikit | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R03B4201A | No | UBE | BXU548623 |  | 1 |  | CRP | A/R Invoice Details | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 5/24/2019 | 5/24/2019 |  | 384 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 05:33 | Joshi, Abhishek N | 56-F-EU-V-190514-S1FI004 |  | Yes | Yes |  |  | T03B4201A dependent DS |  |  |  | 56-F-EU-V-190514-S1FIV04A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564111 | No | APPL | BXU547243 |  | 1 |  | CRP | Item Ledger Inquiry for Finance | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/4/2019 | 6/4/2019 |  | 385 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 23:31 | Joshi, Abhishek N | 56-F-EU-V-190530-S1FI179 | Inquiry | Yes | Y | [6 empty] | 56-F-EU-V-190530-S1FIV179A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74LI01C | No | UBE |  |  | 3 |  |  | Get SAF-T Data - Customer | L3 Not Required |  |  | TRUE | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/3/2019 | 7/2/2019 |  | 386 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-11 01:01 | Verma, Vikas | 56-F-EU-V-190702-S3FI094 |  | Yes | Y |  |  | Object was not available DV920 OL. Hence restored the PD812 Par into DV920 | No KT |  |  | 56-F-EU-V-190702-S3FIV94A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74LI01G | No | UBE |  |  | 3 |  |  | Get SAF-T Data - General Ledger Entries | L3 Not Required |  |  | TRUE | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/3/2019 | 7/3/2019 |  | 387 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-09 07:26 | Byrne, Joanne Aileen | 56-F-EU-V-190628-S3FI050 |  | Yes | Y |  |  |  | No KT |  |  | 56-F-EU-V-190628-S3FIV050A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74LI01D | No | UBE |  |  | 3 |  |  | Get SAF-T Data - Supplier | L3 Not Required |  |  |  | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/8/2019 | 7/5/2019 |  | 388 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-09 07:26 | Byrne, Joanne Aileen | 56-F-EU-V-190708-S3FI0100 |  | Yes |  |  |  |  | No KT |  |  | 56-F-EU-V-190708-S3FIV100A |  |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74LI01E | No | UBE |  |  | 3 |  |  | Get SAF-T Data - Products | L3 Not Required |  |  |  | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/09/2019 | 07/08/2019 |  | 389 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-09 07:26 | Byrne, Joanne Aileen | 56-F-EU-V-190705-S3FI120 |  | Yes |  |  |  |  | No KT |  |  | 56-F-EU-V-190705-S3FIV120A |  |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74LI01F | No | UBE |  |  | 3 |  |  | Get SAF-T Data - TaxTables | L3 Not Required |  |  | TRUE | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/10/2019 | 7/9/2019 |  | 390 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-18 01:32 | Haxton, Keith | 56-F-EU-V-190709-S3FI145 |  | Yes | Y |  |  | The Object not present in DV920 OL. Hence restored the PAR from PD812 | No KT |  |  | 56-F-EU-V-190709-S3FIV145A |  |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74LI02A | No | UBE |  |  | 3 |  |  | SAF-T Generate XML File | L3 Not Required |  |  | TRUE | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/16/2019 | 07/12/2019 |  | 391 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-18 01:32 | Haxton, Keith | 56-F-EU-V-190513-S3FI001 | XML | Yes |  |  |  |  | No KT |  |  | 56-F-EU-V-190513-S3FIV01A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74LI01H | No | UBE |  |  | 3 |  |  | Get SAF-T Data - Source Documents | L3 Not Required |  |  |  | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/12/2019 | 07/11/2019 |  | 392 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-15 05:08 | Tawde, Sameer | 56-F-EU-V-190705-S3FI121 |  | Yes |  |  |  | This UBE does not exist in JDE 9.2, so restored PAR file from PD 8.12 | No KT |  |  | 56-F-EU-V-190705-S3FIV121A |  |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600093 | No | UBE | BXU545939 |  | 2 |  | CRP | Unbilled shipments with VAT Report | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/11/2019 | 6/11/2019 |  | 393 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 01:01 | Joshi, Abhishek N | 56-F-EU-V-190610-S2FI007 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190610-S2FIV007A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL112 | No | UBE | BXU545343 |  | 1 |  | CRP | CPA Status Summary Report | L3 Pass |  |  | TRUE | HNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 04/06/2019 | 04/06/2019 |  | 394 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 00:07 | Joshi, Abhishek N | 56-F-EU-V-190521-S1FI034 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190521-S1FIV34A,56-F-EU-V-190521-S1FIV34B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5622002 | No | UBE | BXU546003 |  | 5 |  | CRP | OPEX2 Report Poland | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/20/2019 | 8/19/2019 |  | 395 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-08 00:18 | Joshi, Abhishek N | 56-F-EU-V-190815-S5FI068 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190815-S5FIV068A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564572IBN | No | UBE |  |  | 5 |  | CRP | Deutsche Bank - Nordic Print Program + IBAN | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/8/2019 | 7/7/2019 |  | 396 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-07 12:11 | Gilthorpe, Peter | 56-F-EU-V-190705-S3FI118 | Printer | Yes | Y | [6 empty] | 56-F-EU-V-190705-S3FIV118A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5612017 | No | UBE | BXU545943 |  | 4 |  | CRP | Fixed Assets to HWT Integrity Report | L3 Pass |  |  | TRUE | HNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/2/2019 | 8/1/2019 |  | 397 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 04:52 | Joshi, Abhishek N | 56-F-EU-V-190731-S4FI070 | Report | Yes |  |  |  | Index change in retrofit |  |  |  | 56-F-EU-V-190731-S4FIV070A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564572CZI | No | UBE |  |  | 5 |  | CRP | Deutche Bank - Czech Republic + IBAN | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/8/2019 | 7/7/2019 |  | 398 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-07 12:11 | Gilthorpe, Peter | 56-F-EU-V-190628-S3FI037 |  | Yes | Y |  |  | Missing object R564572CZC which is called in the event of missing data in the payment data |  |  |  | 56-F-EU-V-190628-S3FIV37A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564572PTI | No | UBE |  |  | 3 |  | CRP | Deutche Bank - Portugal Print Pgm + IBAN | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/8/2019 | 7/7/2019 |  | 399 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-31 10:31 | Gilthorpe, Peter | 56-F-EU-V-190704-S3FI108 | Printer | Yes | Y | [6 empty] | 56-F-EU-V-190704-S3FIV108A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564572PLI | No | UBE | BXU550736 |  | 5 |  | CRP | Deutche Bank - Frgn Print Pgm POLAND + IBAN | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/8/2019 | 7/8/2019 |  | 400 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-23 02:41 | Joshi, Abhishek N | 56-F-EU-V-190701-S3FI004 | Printer | Yes | Y |  |  | Missing object R564572PLC which is called in the event of missing data in the payment data |  |  |  | 56-F-EU-V-190701-S3FIV004A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRAP17 | No | UBE | BXU547509, BXU547729 |  | 4 |  | CRP | PPV (F57PPVD) - CSV Extract - Unmatched | L3 Pass |  |  | TRUE | HNE2E | FALSE | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 08/02/2019 | 08/01/2019 |  | 401 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 07:05 | Joshi, Abhishek N | 56-F-EU-V-190802-S4FI081 |  | Yes | Y | [6 empty] | 56-F-EU-V-190802-S4FIV081A,56-F-EU-V-190802-S4FIV081B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0047B | No | UBE |  |  | 999 |  |  | Coupa Account Master Extract | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 402 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:12 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56EUV15 | No | APPL | BXU547432 |  | 1 |  | CRP | Maintain Vat Tax Rate | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 403 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 00:26 | Joshi, Abhishek N | 56-F-EU-V-190515-S1FI009 | Maintenance | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRAR126 | No | UBE | BXU546659 |  | 5 |  | CRP | Spain VAT Reporting - Accounts Recieveable | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 404 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 09:23 | Joshi, Abhishek N | 56-F-EU-V-190814-S5FI073 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190814-S5FIV073A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P0010 | No | APPL | 1267564 |  | 1 |  | CRP | Companies | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Joanne Byrne | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 5/23/2019 | 5/23/2019 |  | 405 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 04:51 | Joshi, Abhishek N | 56-F-EU-V-190516-S1FI007 |  | Yes | Yes | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5941001 | No | UBE | BXU546498, BXU546389 |  | 4 |  | CRP | Update G/L Class Codes in the F41021 Table | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/2/2019 | 8/2/2019 |  | 406 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 09:54 | Joshi, Abhishek N | 56-F-EU-V-190731-S4FI071 |  | Yes | Y | [6 empty] | 56-F-EU-V-190731-S4FIV071A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R60E0004 | No | UBE |  |  | 6 |  |  | Copia Clienti in Anagrafica Custom PA | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Francisco Alvargonzalez | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 407 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-11 06:06 | Sharma, Nikit | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R60EFAT01 | No | UBE |  |  | 6 |  |  | Estrazione Fattura Elettronica PA | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Francisco Alvargonzalez | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 408 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-11 06:06 | Sharma, Nikit | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R60EFAT02 | No | UBE |  |  | 6 |  |  | Ricontrollo Errori Fattura PA | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Francisco Alvargonzalez | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 409 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-11 06:06 | Sharma, Nikit |  | Error | [12 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R60EFAT03 | No | UBE |  |  | 6 |  |  | Eliminazione Fatture Batch | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Francisco Alvargonzalez | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 410 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-11 06:06 | Sharma, Nikit | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R60EHE01 | No | UBE |  |  | 6 |  |  | CREAZIONE XML FATTURA ELETTRONICA | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Francisco Alvargonzalez | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 411 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-11 06:07 | Sharma, Nikit |  | XML | [12 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R47121 | No | UBE | BXU546389 |  | 4 |  | CRP | EDI Product Activity Data Edit/Create | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/02/2019 | 8/01/2019 |  | 412 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 05:56 | Joshi, Abhishek N | 56-F-EU-V-190801-S4FI007 |  | Yes | Y | [6 empty] | 56-F-EU-V-190801-S4FIV007A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58GLI01 | No | UBE |  |  | 999 |  |  | G/L Class Integrity Report | Obsolete | [5 empty] | Finance GL | Finance | Joanne Byrne |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 413 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:12 | Chiau, Liesbet |  | Report | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56121IRV | No | UBE | BXU546721 |  | 6 |  | CRP | AP Vchr Match - IRV Calculation Russia | L3 Pass | 269 | Open | TRUE | HNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 08/02/2019 | 08/01/2019 |  | 414 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 04:57 | Joshi, Abhishek N | 56-F-EU-V-190802-S4FI089 |  | Yes | [7 empty] | 56-F-EU-V-190802-S4FIV089A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P03B121 | No | APPL | BXU547222 |  | 2 |  | CRP | Work With Electronic Receipts Input | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/20/2019 | 6/20/2019 |  | 415 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-04-01 04:36 | Joshi, Abhishek N | 56-F-EU-V-190613-S2FI039 |  | Yes | Y | [6 empty] | 56-F-EU-V-190613-S2FIV39A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5604571 | No | APPL | BXU550366 |  | 3 |  | CRP | Automatic Payment Groups (Netting) | L3 Pass | 204 | Closed | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/28/2019 | 6/27/2019 |  | 416 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 03:12 | Joshi, Abhishek N | 56-F-EU-V-190702-S3FI091 |  | Yes | Y | [6 empty] | 56-F-EU-V-190702-S3FIV091A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R561202 | No | UBE | BXU545945 |  | 4 |  | CRP | Fixed Assets CSV Download | L3 Pass |  |  | TRUE | HNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/5/2019 | 8/2/2019 |  | 417 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 01:08 | Joshi, Abhishek N | 56-F-EU-V-190801-S4FI077 | Download | Yes | Y | [6 empty] | 56-F-EU-V-190801-S4FIV077A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
RDT09FECHO | No | UBE |  |  | 1 |  |  | Closing of the Year for Debit Credit Balances File | L3 Not Required |  |  | TRUE | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 418 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:50 | Chiau, Liesbet | 56-F-EU-V-190515-S1FI013 |  | Yes | Yes |  |  |  | No KT |  |  | 56-F-EU-V-190515-S1FIV13A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P60A401 | No | APPL |  |  | 6 |  | CRP | Sales Commission Inquiry | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Izaskun Ajuria | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 419 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-06 05:36 | Ajuria, Izaskun |  | Inquiry | [9 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P60A401U | No | APPL |  |  | 6 |  |  | Update Sales Commissions Ledger | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 420 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-24 11:29 | Verma, Vikas | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P60A401X | No | APPL |  |  | 6 |  |  | Manual Transactions Speed Import | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 421 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-24 11:29 | Verma, Vikas | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P60A404 | No | APPL |  |  | 6 |  |  | Agent Information Revision | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 422 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-24 11:29 | Verma, Vikas |  | Revision | [12 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P60A404Z | No | APPL |  |  | 6 |  |  | Agent Batch Input Table Revision | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 423 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-24 11:29 | Verma, Vikas |  | Revision | [12 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P60A405 | No | APPL |  |  | 6 |  |  | Sales Commissions - Adjustments Revision | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 424 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-24 11:29 | Verma, Vikas |  | Revision | [12 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P12214 | No | APPL | BXU547241 |  | 2 |  | CRP | On-line Depreciation Schedule | L3 Pass |  |  | TRUE | LNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 06/21/2019 | 06/20/2019 |  | 425 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 09:02 | Joshi, Abhishek N | 56-F-EU-V-190612-S2FI031 |  | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P60A406 | No | APPL |  |  | 6 |  |  | Draft Days Tolerance | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 426 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-24 11:29 | Verma, Vikas | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P60A410 | No | APPL |  |  | 6 |  |  | Company Sales Commisions Revision | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 427 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-24 11:29 | Verma, Vikas |  | Revision | [12 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5504572 | No | APPL | BXU550365 |  | 3 |  | CRP | Auto Payments Write/Reset - B1 Upg - ICO | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/28/2019 | 6/27/2019 |  | 428 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 03:12 | Joshi, Abhishek N | 56-F-EU-V-190624-S3FI012 |  | Yes | Y |  |  | PG 22/07: awaiting deployment of P5604571 |  |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P554714 | No | APPL | BXU547421 |  | 4 |  | CRP | Target II - MO EDI for Vouchers | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/5/2019 | 8/2/2019 |  | 429 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 09:09 | Joshi, Abhishek N | 56-F-EU-V-190725-S4FI046 |  | Yes | Y |  |  | Awaiting source system data for L2 testing. PG 2108 Test script added |  |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P557101 | No | APPL | BXU547423 |  | 999 |  |  | Custom Text File Processor | Obsolete |  |  | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez |  |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/5/2019 | 8/2/2019 |  | 430 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 09:12 | Joshi, Abhishek N | 56-F-EU-V-190729-S4FI052 | Text | Yes | Y | [6 empty] | 56-F-EU-V-190729-S4FIV052A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P60A412 | No | APPL |  |  | 6 |  |  | ENASARCO Detail by Company | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 431 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-24 11:29 | Verma, Vikas | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P60A414 | No | APPL |  |  | 6 |  |  | Indennità Suppletiva Constants | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 432 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-24 11:29 | Verma, Vikas |  | Constant | [12 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P60A416 | No | APPL |  |  | 6 |  |  | Indennità Suppletiva Accrual | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 433 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-24 11:29 | Verma, Vikas | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P60A417 | No | APPL |  |  | 6 |  |  | Indennità Suppletiva Management | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 434 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-24 11:29 | Verma, Vikas | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P560411Z | No | APPL | BXU545610 |  | 6 |  | CRP | Update F0411Z1 and F0911Z1 | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 9/3/2019 | 9/2/2019 |  | 435 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 23:23 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI003 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5674411 | No | APPL | BXU547430 |  | 5 |  | CRP | Italian Withholding Tax - Entry Screen | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete | L2 Testing completed after rework |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/21/2019 | 8/20/2019 |  | 436 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 23:35 | Joshi, Abhishek N | 56-F-EU-V-190814-S5FI080 |  | Yes | Y |  |  | Defect 285: Hard coded value FormAction change from ADD to AD1 which is passing in N7000340 |  |  |  | 56-F-EU-V-190814-S5FIV080A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P60A419 | No | APPL |  |  | 6 |  |  | Indennità Europea Management | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 437 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-24 11:29 | Verma, Vikas | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P60A41Z1 | No | APPL |  |  | 6 |  |  | Batch Input Revision - Sales Commissions | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 438 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-24 11:30 | Verma, Vikas |  | Revision | [12 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P60A420 | No | APPL |  |  | 6 |  |  | Set Up Anticipated - Fixed - Minimum Garanteed | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 439 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-24 11:30 | Verma, Vikas | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P60A430 | No | APPL |  |  | 6 |  |  | Bank Account Information | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 440 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-24 11:30 | Verma, Vikas | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56R4510 | No | APPL |  |  | 3 |  | CRP | Additional Payment Details | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/26/2019 | 6/27/2019 |  | 441 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-07 05:21 | GOLGE, SERAY | 56-F-EU-V-190626-S3FI026 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P571204 | No | APPL | BXU547223 |  | 5 |  | CRP | Work With Assets(Customised) | L3 Pass |  |  | TRUE | HNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/21/2019 | 8/20/19 |  | 442 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 04:23 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI026 |  | Yes | Y | [6 empty] | 56-F-EU-V-190812-S5FIV026A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P580413M | No | APPL |  |  | 999 |  |  | A/P Manual Payments Restricted | Obsolete |  |  |  | HNE2E |  | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 443 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P580911Z | No | APPL | BXU545338 |  | 4 |  | CRP | Update F0911Z1 and F03B11Z1 | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/5/2019 | 8/2/2019 |  | 444 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 04:26 | Joshi, Abhishek N | 56-F-EU-V-190802-S4FI082 |  | Yes | Y | [6 empty] | 56-F-EU-V-190802-S4FIV082A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P60A4W02 | No | APPL |  |  | 6 |  |  | Proforma Inquiry | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 445 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-24 11:30 | Verma, Vikas |  | Inquiry | [12 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0982 | No | UBE | BXU546935 |  | 3 |  | CRP | GL Transaction Report | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Robbin/Florencia | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/9/2019 | 7/8/2019 |  | 446 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 06:01 | Joshi, Abhishek N | 56-F-EU-V-190701-S3FI070 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3FIV070A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5604425 | No | UBE | BXU549996 |  | 5 |  | CRP | A/P Unrealized Gain/Loss Report Russia | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/21/2019 | 8/20/2019 |  | 447 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 05:43 | Joshi, Abhishek N | 56-F-EU-V-190816-S5FI098 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190816-S5FIV098A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5841112A | No | UBE | BXU549975 |  | 5 |  | CRP | LOCOM Report | L3 Pass | 308 | Closed | TRUE | LNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/21/2019 | 8/20/2019 |  | 448 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 03:52 | Joshi, Abhishek N | 56-F-EU-V-190819-S5FI114 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190819-S5FIV114A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P550015 | No | APPL | BXU547657 |  | 5 |  | CRP | Statutory Exchange Rates | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/21/2019 | 8/21/2019 |  | 449 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 09:06 | Joshi, Abhishek N | 56-F-EU-V-190821-S5FI027 |  | Yes | N |  |  | Project Status is at EU21A. Please Promote to higher status. |  |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRGL120 | No | UBE | BXU548325 |  | 1 |  | CRP | Listado Diario Oficial | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 19\06\06 | 19\06\06 |  | 450 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 09:37 | Joshi, Abhishek N | 56-F-EU-V-190530-S1FI021 |  | Yes | Yes |  |  | No retrofit required |  |  |  | 56-F-EU-V-190530-S1FIV021A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRGL121 | No | UBE | BXU548327 |  | 2 |  | CRP | AN8 Correction for GL to VAT posting UBE | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Nithya Ramachandran | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 451 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 09:39 | Joshi, Abhishek N | 56-F-EU-V-190612-S2FI004 |  | Yes | [7 empty] | 56-F-EU-V-190612-S2FIV004A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P512100 | No | APPL | BXU547656 |  | 3 | 3 | CRP | Job Status Inquiry-Basic | L3 Pass | 164 | Closed | TRUE | LNE2E |  | Finance GL | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/14/2019 | 6/13/2019 |  | 452 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 | Joshi, Abhishek N | 56-F-EU-V-190611-S2FI033 | Inquiry | Yes | Y | [6 empty] | 56-F-EU-V-190611-S2FIV033A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P1114 | No | APPL |  |  | 2 |  | CRP | Review and Revise Company Conversion Computations | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Joanne Byrne | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 453 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-22 06:26 | Touyaa, Manuel | NA |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRGL84C | No | UBE | BXU546591 |  | 5 |  | CRP | PII Transaction Listing F0006, F0901, F0911 | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/21/2019 | 8/21/2019 |  | 454 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 10:49 | Joshi, Abhishek N | 56-F-EU-V-190816-S5FI101 |  | Yes | Y | [6 empty] | 56-F-EU-V-190816-S5FIV101A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRGL85H | No | UBE | BXU545350 |  | 5 |  | CRP | F0902_NMU1 UBE | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 08/21/2019 | 08/20/2019 |  | 455 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 10:53 | Joshi, Abhishek N | 56-F-EU-V-190821-S5FI026 |  | Yes | Y | [6 empty] | 56-F-EU-V-190821-S5FIV026A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL84B | No | UBE | BXU545350 |  | 5 |  | CRP | Expense by Responsibility - Transaction Listing CSV - Russia | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/21/2019 | 8/20/2019 |  | 456 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 00:13 | Joshi, Abhishek N | 56-F-EU-V-190814-S5FI084 |  | Yes | Y | [6 empty] | 56-F-EU-V-190814-S5FIV084A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P0006 | No | APPL | BXU547416 |  | 1 |  | CRP | Business Units | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Joanne Byrne | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 5/23/2019 | 5/23/2019 |  | 457 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 06:50 | Joshi, Abhishek N | 56-F-EU-V-190513-S1FI002 |  | Yes | Yes | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5609404 | No | UBE | BXU545732 |  | 4 |  | CRP | G/L Registration Report-Italy - Custom | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 08/05/2019 | 08/04/2019 |  | 458 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 04:30 | Joshi, Abhishek N | 56-F-EU-V-190806-S4FI092 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190806-S4FIV092A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5618473 | No | UBE | BXU548348 |  | 5 |  | CRP | Extract for AUDIT VAT Reconciliation | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/21/2019 | 8/20/2019 |  | 459 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 00:19 | Joshi, Abhishek N | 56-F-EU-V-190816-S5FI100 | Audit | Yes | Y | [6 empty] | 56-F-EU-V-190816-S5FIV100A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0439 | No | UBE | BXU546387 |  | 3 |  | CRP | Purge Cost Records | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/9/2019 | 7/8/2019 |  | 460 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 10:23 | Joshi, Abhishek N | 56-F-EU-V-190702-S3FIV92 |  | Yes | Y | [6 empty] | 56-F-EU-V-190702-S3FIV092A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0443 | No | UBE | BXU546398 |  | 3 |  | N/A | ACRO Cost Components | L3 Not Required |  |  | FALSE | HNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/28/2019 | 6/27/2019 |  | 461 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 10:25 | Joshi, Abhishek N | 56-F-EU-V-190701-S3FI081 |  | Yes | [7 empty] | 56-F-EU-V-190701-S3FIV81A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0444 | No | UBE | BXU546399 |  | 3 |  |  | R30835 Load Balance Report | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/9/2019 | 7/8/2019 |  | 462 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 05:41 | Joshi, Abhishek N | 56-F-EU-V-190708-S3FI143 | Report | Yes | Y |  |  | R59R0444 report always goes into error and R59R0444 report calls R30835_BXEU2001 and R30834_ZJDE0001 report . The same is confirmed by baxter in email |  |  |  | 56-F-EU-V-190708-S3FIV143A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL30 | No | UBE | BXU548343 |  | 1 |  | CRP | Overhead Spending League Report | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Robbin/Florencia | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/06/2019 | 6/06/2019 |  | 463 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 07:37 | Joshi, Abhishek N | 56-F-EU-V-190530-S1FI190 | Report | Yes | Yes |  |  | Retrofit not required |  |  |  | 56-F-EU-V-190530-S1FIV190A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRGL84 | No | UBE | BXU545680 |  | 5 |  | CRP | Expense by Responsibility - Transaction Listing DB File | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/21/2019 | 8/20/2019 |  | 464 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 09:51 | Joshi, Abhishek N | 56-F-EU-V-190814-S5FI069 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5943121 | No | UBE | BXU546397 |  | 4 |  | CRP | Update GLC in F43121 By X-Level 5 | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/5/2019 | 8/5/2019 |  | 465 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 10:04 | Joshi, Abhishek N | 56-F-EU-V-190805-S4FI001 |  | Yes | Y | [6 empty] | 56-F-EU-V-190805-S4FIV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5943001 | No | UBE | BXU546390 |  | 4 |  | CRP | G/L Class Updates F4311/F43199 | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/05/2019 | 8/02/2019 |  | 466 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 10:01 | Joshi, Abhishek N | 56-F-EU-V-190801-S4FI080 |  | Yes | Y | [6 empty] | 56-F-EU-V-190801-S4FIV080A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5942005 | No | UBE | BXU546702 |  | 4 |  | CRP | G/L Class Updates F4211/F42199 | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 08/06/2019 | 08/05/2019 |  | 467 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 10:00 | Joshi, Abhishek N | 56-F-EU-V-190802-S4FI091 |  | Yes | Y | [6 empty] | 56-F-EU-V-190802-S4FIV091A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R6213G02 | No | UBE | BXU546500 |  | 3 |  | CRP | Supplemental Accounting Creation | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/10/2019 | 07/10/2019 |  | 468 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 07:35 | Joshi, Abhishek N | 56-F-EU-V-190709-S3FI151 |  | Yes | Y | [6 empty] | 56-F-EU-V-190709-S3FIV151A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R6213G04 | No | UBE | BXU546502 |  | 3 |  | CRP | Supplemental Account CTA Adjustment | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/10/2019 | 7/09/2019 |  | 469 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 07:38 | Joshi, Abhishek N | 56-F-EU-V-190709-S3FI148 |  | Yes | Y |  |  | Retrofit not required |  |  |  | 56-F-EU-V-190709-S3FIV148A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R6213G07 | No | UBE | BXU546583 |  | 3 |  | CRP |  | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/11/2019 | 07/10/2019 |  | 470 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 07:40 | Joshi, Abhishek N | 56-F-EU-V-190709-S3FI156 |  | Yes | Y | [6 empty] | 56-F-EU-V-190709-S3FIV156A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5909106 | No | APPL | BXU550724 |  | 4 |  | CRP | Travel Memo Account Range Revision | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Manuel Touyaa | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/5/2019 | 8/2/2019 |  | 471 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-23 01:59 | Joshi, Abhishek N | 56-F-EU-V-190802-S4FI085 | Revision | Yes | Y | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5909107 | No | APPL | BXU548278 |  | 4 |  | CRP | Function Spending Account Range Revision | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Manuel Touyaa | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/5/2019 | 8/2/2019 |  | 472 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 05:10 | Joshi, Abhishek N | 56-F-EU-V-190731-S4FI074 | Revision | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560359A | No | UBE | BXU545714 |  | 5 |  | CRP | AIDA Extract balance for ECEMEA - Cognos | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete | Do not run with Mode="M" in processing options. Reports has bug from 8.12 for CRCD field update. |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/21/2019 | 8/20/2019 |  | 473 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 02:08 | Joshi, Abhishek N | 56-F-EU-V-190816-S5FI104 |  | Yes | Y | [6 empty] | 56-F-EU-V-190816-S5FIV104A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P74L0901 | No | APPL |  |  | 3 |  |  | Accounts - Portuguese Localizations - NEW | L3 Not Required |  |  | FALSE | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/15/2019 | 7/14/2019 |  | 474 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-12 06:16 | Chalawadi, Geeta | 56-F-EU-V-190709-S3FI147 |  | Yes |  |  |  | Object was not present in DV920 so PAR restored including one dependent view-VDT0901T from Dv812 | No KT |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P74L4008 | No | APPL |  |  | 3 |  |  | Tax Area SAF-T Setup | L3 Not Required |  |  |  | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 475 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-12 04:39 | Patil, Neha |  | Setup | [5 empty] | No KT | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P74LDP02 | No | APPL |  |  | 3 |  |  | Consulta Conferencia Mapa IVA | L3 Not Required |  |  | FALSE | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/11/2019 | 7/10/2019 |  | 476 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-10 02:45 | Hota, Twinkle | 56-F-EU-V-190709-S3FI125 |  | Yes |  |  |  |  | No KT |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P74LI01 | No | APPL |  |  | 3 |  |  | SAF-T Detail Files | L3 Not Required |  |  | TRUE | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/16/2019 | 07/12/2019 |  | 477 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-18 01:32 | Haxton, Keith | 56-F-EU-V-190701-S3FI053 |  | Yes | Y |  |  |  | No KT |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P74R0011 | No | APPL | BXU549556 |  | 3 |  |  | Review Correspondences Batches - RUS - 09 - 74R | L3 Not Required |  |  | TRUE | LNE2E |  | Localization | Finance | Keith Haxton | L2 Not required | No KT, test in E2E |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/03/2019 | 07/02/2019 |  | 478 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 01:46 | Joshi, Abhishek N | 56-F-EU-V-190628-S3FI034 |  | Yes | Y |  |  |  | No KT |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P74R9020 | No | APPL | BXU549555 |  | 3 |  |  | Setup G/L Reports - RUS - 09 - 74R | L3 Not Required |  |  | TRUE | LNE2E |  | Localization | Finance | Keith Haxton | L2 Not required | No KT, test in E2E |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/2/2019 | 7/1/2019 |  | 479 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 01:48 | Joshi, Abhishek N | 56-F-EU-V-190701-S3FI077 | Setup / Report | Yes | Y |  |  |  | No KT |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R12108 | No | UBE | BXU548617 |  | 2 |  | CRP | Asset Transfer | L3 Pass |  |  | TRUE | HNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/28/2019 | 6/27/2019 |  | 480 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 05:58 | Joshi, Abhishek N | 56-F-EU-V-190627-S2FI063 |  | Yes | Y | [6 empty] | 56-F-EU-V-190627-S2FIV063A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R12800 | No | UBE | BXU551113 |  | 2 |  | CRP | Post G/L Entries to Assets | L3 Pass |  |  | TRUE | HNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete | Retested after rework |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 06/27/2019 | 06/26/2019 |  | 481 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-04-02 05:53 | Joshi, Abhishek N | 56-F-EU-V-190624-S2FI129 |  | Yes | Y | [6 empty] | 56-F-EU-V-190624-S2FIV129A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5874R0430 | No | UBE | BXU545403 |  | 3 |  | CRP | Purchase Register Report - RUS - 04 - Baxter | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/9/2019 | 7/8/2019 |  | 482 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 08:47 | Joshi, Abhishek N | 56-F-EU-V-190709-S3FI146 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190709-S3FIV146A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900305 | No | APPL | BXU548626 |  | 5 |  | CRP | JDE-ESM Net Change Counter Application | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/21/2019 | 8/20/2019 |  | 483 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-05 06:15 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI042 |  | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P74L091S | No | APPL |  |  | 3 |  |  | Setup Category Codes - new | L3 Not Required |  |  | TRUE | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/4/2019 | 7/3/2019 |  | 484 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-09 07:30 | Byrne, Joanne Aileen | 56-F-EU-V-190703-S3FI100 | Setup | Yes | Y |  |  |  | No KT |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55NSII0 | No | UBE |  |  | 6 |  |  | SII Generacion de XML | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 9/17/2019 | 9/16/2019 |  | 485 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-30 04:25 | Amorini, Luigi | 56-F-EU-V-190912-S6FI155 | XML | Yes | Yes | [6 empty] | 56-F-EU-V-190912-S6FIV155A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55NSIIB | No | UBE |  |  | 6 |  | CRP | SII Generacion de XML B | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth, Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 9/17/2019 | 9/17/2019 |  | 486 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-24 03:24 | Ajuria, Izaskun | 56-F-EU-V-190910-S6FI125 | XML | Yes | [7 empty] | 56-F-EU-V-190910-S6FIV125A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R550011RA | No | UBE | BXU550367 |  | 3 |  |  | Russian POST Post Report | L3 Not Required |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Not required | No KT, test in E2E |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/9/2019 | 7/9/2019 |  | 487 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 05:13 | Joshi, Abhishek N | 56-F-EU-V-190708-S3LO043 | Report | Yes | Y |  |  |  | No KT |  |  | 56-F-EU-V-190708-S3LOV043A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642023O | No | UBE | BXU546733 |  | 5 |  | CRP | SOX Orchestrator Report | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/6/2019 | 8/5/2019 |  | 488 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 00:28 | Joshi, Abhishek N | 56-F-EU-V-190801-S4FI078 | Report | Yes | [7 empty] | 56-F-EU-V-190801-S4FIV078A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FF102 | No | UBE | BXU546066 |  | 3 |  | CRP | Farmafactoring Download F56FF11 to a text file | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/9/2019 | 7/8/2019 |  | 489 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 03:56 | Joshi, Abhishek N | 56-F-EU-V-190709-S3FI001 | Download / Text | Yes | Y | [6 empty] | 56-F-EU-V-190709-S3FIV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900043 | No | APPL |  |  | 999 |  |  | Ariba Company Master Inquiry | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 490 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet |  | Inquiry | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560101A | No | UBE | BXU550592 |  | 1 |  | CRP | Address Book Customer Report | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/4/2019 | 6/4/2019 |  | 491 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 00:41 | Joshi, Abhishek N | 56-F-EU-V-190521-S1FI036 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190521-S1FIV36A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564105Z | No | UBE | BXU545615 |  | 3 |  | CRP | Item Cost records deletion | L3 Pass |  |  | TRUE | HNE2E |  | Finance Cost | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/09/2019 | 07/08/2019 |  | 492 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-08 01:15 | Joshi, Abhishek N | 56-F-EU-V-190708-S3FI0101 |  | Yes | Y | [6 empty] | 56-F-EU-V-190708-S3FIV0101A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0015 | No | UBE |  |  | 999 |  |  | Ariba Company Master Extract | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 493 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0044 | No | UBE |  |  | 999 |  |  | Ariba Business Unit Master Extract | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 494 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0048 | No | UBE |  |  | 999 |  |  | Ariba Address Book Master Extract | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 495 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R4801 | No | UBE | BXU548339 |  | 4 |  | CRP | Ariba Master Data Control Status | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Saurabh Gupta | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/6/2019 | 8/5/2019 |  | 496 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 06:05 | Joshi, Abhishek N | 56-F-EU-V-190725-S4FI047 |  | Yes | Y | [6 empty] | 56-F-EU-V-190725-S4FIV047A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P55NSII1 | No | APPL |  |  | 6 |  |  | SII - Identificacion Inmuebles | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 09/09/2019 | 09/06/2019 |  | 497 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-30 04:25 | Amorini, Luigi | 56-F-EU-V-190909-S6FI118 |  | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56GETPD04 | No | UBE | BXU546009 |  | 1 |  | CRP | GetPaid - Build file F56ARMST, F56ARTRA, F56AREXTI | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Vijey Sesha | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/4/2019 | 6/4/2019 |  | 498 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 06:52 | Joshi, Abhishek N | 56-F-EU-V-190527-S1FI054 |  |  | Y | [6 empty] | 56-F-EU-V-190527-S1FIV054A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56GETPD54 | No | UBE | BXU545888 |  | 1 |  | CRP | GetPaid - Build file F56ARMST, F56ARTRA, F56AREXTI | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Vijey Sesha | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 19/06/07 | 19/06/04 |  | 499 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 04:39 | Joshi, Abhishek N | 56-F-EU-V-190530-S1FI020 |  | Yes | Yes |  |  | No retrofit required |  |  |  | 56-F-EU-V-190530-S1FI020A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P55NSII2 | No | APPL |  |  | 6 |  |  | SII - Identificacion de aduanas | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 9/17/2019 | 9/16/2019 |  | 500 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-30 04:25 | Amorini, Luigi | 56-F-EU-V-190903-S6FI041 |  | Yes | Yes | [6 empty] | N/A |  |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P55NSII4 | No | APPL |  |  | 6 |  |  | SII Control de Registros Emitidos | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 9/17/2019 | 9/16/2019 |  | 501 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-30 04:25 | Amorini, Luigi | 56-F-EU-V-190904-S6FI145 |  | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P55NSII5 | No | APPL |  |  | 6 |  |  | SII - Historico de Presentaciones | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth, Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 09/17/2019 | 09/17/2019 |  | 502 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-30 04:25 | Amorini, Luigi | 56-F-EU-V-190909-S6FI121 |  | Yes | Yes | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R60A401M | No | UBE |  |  | 6 |  |  | Sales Commissions - Close Fully Matured Records | L3 Not Required |  |  | TRUE | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 503 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-11 06:04 | Sharma, Nikit | [7 empty] | No KT | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5612006 | No | UBE | BXU547428 |  | 5 |  | CRP | Asset revaluation indexes Application | L3 Pass |  |  | TRUE | LNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete | Add records functionality will be tested in R1 |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/22/2019 | 8/22/2019 |  | 504 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 23:27 | Joshi, Abhishek N | 56-F-EU-V-190814-S5FI074 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5612006 | No | UBE | BXU545942 |  | 5 |  | CRP | Asset Revaluation insurance Report | L3 Pass |  |  | TRUE | LNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/21/2019 | 8/22/2019 |  | 505 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 04:49 | Joshi, Abhishek N | 56-F-EU-V-190814-S5FI081 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190814-S5FIV081A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5612006R | No | UBE | BXU545942 |  | 5 |  | CRP | Asset Revaluation insurance extract Report | L3 Pass |  |  | TRUE | LNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/22/2019 | 8/21/2019 |  | 506 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 04:51 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI027 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190812-S5FIV027A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564211SA | Yes | UBE | BXU532056 (139511) | BXU532059 (139511) | 3 |  |  | Export Compliance and Sales Authorization check | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete | As discussed with Abdul in scrum call (23rd july), I am making it as L2 pass. This will be tested futher in R1 sprint with the new logic. |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/01/2019 | 06/28/2019 |  | 507 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 07:10 | ANAND, S | 56-F-EU-V-190702-S3LO026 | Export | Yes | Y |  |  |  | KTW6 |  |  | 56-F-EU-V-190702-S3LOV026A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564736P | No | UBE |  |  | 4 |  |  | Poltraf Waybill Report | L3 Pass |  |  | TRUE | MNE2E |  | Transportation | Logistics | Puneet Sharma | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/22/2019 | 7/22/2019 |  | 508 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-29 08:17 | Sharma, Puneet | 56-F-EU-V-190722-S4LO025 | Report | Yes | Y |  |  |  | KTT3 |  |  | 56-F-EU-V-190722-S4LOV025A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5843001 | No | APPL | BXU547051 |  | 1 |  | CRP | Landed Cost Custom Form | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/7/2019 | 6/7/2019 |  | 509 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-05 06:01 | Joshi, Abhishek N | 56-F-EU-V-190530-S1FI188 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P60E0001 | No | APPL |  |  | 6 |  |  | GESTIONE SET UP FILE XML PA | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 510 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-27 07:18 | Bodin, Fatiha |  | XML | [12 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P60E0002 | No | APPL |  |  | 6 |  |  | Anagrafica Sociotà | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 511 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-27 07:18 | Bodin, Fatiha | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0491 | No | UBE |  |  | 1 |  | CRP | Workday JDE Integration - Employee Info | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/3/2019 | 6/3/2019 |  | 512 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-14 08:09 | Krithivasan Natarajan, Sriram | 56-F-EU-V-190530-S1FI183 |  | Yes | Y | [6 empty] | 56-F-EU-V-190530-S1FIV183A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0493 | No | UBE |  |  | 1 |  | CRP | Workday to JDE Detail Info Interface UBE | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/3/2019 | 6/3/2019 |  | 514 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-14 08:10 | Krithivasan Natarajan, Sriram | 56-F-EU-V-190530-S1FI068 | Interface | Yes | Y | [6 empty] | 56-F-EU-V-190530-S1FI068A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0494 | No | UBE |  |  | 1 |  | CRP | UBE To Populate F0101Z2 and F0401Z1 Files | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/3/2019 | 6/3/2019 |  | 515 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-14 08:11 | Krithivasan Natarajan, Sriram | 56-F-EU-V-190527-S1FI063 |  | Yes | Y | [6 empty] | 56-F-EU-V-190527-S1FIV63A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0495 | No | UBE |  |  | 1 |  | CRP | Workday to JDE Bank Info Interface UBE | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/3/2019 | 6/3/2019 |  | 516 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-14 08:12 | Krithivasan Natarajan, Sriram | 56-F-EU-V-190522-S1FI039 | Interface | Yes | Y | [6 empty] | 56-F-EU-V-190522-S1FIV39A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0496 | No | UBE |  |  | 1 |  | CRP | UBE to populate F0030 | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/3/2019 | 5/31/2019 |  | 517 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-14 08:12 | Krithivasan Natarajan, Sriram | 56-F-EU-V-190523-S1FI049 |  | Yes | Y | [6 empty] | 56-F-EU-V-190523-S1FIV049A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P55JDRCP1 | No | UBE |  |  | 999 |  |  | MILD - Receipts to JDE - Set up | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 518 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P60E0003 | No | APPL |  |  | 6 |  |  | Anagrafica Trasmittente | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 519 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-27 07:18 | Bodin, Fatiha | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P60E0004 | No | APPL |  |  | 6 |  |  | Anagrafica Cliente PA | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 520 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-27 07:18 | Bodin, Fatiha | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P60E0005 | No | APPL |  |  | 3 |  |  | FATTURA ELETTRONICA - FORMATI TRASMISSIONE | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/11/2019 | 7/10/2019 |  | 521 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-30 03:29 | Amorini, Luigi | 56-F-EU-V-190711-S3FI001 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P60E0010 | No | APPL |  |  | 6 |  |  | Errori Elaborazione | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 522 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-27 07:18 | Bodin, Fatiha |  | Error | [12 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P60E0021 | No | APPL |  |  | 6 |  |  | Causali di Default | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 523 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-27 07:19 | Bodin, Fatiha | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P60E0041 | No | APPL |  |  | 6 |  |  | Set Up Tipi Documento | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 524 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-27 07:19 | Bodin, Fatiha | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P60E0042 | No | APPL |  |  | 6 |  |  | Set Up Codici IVA | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 525 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-27 07:19 | Bodin, Fatiha | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P60E0051 | No | APPL |  |  | 6 |  |  | Set Up Articoli Esclusione Controlli CIG | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 526 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-27 07:19 | Bodin, Fatiha | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P48014 | No | APPL | BXU550996 |  | 3 |  | CRP | Project Task Details | L3 Pass |  |  | TRUE |  |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/12/2019 | 7/10/2019 |  | 527 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-04-02 06:01 | Joshi, Abhishek N | 56-F-EU-V-190710-S3FI160 |  | Yes | Y |  |  |  | Obsolete |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P48201 | No | APPL | BXU547234 |  | 3 |  | CRP | Work With Work Orders | L3 Pass |  |  | TRUE | HNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete | 05/07/2019 - Need data to test the object so maild to Libor and waiting for his reply |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/24/2019 | 6/21/2019 |  | 528 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-05 06:54 | Joshi, Abhishek N | 56-F-EU-V-200620-S2FI054 |  | Yes | Y | [6 empty] | 56-F-EU-V-200620-S2FIV054A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P60EHE01 | No | APPL |  |  | 6 |  |  | GESTIONE FATTURE ELETTRONICHE PA | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 529 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-27 07:19 | Bodin, Fatiha | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5543214 | No | APPL | BXU547239 |  | 4 |  | CRP | Purchase Receipts Inquiry - Baxter | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Saurabh Gupta | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/6/2019 | 8/5/2019 |  | 530 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-23 01:57 | Joshi, Abhishek N | 56-F-EU-V-190729-S4FI053 | Inquiry | Yes | Y | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P55FREXQ | No | APPL | BXU547135 |  | 6 |  | CRP | Inspect and change SQL statements in F55FREXQ | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/3/2019 | 6/28/2019 |  | 531 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 09:14 | Joshi, Abhishek N | 56-F-EU-V-190624-S3FI013 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P560030 | No | APPL | BXU544991 | BXU545048 | 2 |  |  | Bank Information - Address Book | L3 Pass |  |  | TRUE | L |  | MDM | MDM | Carlos Barrera | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | VV-09/07 - Code reviewed by Vikas after the Rework | Devi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 06/27/2019 | 06/27/2019 |  | 532 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-27 07:29 | Vishnubhatla, Mithra | 56- F-EU-V-190619-S2MD41 |  | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642989 | No | APPL |  |  | 1 |  |  | Portugal Digital Invoice Certification | L3 Not Required |  |  | TRUE | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 533 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:51 | Chiau, Liesbet | 56-F-EU-V-190521-S1FI038 |  | Yes | Y |  |  |  | No KT |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56JDRCP | No | APPL | BXU547492, BXU547493 |  | 4 |  | CRP | MILD - JDRCPT Receipts to JDE : Maintenance | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/6/2019 | 8/5/2019 |  | 534 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 00:32 | Joshi, Abhishek N | 56-F-EU-V-190802-S4FI083 | Maintenance | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P570030 | No | APPL | BXU544568 | BXU545052 | 2 |  |  | Bank Information - Address Book | L3 Pass |  |  | TRUE | L |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/28/2019 | 6/28/2019 |  | 535 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 06:21 | Joshi, Abhishek N | 56-F-EU-V-190619-S2MD042 |  | Yes | Y | [6 empty] | 56-F-EU-V-190619-S2MDV042A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P570030S | No | APPL | BXU544670 |  | 2 |  |  | Bank Information - Address Book - Secured | L3 Pass | 132 | Closed | TRUE | L |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 536 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 06:18 | Joshi, Abhishek N | 56-F-EU-V-190625-S2MD003 |  | Yes |  |  |  |  | DEFECT ID: 132 |  |  | 56-F-EU-V-190625-S2MDV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P570050C | No | APPL |  |  | 4 |  | CRP | COUPA Purchase Order Request Inquiry | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 08/06/2019 | 08/05/2019 |  | 537 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-08 03:19 | Touyaa, Manuel | 56-F-EU-V-190806-S4FI097 | Inquiry | Yes | Y | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5743214 | No | APPL | BXU547136 |  | 4 |  | CRP | Purchase Receipts Inquiry - Customized | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/6/2019 | 8/6/2019 |  | 538 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 03:13 | Joshi, Abhishek N | 56-F-EU-V-190806-S4FI001 | Inquiry | Yes | Y | [6 empty] | 56-F-EU-V-190806-S4FIV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P574352 | No | APPL | BXU547659 |  | 3 |  | CRP | PO Receipts - Currency Mismatch - Auto Reversal | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/09/2019 | 07/09/2019 |  | 539 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 00:53 | Joshi, Abhishek N | 56-F-EU-V-190708-S3FI141 |  | Yes | Y |  |  | VV-24/06- Moved to Sprint 3 as per request from Seray |  |  |  | 56-F-EU-V-190708-S3FIV141A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5801012 | Yes | APPL | BXU544992 (19802) | 1230569, BXU545117 | 2 | P5900028 (Additional Codes) is called but not loaded. This appl will be tested individually in Sprint 5 |  | Address Book - Country Specific | L3 Pass | 140 | Closed | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 28/06/2019 | 28/06/2019 |  | 540 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-12 13:41 | Singh, Sunil Kumar | 56-F-EU-V-190625-S2MD002 |  | Yes | Y |  |  |  | DEFECT ID: 140 |  |  | 56-F-EU-V-190625-S2MDV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P594314 | No | APPL |  |  | 999 |  |  | Voucher Match | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 541 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R4311Z1I | Yes | UBE | 1260788 (3411), BXU544569 (RE83933) | BXU546900 (83933) 1260792 3411 | 4 |  |  | PO Unedited Transaction Inbound Processor | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/24/2019 | 7/23/2019 |  | 542 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 06:20 | Vishnubhatla, Mithra | 56-F-EU-V-190701-S4LO038 | Inbound | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190701-S4LOV038A,56-F-EU-V-190701-S4LOV038B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5530Z1A | No | UBE | BXU544568 |  | 2 |  |  | Upload Bank Transit Number Batch File | L3 Pass | 143 | Closed | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/27/2019 | 6/27/2019 |  | 543 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 06:21 | Joshi, Abhishek N | 56-F-EU-V-190619-S2MD041 | Upload | Yes | Y |  |  |  | DEFECT ID: 143 |  |  | 56-F-EU-V-190619-S2MDV041A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5626513 | No | UBE | BXU550713 |  | 5 |  |  | Report For Deleting Data in F5530Z2 Automation | L3 Pass |  |  | TRUE | L |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/12/2019 | 8/9/2019 |  | 544 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-24 04:54 | Joshi, Abhishek N | 56-F-EU-V-190812-S5MD001 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5MDV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0194 | No | UBE | BXU546700 |  | 3 |  | CRP | Transfer Price Data Z-File Purge | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/10/2019 | 7/09/2019 |  | 545 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 05:18 | Joshi, Abhishek N | 56-F-EU-V-190704-S3FI113 |  | Yes | Y | [6 empty] | 56-F-EU-V-190704-S3FIV113A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564311C | No | UBE | BXU550590 |  | 4 |  | CRP | Coupo PO Reconciliation CVS | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Saurabh Gupta | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/06/2019 | 8/05/2019 |  | 546 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-19 02:58 | Joshi, Abhishek N | 56-F-EU-V-190802-S4FI088 |  | Yes | Y | [6 empty] | 56-F-EU-V-190802-S4FIV088A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643FG1 | No | UBE |  |  | 1 |  | CRP | Order and GRN Creation from Fieldglass | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/3/2019 | 6/3/2019 |  | 547 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-19 05:01 | Gilthorpe, Peter | 56-F-EU-V-190521-S1FI044 |  | Yes | Y | [6 empty] | 56-F-EU-V-190521-S1FIV044A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643FGA | No | UBE |  |  | 1 |  | CRP | Fieldglass COA Upload-Update F5643FGC | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 03/06/2019 | 03/06/2019 |  | 548 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-07 05:17 | GOLGE, SERAY | 56-F-EU-V-190521-S1FI032 | Upload | Yes | Y | [6 empty] | 56-F-EU-V-190521-S1FIV32A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643FGC | No | UBE |  |  | 2 |  | CRP | Chart of Accounts Report – File Generation | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/11/2019 | 6/11/2019 |  | 549 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-23 08:56 | GOLGE, SERAY | 56- F-EU-V-190611-S2FI024 | Report | Yes | Yes | [6 empty] | 56- F-EU-V-190611-S2FIV024A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643FGU | No | UBE |  |  | 1 |  | CRP | Fieldglass to JDE File Upload | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 550 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-23 08:57 | GOLGE, SERAY | 56-F-EU-V-190515-S1FI007 | Upload | Yes | Yes | [6 empty] | 56-F-EU-V-190515-S1FIV07A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56BREXT | No | UBE |  |  | 3 |  | CRP | BBR Extracts to Staging Files | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 07/10/2019 | 07/09/2019 |  | 551 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-08 04:59 | GOLGE, SERAY | 56-F-EU-V-190704-S3FI106 |  | Yes | Y | [6 empty] | 56-F-EU-V-190704-S3FIV106A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56BRUDC | No | UBE | BXU550370 |  | 3 |  | CRP | Populate BBR UDC Staging File | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 7/10/2019 | 7/09/2019 |  | 552 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 04:47 | Joshi, Abhishek N | 56-F-EU-V-190709-S3FI149 |  | Yes | Y | [6 empty] | 56-F-EU-V-190709-S3FIV149A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5942005 | No | APPL | BXU548625 |  | 4 |  | CRP | Work with From -To GL Class | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 08/06/2019 | 08/02/2019 |  | 553 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 05:22 | Joshi, Abhishek N | 56-F-EU-V-190802-S4FI092 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R590401 | No | UBE |  |  | 2 |  |  | MILD Vendor Interface | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 554 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:03 | Chiau, Liesbet | 56-F-EU-V-190625-S2MD001 | Interface | Yes | [7 empty] | 56-F-EU-V-190625-S2MDV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL84 | No | UBE | BXU547507 |  | 1 |  | CRP | Expense by Responsibility - Transaction Listing CSV | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/6/2019 | 6/4/2019 |  | 555 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 10:03 | Joshi, Abhishek N | 56-F-EU-V-190531-S1FI073 |  | Yes | Y |  |  | PO T55FRGL84 added in 56-F-EU-V-190428-S1FI065 and promoted. Hence did not include in the Project 56-F-EU-V-190531-S1FI073 |  |  |  | 56-F-EU-V-190531-S1FIV73A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0058 | No | UBE |  |  | 999 |  |  | Ariba Purchase Order Request | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri |  |  |  | 556 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0058C | No | UBE |  |  | 4 |  | CRP | COUPA Purchase Order Request | L3 Pass |  |  | TRUE | HNE2E | FALSE | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/6/2019 | 8/5/2019 |  | 557 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-28 05:59 | GOLGE, SERAY | 56-F-EU-V-190805-S4FI093 |  | Yes | Y | [6 empty] | 56-F-EU-V-190805-S4FIV093A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R43Z1 | No | UBE |  |  | 4 |  | CRP | ARIBA BBR PO Auto Receipts | L3 Pass |  |  | TRUE | HNE2E | FALSE | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 8/6/2019 | 8/5/2019 |  | 558 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-28 05:59 | GOLGE, SERAY | 56-F-EU-V-190805-S4FI091 |  | Yes | Y | [6 empty] | 56-F-EU-V-190805-S4FIV091A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5674L41 | No | UBE |  |  | 1 |  |  | Technical Services Data Conversion from csv | L3 Not Required |  |  | TRUE | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:52 | Kishi, Sayuri | 6/7/2019 | 6/7/2019 |  | 559 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:51 | Chiau, Liesbet | 56-F-EU-V-190527-S1FI057 |  | Yes | Yes |  |  |  | No KT |  |  | 56-F-EU-V-190527-S1FIV057A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642988 | No | UBE |  |  | 1 |  |  | Identify Unsigned Shipping Documents | L3 Not Required |  |  | TRUE | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 19\06\07 | 19\06\06 |  | 560 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:51 | Chiau, Liesbet | 56-F-EU-V-190530-S1FI018 |  | Yes | Yes |  |  | No retrofit required | No KT |  |  | 56-F-EU-V-190530-S1FIV018A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642988 | No | APPL |  |  | 999 |  |  | View Digital Signature | Obsolete | [5 empty] | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 561 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564288A | No | APPL |  |  | 1 |  |  | Attach reason code to Unsigned document | L3 Not Required |  |  | TRUE | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/7/2019 | 6/6/2019 |  | 562 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:51 | Chiau, Liesbet | 56-F-EU-V-190603-S1FI074 |  | Yes | Yes |  |  | As Baxter Sharepoint L2 not required . Hence Unit Test not done and moved for Baxter Review | No KT |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564289A | No | APPL |  |  | 1 |  |  | Attach reason code to cancelled signed documents | L3 Not Required |  |  | TRUE | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/7/2019 | 6/7/2019 |  | 563 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:51 | Chiau, Liesbet | 56-F-EU-V-190603-S1FI195 |  | Yes | Y |  |  |  | No KT |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5803012 | No | UBE | BXU548333 |  | 4 |  | CRP | New Customer Audit Report | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/7/2019 | 8/6/2019 |  | 564 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 08:40 | Joshi, Abhishek N | 56-F-EU-V-190801-S4FI079 | Audit / Report | Yes | Y | [6 empty] | 56-F-EU-V-190801-S4FIV079A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5909302 | No | APPL | BXU550350 |  | 4 |  | CRP | HI Principal/Commissionaire Object Mapping | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Robbin/Florencia | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/7/2019 | 8/6/2019 |  | 565 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 10:34 | Joshi, Abhishek N | 56-F-EU-V-190801-S4FI076 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FEC034 | No | UBE |  |  | 6 |  |  | FEC - Extractor CSV Statutory Accounting Audit File V4 | L3 Not Required |  |  | TRUE | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 9/18/2019 | 9/18/2019 |  | 566 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-18 05:19 | Haxton, Keith | 56-F-EU-V-190912-S6FI115 | Audit | Yes | Yes |  |  |  | NoKT |  |  | 56-F-EU-V-190912-S6FIV115A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R60A4310 | No | UBE |  |  | 6 |  | CRP | Proforma Invoice (OA) | L3 Not Required |  |  | TRUE | HNE2E |  | Finance External | Finance | Izaskun Ajuria | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 567 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-06 05:34 | Ajuria, Izaskun | [7 empty] | NoKT |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R60A4BX002 | No | UBE |  |  | 6 |  | CRP | Commission Credit Note X-ref u | L3 Not Required |  |  | TRUE | HNE2E |  | Finance External | Finance | Izaskun Ajuria | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 568 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-06 05:34 | Ajuria, Izaskun | [7 empty] | NoKT |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R60A4BX003 | No | UBE |  |  | 6 |  | CRP | Commission Exchange Rate Diffe | L3 Not Required |  |  | TRUE | HNE2E |  | Finance External | Finance | Izaskun Ajuria | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 569 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-06 05:35 | Ajuria, Izaskun | [7 empty] | NoKT |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600037 | No | UBE | BXU548844 |  | 3 |  | CRP | Populate Grants File - F590113 | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Eileen Paula | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 03/07/2019 | 03/07/2019 |  | 570 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 06:25 | Joshi, Abhishek N | 56- F-EU-V-190628-S3FI034 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5839902 | No | UBE | BXU545360 |  | 1 |  | CRP | Stock Valuation File Purge | L3 Pass |  |  | TRUE | LNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/7/2019 | 6/7/2019 |  | 571 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 05:09 | Joshi, Abhishek N | 56-F-EU-V-190604-S1FI077 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190604-S1FIV077A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R30835 | No | UBE | BXU546399 |  | 3 |  | CRP | Item Cost Component - Frozen U | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 06/28/2019 | 06/27/2019 |  | 572 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-05 06:25 | Joshi, Abhishek N | 56-F-EU-V-190626-S3FI020 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190626-S3FIV020A, 56-F-EU-V-190626-S3FIV020B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRAP126 | No | UBE | BXU546847 |  | 6 |  | CRP | Spain VAT Reporting - Account | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 9/03/2019 | 9/03/2019 |  | 573 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 09:10 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI050 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV050A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL113 | No | UBE | BXU545343 |  | 1 |  | CRP | CPA Status Detail Report - called by R55FRGL112 | L3 Pass |  |  | TRUE | HNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/3/2019 | 6/3/2019 |  | 574 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 00:10 | Joshi, Abhishek N | 56-F-EU-V-190524-S1FI051 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190524-S1FIV051A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560010CC | No | UBE |  |  | 5 |  | CRP | Canon Capture Company Extract | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/22/2019 | 8/21/2019 |  | 575 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-17 08:19 | Touyaa, Manuel | 56-F-EU-V-190816-S5FI099 |  | Yes | Y | [6 empty] | 56-F-EU-V-190816-S5FIV099A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560401CC | No | UBE |  |  | 5 |  | CRP | Canon Capture Supplier Extract | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete | Defect 295 _R560401CC report ends in error |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/22/2019 | 8/21/2019 |  | 576 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-17 08:48 | Touyaa, Manuel | 56-F-EU-V-190820-S5FI120 |  | Yes | Y | [6 empty] | 56-F-EU-V-190820-S5FIV120A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5774214 | No | APPL | BXU547660 |  | 1 |  | CRP | Purchase Receipts Inquiry - COMM - 43 | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/7/2019 | 6/7/2019 |  | 577 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 03:18 | Joshi, Abhishek N | 56-F-EU-V-190603-S1FI024 | Inquiry | Yes | Yes | [6 empty] | 56-F-EU-V-190603-S1FIV024A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R563B802 | No | UBE | BXU550737 |  | 1 |  | CRP | Update A/R from Address Book | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/3/2019 | 6/3/2019 |  | 578 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-20 06:57 | Joshi, Abhishek N | 56-F-EU-V-190523-S1FI048 |  | Yes | Y | [6 empty] | 56-F-EU-V-190523-S1FIV48A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P31114 | Yes | APPL | 1260283 | 1268370 | 2 |  |  | Work Order Completions | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/14/2019 | 6/13/2019 |  | 579 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-24 04:35 | Singh, Sunil Kumar | 56-F-EU-V-190611-S2LO062 |  | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190611-S2LOV062A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4310 | Yes | APPL |  |  | 2 |  |  | Purchase Orders AP: Passed L3 testing in 64 bit environment. | L3 Pass |  |  | TRUE | HE2E |  | Procurement | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 06/28/2019 | 06/10/2019 |  | 580 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-20 08:10 | Partanen, Aki | 56-F-EU-V-190605-S2LO001 |  | Yes | Y |  |  |  | KTW1 |  |  | 56-F-EU-V-190605-S2LO001A, 56-F-EU-V-190605-S2LO001B, 56-F-EU-V-190605-S2LO001C, 56-F-EU-V-190605-S2LO001D | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4312 | No | APPL | BXU545508 | BXU537484 | 2 |  |  | PO Receipts | L3 Pass |  |  | TRUE | HE2E |  | Procurement | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 06/20/2019 | 06/13/2019 |  | 581 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-27 03:03 | Singh, Sunil Kumar | 56-F-EU-V-190614-S2LO090 |  | Yes | Y |  |  |  | KTW1 |  |  | 56-F-EU-V-190614-S2LO090A, 56-F-EU-V-190614-S2LO090B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P43214 | Yes | APPL |  |  | 2 |  |  | Purchase Receipts Inquiry | L3 Pass |  |  | TRUE | H |  | Procurement | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 06/18/2019 | 06/17/2019 |  | 582 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:03 | Chiau, Liesbet | 56-F-EU-V-190612-S2LO073 | Inquiry | Yes | Y |  |  |  | KTW1 |  |  | 56-F-EU-V-190612-S2LO073A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P43250 | Yes | APPL |  | BXU545767, 1235851 | 2 |  |  | Receipt Routing Movement and Disposition | L3 Pass |  |  | TRUE | HE2E |  | Procurement | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/21/2019 | 6/21/2019 |  | 583 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-05 02:59 | Joshi, Abhishek N | 56- F-EU-V-190618-S2LO109 |  | Yes | Y |  |  |  | KTW1 |  |  | 56- F-EU-V-190618-S2LOV109A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P43252 | No | APPL | BXU549761 (19637) |  | 3 |  |  | Routing Ledger Inquiry | L3 Pass |  |  | TRUE | L |  | Procurement | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 07/08/2019 | 07/06/2019 |  | 584 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 07:59 | ANAND, S | 56-F-EU-V-190701-S3LO073 | Inquiry | Yes | Y |  |  |  | KTW1 |  |  | 56-F-EU-V-190701-S3LOV073A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P43253 | Yes | APPL |  | BXU537484, 1242970, BXU549773 (18513) | 3 |  |  | Routing Disposition | L3 Pass |  |  | TRUE | L |  | Procurement | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/5/2019 | 7/3/2019 |  | 585 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 07:30 | Singh, Sunil Kumar |  |  | Yes | Y |  |  |  | KTW1 |  |  | 56-F-EU-V-190701-S3LO011 | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4600 | No | APPL |  |  | 999 |  |  | Request Inquiry | Obsolete | [5 empty] | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 586 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet |  | Inquiry |  |  |  |  | configuration | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P46011 | No | APPL |  |  | 6 |  |  | Item Unit Of Measure Definition | L3 Not Required | [5 empty] | MDM | MDM | Carlos M. Barrera |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 587 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 04:00 | Greenard, Terry | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4605 | No | APPL |  |  | 999 |  |  | Location Detail Selection | Obsolete | [5 empty] | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 588 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P46130 | No | APPL |  |  | 999 |  |  | Online Putaway Reservations | Obsolete | [5 empty] | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 589 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P46321 | No | APPL |  |  | 999 |  |  | Location Detail Inquiry | Obsolete | [5 empty] | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 590 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet |  | Inquiry | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P47036 | Yes | APPL |  |  | 2 |  |  | Work With Ship Notice | L3 Pass |  |  | TRUE | LE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/26/2019 | 6/23/2019 |  | 591 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:03 | Chiau, Liesbet | 56-F-EU-V-190624-S2LO135 |  | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190624-S2LOV135A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P470371 | Yes | APPL |  |  | 2 |  |  | Work With Ship Notice Details | L3 Pass |  |  | TRUE | LE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/11/2019 | 6/10/2019 |  | 592 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:03 | Chiau, Liesbet | 56-F-EU-V-190610-S2LO019 |  | Yes | Y |  |  | Retrofitted | KTW3 |  |  | 56-F-EU-V-190610-S2LOV19A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4915 | Yes | APPL |  |  | 2 |  |  | Work with Shipments | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/28/2019 | 6/20/2019 |  | 593 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:03 | Chiau, Liesbet | 56-F-EU-V-190626-S2LO147 |  | Yes | Y |  |  |  | KTT2 |  |  | 56-F-EU-V-190626-S2LOV147A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P49151 | No | APPL |  |  | 1 |  |  | Work with Shipments - Manual Shipment Consolidation | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/22/2018 | 5/23/2018 |  | 594 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:51 | Chiau, Liesbet | 56-F-EU-V-190510-S1LO002 |  | Yes | Yes |  |  |  | KTT2 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4947 | No | APPL |  |  | 1 |  |  | Shipment Tracking | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 22-05-2019 | 22-05-2019 |  | 595 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:51 | Chiau, Liesbet | 56-F-EU-V-190513-S1LO003 |  | Yes | Yes |  |  |  | KTT1 |  |  | 56-F-EU-V-190513-S1LOV03A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4960 | No | APPL |  |  | 1 |  |  | Work With Loads | L3 Not Required |  |  |  | NA |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber | L2 Not required | No KT needed . Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma |  | na |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 596 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:51 | Chiau, Liesbet | [6 empty] | On Hold N/A for EMEA | na |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5543025 | No | APPL | BXU550719 | BXU544855 | 1 |  |  | PO Speed Status Update - BAX | L3 Pass |  |  | TRUE | L |  | Procurement | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 597 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-20 06:30 | Joshi, Abhishek N | 56-F-EU-V-190521-S1LO077 |  | Yes | Y |  |  |  | KTW1 |  |  | 56-F-EU-V-190521-S1LOV077A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P55PMI04 | Yes | APPL |  |  | 999 |  |  | QTS Interface Data | Obsolete | [5 empty] | Quality | Logistics | Miruna Danes, Douglas Roussel, Pawel Oskroba |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 598 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet |  | Interface | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P55PMI06 | Yes | APPL |  |  | 999 |  |  | Trackwise Setup Data Application (QTS) | Obsolete | [5 empty] | Quality | Logistics | Miruna Danes, Douglas Roussel, Pawel Oskroba |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 599 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet |  | Setup | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P55PMIZ1 | Yes | APPL |  |  | 999 |  |  | QTS Interface - Z File | Obsolete | [5 empty] | Quality | Logistics | Miruna Danes, Douglas Roussel, Pawel Oskroba |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 600 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet |  | Interface | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P560005S | Yes | APPL | 1262620 (6998) | 1264176 | 2 |  |  | Equipment Type Search and Select | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Leonard Dartois | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/11/2019 | 6/11/2019 |  | 601 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 05:18 | Singh, Sunil Kumar | 56-F-EU-V-190610-S2LO005 |  | Yes | Y |  |  | Serach & select : Calling from P564915A | KTW5 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5600099 | Yes | APPL | 1248870 (21934), 1274145 (50878) | 1248871, 1274146 | 4 | 4 |  | Manual Logistics WarehouseMove Ticket Application | L3 Pass | 179 | L3 Later Sprint | TRUE | H |  | Warehouse | Logistics | Leonard Dartois | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/11/2019 | 6/11/2019 |  | 602 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 10:50 | Singh, Sunil Kumar | 56-F-EU-V-190610-S2LO015 |  | Yes | Y |  |  | Retrofitted under sprit2 | KTW3 |  |  | 56-F-EU-V-190610-S2LOV15A, 56-F-EU-V-190610-S2LOV15B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P560018 | Yes | APPL | BXU545181 | BXU544870 | 5 |  |  | Intrastat Country Company File - Maintenance | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 08/12/2019 | 08/09/2019 |  | 603 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-21 07:11 | Joshi, Abhishek N | 56-F-EU-V-190812-S5LO016 | Maintenance | Yes | Yes |  |  |  | KTW4 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P560018T | No | APPL | BXU545181 |  | 5 |  |  | Intrastat Data Revisions | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/12/2019 | 8/12/2019 |  | 604 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-21 05:23 | Singh, Sunil Kumar | 56-F-EU-V-190812-S5LO006 | Revision | Yes | Yes |  |  |  | KTW4 |  |  | 56-F-EU-V-190812-S5LOV006A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P560018Y | No | APPL |  |  | 3 | 3 |  | Expeditor XML Generation | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 07/11/2019 | 07/11/2019 |  | 605 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-15 05:29 | weber, scott | 56-F-EU-V-190709-S3LO049 | XML | Yes | Y |  |  |  | various2 |  |  | 56-F-EU-V-190709-S3LOV049A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P560019 | No | APPL | BXU545181 (15081) | BXU544870 | 5 |  |  | Maintain the Customs/Intrastat Designation table | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/12/2019 | 8/9/2019 |  | 606 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 08:30 | Singh, Sunil Kumar | 56-F-EU-V-190812-S5LO003 | Maintenance | Yes | Yes |  |  |  | KTW1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P560020 | No | APPL | BXU545181 | BXU548166 | 5 |  |  | Intrastat Statistical Value Definition | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/12/2019 | 8/09/2019 |  | 607 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-21 08:21 | Joshi, Abhishek N | 56-F-EU-V-190812-S5LO004 |  | Yes | Yes |  |  |  | KTW1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P560021 | No | APPL | BXU545181 | BXU544918 | 5 |  |  | MRO item Intrastat Information | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/12/2019 | 8/12/2019 |  | 608 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-28 12:34 | Singh, Sunil Kumar | 56-F-EU-V-190812-S5LO024 |  | Yes | Yes |  |  |  | KTW1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P560070 | No | APPL | 1238862 (14849) | BXU544984 | 4 |  |  | Maintain EDI FFA Carrier Mode Of Transport Service Level | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Puneet Sharma | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/22/2019 | 7/22/2019 |  | 609 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-01 06:39 | Singh, Sunil Kumar | 56-F-EU-V-190722-S4LO020 | Maintenance | Yes | Y |  |  |  | KTS6 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P560120 | No | APPL | 1265079 (24737) | 1265080 | 2 |  |  | Forwarder Label Reprint | L3 Pass |  |  | TRUE | ME2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete | Printer not setup in 9.2DV. Baxter to test in L3. Mail attached for reference |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/11/2019 | 6/11/2019 |  | 610 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 10:47 | Singh, Sunil Kumar | 56-F-EU-V-190610-S2LO009 | Printer | Yes | Y |  |  |  | KTS6 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P560130 | No | APPL | 1257192 (27241) | 1258344 | 2 |  |  | Tote Bin Label Reprint | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 611 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 12:56 | Singh, Sunil Kumar | 56-F-EU-V-190610-S2LO001 | Printer | Yes | Y |  |  |  | KTW1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5641003 | Yes | APPL | 1258827, 1240723, BXU545198 (18880), BXU545199 (20555) | 1241633, BXU533972, BXU545986, 1258829 | 4 |  |  | WCS IG/IF Recovery App | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/22/2019 | 7/19/2019 |  | 612 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 13:58 | Singh, Sunil Kumar | 56-F-EU-V-190722-S4LO011 |  | Yes | Y |  |  |  | KTW1 |  |  | 56-F-EU-V-190722-S4LOV011A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5641004 | Yes | APPL | 1240723 (18880) | 1241633, BXU545986 | 4 |  |  | WCS Open Requests | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/22/2019 | 7/19/2019 |  | 613 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 13:47 | Singh, Sunil Kumar | 56-F-EU-V-190722-S4LO004 |  | Yes | Y |  |  |  | KTW1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5641005 | Yes | APPL | 1250897 (22485) | 1250898, 1258829, 1242681, 1266997 (11226), 1244875 (19727) | 6 | 6 |  | Inventory Transaction Processor | L3 Not Required |  |  | TRUE | H |  | Warehouse | Logistics | Leonard Dartois | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 28/05/2019 | 28/05/2019 |  | 614 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 08:27 | Singh, Sunil Kumar | 56-F-EU-V-190523-S1LO099 |  | Yes | Y |  |  | Move to CRP | KTW1 |  |  | 56-F-EU-V-190523-S1LOV99A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5641006 | No | APPL |  | BXU547216, BXU547662 | 2 |  |  | Item Availability by Grade | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Leonard Dartois | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 11/06/19 | 11/06/19 |  | 615 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-21 08:31 | Joshi, Abhishek N | 56-F-EU-V-190610-S2LO010 |  | Yes | Yes |  |  |  | KTW1 |  |  | 56-F-EU-V-190610-S2LOV10A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5641007 | No | APPL | 1258604 (25917) | 1258609 (25917) | 1 |  |  | Logistics WarehouseItem Attributes | L3 Pass |  |  | TRUE | H |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 28-05-19 | 28-05-19 |  | 616 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 02:06 | Singh, Sunil Kumar | 56-F-EU-V-190517-S1LO043 |  | Yes | Yes |  |  |  | KTW1 |  |  | 56-F-EU-V-190517-S1LOV43A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5641009 | Yes | APPL | 1267375 | 1267378 (15408) | 3 |  |  | Pobis Changes: BSFN Mappings | L3 Pass |  |  | TRUE | H |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/02/2019 | 7/01/2019 |  | 617 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-29 09:45 | Singh, Sunil Kumar | 56-F-EU-V-190701-S3LO016 |  | Yes | Y |  |  | Retrofit not required | KTW1 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5641014 | No | APPL | 1258611 (25919) | 1258613 | 1 |  |  | Logistics WarehouseOnline Stock Inquiry | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 19/05/28 | 19/05/28 |  | 618 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 08:31 | Singh, Sunil Kumar | 56-F-EU-V-190528-S1LO121 | Inquiry | Yes | Yes |  |  | No retrofit required | KTW1 |  |  | 56-F-EU-V-190528-S1LOV121A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5641016 | Yes | APPL | 24450, 16250 (1242679) | 1254243(24450), 16250 (1242681) | 1 |  |  | Transaction Control Maintenance Application | L3 Pass |  |  | TRUE | H |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/28/2019 | 5/27/2019 |  | 619 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-29 10:44 | Singh, Sunil Kumar | 56-F-EU-V-190520-S1LO067 | Maintenance | Yes | Yes |  |  | Retrofit not required | KTW1 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5641017 | No | APPL |  | BXU545108 | 4 |  |  | Customer Demand - Filter Table review | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/22/2019 | 7/19/2019 |  | 620 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-21 08:34 | Joshi, Abhishek N | 56-F-EU-V-190722-S4LO001 |  | Yes | Y |  |  |  | KTW1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5641020 | No | APPL | 24167 (1251754), 1248389 (21264) | 1249499 (21264), 1250902 (23763), 1251660 (24032), 1251775 (24363), 24167 (1251755) | 3 |  |  | Bollini Extract | L3 Pass | 171 | Closed | TRUE | LE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 07/01/2019 | 07/01/2019 |  | 621 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-05 13:10 | Singh, Sunil Kumar | 56-F-EU-V-190701-S3LO012 |  | Yes | Y |  |  | Review E2E process exists | KTW4 |  |  | 56-F-EU-V-190701-S3LOV012A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564102C | No | APPL | 1248389 (21264) | 1249499 (21264) | 3 |  |  | Bollini Control table setup | L3 Pass |  |  | TRUE | LE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/1/2019 | 7/1/2019 |  | 622 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-05 13:15 | Singh, Sunil Kumar | 56-F-EU-V-190628-S3LO003 | Setup | Yes | Y |  |  | Review E2E process exists | KTW4 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564102O | No | APPL | 1248389 (21264) | 1249499 (21264) | 4 |  |  | Set Bollini Overrides | L3 Pass |  |  | TRUE | LE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/22/2019 | 7/19/2019 |  | 623 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-05 13:16 | Singh, Sunil Kumar | 56-F-EU-V-190722-S4LO012 |  | Yes | Y |  |  | Review E2E process exists | KTW1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5641034 | No | APPL | 1257268 (21893) | 1257269 | 1 |  |  | Inventory Status Inquiry Application | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/24/2019 | 5/24/2019 |  | 624 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-12 05:07 | Singh, Sunil Kumar | 56-F-EU-V-190515-S1LO032 | Inquiry | Yes | Y |  |  |  | KTW1 |  |  | 56-F-EU-V-190515-S1LOV032A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564108A | Yes | APPL |  | 1241781 (17044) | 2 |  |  | On Status Shipment Relationships | L3 Pass |  |  | TRUE | H |  | Quality | Logistics | Miruna Danes | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/28/2019 | 6/27/2019 |  | 625 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-30 02:45 | Singh, Sunil Kumar | 56-F-EU-V-190625-S2LO146 |  | Yes | Y |  |  |  | KTQ1 |  |  | 56-F-EU-V-190625-S2LOV146A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564108C | Yes | APPL | BXU542225 | 11407 BXU545517 | 3 |  |  | POBS JDE to WMS RTE Re-Send | L3 Pass |  |  | TRUE | H |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 07/01/2019 | 07/01/2019 |  | 626 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 05:08 | Vishnubhatla, Mithra | 56-F-EU-V-190701-S3LO009 |  | Yes | Y |  |  |  | KTW1 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564108P | Yes | APPL | BXU545597 (17303),BXU545921 (15840) | 11407&nbsp; 1241568 15840 | 1 |  |  | Maintain Move Ticket Print Requirements Table | L3 Pass |  |  | TRUE | H |  | Quality | Logistics | Miruna Danes | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/24/2019 | 5/24/2019 |  | 627 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 05:10 | Singh, Sunil Kumar | 56-F-EU-V-190515-S1LO025 | Maintenance / Printer | Yes | Yes |  |  |  | KTQ1 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564108Z | Yes | APPL |  | 1241781 (17044) | 4 |  |  | Work With Inbound Status Flag Integration | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Douglas Roussel | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/22/2019 | 7/22/2019 |  | 628 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-30 02:58 | Singh, Sunil Kumar | 56-F-EU-V-190722-S4LO009 | Inbound | Yes | Y |  |  |  | KTQ2 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564116 | Yes | APPL | 1222622 | 11409 1223007 | 3 |  |  | WMS QC Status - JDE Location Mapping | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/2/2019 | 7/2/2019 |  | 629 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 05:50 | Vishnubhatla, Mithra | 56-F-EU-V-190628-S3LO007 |  | Yes | Y |  |  |  | KTW1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564121 | Yes | APPL | BXU545445, 1255076 (21228) BXU545449 11411 14060 15519 21228 21824 | 11411 1269575&nbsp; 14060; BXU545543 ;&nbsp; 1241410&nbsp; 21228&nbsp; 1255077 21824 1251324 | 1 |  |  | Stock Quantity Synchronisation Errors | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/24/2019 | 5/24/2019 |  | 630 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-27 07:53 | Vishnubhatla, Mithra | 56-F-EU-V-190520-S1LO064 | Error | Yes | Yes |  |  | Retrofit Not Required | KTW1 |  |  | 56-F-EU-V-190520-S1LOV64A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564121Z | Yes | APPL | BXU545445, BXU545446 (21832) | 21824 1251324 | 4 |  |  | Whse Stock Recon Appl | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/22/2019 | 7/19/2019 |  | 631 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 07:40 | Singh, Sunil Kumar | 56-F-EU-V-190722-S4LO010 |  | Yes | Y |  |  |  | KTW1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642001 | Yes | APPL | 1222943 1240724 | 11405 1223006 15528 1241315 | 2 |  |  | Pack Confirm App | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/28/2019 | 6/28/2019 |  | 632 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 08:23 | Vishnubhatla, Mithra | 56-F-EU-V-190702-S2LO150 |  | Yes | Y |  |  |  | KTW1 |  |  | 56-F-EU-V-190702-S2LOV150A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642002 | Yes | APPL | 1240724 (15528) | 1241315 15528 | 4 | 4 |  | Pack Confirm: Recovery | L3 Pass |  |  | TRUE | H |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete | This object will be tested in sprit 4 as it has dependancy on R56PL42535 which is a sprint 4 object |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/28/2019 | 6/27/2019 |  | 633 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 08:25 | Vishnubhatla, Mithra | 56-F-EU-V-190625-S2LO142 |  | Yes | Y |  |  | Retrofit not required | KTW1 |  |  | 56-F-EU-V-190625-S2LOV142A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642003 | Yes | APPL | 1222930 | 1224451 (11404) | 3 |  |  | Maintain SO Interface Message Statuses | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/2/2019 | 7/1/2019 |  | 634 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-30 08:38 | Singh, Sunil Kumar | 56-F-EU-V-190628-S3LO001 | Maintenance / Interface | Yes | Y |  |  |  | KTW1 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642004 | No | APPL | 1222666 | BXU545619 | 1 |  |  | SO Interface WHSE Printer Location Management | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete | issue reported |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 19\05\21 | 19\05\21 |  | 635 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-21 08:37 | Joshi, Abhishek N | 56-F-EU-V-190516-S1LO001 | Printer / Interface | Yes | Yes |  |  |  | KTW1 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642005 | No | APPL | 1222930 | 1224451 (11404) | 1 |  |  | Review SO Interface Errors | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/21/2019 | 5/21/2019 |  | 636 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-30 08:39 | Singh, Sunil Kumar | 56-F-EU-V-190516-S1LO002 | Error / Interface | Yes | Yes |  |  | Retrofit Not Required | KTW1 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642006 | No | APPL | 1222930 | 1224451 (11404) | 1 |  |  | Maintain Order & Order Line Interface Map | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/21/2019 | 5/21/2019 |  | 637 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-30 08:40 | Singh, Sunil Kumar | 56-F-EU-V-190515-S1LO015 | Maintenance / Interface | Yes | Yes |  |  |  | KTW1 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642007 | Yes | APPL | BXU545783 | 12405 BXU545748 | 1 |  |  | Maintain Lot Grade & QC Status Rules | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/21/2019 | 5/21/2019 |  | 638 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 08:29 | Vishnubhatla, Mithra | 56-F-EU-V-190517-S1LO057 | Maintenance | Yes | Yes |  |  |  | KTW1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642008 | No | APPL | 1222930 | 1224451 (11404) | 2 |  |  | Maintain Shipment Locking Rules | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 06/28/2019 | 06/27/2019 |  | 639 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-30 08:42 | Singh, Sunil Kumar | 56-F-EU-V-190611-S2LO058 | Maintenance | Yes | Y |  |  |  | KTT1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642010 | No | APPL | 1222930 | 1224451 (11404) | 1 |  |  | Maintain Shipment Types | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics |  | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/20/2019 | 5/20/2019 |  | 640 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-30 08:44 | Singh, Sunil Kumar | 56-F-EU-V-190513-S1LO007 | Maintenance | Yes | Y |  |  | done. Index verified. DS generated. No PO exists. L1 done. | KTT1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642012 | No | APPL | 1222930 | 1224451 (11404) | 3 |  |  | Maintain Pallet Types | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 07/02/2019 | 07/01/2019 |  | 641 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-30 08:45 | Singh, Sunil Kumar | 56-F-EU-V-190701-S3LO015 | Maintenance | Yes | Y |  |  |  | KTT1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642013 | Yes | APPL | 1222930 | 1224451 (11404) | 2 |  |  | Maintain Document Type to QC Status Map | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Leonard Dartois | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 26/06/2019 | 26/06/2019 |  | 642 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-30 08:47 | Singh, Sunil Kumar | 56-F-EU-V-190625-S2LO001 | Maintenance | Yes | Y |  |  |  | KTW1 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642014 | No | APPL | 1222930 | 1224451 (11404) | 1 |  |  | Maintain Pick And Pack Instructions | L3 Not Required |  |  | TRUE | L |  | Warehouse | Logistics |  | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/23/2019 | 5/23/2019 |  | 643 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-30 08:49 | Singh, Sunil Kumar | 56-F-EU-V-190516-S1LO036 | Maintenance | Yes | Y |  |  | on Hold not applicable for EMEA | KTW1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642015 | No | APPL |  |  | 999 |  |  | Pallet Tracking Maintenace Application | Obsolete |  |  |  | NA |  | Transportation | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 644 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet |  | Maintenance | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642016 | No | APPL | 1248691 (22032) | 1250559 | 2 |  |  | Batch Reservations Inquiry | L3 Pass |  |  | TRUE | H |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/27/2019 | 6/26/2019 |  | 645 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 05:40 | Singh, Sunil Kumar | 56-F-EU-V-190625-S2LO145 | Inquiry | Yes | Y |  |  |  | KTW1 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642017 | Yes | APPL | BXU545198 (18880) | BXU533972 | 4 |  |  | WCS Message Recovery - Picking | L3 Pass |  |  | TRUE | H |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/22/2019 | 7/19/2019 |  | 646 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-05 05:34 | Singh, Sunil Kumar | 56-F-EU-V-190723-S4LO034 |  | Yes | Y |  |  |  | KTW1 |  |  | 56-F-EU-V-190723-S4LOV034A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642018 | No | APPL |  |  | 2 |  |  | Set up Zebra Defaults by machine | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/27/2019 | 6/26/2019 |  | 647 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:03 | Chiau, Liesbet | 56-F-EU-V-250619-S2LO139 |  | Yes | Y |  |  |  | KTW1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642019 | No | APPL | 1265850 | 1265851&nbsp;&nbsp; 13827, BXU549012, BXU547513 | 2 |  |  | Maintain Zebra Label Raw Code | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/25/2019 | 6/24/2019 |  | 648 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 09:17 | Joshi, Abhishek N | 56-F-EU-V-190624-S2LO132 | Maintenance | Yes | Y |  |  | Retrofit not required | KTW1 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642020 | Yes | APPL | BXU545198 (18880) | BXU533972 | 4 |  |  | WCS SH/SP Message Recovery - Resending | L3 Pass |  |  | TRUE | MNE2E |  | Transportation | Logistics | Puneet Sharma | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/23/2019 | 7/22/2019 |  | 649 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-05 05:38 | Singh, Sunil Kumar | 56-F-EU-V-190722-S4LO027 |  | Yes | Y |  |  |  | various |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642021 | Yes | APPL | 1271560 | 1241631 (15819) | 2 |  |  | Maintain QC Status mapping table | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Leonard Dartois | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 06/27/2019 | 06/27/2019 |  | 650 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-30 08:06 | Singh, Sunil Kumar | 56-F-EU-V-190611-S2LO056 | Maintenance | Yes | Y |  |  |  | KTW1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642022 | No | APPL | 1240716 (15523) | 15523 1241119 | 4 |  |  | WCS Order Reference | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/23/2019 | 7/22/2019 |  | 651 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 08:43 | Vishnubhatla, Mithra | 56-F-EU-V-190723-S4LO031 |  | Yes | Y |  |  |  | KTT1 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642023 | Yes | APPL | BXU548594 20231 | BXU547952 20231 | 4 |  |  | WCS SF Message Recovery | L3 Pass |  |  | TRUE | H |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/23/2019 | 7/22/2019 |  | 652 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 08:02 | ANAND, S | 56-F-EU-V-190722-S4LO021 |  | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190722-S4LOV021A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642024 | Yes | APPL | BXU548594 (20231) | 20231 BXU547951 | 4 |  |  | WCS Order Number XRef Maintenance | L3 Pass |  |  | TRUE | H |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/23/2019 | 7/22/2019 |  | 653 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 06:51 | Singh, Sunil Kumar | 56-F-EU-V-190722-S4LO013 | Maintenance | Yes | Y |  |  |  | KTW1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642027 | No | APPL | 1240722 (15527) | 1241039 15527 | 4 |  |  | WCS SM Header Text Inquiry and Maintenance | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/23/2019 | 7/22/2019 |  | 654 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 07:21 | Singh, Sunil Kumar | 56-F-EU-V-190722-S4LO005 | Inquiry / Maintenance / Text | Yes | Y |  |  |  | KTW1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642028 | No | APPL | 1240722 (15527), 1248691 (22032) | 1241309 15527 | 4 |  | 56-F-EU-V-190722-S4LO002 | WCS Ship Note Inquiry and Maintenance | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/23/2019 | 7/22/2019 |  | 655 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 14:08 | Singh, Sunil Kumar |  | Inquiry | Yes | Y |  |  |  | KTW1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564202A | OBS | APPL |  |  | 999 |  |  | Revise HWT WISOPU outbound records | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 656 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet |  | Outbound | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642030 | No | APPL |  |  | 999 |  |  | Pallet Enquiry | Obsolete |  |  |  | NA |  | Transportation | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 657 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet |  | Inquiry | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642031 | No | APPL |  |  | 999 |  |  | ePedigree User Interface | Obsolete |  |  |  | L |  | Quality | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 658 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet |  | Interface | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642032 | No | APPL |  |  | 999 |  |  | ePedigree Workfile Maintenance | Obsolete |  |  |  | L |  | Quality | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 659 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet |  | Maintenance | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642035 | Yes | APPL | 1240725, 1258803 (25961) | 1259574 25961 | 2 |  |  | WUK Shipment Feedback Recovery | L3 Pass |  |  | TRUE | H |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 660 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 08:47 | Singh, Sunil Kumar | 56-F-EU-V-190610-S2LO031 |  | Yes | Y |  |  |  | KTW1 |  |  | 56-F-EU-V-190610-S2LOV31A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564204S | No | APPL |  |  | 1 |  |  | SO Interface WHSE Printer Location Search and Select | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/28/2019 | 5/27/2019 |  | 661 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:51 | Chiau, Liesbet | 56-F-EU-V-190527-S1LO117 | Printer / Interface | Yes | Yes |  |  | Its a Search/Select form and Entry point As per 812 & 920 Xref the P564204S application is not called by any application neither this application is calling any other application. Hence Unit tested the application directly | KTW1 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642053 | Yes | APPL | 1253299 (22471) |  | 2 |  |  | EMEA Locate Goods - Manual Branch | L3 Pass | 130 | Closed | TRUE | HE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 06/27/2019 | 06/26/2019 |  | 662 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-09 06:10 | Singh, Sunil Kumar | 56-F-EU-V-190617-S2LO097 |  | Yes | Y |  |  | Jazz Error | KTW3 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642056 | Yes | APPL | BXU532401, BXU532402 (146168) | BXU532403 146168 | 2 |  |  | Override Lot Grade in Sales Order | L3 Pass |  |  | TRUE | H |  | Quality | Logistics | Pawel Oskroba | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/27/2019 | 6/27/2019 |  | 663 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 00:05 | Singh, Sunil Kumar | 56-F-EU-V-190611-S2LO066 |  | Yes | Y |  |  |  | KTQ4 |  |  | 56-F-EU-V-190611-S2LOV066A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564210A | Yes | APPL | 1266846 1253922 | 1266848 20546 1254243 24450 | 2 |  |  | Replenishment Order Call Control Maintenance | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/27/2019 | 6/26/2019 |  | 664 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 06:49 | ANAND, S | 56-F-EU-V-190625-S2LO140 | Maintenance | Yes | Y |  |  |  | KTW3 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564210B | No | APPL | 1266846 (20546), 1258020 (23122) | 1266848 (20546), 1258021 (23122) | 1 |  |  | Replenishment Orders Version Control Application | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete | Data needed |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/28/2019 | 5/28/2019 |  | 665 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-09 06:11 | Singh, Sunil Kumar | 56-F-EU-V-190523-S1LO106 |  | Yes | Y |  |  |  | KTW1 |  |  | 56-F-EU-V-190523-S1LOV106A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564215A | No | APPL | BXU545443 |  | 1 |  |  | Shipment Status Recovery | L3 Pass |  |  | TRUE | MNE2E |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 31/05/2019 | 31/05/2019 |  | 666 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 04:46 | Joshi, Abhishek N | 56-F-EU-V-190520-S1LO068 |  | Yes | Y |  |  |  | KTS6 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564215Z | No | APPL |  |  | 4 |  |  | Single Transportation Screen - Inquiry | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Puneet Sharma | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 07/23/2019 | 07/22/2019 |  | 667 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-01 22:50 | Sharma, Puneet | 56-F-EU-V-190722-S4LO022 | Inquiry | Yes | Y |  |  |  | KTT1 |  |  | 56-F-EU-V-190722-S4LOV022A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564234 | No | APPL |  |  | 3 |  |  | Pallet Tails Application | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 668 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-10 04:30 | De Brouwer, Peter | 56-F-EU-V-190701-S3LO001 |  | Yes | Y |  |  |  | KTW3 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5643001 | No | APPL |  |  | 1 |  |  | Receiving Repository Inquiry | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/28/2019 | 5/28/2019 |  | 669 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:52 | Chiau, Liesbet | 56-F-EU-V-190524-S1LO109 | Inquiry | Yes | Y |  |  | Index verified. DS generated. L1 done. No Proc Option. | FCA2 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5643002 | No | APPL |  |  | 2 |  |  | View Invoices and Receipts | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 18/06/19 | 18/06/19 |  | 670 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-12 05:03 | Destrebecq, Eric | 56-F-EU-V-190618-S2LO105 |  | Yes | Yes |  |  |  | FCA2 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5643003 | No | APPL |  | BXU516809 | 2 |  |  | Invoice File Upload - Inbound | L3 Pass | 156 | Closed | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/25/2019 | 6/25/2019 |  | 671 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-22 03:23 | Joshi, Abhishek N | 56-F-EU-V-240619-S2LO127 | Upload | Yes | Y |  |  | VV-23/06 Moved to Sprint 2 as per request from Eric | FCA2 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5643004 | No | APPL |  |  | 3 |  |  | Unallocated Receipts Inquiry | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/02/2019 | 6/28/2019 |  | 672 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-11 02:00 | Destrebecq, Eric | 56- F-EU-V-190701-S3LO010 | Inquiry | Yes | Y |  |  |  | FCA2 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5643007 | Yes | APPL | 1240727 | 1239326 | 2 |  |  | MILD-JDE Lot Status Translation | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/26/2019 | 6/26/2019 |  | 673 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-28 04:50 | Singh, Sunil Kumar | 56-F-EU-V-190619-S2LO116 |  | Yes | Y |  |  |  | KTW1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5643008 | No | APPL | 1240727, 1249510 (22075) | 1239326 | 5 | 5 |  | MILD Fast Transit Rejected Messages | L3 Pass |  |  | TRUE | H |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 674 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 07:53 | Singh, Sunil Kumar | 56-F-EU-V-190624-S2LO002 |  | Yes | Y |  |  |  | KTW1 |  |  | 56-F-EU-V-190624-S2LOV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5643009 | Yes | APPL | 1246226 (20497) | BXU546266 (20497) | 2 |  |  | On-Status ASN Relationship | L3 Pass |  |  | TRUE | H |  | Quality | Logistics | Miruna Danes | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 27/06/2019 | 27/06/2019 |  | 675 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 08:03 | ANAND, S | 56-F-EU-V-190624-S2LO004 |  | Yes | Y |  |  |  | KTW1 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5643018 | No | APPL | 1240712 (18324) |  | 2 |  |  | Preferred Receiving Logistics WarehouseMaintenance | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/26/2019 | 6/25/2019 |  | 676 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 05:31 | Singh, Sunil Kumar | 56-F-EU-V-190625-S2LO144 | Maintenance | Yes | Y |  |  |  | KTW1 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564303H | No | APPL |  |  | 4 |  |  | Freight Cost Allocation History INBOUND | L3 Not Required |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/5/2019 | 8/2/2019 |  | 677 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-08 03:22 | Destrebecq, Eric | 56-F-EU-V-190731-S4LO085 | Inbound | Yes | Y |  |  | On Hold N/A for EMEA | na |  |  | NA | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5643090 | No | APPL | BXU545508 | BXU537484 | 1 |  |  | Default Supplier Route Code | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/27/2019 | 5/27/2019 |  | 678 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-27 03:17 | Singh, Sunil Kumar | 56-F-EU-V-190516-S1LO038 |  | Yes | Y |  |  | No Retrofit Required | KTW1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5643121 | Yes | APPL | 1247266 (20658) | BXU546335 (20658) | 2 |  |  | SSCC18 Recovery Application | L3 Pass |  |  | TRUE | H |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/26/2019 | 6/25/2019 |  | 679 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 08:19 | ANAND, S | 56-F-EU-V-190625-S2LO143 |  | Yes | Y |  |  |  | KTW1 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5643129 | No | APPL | 1258017 (26923) | 1258019 (26923) | 1 |  |  | Receipt Routing Mass Update | L3 Pass |  |  | TRUE | LE2E |  | Procurement | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/27/2019 | 5/26/2019 |  | 680 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 08:24 | ANAND, S | 56-F-EU-V-190517-S1LO055 |  | Yes | Yes |  |  | Review E2E process exists | KTW3 |  |  | 56-F-EU-V-190517-S1LOV55A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564312A | No | APPL | BXU545508 | BXU537484 | 3 |  |  | WMS Split Pallet | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/2/2019 | 7/2/2019 |  | 681 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-27 03:18 | Singh, Sunil Kumar | 56-F-EU-V-190628-S3LO008 |  | Yes | Y |  |  |  | KTW1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5643214 | Yes | APPL | 1240671 (18132), 1253299 (22471) | 1241784 (18132), BXU546336 (20657), 1253300 (22471) | 1 |  |  | EMEA Purchase Receipts Inquiry | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete | Asked SME to check the issue |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/27/2019 | 5/27/2019 |  | 682 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 08:44 | ANAND, S | 56-F-EU-V-190521-S1LO087 | Inquiry | Yes | Y |  |  |  | KTW1 |  |  | 56-F-EU-V-190521-S1LOV087A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564321R | Yes | APPL | BXU545313 (111289) | BXU517770 (111289) | 1 |  |  | EMEA Purchase Receipts Inquiry | L3 Pass |  |  | TRUE | LNE2E |  | Procurement | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 27/05/2019 | 27/05/2019 |  | 683 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-09 06:27 | Singh, Sunil Kumar | 56-F-EU-V-190515-S1LO022 | Inquiry | Yes | Y |  |  |  | KTW1 |  |  | 56-F-EU-V-190515-S1LOV22A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5646001 | Yes | APPL | 1222675 | 1223173 | 2 |  |  | Trusted Sites Table Maintenance | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Leonard Dartois | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 06/26/2019 | 06/26/2019 |  | 684 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-28 21:29 | Singh, Sunil Kumar | 56-F-EU-V-190611-S2LO054 | Maintenance | Yes | Y |  |  |  | KTW1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5646002 | Yes | APPL |  | 1223173 | 2 |  |  | Global Logistics Warehouseattributes maintenance | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 685 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-28 21:33 | Singh, Sunil Kumar | 56-F-EU-V-190610-S2LO030 | Maintenance | Yes | Y |  |  |  | KTW1 |  |  | 56-F-EU-V-190610-S2LOV30A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5647006 | No | APPL | 1235782 (14853) | BXU547926 (14853) | 4 |  |  | EDI FFA Audit Enquiry | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/23/2019 | 7/22/2019 |  | 686 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-14 09:49 | ANAND, S | 56-F-EU-V-190722-S4LO015 | Inquiry / Audit | Yes | Y |  |  |  | KTS6 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5647010 | No | APPL | BXU545217 107665 |  | 2 |  |  | Inbound EDI Order Inquiry - SFDC | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 687 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 04:09 | Vishnubhatla, Mithra | 56-F-EU-V-190610-S2MO010 | Inquiry / Inbound | Yes | [7 empty] | 56-F-EU-V-190610-S2MOV10A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5647019 | No | APPL |  |  | 2 |  |  | Sales Order Error | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 06/28/2019 | 06/27/2019 |  | 688 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 05:58 | Kamatham, Deepika | 56-F-EU-V-190617-S2OM034 | Error | Yes | Y | [6 empty] | 56-F-EU-V-190617-S2OMV034A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5647071 | No | APPL | 1240731 (17485) | 1240751 (17485) | 2 |  |  | Register Number Requirement Maintenance | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/26/2019 | 6/25/2019 |  | 689 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 09:34 | ANAND, S | 56-F-EU-V-190614-S2LO089 | Maintenance | Yes | Yes |  |  |  | KTW3 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5647118 | No | APPL |  | BXU544917 | 6 | 6 |  | Intrastat Inbound Transaction Maintenance | L3 Pass | 150 | Closed | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 25/06/2019 | 25/06/2019 |  | 690 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-22 03:40 | Joshi, Abhishek N | 56-F-EU-V-190624-S2LO003 | Maintenance / Inbound | Yes | Y |  |  |  | KTW5 |  |  | 56-F-EU-V-190624-S2LOV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5647210 | Yes | APPL | 1264842 (11672) | 1264843 (11672) | 5 |  |  | SAP Inventory Conversion Data Maintenance | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 08/12/2019 | 08/09/2019 |  | 691 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 09:41 | ANAND, S | 56-F-EU-V-190812-S5LO023 | Maintenance | Yes | Yes |  |  |  | KTW4 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56472Z1 | OBS | APPL |  |  | 999 |  |  | F56472Z1 Maintenance Application | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 692 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet |  | Maintenance | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5647341 | Yes | APPL | 1253922 (24450) | 1254243 (24450) | 3 |  |  | APS Maintenance App | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/2/2019 | 7/1/2019 |  | 693 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 05:21 | Singh, Sunil Kumar | 56-F-EU-V-190701-S3LO018 | Maintenance | Yes | Y |  |  |  | KTW1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564736 | No | APPL | BXU546232 (19778), 1235782 (14853) | BXU546352, 1235723 (14853) | 3 | 3 |  | Maintain/Send Freight Forwarder EDI Data | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Puneet Sharma | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/18/2019 | 7/17/2019 |  | 694 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 10:15 | ANAND, S | 56-F-EU-V-190717-S3LO153 | Maintenance | Yes | Y |  |  |  | KTS6 |  |  | 56-F-EU-V-190717-S3LOV153A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564738 | Yes | APPL | 1241626 (17985) | 1242778 (17985) | 4 |  |  | EDI FFA Weight and Production Types Maintenance | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Puneet Sharma | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/23/2019 | 7/22/2019 |  | 695 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 10:22 | ANAND, S | 56-F-EU-V-190722-S4LO029 | Maintenance | Yes | Y |  |  |  | KTS6 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564742 | No | APPL |  | BXU547742 | 1 |  |  | Work with System Integrated SO Cross Reference | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Leonard Dartois | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/31/2019 | 5/31/2019 |  | 696 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-22 03:48 | Joshi, Abhishek N | 56-F-EU-V-190517-S1LO047 | Cross Refer | Yes | Y |  |  |  | KTW1 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564749A | No | APPL |  |  | 3 |  |  | Maintain Paragon Outbound Load Planning | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/3/2019 | 7/2/2019 |  | 697 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-15 08:37 | Destrebecq, Eric | 56-F-EU-V-190702-S3LO029 | Maintenance / Outbound | Yes | Y |  |  |  | KTT5 |  |  | 56-F-EU-V-190702-S3LOV29A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564750A | No | APPL |  |  | 3 |  |  | Maintain Inbound Load Planning | L3 Pass | 162 | Closed | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/3/2019 | 7/2/2019 |  | 698 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-05 03:26 | Chiau, Liesbet | 56-F-EU-V-190703-S3LO032 | Maintenance / Inbound | Yes | Y |  |  |  | KTT5 |  |  | 56-F-EU-V-190703-S3LOA032A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649001 | No | APPL |  | BXU546111 | 2 |  |  | Shipping Repository Inquiry | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/25/2019 | 6/24/2019 |  | 699 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-22 04:01 | Joshi, Abhishek N | 56-F-EU-V-190620-S2LO124 | Inquiry | Yes | Y |  |  |  | FCA OUT |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649002 | No | APPL |  | BXU546815, BXU547082, BXU547040, BXU547089, BXU546258, BXU547164, BXU547512 | 2 |  |  | Invoice Inquiry | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/26/2019 | 6/25/2019 |  | 700 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-22 04:31 | Joshi, Abhishek N | 56-F-EU-V-250619-S2LO143 | Inquiry | Yes | Y |  |  |  | FCA OUT |  |  | 56-F-EU-V-250619-S2LOV143A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649003 | No | APPL |  |  | 2 |  |  | Manual Invoice Entry | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 06/25/2019 | 06/24/2019 |  | 701 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-10 03:35 | Destrebecq, Eric | 56-F-EU-V-190611-S2LO053 |  | Yes | Y |  |  |  | FCA OUT |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649004 | No | APPL |  |  | 2 |  |  | View Invoices and Shipments | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 702 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-10 03:49 | Destrebecq, Eric | 56-F-EU-V-190610-S2LO029 |  | Yes | Y |  |  |  | FCA OUT |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649005 | No | APPL |  | BXU516809, BXU547040, BXU547165, BXU546258 | 4 |  |  | Invoice File Upload - Outbound | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Puneet Sharma | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/23/2019 | 7/22/2019 |  | 703 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 09:26 | Joshi, Abhishek N | 56-F-EU-V-190723-S4LO032 | Upload / Outbound | Yes | Y |  |  |  | FCA OUT |  |  | 56-F-EU-V-190723-S4LOV032A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649006 | No | APPL |  | BXU547378 | 2 | 3 |  | Unallocated Invoices in Suspense Account | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/25/2019 | 6/24/2019 |  | 704 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 09:30 | Joshi, Abhishek N | 56-F-EU-V-190614-S2LO082 |  | Yes | Yes |  |  |  | FCA OUT |  |  | 56-F-EU-V-190614-S2LOV082A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649007 | No | APPL |  |  | 2 |  |  | Unallocated Shipments Inquiry | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/25/2019 | 6/23/2019 |  | 705 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-12 08:41 | Destrebecq, Eric | 56-F-EU-V-190611-S2LO065 | Inquiry | Yes | Y |  |  |  | FCA OUT |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649008 | No | APPL |  | BXU545926 | 2 | 3 |  | Invoice Status Update | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 06/25/2019 | 06/24/2019 |  | 706 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 09:33 | Joshi, Abhishek N | 56-F-EU-V-190625-S2LO141 |  | Yes | Y |  |  |  | FCA OUT |  |  | 56-F-EU-V-190625-S2LOV141A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649009 | No | APPL |  |  | 2 |  |  | Work With Valid Suspense Accounts | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/25/2019 | 6/24/2019 |  | 707 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:04 | Chiau, Liesbet | 56-F-EU-V-190618-S2LO105 |  | Yes | Y |  |  |  | FCA OUT |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564900P | No | APPL |  | BXU547166 | 3 |  |  | Load Planning Interface - EMEA | L3 Pass |  |  | TRUE | HNE2E |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 3/7/2019 | 3/7/2019 |  | 708 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 09:39 | Joshi, Abhishek N | 56-F-EU-V-190703-S3LO034 | Interface | Yes | Y |  |  |  | KTS6 |  |  | 56-F-EU-V-190703-S3LOV034A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649011 | No | APPL |  | BXU547455 | 2 |  |  | Freight Cost Allocation - Inquiry Form | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/24/2019 | 6/24/2019 |  | 709 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 09:43 | Joshi, Abhishek N | 56-F-EU-V-190624-S2LO133 | Inquiry | Yes | Y |  |  |  | FCA OUT |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649012 | No | APPL |  | BXU547167 | 1 |  |  | Transportation Carrier Changes | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete | issue reported |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 19/05/30 | 19/05/30 |  | 710 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 09:46 | Joshi, Abhishek N | 56-F-EU-V-190529-S1LO133 |  | Yes | Yes |  |  | No retrofit required | KTW5 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649013 | No | APPL |  | BXU546711, BXU546716 | 1 |  |  | QED Maintenance Program | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 711 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 09:57 | Joshi, Abhishek N | 56-F-EU-V-190515-S1LO007 | Maintenance | Yes | Y |  |  |  | KTW1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649014 | Yes | APPL | 1240720, BXU545198 (18880) | BXU533972, 1241121 (15526) | 2 |  |  | Send OC HC RTE | L3 Pass |  |  | TRUE | H |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/24/2019 | 6/21/2019 |  | 712 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 10:35 | ANAND, S | 56-F-EU-V-190613-S2LO084 |  | Yes | Y |  |  | Retrofit not required | KTW1 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649015 | No | APPL | 1240719 (16244) | BXU549191 | 1 |  |  | Custom Shipment Selection Template | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/31/2019 | 5/30/2019 |  | 713 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 03:24 | Joshi, Abhishek N | 56-F-EU-V-190527-S1LO119 |  | Yes | Yes |  |  | Retrofit not required | KTT1 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649016 | No | APPL |  | BXU546571 | 1 |  |  | Multi-Branch Consolidation Setup | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/30/2019 | 5/30/2019 |  | 714 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 10:00 | Joshi, Abhishek N | 56-F-EU-V-190516-S1LO040 | Setup | Yes | Yes |  |  | No Retrofit Required | KTT1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649017 | No | APPL | 1240726 (15529) | 1241787 (15529) | 2 |  |  | Label Information Maintenance Application | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 06/24/2019 | 06/24/2019 |  | 715 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 07:02 | ANAND, S | 56-F-EU-V-190611-S2LO052 | Maintenance | Yes | Y |  |  |  | KTT1 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649018 | No | APPL | 1240721 | 12649 1240744 | 1 |  |  | Packing List Entry | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 05/30/2019 | 05/29/2019 |  | 716 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-31 08:05 | Vishnubhatla, Mithra | 56-F-EU-V-190523-S1LO104 |  | Yes | Y |  |  |  | KTT3 |  |  | 56-F-EU-V-190523-S1LOV104A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649019 | No | APPL | 1242084 | BXU546716 | 2 |  |  | QED Iframe | L3 Pass |  |  | TRUE | H |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 717 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 03:30 | Joshi, Abhishek N | 56-F-EU-V-190610-S2LO028 |  | Yes | Yes |  |  |  | KTW1 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564901G | No | APPL | BXU513247 (104668) | BXU512852 (104668) | 4 | 4 |  | Packing List Entry - GLAB | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/23/2019 | 6/22/2019 |  | 718 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 07:12 | ANAND, S | 56-F-EU-V-190613-S2LO082 |  | No |  |  |  |  | KTW1 |  |  | 56-F-EU-V-190613-S2LOV082A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564901T | No | APPL |  | BXU547568, BXU546993 | 2 | 2 |  | Manual Forwarder Label Print Application | L3 Pass |  |  | TRUE | HNE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/4/2019 | 6/4/2019 |  | 719 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 03:34 | Joshi, Abhishek N | 56-F-EU-V-190531-S1LO138 | Printer | Yes | Yes |  |  |  | Various2 |  |  | 56-F-EU-V-190531-S1LOV138A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649020 | No | APPL |  | BXU546651 | 2 |  |  | Prenotifications | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/24/2019 | 6/23/2019 |  | 720 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 03:39 | Joshi, Abhishek N | 56-F-EU-V-190611-S2LO064 |  | Yes | Y |  |  |  | KTT2 |  |  | 56-F-EU-V-190611-S2LO0V64A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649024 | No | APPL |  |  | 999 |  |  | Pallet Traffic Recording | Obsolete |  |  |  | NA |  | Transportation | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 721 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649025 | No | APPL | 1242967 (18727) | 1264176 1242969 (18727) | 3 |  |  | Load Reference Shipment Status Enquiry | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/3/2019 | 7/3/2019 |  | 722 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 07:16 | ANAND, S | 56-F-EU-V-190703-S3LO002 | Inquiry | Yes | Y |  |  |  | KTT1 |  |  | 56-F-EU-V-190703-S3LOV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649027 | No | APPL |  |  | 999 |  |  | Pallet Tracking Maintenance | Obsolete |  |  |  | NA |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 723 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet |  | Maintenance | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649028 | No | APPL |  |  | 999 |  |  | Load Picker Checker Application | Obsolete |  |  |  | NA |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 724 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649029 | No | APPL |  |  | 999 |  |  | Consolidation Depot Search | Obsolete |  |  |  | NA |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 725 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649030 | YES | APPL | BXU546544 (27074) | BXU547206 (27074) | 2 |  |  | Journey Build | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 06/24/2019 | 06/21/2019 |  | 726 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 07:25 | ANAND, S | 56-F-EU-V-190624-S2LO128 |  | Yes | Y |  |  |  | KTT5 |  |  | 56-F-EU-V-190624-S2LOV128A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649033 | No | APPL |  |  | 2 |  |  | Maintain Carrier Type Control Table | L3 Pass | 146 | Closed | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/24/2019 | 6/21/2019 |  | 727 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-12 03:49 | Chiau, Liesbet | 56-F-EU-V-190618-S2LO104 | Maintenance | Yes | Y |  |  |  | KTT5 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649035 | No | APPL | BXU546544 (27074) | BXU547206 (27074) | 3 |  |  | Load Header Search | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 03/07/2019 | 03/07/2019 |  | 728 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 07:31 | ANAND, S | 56-F-EU-V-190703-S3LO001 |  | Yes | Y |  |  |  | KTT5 |  |  | 56-F-EU-V-190703-S3LOV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564906 | No | APPL |  |  | 999 |  |  | Carrier Master - Baxter EMEA | Obsolete |  |  |  | NA |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 729 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet | [7 empty] | KTT1 | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564907H | No | APPL |  | BXU516681 | 4 |  |  | Freight Cost Allocation History OUTBOUND | L3 Not Required |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/5/2019 | 8/4/2019 |  | 730 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 03:46 | Joshi, Abhishek N | 56-F-EU-V-190802-S4LO108 | Outbound | Yes | Y |  |  | On Hold N/A for EMEA | na |  |  | NA | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564908 | Yes | APPL | 1277027 (81628) | 1277537 (81628) | 6 |  |  | Hazardous Information Maintenance Program | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 9/3/2019 | 9/1/2019 |  | 731 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 07:35 | ANAND, S | 56-F-EU-V-190827-S6LO002 | Maintenance | Yes | Yes |  |  |  | KTW4 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564908A | No | APPL | 1277027 (81628) | 1277537 (81628) | 6 |  |  | Hazardous Goods Language Specific Descriptions | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 9/3/2019 | 9/3/2019 |  | 732 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 07:40 | ANAND, S | 56-F-EU-V-190827-S6LO007 |  | Yes | Yes |  |  |  | KTW4 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564908B | Yes | APPL | BXU546676 (81627) | BXU546698 (81627) | 6 |  |  | Hazardous Goods Weight Information | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 9/3/2019 | 9/2/2019 |  | 733 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 07:44 | ANAND, S | 56-F-EU-V-190827-S6LO001 |  | Yes | Yes |  |  |  | KTW4 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649090 | No | APPL |  |  | 999 |  |  | Inquiry Over F5649009 Tag file | Obsolete |  |  |  | NA |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 734 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet |  | Inquiry | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649100 | Yes | APPL |  | 1264176 | 2 |  |  | Maintain Temperature Compatability Setup Table | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/24/2019 | 6/24/2019 |  | 735 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-28 12:11 | Singh, Sunil Kumar | 56-F-EU-V-190624-S2LO001 | Maintenance / Setup | Yes | Y |  |  |  | KTS6 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564915 | Yes | APPL | BXU543060, 1247267 (20730), 1264519 (12127), 1240720 (15526) | 1241564 (12127), 1241121 (15526), 1250551 (20730) | 1 |  |  | Delete Order from Warehouse | L3 Pass | 79 | Closed | TRUE | MNE2E |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 30/05/2019 | 30/05/2019 |  | 736 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 08:38 | ANAND, S | 56-F-EU-V-190521-S1LO035 |  | Yes | Yes |  |  |  | KTT1 |  |  | 56-F-EU-V-190521-S1LOV35A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564915A | Yes | APPL | 1240719 (16244), BXU546752 (21933), 1251776 (23552) | 1264176, 1241778 (16244), BXU531175 (21933), 1251777 (23552), BXU547514 (25713) | 1 |  |  | Work with Shipments - Baxter EMEA | L3 Pass | 52 | Closed | TRUE | HE2E |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 737 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 09:31 | ANAND, S | 56-F-EU-V-190515-S1LO012 |  | Yes | Yes |  |  |  | KTT2 |  |  | 56-F-EU-V-190515-S1LOV12A , 56-F-EU-V-190515-S1LOV12B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564915C | Yes | APPL | 1248692 (22465) | 1248865 (22465) | 4 | 4 |  | Shipment Confirmation for Manual Wareouses | L3 Pass | 231 |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/30/2019 | 5/30/2019 |  | 738 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 09:51 | ANAND, S | 56-F-EU-V-190521-S1LO085 |  | Yes | Yes |  |  |  | KTT2 |  |  | 56-F-EU-V-190522-S1LOV85A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564915I | No | APPL |  |  | 2 |  |  | Work with Shipments - Iframe | L3 Not Required |  |  | TRUE | HNE2E |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/12/2019 | 6/12/2019 |  | 739 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:04 | Chiau, Liesbet | 56-F-EU-V-190611-S2OM004 |  | Yes | Y | [6 empty] | 56-F-EU-V-190611-S2OMV04A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564915U | No | APPL |  | BXU545689, BXU546718 | 3 |  |  | Work with Shipments for Paragon | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/03/2019 | 7/02/2019 |  | 740 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 03:53 | Joshi, Abhishek N | 56-F-EU-V-190702-S3LO025 |  | Yes | Y |  |  | Retrofit not required | KTT5 |  |  | 56-F-EU-V-190702-S3LOV025A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564919A | No | APPL |  |  | 4 | 4 |  | Paragon Load Status Inquiry | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 07/03/2019 | 07/03/2019 |  | 741 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-13 09:06 | weber, scott | 56-F-EU-V-190701-S3LO013 | Inquiry | Yes |  |  |  |  | KTT5 |  |  | 56-F-EU-V-190701-S3LOV013A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564925 | No | APPL |  | BXU546720 | 2 |  |  | Incoterm Qualifier - Maintenance | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/21/2019 | 6/20/2019 |  | 742 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 04:08 | Joshi, Abhishek N | 56- F-EU-V-190620-S2LO122 | Maintenance | Yes |  |  |  |  | KTT1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564926 | No | APPL | 1238862 (14849) | BXU547562 | 3 |  |  | Pallet Stacking Code by X3 level | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | Y | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/4/2019 | 7/4/2019 |  | 743 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 04:11 | Joshi, Abhishek N | 56-F-EU-V-190702-S3LO028 |  | Yes |  |  |  |  | KTT1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564927 | No | APPL | 1238862 (14849) | BXU547563 | 3 |  |  | Pallet Stacking Code by Pallet Height and Weight | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 07/04/2019 | 07/03/2019 |  | 744 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 04:14 | Joshi, Abhishek N | 56-F-EU-V-190701-S3LO019 |  | Yes | Y |  |  |  | KTT1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564941 | No | APPL | BXU546403 (21272) | BXU546814 | 3 |  |  | Italy Load Enquiry | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/4/2019 | 7/4/2019 |  | 745 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 04:23 | Joshi, Abhishek N | 56-F-EU-V-190628-S3LO032 | Inquiry | Yes | Y |  |  |  | KTT1 |  |  | 56-F-EU-V-190628-S3LOV032A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564950 | No | APPL | BXU550585 | 1256935 (25543) | 1 |  |  | Routing Entries - Baxter version | L3 Pass |  |  | TRUE | MNE2E |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 30/05/2019 | 30/05/2019 |  | 746 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 01:11 | Joshi, Abhishek N | 56-F-EU-V-190520-S1LO063 |  | Yes | Yes |  |  |  | KTT1 |  |  | 56-F-EU-V-190520-S1LOV63A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564950H | No | APPL |  | BXU546653 | 2 | 2 |  | Import Carrier Information for Route Planning | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/30/2019 | 5/30/2019 |  | 747 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 04:26 | Joshi, Abhishek N | 56-F-EU-V-190517-S1LO048 |  | Yes | Y |  |  |  | KTS6 |  |  | 56-F-EU-V-190517-S1LOV48A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564950T | No | APPL | 1240716 (15523) | 1241119 (15523), BXU547168 | 2 |  |  | Route Code Tag Set Up Application | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/21/2019 | 6/20/2019 |  | 748 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 04:29 | Joshi, Abhishek N | 56-F-EU-V-190613-S2LO083 |  | Yes |  |  |  | Retrofit not required | KTT1 |  |  | 56-F-EU-V-190613-S2LOV083A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649601 | Yes | APPL | 1235447 (16181), 1258830 (25959) | 1259573 (25959) | 2 |  |  | Review/Resend Shipments Sent to WMS | L3 Pass | 131 | Closed | TRUE | MNE2E |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 06/21/2019 | 06/21/2019 |  | 749 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 08:40 | ANAND, S | 56-F-EU-V-190611-S2LO051 |  | Yes | Y |  |  |  | KTS6 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649602 | No | APPL |  |  | 999 |  |  | Deliveries by Load Inquiry | Obsolete |  |  |  | NA |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 750 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet |  | Inquiry | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649607 | No | APPL | 1258830 (25959) | 1259573 (25959) | 1 |  |  | Send Shipment UK | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 19/05/30 | 19/05/30 |  | 751 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 10:12 | ANAND, S | 56-F-EU-V-190529-S1LO131 |  | Yes | Yes |  |  | No retrofit required | KTT5 |  |  | 56-F-EU-V-190529-S1LOV131A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649990 | No | APPL |  |  | 999 |  |  | Consolidation History Inquiry | Obsolete |  |  | FALSE | L |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 752 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet |  | Inquiry |  |  |  |  | VV-27/06 - Obsoleted the object as per suggestion from Scott and Sameer, On Hold N/A for EMEA | na |  |  |  | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P566101E | No | APPL | 1258371 (4102) | 1259927 (4102) | 2 |  |  | Review Equipment Export Errors | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/25/2019 | 6/21/2019 |  | 753 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 10:19 | ANAND, S | 56-F-EU-V-190621-S1LO127 | Error / Export | Yes | Y |  |  |  | KTTS5 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P566111Z | OBS | APPL |  |  | 999 |  |  | Gambro SAP to JDE Equipment Conversion | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 754 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56BPCON | Yes | APPL | BXU545567 (11450) |  | 1 |  |  | Branch plant JDE WMS Mapping maintenance | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/30/2019 | 5/29/2019 |  | 755 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 04:43 | Singh, Sunil Kumar | 56-F-EU-V-190522-S1LO095 | Maintenance | Yes | Yes |  |  | Retrofit not required | KTW1 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56CALTP | No | APPL | BXU546356 | BXU546994, BXU546997 | 1 |  |  | Baxter Calendar Templates Table Maintenance | L3 Pass |  |  | TRUE | MNE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/30/2019 | 5/29/2019 |  | 756 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 04:43 | Joshi, Abhishek N | 56-F-EU-V-190529-S1LO130 | Maintenance | Yes | Yes |  |  |  | KTT2 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56CARSS | No | APPL |  |  | 999 |  |  | Carrier Service Level Search and Select | Obsolete |  |  | FALSE | L |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/30/2019 | 5/30/2019 |  | 757 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet |  |  | Yes |  |  |  | On Hold N/A for EMEA | na |  |  |  | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56CARSV | No | APPL | 1241407 | 14845 1241408 | 2 |  |  | Maintenance Program for F56CARSV | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/21/2019 | 6/21/2019 |  | 758 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 06:49 | Vishnubhatla, Mithra | 56-F-EU-V-190610-S2LO027 | Maintenance | Yes | Yes |  |  |  | KTT4 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56CDNIN | No | APPL |  | BXU547210 | 2 |  |  | CDN Ledger Inquiry | L3 Pass |  |  | TRUE | LE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/20/2019 | 6/19/2019 |  | 759 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 08:00 | Joshi, Abhishek N | 56-F-EU-V-190612-S2LO072 | Inquiry | Yes | Y |  |  | Review E2E process exists | KTW4 |  |  | 56-F-EU-V-190612-S2LOV072A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56CDNIQ | No | APPL |  | BXU547210 | 2 |  |  | CDN Ledger Inquiry - By CDN | L3 Pass |  |  | TRUE | LE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/21/2019 | 6/21/2019 |  | 760 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 08:02 | Joshi, Abhishek N | 56-F-EU-V-190611-S2LO048 | Inquiry | Yes |  |  |  | Review E2E process exists | KTW4 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56CDNSW | No | APPL |  |  | 4 |  |  | Swap CDN between Branch Plants | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/24/2019 | 7/23/2019 |  | 761 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-12 07:08 | Mughal, Abdul | 56-F-EU-V-190723-S4LO033 |  | Yes | Yes |  |  |  | KTW4 |  |  | 56-F-EU-V-190723-S4LOV033A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56CODN | No | APPL |  | BXU546998 | 5 |  |  | Russian Conformity Declaration Number - Maintenance | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/12/2019 | 8/12/2019 |  | 762 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 08:05 | Joshi, Abhishek N | 56-F-EU-V-190812-S5LO001 | Maintenance | Yes | Yes |  |  |  | KTW4 |  |  | 56-F-EU-V-190812-S5LOV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56CONV | Yes | APPL | 1275357 (67534) | 67534&nbsp; 1277714, BXU549379 | 1 |  |  | Work with Inventory Extract to Swisslog | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/27/2019 | 5/27/2019 |  | 763 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 08:09 | Joshi, Abhishek N | 56-F-EU-V-190521-S1LO072 |  | Yes | Yes |  |  |  | KTW1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56EQL01 | Yes | APPL | BXU531848 (148540) | BXU532520 148540 | 5 |  |  | Expired Qty List - F56EQL01 | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Douglas Roussel | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/12/2019 | 8/9/2019 |  | 764 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 00:22 | Singh, Sunil Kumar | 56-F-EU-V-190812-S5LO017 |  | Yes | Yes |  |  |  | KTQ3 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56FFASM | Yes | APPL | BXU546232 (19778)&nbsp;&nbsp;&nbsp; 1241407 14845 1235782 | 1241408 14845 1235723 14843 28082 BXU547626 | 2 |  |  | F56FFASM - Maintenance Program | L3 Pass |  |  | TRUE | MNE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/21/2019 | 6/20/2019 |  | 765 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 09:17 | Vishnubhatla, Mithra | 56-F-EU-V-190618-S2LO122 | Maintenance | Yes |  |  |  |  | KTS4 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56FRFMT | No | APPL |  |  | 1 |  |  | Freight Routing Format Maintenance Program | L3 Pass |  |  | TRUE | MNE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/30/2019 | 5/30/2019 |  | 766 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:52 | Chiau, Liesbet | 56-F-EU-V-190529-S1LO136 | Maintenance | Yes | Yes |  |  | done. Index verified. DS generated. L1 done. No Proc Option. | KTT4 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56FROUT | No | APPL |  |  | 1 |  |  | Freight Routing Maintenance Program | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/30/2019 | 5/30/2019 |  | 767 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-15 02:41 | Destrebecq, Eric | 56-F-EU-V-190524-S1LO107 | Maintenance | Yes | Y |  |  |  | KTT4 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56FRTO | No | APPL | 1240670 (17977) | 1241904 17977 | 1 |  |  | Maintain Fast Transits Movement Extract | L3 Pass |  |  | TRUE | LE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete | Asked SME to check the issue |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/30/2019 | 5/30/2019 |  | 768 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 09:20 | Vishnubhatla, Mithra | 56-F-EU-V-190515-S1LO023 | Maintenance | Yes | Y |  |  | Review E2E process exists | KTW1 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56G0002 | No | APPL | BXU533639 | 3409 BXU544770 | 4 |  |  | Gambro: Integration DirectShip XRef Maintenance | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/24/2019 | 7/23/2019 |  | 769 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 09:23 | Vishnubhatla, Mithra | 56-F-EU-V-190722-S4LO024 | Maintenance | Yes | Y |  |  |  | KTW1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56G0003 | Yes | APPL | 1267636 (19294) | 1267640 | 4 |  |  | Gambro: Align Expiry dates between ASN/Lot Master | L3 Pass |  |  | TRUE | H |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/24/2019 | 7/23/2019 |  | 770 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-05 05:52 | Singh, Sunil Kumar | 56-F-EU-V-190722-S4LO014 |  | Yes | Y |  |  |  | KTW1 |  |  | 56-F-EU-V-190722-S4LOV014A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56G0004 | Yes | APPL |  | 1267640 | 4 |  |  | Gambro: F47072 Audit Table Inquiry | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Miruna Danes | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/24/2019 | 7/23/2019 |  | 771 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-28 07:28 | Singh, Sunil Kumar | 56-F-EU-V-190722-S4LO008 | Inquiry / Audit | Yes | Y |  |  |  | KTQ1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56G0041 | OBS | APPL |  |  | 999 |  |  | Gambro: Maintenace - Resend Stock Information | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 772 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet |  | Maintenance | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56G0042 | OBS | APPL |  |  | 999 |  |  | Gambro: Maintenace - Resend Receipt Information | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 773 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet |  | Maintenance | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56G0043 | OBS | APPL |  |  | 999 |  |  | Gambro: Maintenace - Resend Load Confirm Information | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 774 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet |  | Maintenance | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56H6001 | Yes | APPL |  |  | 999 |  |  | HWT OUT Security Code Set-up Maintenance | Obsolete | [5 empty] | Technical Services | Logistics | Mandy Corbett, Swetha M S, Thierry Kestens |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 775 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet |  | Maintenance | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56HWT01 | No | APPL | 1278647 (82802) | 82802 1278736 | 4 | 4 |  | HWT Issue Resolution Table - Inquiry | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/24/2019 | 7/23/2019 |  | 776 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 10:26 | Vishnubhatla, Mithra | 56-F-EU-V-190722-S4LO006 | Inquiry | Yes | Y |  |  |  | KTTS4 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56HWT16 | Yes | APPL |  |  | 999 | 4 |  | Review Missing Transactions Table | Obsolete |  |  |  | L |  | Technical Services | Logistics | Mandy Corbett, Swetha M S, Thierry Kestens |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 777 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56IM173 | No | APPL | 1259324 | 4523 1259734 | 2 |  |  | Import/Review Inventory Discrepancies JDE vs GSP/GFS | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/21/2019 | 6/20/2019 |  | 778 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 10:50 | Vishnubhatla, Mithra | 56-F-EU-V-190620-S2LO120 |  | Yes | Y |  |  | Retrofit not required | KTTS5 |  |  | 56-F-EU-V-190620-S2LOV120A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56ITMS | No | APPL |  | 1271288 | 999 |  |  | Product Search and Select for License Link | Obsolete |  |  | TRUE | L |  | MDM | MDM |  | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma | VV-13/09 -Obsoleted as per advise from Carlos | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/12/2019 | 8/12/2019 |  | 779 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-14 04:18 | Singh, Sunil Kumar | 56-F-EU-V-190812-S5MD003 |  | Yes | Yes |  |  |  | KTW4 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56LOCON | Yes | APPL | BXU545567 (11450) |  | 1 |  |  | Locations JDE – WMS Mapping Maintenace | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 27/05/2019 | 27/05/2019 |  | 780 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 04:49 | Singh, Sunil Kumar | 56-F-EU-V-190515-S1LO028 | Maintenance | Yes | Yes |  |  |  | KTW1 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56SCC18 | Yes | APPL |  | 11537 BXU547452 | 2 |  |  | Test of SSCC18 | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/21/2019 | 6/20/2019 |  | 781 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 03:15 | Vishnubhatla, Mithra | 56-F-EU-V-190618-S2LO103 |  | Yes |  |  |  |  | KTW3 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56SLOG1 | No | APPL | BXU548587 (133080A) | BXU547397 (133080B) | 2 |  |  | Serialised Log Maintenance | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/21/2019 | 6/21/2019 |  | 782 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-05-26 08:25 | Singh, Sunil Kumar | 56-F-EU-V-190621-S2LO001 | Maintenance | Yes |  |  |  |  | KTW1 |  |  | 56-F-EU-V-190621-S2LOV01A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P584108 | Yes | APPL | BXU542225 | BXU545517 11407 | 5 |  |  | Lot Master - Russia | L3 Pass |  |  | TRUE | H |  | Quality | Logistics | Pawel Oskroba | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/13/2019 | 8/12/2019 |  | 783 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 04:34 | Vishnubhatla, Mithra | 56-F-EU-V-190812-S5LO020 |  | Yes | Yes |  |  |  | KTQ4 |  |  | 56-F-EU-V-190812-S5LOV020A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5841280 | Yes | APPL | 12641 BXU549784 |  | 4 |  |  | Lot Master Availability - Russia | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 07/24/2019 | 07/23/2019 |  | 784 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 04:36 | Vishnubhatla, Mithra | 56-F-EU-V-190723-S4LO035 |  | Yes | Yes |  |  |  | KTW4 |  |  | 56-F-EU-V-190723-S4LOV035A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P584205A | No | APPL | 1235608 | 1235888 | 999 |  |  | Run Delivery Note Window | Obsolete |  |  |  | NA |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber | L2 Not required | No KT needed . Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma | VV-30/10 Obsoleted as it was found in PD full build log as dependency. It was agreed with Terry and BSL that these objects will be obsoleted and call to these will be commented in calling objects | NA |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 785 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-24 04:48 | Singh, Sunil Kumar | [6 empty] | On Hold N/A for EMEA | na |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5847030 | OBS | APPL |  |  | 999 |  |  | Inbound EDI 945 Inquiry Application | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 786 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet |  | Inquiry / Inbound | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5847120 | No | APPL |  | BXU548137 | 4 |  |  | EDI Product Activity Data Inquiry - Inbound | L3 Pass |  |  | TRUE | LE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/24/2019 | 7/23/2019 |  | 787 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 08:14 | Joshi, Abhishek N | 56-F-EU-V-190722-S4LO016 | Inquiry / Inbound | Yes | Y |  |  | Review E2E process exists | KTW1 |  |  | 56-F-EU-V-190722-S4LOV016A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5847133 | No | APPL |  |  | 999 |  |  | ASN Detail Inbound Inquiry Application | Obsolete |  |  | TRUE | LNE2E |  | Procurement | Logistics |  | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/30/2019 | 5/30/2019 |  | 788 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet | 56-F-EU-V-190521-S1LO076 | Inquiry / Inbound | Yes | Y |  |  |  | KTW1 |  |  | NA | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5847200 | No | APPL |  |  | 4 |  |  | EDI Error Log Details | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/24/2019 | 7/23/2019 |  | 789 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-19 07:40 | Verma, Vikas | 56-F-EU-V-190722-S4LO030 | Error | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190722-S4LOV030A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5847329 | No | APPL |  | BXU548139 | 4 |  |  | EDI 945 Detail Ledger Inquiry Application | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/25/2019 | 7/24/2019 |  | 790 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 08:13 | Joshi, Abhishek N | 56-F-EU-V-190723-S4LO037 | Inquiry | Yes | Yes |  |  |  | KTW2 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5849500 | No | APPL |  |  | 999 |  |  | Ship Confirmation Error Queue | Obsolete |  |  | FALSE | LNE2E |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 791 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet |  | Error |  |  |  |  | object marked as Obsolete mail reference is attached. | KTW2 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5874108 | No | APPL | 1260383 (18020) |  | 2 |  |  | CDN Maintenance | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/20/2019 | 6/20/2019 |  | 792 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 04:55 | Singh, Sunil Kumar | 56- F-EU-V-190618-S2LO107 | Maintenance | Yes |  |  |  |  | KTW4 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P58CD001 | OBS | APPL |  |  | 999 |  |  | Check Digit Generation | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 793 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P58CD002 | OBS | APPL |  |  | 999 |  |  | Check Digit Audit File Inquiry | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 794 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet |  | Inquiry / Audit | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P58CD004 | OBS | APPL |  |  | 999 |  |  | Check Digit Reason Code Maintenance | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 795 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet |  | Maintenance | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P58LOCN | No | APPL | BXU549830 |  | 2 |  |  | Location Search and Select | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/20/2019 | 6/19/2019 |  | 796 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 04:38 | Joshi, Abhishek N | 56-F-EU-V-190613-S2LO081 |  | Yes |  |  |  | Retrofit not required | KTW4 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900002 | No | APPL |  |  | 1 |  |  | Shipment Cut Off Time Maintenance | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/30/2019 | 5/30/2019 |  | 797 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:52 | Chiau, Liesbet | 56-F-EU-V-190516-S1LO039 | Maintenance | Yes | Yes |  |  | No Retrofit Required | KTT3 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900003 | Yes | APPL |  |  | 5 |  |  | QTS Location Cross Reference maintenance Application | L3 Pass |  |  | TRUE | H |  | Quality | Logistics | Miruna Danes | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Thippulla Sreekanth |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 08/13/2019 | 08/12/2019 |  | 798 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-30 09:14 | Danes, Miruna | 56-F-EU-V-190812-S5LO019 | Cross Ref / Maintenance | Yes | Yes |  |  |  | KTQ3 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900004 | Yes | APPL |  |  | 5 |  |  | QTS Supplier Cross Reference Maintenance Application | L3 Pass |  |  | TRUE | H |  | Quality | Logistics | Miruna Danes | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/13/2019 | 8/12/2019 |  | 799 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-30 09:14 | Danes, Miruna | 56-F-EU-V-190812-S5LO008 | Cross Ref / Maintenance | Yes | Yes |  |  |  | KTQ3 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900005 | Yes | APPL |  |  | 2 |  |  | GSQ Z-file maintenance Application | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Miruna Danes | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 19/06/21 | 19/06/20 |  | 800 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:04 | Chiau, Liesbet | 56- F-EU-V-190620-S2LO119 | Maintenance | Yes |  |  |  |  | KTQ4 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900006 | Yes | APPL |  |  | 2 |  |  | QTS Interface Data Maintenance Application | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Miruna Danes | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 19/06/21 | 19/06/20 |  | 801 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:04 | Chiau, Liesbet | 56- F-EU-V-190620-S2LO120 | Maintenance / Interface | Yes |  |  |  |  | KTQ4 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900007 | Yes | APPL |  |  | 5 |  |  | QTS Supplier Item Restrictions Maintenance Application | L3 Pass |  |  | TRUE | H |  | Quality | Logistics | Miruna Danes | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 06/20/2019 | 06/19/2019 |  | 802 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-30 09:14 | Danes, Miruna | 56-F-EU-V-190611-S2LO050 | Maintenance | Yes | Y |  |  | VV- 21-06, Moved to Sprint 5, as per Miruna's request | KTQ3 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900014 | No | APPL | BXU548630 |  | 3 |  | CRP | Cost Upload Application | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/28/2019 | 6/28/2019 |  | 803 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-05 06:03 | Joshi, Abhishek N | 56-F-EU-V-190625-S3FI016 | Upload | Yes | Y | [6 empty] | 56-F-EU-V-190625-S3FIV016A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900016 | No | APPL |  |  | 3 |  |  | Compliance Signature Date and Form Entry | L3 Not Required |  |  | TRUE | L |  | Order Management | OM | John Whalley | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 19/07/02 | 19/07/01 |  | 804 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-11 05:18 | Whalley, John | 56-F-EU-V-190628-S3OM005 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900022 | No | APPL |  |  | 3 |  |  | Reason Code Business Purpose Ownership Maintainence | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/4/2019 | 7/3/2019 |  | 805 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-16 04:35 | Yadav, Shweta | 56-F-EU-V-190628-S3LO002 | Maintenance | Yes | Y |  |  |  | KTTS3 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900023 | No | APPL |  |  | 3 |  |  | Reason Code Warranty Months Maintenance | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/4/2019 | 7/2/2019 |  | 806 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-10 03:40 | Corbett, Mandy | 56-F-EU-V-190701-S3LO017 | Maintenance | Yes | Y |  |  |  | KTTS3 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900024 | No | APPL |  |  | 3 |  |  | Generic Code to Specific Code Maintenance | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/4/2019 | 7/4/2019 |  | 807 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-17 09:25 | BILENSOY, NURI | 56-F-EU-V-190701-S3LO002 | Maintenance | Yes | Y |  |  |  | KTTS5 |  |  | 56-F-EU-V-190701-S3LOV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900025 | No | APPL |  |  | 3 |  |  | Mass Update Error | L3 Not Required |  |  | TRUE |  |  | Technical Services | Logistics | Mandy Corbett, Swetha M S, Thierry Kestens | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/4/2019 | 7/3/2019 |  | 808 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-11 08:35 | BILENSOY, NURI | 56- F-EU-V-190701-S3LO014 | Error | Yes | Y |  |  | On Hold N/A for EMEA |  |  |  | NA | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900032 | OBS | APPL |  |  | 999 |  |  | Transportation Expiry Date and Time Limit | Obsolete |  |  |  | NA |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 809 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900054 | No | APPL | 1213031 159798 | 159798 BXU549330 | 3 | 3 |  | Transaction Detail Inquiry | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/27/2019 | 6/26/2019 |  | 810 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 09:39 | Vishnubhatla, Mithra | 56-F-EU-V-260619-S2LO148 | Inquiry | Yes | Y |  |  |  | KTTS3 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900055 | No | APPL |  |  | 3 |  |  | Daily Shipments Inquiry | L3 Not Required |  |  | TRUE |  |  | Technical Services | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/5/2019 | 7/4/2019 |  | 811 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-11 05:29 | Corbett, Mandy | 56-F-EU-V-190702-S3LO023 | Inquiry | Yes | Y |  |  | On Hold N/A for EMEA |  |  |  | NA | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900056 | No | APPL |  |  | 3 |  |  | Transaction Detail Error Listing | L3 Not Required |  |  | TRUE |  |  | Technical Services | Logistics | Mandy Corbett, Swetha M S, Thierry Kestens | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/5/2019 | 7/4/2019 |  | 812 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-11 05:28 | Corbett, Mandy | 56-F-EU-V-190701-S3LO022 | Error | Yes | Y |  |  | On Hold N/A for EMEA |  |  |  | NA | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900057 | No | APPL |  |  | 3 |  |  | Primary Mass Transaction Detail Listing | L3 Not Required |  |  | TRUE |  |  | Technical Services | Logistics | Mandy Corbett, Swetha M S, Thierry Kestens | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/5/2019 | 7/4/2019 |  | 813 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-11 05:28 | Corbett, Mandy | 56-F-EU-V-190704-S3LO038 |  | Yes | Y |  |  | On Hold N/A for EMEA |  |  |  | N/A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900058 | No | APPL |  |  | 3 |  |  | Item Serial Number search | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/5/2019 | 7/4/2019 |  | 814 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-10 04:29 | Corbett, Mandy | 56-F-EU-V-190704-S3LO036 |  | Yes | Y |  |  |  | KTTS3 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900059 | No | APPL |  |  | 2 |  |  | Customer Number List Uploading | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/24/2019 | 6/24/2019 |  | 815 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:04 | Chiau, Liesbet | 56-F-EU-V-190620-S2LO122 | Upload | Yes | Y |  |  |  | KTTS3 |  |  | 56-F-EU-V-190620-S2LO122 | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900062 | Yes | APPL |  |  | 3 |  |  | Product Sourcing Reusable Subform | L3 Not Required |  |  | TRUE | HE2E |  | Order Management | OM | John Whalley | L2 Not required | Functionally obsolete - only required for P42101 to execute |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 07/01/2019 | 06/28/2019 |  | 816 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-23 09:41 | Van Gijseghem, Piet | 56-F-EU-V-190701-S3OM076 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900063 | Yes | APPL |  | BXU545124 | 3 |  |  | Maintain Branch Plant, Version & Date Details | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/1/2019 | 6/30/2019 |  | 817 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-23 02:49 | Singh, Sunil Kumar | 56-F-EU-V-190628-S3MD007 | Maintenance | Yes | Y | [6 empty] | 56-F-EU-V-190628-S3MD007,56-F-EU-V-190628-S3MDV007A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900064 | Yes | APPL |  |  | 4 |  |  | EDI Lot Master Data maintenance Application | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/25/2019 | 7/24/2019 |  | 818 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-19 07:40 | Verma, Vikas | 56-F-EU-V-190724-S4LO043 | Maintenance | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190724-S4LOV043A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900065 | No | APPL |  |  | 3 |  |  | User Country Authority Maintenance | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/5/2019 | 7/5/2019 |  | 819 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-10 04:20 | Corbett, Mandy | 56-F-EU-V-190703-S3LO035 | Maintenance | Yes | Y |  |  |  | KTTS3 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900066 | Yes | APPL |  |  | 4 | 4 |  | Item Serial Number Key Change | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/5/2019 | 7/5/2019 |  | 820 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-19 06:24 | BILENSOY, NURI | 56-F-EU-V-190705-S3LO001 |  | Yes | Y |  |  |  | KTTS3 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900067 | No | APPL |  |  | 2 |  |  | Serial Number List Uploading | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/18/2019 | 6/18/2019 |  | 821 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:04 | Chiau, Liesbet | 56-F-EU-V-190618-S2LO098 | Upload | Yes | Y |  |  |  | KTTS5 |  |  | 56-F-EU-V-190618-S2LOV098A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900070 | Yes | APPL |  |  | 5 |  |  | Check Digit Audit Application | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Miruna Danes | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/13/2019 | 8/12/2019 |  | 822 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-30 03:49 | Danes, Miruna | 56-F-EU-V-190812-S5LO005 | Audit | Yes | Yes |  |  |  | KTQ1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900071 | Yes | APPL |  |  | 2 |  |  | Check Digit Reason Code Maintenance | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Pawel Oskroba | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/20/2019 | 6/20/2019 |  | 823 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:04 | Chiau, Liesbet | 56-F-EU-V-190610-S2LO026 | Maintenance | Yes | Yes |  |  |  | KTQ1 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900072 | Yes | APPL |  |  | 2 |  |  | Lot Status Security | L3 Pass |  |  | TRUE | H |  | Quality | Logistics | Pawel Oskroba | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/11/2019 | 6/10/2019 |  | 824 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:04 | Chiau, Liesbet | 56-F-EU-V-190606-S2LO002 |  | Yes | Y |  |  |  | KTQ1 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900073 | Yes | APPL |  |  | 4 |  |  | Intermediate Lot Status | L3 Pass |  |  | TRUE | H |  | Quality | Logistics | Douglas Roussel | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/25/2019 | 7/24/2019 |  | 825 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-07 08:09 | Danes, Miruna | 56-F-EU-V-190724-S4LO047 |  | Yes | Y |  |  |  | KTQ1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900074 | Yes | APPL |  |  | 3 |  |  | Lot Master Maintenance | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 07/05/2019 | 07/04/2019 |  | 826 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-11 08:32 | BILENSOY, NURI | 56-F-EU-V-190704-S1LO001 | Maintenance | Yes | Y |  |  |  | KTTS5 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900075 | Yes | APPL |  |  | 3 |  |  | Daily Shipments Processing | L3 Not Required |  |  | TRUE |  |  | Technical Services | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/08/2019 | 7/05/2019 |  | 827 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-11 08:35 | BILENSOY, NURI | 56-F-EU-V-190705-S3LO041 |  | Yes | Y |  |  | On Hold N/A for EMEA |  |  |  | N/A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900083 | No | APPL |  |  | 3 |  |  | Inquiry Product List by Country Code | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 07/08/2019 | 07/08/2019 |  | 828 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-22 03:14 | Corbett, Mandy | 56-F-EU-V-190704-S3LO037 | Inquiry | Yes | Y |  |  |  | KTTS5 |  |  | 56-F-EU-V-190704-S3LOV037A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900085 | No | APPL | BXU544671 |  | 3 |  |  | Item Pull Inquiry Application | L3 Not Required |  |  | TRUE | L |  | MDM | MDM |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/1/2019 | 6/28/2019 |  | 829 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 06:23 | Joshi, Abhishek N | 56-F-EU-V-190701-S3MD014 | Inquiry | Yes | Y | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900086 | Yes | APPL |  |  | 1 |  |  | Location by Lot Status | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/27/2019 | 5/27/2019 |  | 830 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:52 | Chiau, Liesbet | 56-F-EU-V-190521-S1LO079 |  | Yes | Y |  |  |  | KTW2 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900089 | No | APPL | BXU548629 |  | 3 |  | CRP | Default Transaction Currency Revisions | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/28/2019 | 6/28/2019 |  | 831 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-05 06:05 | Joshi, Abhishek N | 56-F-EU-V-190625-S3FI017 | Revision | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900091 | Yes | APPL |  |  | 5 |  |  | Check Digit Generation Application | L3 Pass |  |  | TRUE | H |  | Quality | Logistics | Miruna Danes | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | CIZMECI,TANKUT |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/13/2019 | 8/13/2019 |  | 832 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-29 07:18 | Danes, Miruna | 56-F-EU-V-190814-S5LO045 |  | Yes | Y |  |  |  | KTQ1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900092 | OBS | APPL |  |  | 999 |  |  | Re-invoicing | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 833 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900093 | No | APPL |  |  | 999 |  |  | Form 222 Number and DEA Enhancement | Obsolete |  |  |  | HE2E |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 834 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet | [6 empty] | Obsolete | KTW3 | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900094 | OBS | APPL |  |  | 999 |  |  | Form 222 and DEA Information | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 835 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:13 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900101 | Yes | APPL |  |  | 1 |  |  | Location by status and by branch/plant Application | L3 Pass |  |  | TRUE | HE2E |  | Procurement | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/27/2019 | 5/27/2019 |  | 836 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:52 | Chiau, Liesbet | 56-F-EU-V-190514-S1LO022 |  | Yes | Y |  |  | done. Index verified. DS generated. No PO exists. L1 done. | KTW2 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900102 | OBS | APPL |  |  | 999 |  |  | Auto Substitute Confirmation | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 837 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900113 | No | APPL |  |  | 1 |  |  | ASN Detail Custom Tag Application | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/27/2019 | 5/27/2019 |  | 838 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:52 | Chiau, Liesbet | 56-F-EU-V-190515-S1LO034 |  | Yes | Y |  |  |  | KTW2 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900115 | No | APPL |  |  | 1 |  |  | Test Copy of Item Price Manager | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/27/2019 | 5/27/2019 |  | 839 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:52 | Chiau, Liesbet | 56-F-EU-V-190515-S1LO017 |  | Yes | Y |  |  |  | KTW2 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900124 | No | APPL | BXU548628 |  | 3 |  | CRP | Cost component Z-File Application | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/28/2019 | 6/27/2019 |  | 840 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 00:28 | Joshi, Abhishek N | 56-F-EU-V-190626-S3FI023 |  | Yes | Y | [6 empty] | 56-F-EU-V-190626-S3FIV023A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900125 | No | APPL | BXU548627 |  | 1 |  | CRP | Transfer Price Data Z-File Revision Application | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 841 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-05 06:11 | Joshi, Abhishek N | 56-F-EU-V-190515-S1OM025 | Revision | Yes | Y | [6 empty] | 56-F-EU-V-190515-S1OMV25A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900142 | OBS | APPL |  |  | 999 |  |  | Search & Select By Item Cross Reference | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 842 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet |  | Cross Refer | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900173 | No | APPL |  |  | 6 |  |  | HT Customer List for FCA Label | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Nuri Bilensoy | L2 Pass / Complete | 8/28/2019 |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 9/3/2019 | 9/3/2019 |  | 843 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-05 03:36 | BILENSOY, NURI | 56-F-EU-V-190828-S6LO024 |  | Yes | Yes |  |  |  | KTTS2 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900175 | Yes | APPL | 1274723 | 18628 BXU547519 | 4 |  |  | Item Serial Change Specific Code Maintenance | L3 Pass |  |  | TRUE |  |  | Technical Services | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/5/2019 | 8/3/2019 |  | 844 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 03:53 | Vishnubhatla, Mithra | 56-F-EU-V-190805-S4LO113 | Maintenance | Yes | Yes |  |  | Updated as Not required in EMEA- This is a mistake and requires retrofitting |  |  |  | N/A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P590020 | No | APPL |  |  | 999 |  |  | Dclink Users Label Default attaribute | Obsolete |  |  | TRUE |  |  | Warehouse | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/28/2019 | 8/28/2019 |  | 845 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-29 08:37 | Greenard, Terry | 56-F-EU-V-190819-S5LO062 |  | Yes | Y |  |  | On Hold N/A for EMEA |  |  |  | NA | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P590021 | No | APPL |  |  | 999 |  |  | Dclink - Loftware Printer defination | Obsolete |  |  | TRUE |  |  | Warehouse | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/28/2019 | 8/27/2019 |  | 846 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-29 08:37 | Greenard, Terry | 56-F-EU-V-190820-S5LO073 | Printer | Yes | Y |  |  | On Hold N/A for EMEA |  |  |  | NA | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P590021S | No | APPL |  |  | 999 |  |  | Dclink - Loftware Printer Search | Obsolete |  |  | TRUE |  |  | Warehouse | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/29/2019 | 8/28/2019 |  | 847 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-29 08:39 | Greenard, Terry | 56-F-EU-V-190821-S5LO080 | Printer | Yes | Y |  |  | On Hold N/A for EMEA |  |  |  | NA | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900300 | No | APPL | BXU516652 (109164) | 109164 BXU546030, BXU549442 | 4 |  |  | Shippers Workbench Application | L3 Not Required |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Léonard Dartois | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/5/2019 | 8/2/2019 |  | 848 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 08:16 | Joshi, Abhishek N | 56-F-EU-V-190731-S4LO003 |  | Yes | Y |  |  | On Hold N/A for EMEA | KTW3 |  |  | 56-F-EU-V-190731-S4LOV003A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900303 | No | APPL |  |  | 2 |  |  | XUDI - Regulated Items - Exclusion Rule | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/27/2019 | 6/26/2019 |  | 849 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-09 07:07 | Barrera Perez, Carlos Manuel | 56-F-EU-V-190618-S2MD038 |  | Yes | Y | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5930021 | No | APPL |  | BXU547934 | 3 |  |  | BOM Upload | L3 Not Required |  |  | TRUE |  |  | Warehouse | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/8/2019 | 7/5/2019 |  | 850 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 08:19 | Joshi, Abhishek N | 56-F-EU-V-190702-S3LO074 | Upload | Yes | Y |  |  | On Hold N/A for EMEA |  |  |  | NA | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5940306 | No | APPL | BXU546671 |  | 3 |  |  | Source Changes Inquiry | PPD Passed |  |  | TRUE |  | FALSE | ECC | ARO | Ravi / Cosmin | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/15/2019 | 7/12/2019 |  | 851 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:20 | Joshi, Abhishek N | 56-F-EU-V-190710-S3AR119 | Inquiry | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P594101H | No | APPL |  | BXU549684 | 4 |  |  | Item Epedigree Parameters | L3 Not Required |  |  | TRUE |  |  | Warehouse | Logistics | Léonard Dartois | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 08/05/2019 | 08/02/2019 |  | 852 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-20 03:46 | Joshi, Abhishek N | 56-F-EU-V-190801-S4LO098 |  | Yes | Y |  |  | On Hold N/A for EMEA | KTW2 |  |  | 56-F-EU-V-190801-S4LOV098A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P594104 | No | APPL | BXU546671 |  | 2 |  |  | Draft Budgeted costs Inquiry | L3 Pass |  |  | TRUE |  |  | ECC | ARO | Ravi | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 06/25/2019 | 06/24/2019 |  | 853 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:51 | Joshi, Abhishek N | 56-F-EU-V-190620-S2FI121 | Inquiry | Yes | Y |  |  |  | KTW2 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P594105 | No | APPL | BXU546671 |  | 1 |  |  | Mfg Cost Revisions | L3 Pass |  |  | TRUE |  |  | ECC | ARO | Ravi / Cosmin | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/27/2019 | 5/27/2019 |  | 854 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:50 | Joshi, Abhishek N | 56-F-EU-V-190516-S1LO037 | Revision | Yes | Y |  |  | No Retrofit Required | KTW2 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P594106 | No | APPL | BXU546671 |  | 1 |  |  | Draft Mfg Costs Maintenance | L3 Pass |  |  | TRUE |  |  | ECC | ARO | Ravi / Cosmin | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 05/27/2019 | 05/26/2019 |  | 855 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:44 | Joshi, Abhishek N | 56-F-EU-V-190517-S1LO053 | Maintenance | Yes | Yes |  |  |  | KTW2 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P594107 | No | APPL | BXU546671 |  | 2 |  |  | Historical Budgeted Mfg Costs Browser | L3 Pass |  |  | TRUE |  |  | ECC | ARO | Ravi | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 06/24/2019 | 06/21/2019 |  | 856 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 02:00 | Joshi, Abhishek N | 56-F-EU-V-190620-S2FI120 |  | Yes | Y |  |  |  | KTW2 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P594108 | No | APPL | BXU546671 |  | 2 |  |  | Historical Manufactured Costs Browser | L3 Pass |  |  | TRUE |  |  | ECC | ARO | ravi | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/24/2019 | 6/21/2019 |  | 857 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:50 | Joshi, Abhishek N | 56-F-EU-V-190618-S2FI049 |  | Yes | Y |  |  |  | KTW2 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P594108A | Yes | APPL |  |  | 1 |  |  | Lot Master Application | L3 Pass |  |  | TRUE | H |  | Quality | Logistics | Pawel Oskroba | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/27/2019 | 5/27/2019 |  | 858 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:52 | Chiau, Liesbet | 56-F-EU-V-190521-S1LO086 |  | Yes | Yes |  |  |  | KTQ1 |  |  | 56-F-EU-V-190521-S1LOV086A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P594109 | No | APPL | BXU546671 |  | 1 |  |  | Budgeted Mfg Costs Revisions | L3 Pass |  |  | TRUE |  |  | ECC | ARO | Ravi / Cosmin | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 27/05/2019 | 27/05/2019 |  | 859 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:44 | Joshi, Abhishek N | 56-F-EU-V-190515-S1LO021 | Revision | Yes | Yes |  |  |  | KTW2 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P594110 | Yes | APPL |  |  | 1 |  |  | Grouping Matrix maintenance | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Carlos Barrera | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 860 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:52 | Chiau, Liesbet | 56-F-EU-V-190515-S1LO006 | Maintenance | Yes | Y |  |  |  | KTW2 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P594111 | No | APPL | 1247143 | 12817, BXU545672 | 1 |  |  | Complete CE Marked parts inquiry | L3 Pass |  |  | TRUE | L |  | MDM | MDM | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 861 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 10:38 | Joshi, Abhishek N | 56-F-EU-V-190515-S1LO016 | Inquiry | Yes | Yes |  |  |  | KTW2 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P594114 | No | APPL |  | BXU545672 | 1 |  |  | Uncomplete CE Marked parts inquiry | L3 Pass |  |  | TRUE | L |  | MDM | MDM |  | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 27/05/2019 | 27/05/2019 |  | 862 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 10:38 | Joshi, Abhishek N | 56-F-EU-V-190515-S1LO027 | Inquiry | Yes | Yes |  |  |  | KTW2 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P594116S | Yes | APPL | 1242584 (22118) 1267711 (23947) | 1244875 (19727)&nbsp;&nbsp; 1242587&nbsp; 18469&nbsp;&nbsp; 22118&nbsp; BXU547954 1267712 23947 | 1 |  |  | SubLot Creation - Item Reclassifications | L3 Pass |  |  | TRUE | H |  | Quality | Logistics | Miruna Danes | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 27-05-2019 | 27-05-2019 |  | 863 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-19 06:42 | ANAND, S | 56-F-EU-V-190517-S1LO041 |  | Yes | Yes |  |  |  | KTQ2 |  |  | 56-F-EU-V-190517-S1LOV41A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P594135 | Yes | APPL | 1242584 | 18469 1242587 | 2 |  |  | Lot Grade Security Maintenance | L3 Pass |  |  | TRUE | H |  | Quality | Logistics | Pawel Oskroba | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/11/2019 | 6/10/2019 |  | 864 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 06:05 | Vishnubhatla, Mithra | 56-F-EU-V-190606-S2LO001 | Maintenance | Yes | Y |  |  |  | KTQ1 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5942053 | Yes | APPL |  |  | 1 |  |  | Select Multiple Locations | L3 Pass |  |  | TRUE | H |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 19/05/30 | 19/05/30 |  | 865 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:52 | Chiau, Liesbet | 56-F-EU-V-190528-S1LO127 |  | Yes | Yes |  |  | No retrofit required | KTW2 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P594312 | Yes | APPL |  |  | 1 |  |  | Receive by Load Number – PO Receipts | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/27/2019 | 5/24/2019 |  | 866 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:52 | Chiau, Liesbet | 56-F-EU-V-190516-S1LO005 |  | Yes | Yes |  |  | Retrofit not required | KTW2 |  |  | 56-F-EU-V-190516-S1LOV05A,56-F-EU-V-190516-S1LOV05B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5943250 | Yes | APPL |  |  | 1 |  |  | Movement and Disposition By Load Number | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/27/2019 | 5/24/2019 |  | 867 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:52 | Chiau, Liesbet | 56-F-EU-V-190527-S1LO115 |  | Yes | Yes |  |  |  | KTW2 |  |  | 56-F-EU-V-190527-S1LOV115A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5946013 | OBS | APPL |  |  | 999 |  |  | Wave Workbench | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 868 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P594602 | OBS | APPL |  |  | 999 |  |  | Wave Creation | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 869 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P594617 | OBS | APPL |  |  | 999 |  |  | Custom - Logistics WarehouseMovement Confirmations | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 870 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5949645 | No | APPL |  |  | 1 |  |  | Transportation Shipment Confirmation | L3 Not Required |  |  | FALSE | NA |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber | L2 Not required | No KT needed . Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma |  | na |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 871 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:52 | Chiau, Liesbet | [6 empty] | On Hold N/A for EMEA | na |  |  |  | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P594980 | No | APPL |  | BXU547565 | 1 |  |  | Routing Options | L3 Not Required |  |  | FALSE | NA |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber | L2 Not required | No KT needed . Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma |  | na |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 872 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 08:23 | Joshi, Abhishek N | [6 empty] | On Hold N/A for EMEA | na |  |  |  | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P596111Z | No | APPL | 1258233 (27760) | 1258234 27760 | 2 | 5 |  | Revise HWT Detail Records Z-file | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/25/2019 | 6/24/2019 |  | 873 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 06:13 | Vishnubhatla, Mithra | 56-F-EU-V-190624-S2LO131 |  | Yes | Yes |  |  |  | KTTS2 |  |  | 56-F-EU-V-190624-S2LOV131A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P596116 | No | APPL |  | BXU547566 | 3 | 3 |  | Generic Code for FCA Report | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/18/2019 | 6/18/2019 |  | 874 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 08:30 | Joshi, Abhishek N | 56-F-EU-V-190618-S2LO100 | Report | Yes | Y |  |  |  | KTTS2 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P59MD018 | No | APPL |  |  | 3 |  |  | X Levels Review | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/3/2019 | 7/2/2019 |  | 875 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-11 03:12 | Barrera Perez, Carlos Manuel | 56-F-EU-V-190702-S3MD015 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P59MD019 | No | APPL | BXU550716 |  | 3 |  |  | X - Level Upload Maintenance | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 2/7/2019 | 2/7/2019 |  | 876 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-24 04:56 | Joshi, Abhishek N | 56-F-EU-V-190628-S3MD005 | Maintenance / Upload | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P59MD96 | No | APPL |  |  | 999 |  |  | BFDM Item Related Primary Keys Application | Obsolete |  |  | FALSE | H |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/2/2019 | 7/1/2019 |  | 877 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 03:02 | Greenard, Terry | 56-F-EU-V-190628-S3MD001 | SECURE | Yes |  |  |  | Carlos, Objects to Obsolete |  |  |  | N/A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P59TRNST | No | APPL |  | BXU547921 | 2 |  |  | F59TRNST Maintenance | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/20/2019 | 6/17/2019 |  | 878 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 09:09 | Joshi, Abhishek N | 56-F-EU-V-190611-S2LO047 | Maintenance | Yes |  |  |  |  | KTW2 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P7464108 | Yes | APPL | 1260383 (18020) |  | 2 |  |  | Lot Additional Information - COMM - 41 | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/20/2019 | 6/20/2019 |  | 879 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 05:01 | Singh, Sunil Kumar | 56-F-EU-V-190619-S2LO117 |  | Yes |  |  |  | Review E2E process exists,Vikas Verm-> Moved from Sprint 3 to Sprint 2 as per Sameer's Request | KTW2 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P74LI5I | No | APPL | 1266483 | BXU546473 | 2 | 2 |  | Transport Documents Info | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete | No integration with Portuguese authorities web portal in DV or UT. Step 14 & 15 cannot be tested. |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/26/2019 | 6/24/2019 |  | 880 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 09:12 | Joshi, Abhishek N | 56-F-EU-V-190626-S2LO002 |  | Yes | Y |  |  |  | various |  |  | 56-F-EU-V-190626-S2LOV02A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P74P018I | No | APPL | BXU550846 | BXU547918 | 3 |  |  | INTRASTAT - Poland | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/12/2019 | 7/12/2019 |  | 881 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-23 02:47 | Joshi, Abhishek N | 56-F-EU-V-190710-S3LO052 |  | Yes | Y |  |  | Restored PAR file from 812 | KTW2 |  |  | 56-F-EU-V-190710-S3LOV052A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R31802A | No | UBE | BXU548616 |  | 2 |  | CRP | Manufacturing Accounting Journal Entries | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/27/2019 | 6/26/2019 |  | 882 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 06:00 | Joshi, Abhishek N | NA |  | Yes | Y |  |  | No Retrofit Required |  |  |  | 56-F-EU-V-190625-BV0133A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R43092Z1I | yes | UBE | 1258017 | BXU549418 | 1 | 2 |  | Receipt Routing Unedited Transactions Inbound Processor | L3 Pass |  |  | TRUE | HE2E |  | Procurement | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 883 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-08-03 09:03 | Singh, Sunil Kumar |  | Inbound | Yes | Y |  |  | Review E2E process exists; No retrofit required | KTW2 |  |  | 56-F-EU-V-190517- -BV0005A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R43500 | No | UBE |  |  | 1 |  |  | Purchase Order Print | L3 Pass | 21 | Closed | TRUE | HE2E |  | Procurement | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/24/2019 | 5/24/2019 |  | 884 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-12 03:50 | Chiau, Liesbet | 56-F-EU-V-190523-S1LO100 | Printer | Yes | Yes |  |  | Review E2E process exists | KTW2 |  |  | 56-F-EU-V-190523-S1LOV100A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R47071 | No | UBE | BXU544569 (83933) | BXU547743 | 3 |  |  | EDI Receiving Advice Edit/Create - Purchasing | L3 Pass |  |  | TRUE | HE2E |  | Procurement | Logistics | Mandy Corbett | L2 Pass / Complete | 29/7/2019 PD: L2 Pass as per distribution script |  |  | Terry Greenard / Vikas Verma | VV-18/07 - Object Open again for Rework due to the defect -183, VV-18/07 code reviewed by Vikas after Rework | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/24/2019 | 5/24/2019 |  | 885 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-07-24 03:34 | Singh, Sunil Kumar | 56-F-EU-V-190515-S1LO030 |  | Yes | Yes |  |  |  | KTW5 |  |  | 56-F-EU-V-190515-S1LOV30A, 56-F-EU-V-190515-S1LOV30B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600016 | Yes | UBE | 1219793 (12028) | BXU547515 (12028) | 1 |  |  | JDE WMS Internal Label Print | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 886 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 06:31 | ANAND, S | 56-F-EU-V-190515-S1LO011 | Printer | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190515-S1LOV11A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600017 | Yes | UBE | 1222476 (12113) | BXU547516 (12113) | 1 |  |  | JDE WMS Conversion Label Print | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/30/2019 | 5/30/2019 |  | 887 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 06:39 | ANAND, S | 56-F-EU-V-190521-S1LO083 | Printer | Yes | Yes |  |  |  | KTW2 |  |  | 56-F-EU-V-190521-S1LOV083A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600020 | No | UBE |  |  | 1 |  |  | Voice License Label Print | L3 Pass |  |  | TRUE | H |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/30/2019 | 5/30/2019 |  | 888 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:52 | Chiau, Liesbet | 56-F-EU-V-190520-S1LO061 | Printer | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190520-S1LOV61A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600030 | Yes | UBE | 1231851 (13044) | 1231852 (13044) | 1 |  |  | Conversion of WMS Inventory Balance. | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/30/2019 | 5/30/2019 |  | 889 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 06:42 | ANAND, S | 56-F-EU-V-190517-S1LO045 |  | Yes | Y |  |  |  | KTW2 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600056 | Yes | UBE | 1239874 (17210) | 1246232 (17210) | 1 |  |  | Registered Products Report | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Pawel Oskroba | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 19/05/30 | 19/05/30 |  | 890 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 06:51 | ANAND, S | 56-F-EU-V-190528-S1LO124 | Report | Yes | Yes |  |  | No retrofit required | KTQ1 |  |  | 56-F-EU-V-190528-S1LOV124A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600057 | Yes | UBE | 1239875 (17211) | 1241567 (17211) | 1 |  |  | Returns Report | L3 Pass |  |  | TRUE | LE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/30/2019 | 5/29/2019 |  | 891 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 06:53 | ANAND, S | 56-F-EU-V-190522-S1LO094 | Report | Yes | Yes |  |  | Review E2E process exists | KTW2 |  |  | 56-F-EU-V-190522-S1LOV94A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600076 | No | UBE |  | BXU546828 | 2 |  |  | Nordics Waybill Document UBE | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 06/25/2019 | 06/19/2019 |  | 892 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 09:27 | Joshi, Abhishek N | 56-F-EU-V-190619-S2LO112 |  | Yes | Y |  |  |  | KTT3 |  |  | 56-F-EU-V-190619-S2LOV112A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600094 | No | UBE |  | BXU546830 | 1 |  |  | Inventory Movements | L3 Pass |  |  | TRUE | LE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/29/2019 | 5/29/2019 |  | 893 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 04:30 | Reddy, Deepak | 56-F-EU-V-190522-S1LO097 |  | Yes | Y |  |  | Review E2E process exists | KTW2 |  |  | 56-F-EU-V-190522-S1LOV97A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600100 | Yes | UBE | 1248870 (21934) | 1248871 | 1 |  |  | Move Ticket Print UBE | L3 Pass |  |  | TRUE | H |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/25/2019 | 6/24/2019 |  | 894 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-05 14:05 | Singh, Sunil Kumar | 56-F-EU-V-190524-S1LO110 | Printer | Yes |  |  |  |  | KTW2 |  |  | 56-F-EU-V-190524-S1LOV110A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600106 | Yes | UBE | 1274191 (49004) | BXU545127 | R1 |  |  | Transport Report for Temperature | PPD Passed |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Not required | Retrofit Not required |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/29/2019 | 5/29/2019 |  | 895 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-12 14:11 | Singh, Sunil Kumar | 56-F-EU-V-190521-S1LO078 | Report | Yes | Yes |  |  | UDC 56/N3 hardcoded in code | KT unplanned |  |  | 56-F-EU-V-190521-S1LOV78A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600110 | No | UBE |  |  | 3 | 3 |  | Unprocessed Receipts Report 23/07 - AM - Email functionality by R5600103 UBE will be tested separately, since this UBE is called by multiple other programs. | L3 Pass |  |  | TRUE | LE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/20/2019 | 6/19/2019 |  | 896 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-23 04:55 | Mughal, Abdul | 56-F-EU-V-190618-S2LO102 | Report | Yes | Y |  |  | Review E2E process exists | KTW2 |  |  | 56-F-EU-V-190618-S2LOV102A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600114 | Yes | UBE |  |  | 999 |  |  | CQA Retention Sample Report | Obsolete | [5 empty] | Quality | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 897 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet |  | Report | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600118 | No | UBE |  | BXU546890 | 1 |  |  | Ship To extract for Sesto Database | L3 Pass |  |  | TRUE | LE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/29/2019 | 5/29/2019 |  | 898 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 05:34 | Reddy, Deepak | 56-F-EU-V-190528-S1LO126 |  | Yes | Y |  |  | Review E2E process exists | KTW2 |  |  | 56-F-EU-V-190528-S1LO126A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600119 | Yes | UBE | 1275357 (67534) | 1277714 (67534) | 1 |  |  | Expiration Date Alignment | L3 Pass |  |  | TRUE | LE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/29/2019 | 5/29/2019 |  | 899 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 08:14 | ANAND, S | 56-F-EU-V-190521-S1LO073 |  | Yes | Y |  |  | Review E2E process exists | KTW2 |  |  | 56-F-EU-V-190520-S1LOV73A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0123 | No | UBE |  |  | 3 | 3 |  | Report for HWT Sales Data | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/16/2019 | 7/16/2019 |  | 900 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-22 03:14 | Corbett, Mandy | 56-F-EU-V-190716-S3LO099 | Report | Yes | Y |  |  |  | KTTS5 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600129 | Yes | UBE | BXU514348 | BXU514437 (108075) BXU549358 | 2 |  |  | CQA Retention Sample and Discard Report | L3 Pass | 147 | Closed | TRUE | H |  | Quality | Logistics | Miruna Danes | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 901 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 08:57 | Vishnubhatla, Mithra | [7 empty] | KTQ2 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600144 | No | UBE | 1259920 (27458) | 1259926 (27458) | 1 |  |  | Customer Returns - Corporate Hold Lots | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Miruna Danes | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/30/2019 | 5/29/2019 |  | 902 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 08:36 | ANAND, S | 56-F-EU-V-190529-S1LO129 |  | Yes | Yes |  |  |  | KTQ2 |  |  | 56-F-EU-V-190529-S1LOV129A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600158 | No | UBE |  |  | 4 |  |  | Inventory Placement Report | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/25/2019 | 7/23/2019 |  | 903 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-29 05:49 | Mughal, Abdul | 56-F-EU-V-190722-S4LO023 | Report | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190722-S4LOV023A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600162 | OBS | UBE |  |  | 999 |  |  | New programs since PO Date | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 904 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560018I1 | No | UBE | BXU545181 |  | 5 |  |  | Intrastat Outbound Sales and Inbound Deemed Move Extract | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/13/2019 | 8/12/2019 |  | 905 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-21 05:28 | Singh, Sunil Kumar | 56-F-EU-V-190812-S5LO002 | Outbound | Yes | Yes |  |  |  | KTW2 |  |  | 56-F-EU-V-190812-S5LOV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560018I2 | No | UBE |  |  | 5 |  |  | Intrastat Inbound Purchase Receipts Extract | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/13/2019 | 8/12/2019 |  | 906 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-21 03:43 | De Brouwer, Peter | 56-F-EU-V-190812-S5LO018 | Inbound | Yes | Yes |  |  |  | KTW2 |  |  | 56-F-EU-V-190812-S5LOV018A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560018IB | No | UBE | BXU544776 (18535) |  | 5 |  |  | Statutory Intrastat Reporting Belgium | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/13/2019 | 8/12/2019 |  | 907 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 10:04 | Singh, Sunil Kumar | 56-F-EU-V-190812-S5LO007 | Report | Yes | Yes |  |  |  | KTW2 |  |  | 56-F-EU-V-190812-S5LOV007A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560018IC | No | UBE | BXU545596 | BXU545702 | 5 |  |  | Intrastat Report - Czech Republic | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Leonard Dartois | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/14/2019 | 8/13/2019 |  | 908 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 04:29 | Joshi, Abhishek N | 56-F-EU-V-190812-S5LO021 | Report | Yes | Yes |  |  |  | KTW2 |  |  | 56-F-EU-V-190812-S5LOV021A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560018IE | No | UBE |  |  | 5 |  |  | Intrastat Report - Ireland | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Léonard Dartois | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 08/14/2019 | 08/13/2019 |  | 909 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-03 05:53 | Dartois, Léonard | 56-F-EU-V-190813-S5LO036 | Report | Yes | Yes |  |  |  | KTW2 |  |  | 56-F-EU-V-190813-S5LOV036A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560018IF | No | UBE |  | BXU545702 | 5 |  |  | Statutory Intrastat Reporting - France | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/14/2019 | 8/13/2019 |  | 910 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 04:35 | Joshi, Abhishek N | 56-F-EU-V-190812-S5LO009 | Report | Yes | Yes |  |  |  | KTW2 |  |  | 56-F-EU-V-190812-S5LOV009A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560018IG | No | UBE |  |  | 5 |  |  | Intrastat Report - Germany | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/14/19 | 8/13/19 |  | 911 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-22 07:45 | De Brouwer, Peter | 56-F-EU-V-190812-S5LO012 | Report | Yes | Yes |  |  |  | KTW2 |  |  | 56-F-EU-V-190812-S5LOV012A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560018II | No | UBE |  | BXU545702 | 5 |  |  | Statutory Intrastat Reporting Italy | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/14/2019 | 8/13/2019 |  | 912 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 04:36 | Joshi, Abhishek N | 56-F-EU-V-190812-S5LO022 | Report | Yes | Yes |  |  |  | KTW2 |  |  | 56-F-EU-V-190812-S5LOV022A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560018IN | No | UBE | BXU545596, BXU544776 (18535) | BXU545702 | 5 |  |  | Intrastat Report - Netherlands | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | CIZMECI,TANKUT |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/14/2019 | 8/14/2019 |  | 913 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 04:37 | Joshi, Abhishek N | 56-F-EU-V-190814-S5LO046 | Report | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190814-S5LOV046A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560018IP | No | UBE |  |  | 5 |  |  | Statutory Intrastat Reporting- Portugal | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/14/2019 | 8/13/2019 |  | 914 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-21 06:53 | Partanen, Aki | 56-F-EU-V-190813-S5LO034 | Report | Yes | Yes |  |  |  | KTW2 |  |  | 56-F-EU-V-190813-S5LOV034A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560018IS | No | UBE |  |  | 5 |  |  | Intrastat Report - Spain | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 08/14/2019 | 08/13/2019 |  | 915 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-29 08:40 | Mughal, Abdul | 56-F-EU-V-190813-S5LO040 | Report | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190813-S5LOV040A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560018IU | No | UBE |  | BXU545702 | 5 |  |  | Intrastat Report - UK | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/14/2019 | 8/13/2019 |  | 916 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 04:38 | Joshi, Abhishek N | 56-F-EU-V-190813-S5LO038 | Report | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190813-S5LOV038A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560018IW | No | UBE |  |  | 5 |  |  | Intrastat Deemed Move Interface -WISE | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/16/2019 | 8/14/2019 |  | 917 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-29 14:13 | Partanen, Aki | 56-F-EU-V-190813-S5LO029 | Interface | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190813-S5LOV029A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560018P | No | UBE |  |  | 5 |  |  | Intrastat Validation Report -Poland | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 08/16/2019 | 08/14/2019 |  | 918 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-23 05:45 | Partanen, Aki | 56-F-EU-V-190813-S5LO037 | Report | Yes | Yes |  |  |  | KTW2 |  |  | 56-F-EU-V-190813-S5LOV037A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560018PL | No | UBE |  |  | 5 |  |  | Intrastat Report -Poland | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/16/2019 | 8/14/2019 |  | 919 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-22 09:55 | De Brouwer, Peter | 56-F-EU-V-190812-S5LO010 | Report | Yes | Yes |  |  |  | KTW2 |  |  | 56-F-EU-V-190812-S5LOV010A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560018VS | No | UBE |  |  | 5 |  |  | Intrastat VAT Reconciliation Report - Spain | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | CIZMECI,TANKUT |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/14/19 | 8/13/19 |  | 920 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-30 04:10 | Partanen, Aki | 56-F-EU-V-190812-S5LO013 | Report | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190812-S5LOV013A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560018X | No | UBE |  |  | 5 |  |  | Intrastat Extraction by Country & Date Range | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/16/2019 | 8/15/2019 |  | 921 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-27 09:23 | Partanen, Aki | 56-F-EU-V-190814-S5LO052 |  | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190814-S5LOV052A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560018X1 | No | UBE |  |  | 4 | 4 |  | Customs Declaration XML Work File Build | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/25/2019 | 7/24/2019 |  | 922 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-12 06:22 | weber, scott | 56-F-EU-V-190701-S3LO020 | XML | Yes | Y |  |  |  | various2 |  |  | 56-F-EU-V-190701-S3LOV020A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560018X2 | No | UBE |  |  | 3 |  |  | Generate XML file for Customs Declaration | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/8/2019 | 7/5/2019 |  | 923 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-15 05:29 | weber, scott | 56-F-EU-V-190705-S3LO040 | XML | Yes | Y |  |  |  | various2 |  |  | 56-F-EU-V-190705-S3LOV040A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560018Z2 | No | UBE |  | BXU546886, BXU546892 | 4 |  |  | Generate Customs Data for Receipts | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 07/25/2019 | 07/24/2019 |  | 924 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 05:58 | Joshi, Abhishek N | 56-F-EU-V-190724-S4LO045 |  | Yes | Y | [6 empty] | 56-F-EU-V-190724-S4LOV045A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600209 | Yes | UBE | 1274145 (50878) | 1274146 | 2 |  |  | Move Ticket Print UBE - Ext | L3 Pass |  |  | TRUE | H |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/29/2019 | 5/29/2019 |  | 925 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 10:58 | Singh, Sunil Kumar | 56-F-EU-V-190517-S1LO051 | Printer | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190517-S1LOV51A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5603016C | Yes | UBE |  |  | 999 |  |  | Import and Load UK Special Delivery Instructions to F5603016 | Obsolete |  |  |  | NA |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 926 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5609001 | No | UBE | BXU545728 |  | 999 |  |  | Baxter South Africa 08415 Inventory Report | Obsolete |  |  | TRUE | LNE2E |  | Finance GL | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/10/2019 | 7/09/2019 |  | 927 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 03:06 | Joshi, Abhishek N | 56-F-EU-V-190628-S3FI043 | Report | Yes | Y |  |  | JB 23/07: Ayse confirmed that this object is no longer used as the process for the 3PL inventory interface has changed |  |  |  | 56-F-EU-V-190628-S3FIV43A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5619211 | No | UBE | BXU548596 | BXU547924 | 3 |  |  | Aging Report for Saudi | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Douglas Roussel | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/9/2019 | 7/8/2019 |  | 928 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 04:41 | Joshi, Abhishek N | 56-F-EU-V-190628-S3LO005 | Report | Yes | Y |  |  |  | KTQ3 |  |  | 56-F-EU-V-190628-S3LOV05A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5621870 | No | UBE | 1268719 (21870) | 1268720 (21870) | 1 |  |  | New report for Receipts list for goods | L3 Pass |  |  | TRUE | LNE2E |  | Procurement | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 05/29/2019 | 05/28/2019 |  | 929 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 08:39 | ANAND, S | 56-F-EU-V-190523-S1LO103 | Report | Yes | Yes |  |  |  | KTW2 |  |  | 56-F-EU-V-190523-S1LOV103A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R563460A | No | UBE | 1236456 (15947) | 1236461 (15947) | 1 |  |  | Replenishment Report | L3 Pass |  |  | TRUE | LE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/29/2019 | 5/29/2019 |  | 930 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 08:42 | ANAND, S | 56-F-EU-V-190521-S1LO091 | Report | Yes | Yes |  |  | Review E2E process exists | KTW2 |  |  | 56-F-EU-V-190521-S1LOV091A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641001 | Yes | UBE | 1235751 (16138), 1267644 (15409) | 1235930 (16138), 1267645 (15409) | 2 |  |  | T01B Fix Populate Lot Grade | L3 Pass |  |  | TRUE | LE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/19/2019 | 6/18/2019 |  | 931 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 08:51 | ANAND, S | 56-F-EU-V-190614-S2LO093 |  | Yes |  |  |  | Review E2E process exists.Retrofitted the Report the F4102 index 2nd Item was Index 12 in PD812 but in DV920 Index no 16 .Hence retrofitted for index change | KTW2 |  |  | 56-F-EU-V-190614-S2LOV93A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641003 | Yes | UBE | 1240723 | 1241633 | 1 |  |  | Whse Pobis Change and Moves Repost Report | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/24/2019 | 5/24/2019 |  | 932 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-28 22:00 | Singh, Sunil Kumar | 56-F-EU-V-190517-S1LO050 | Report | Yes | Yes |  |  |  | KTW2 |  |  | 56-F-EU-V-190517-S1LOV050A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641003A | No | UBE | 1240723 | 1241633 | 3 |  |  | Pobis Repost UBE - WO Committments | L3 Pass |  |  | TRUE | LE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/9/2019 | 7/8/2019 |  | 933 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-28 22:03 | Singh, Sunil Kumar | 56-F-EU-V-190705-S3LO075 |  | Yes | Y |  |  | Review E2E process exists | KTW2 |  |  | 56-F-EU-V-190705-S3LOV075A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641021A | No | UBE |  |  | 1 |  |  | Stock Rec Error Details | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 29/05/2019 | 29/05/2019 |  | 934 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:53 | Chiau, Liesbet | 56-F-EU-V-190521-S1LO031 | Error | Yes | Y |  |  |  | KTW1 |  |  | 56-F-EU-V-190521-S1LOV31A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641021B | No | UBE | BXU546575 | BXU547107 | 1 |  |  | Stock Recon Metrics | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 935 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-08-07 04:20 | Singh, Sunil Kumar | 56-F-EU-V-190515-S1LO010 |  | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190515-S1LOV10A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641021E | No | UBE |  |  | 1 |  |  | Report on Negative Stock - By Branch Plant (with E-mail) | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 936 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:53 | Chiau, Liesbet | 56-F-EU-V-190521-S1LO080 | Report | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190521-S1LOV80A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641022 | OBS | UBE |  |  | 999 |  |  | WISE to JDE - Create Non Stock PO Report | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 937 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet |  | Report | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641023 | OBS | UBE |  |  | 999 |  |  | WISE to JDE - Create Non Stock SO Report | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 938 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet |  | Report | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641025 | Yes | UBE | 1251326 (21837) | BXU547553 (19614) | 2 |  |  | Create PO from SO - Interco | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/19/2019 | 6/18/2019 |  | 939 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-20 07:15 | ANAND, S | 56-F-EU-V-190618-S2LO106 |  | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190618-S2LOV106 | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564102A | Yes | UBE |  |  | 999 |  |  | Copy batch to new batch F4101Z1 & F594101Z | Obsolete | [5 empty] | Quality | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 940 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564102Q | Yes | UBE | 1240516 (16630) | 1240585 (16630) | 4 |  |  | RAQA Conversion from WISE to JDE | L3 Pass | 235 | Closed | TRUE | L |  | Quality | Logistics | Miruna Danes | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/25/2019 | 7/24/2019 |  | 941 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 10:02 | ANAND, S | 56-F-EU-V-190722-S4LO017 |  | Yes | Y |  |  |  | KTQ2 |  |  | 56-F-EU-V-190722-S4LOV017A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564102U | No | UBE |  |  | 5 |  |  | Obsolescence report | L3 Pass | 280 | Open | TRUE | LNE2E |  | Warehouse | Logistics | Leonard Dartois | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/16/2019 | 8/15/2019 |  | 942 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-04 08:34 | Mughal, Abdul | 56-F-EU-V-190813-S5LO028 | Report | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190813-S5LOV028A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564102Z | No | UBE |  |  | 999 |  |  | Load Branch Plant records into F4101Z1 and F594101Z | Obsolete | [5 empty] | Quality | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 943 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641030 | Yes | UBE | 1270145 |  | 6 | 6 |  | CLM Whse Receipt Processing | L3 Not Required |  |  | TRUE | LE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Not required |  |  |  | Terry Greenard / Vikas Verma | Blank Report Output | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 29/05/2019 | 29/05/2019 |  | 944 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-07 02:20 | Singh, Sunil Kumar | 56-F-EU-V-190520-S1LO060 |  | Yes | Yes |  |  | Move to CRP | KTW2 |  |  | 56-F-EU-V-190520-S1LOV60A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641033 | No | UBE | 1272865 (23357) | 1272955 | 5 |  |  | Emergency Item Listing Report | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | CIZMECI,TANKUT |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/16/2019 | 8/16/2019 |  | 945 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 09:02 | Singh, Sunil Kumar | 56-F-EU-V-190816-S5LO061 | Report | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190816-S5LOV061A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641035 | No | UBE | 1251323, BXU545445 (21824) | 1251324 (21824) | 1 |  |  | External Stock Reconciliation Report | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 29-05-19 | 29-05-19 |  | 946 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 10:08 | ANAND, S | 56-F-EU-V-190517-S1LO044 | Report | Yes | Yes |  |  |  | KTW2 |  |  | 56-F-EU-V-190517-S1LOV44A , 56-F-EU-V-190517-S1LOV44B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641048 | Yes | UBE |  |  | 999 |  |  | Populate Target LLM F4108 from Source This is confirmed by Vikas: We can obsolete this report as it was only run in Feb Last Year | Obsolete |  |  |  | LNE2E |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 19/05/29 | 19/05/29 |  | 947 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet |  |  | Yes |  |  |  | All the versions of this object are BI versions | KTW2 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564104H | Yes | UBE | 1270824 (17770) | BXU545129 | 2 |  |  | National Hospital Number integration into F4104 | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/27/2019 | 6/27/2019 |  | 948 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-12 14:12 | Singh, Sunil Kumar | 56-F-EU-V-190627-S2MD001 |  | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190627-S2MDV01A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564108SL | Yes | UBE | 1231851 (13044) | 1231852 13044 | 1 |  |  | Update Parent Lot field in sublots | L3 Pass |  |  | TRUE | H |  | Quality | Logistics | Miruna Danes | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/29/2019 | 5/28/2019 |  | 949 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 06:28 | Vishnubhatla, Mithra | 56-F-EU-V-190521-S1LO082 |  | Yes | Yes |  |  | Retrofit not required | KTQ2 |  |  | 56-F-EU-V-190521-S1LOV82A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564108X | Yes | UBE | 1244526 (20309) | 20309 1246231 | 1 |  |  | Lot Master Quickcert Interface Exceptions Report | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Pawel Oskroba | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/29/2018 | 5/28/2019 |  | 950 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-20 07:19 | ANAND, S | 56-F-EU-V-190528-S1LO123 | Interface / Report | Yes | Yes |  |  |  | KTQ2 |  |  | 56-F-EU-V-190528-S1LOV123A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564108Z | Yes | UBE |  |  | 999 |  |  | Central Lot Master Conversion Inbound UBE | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 951 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet |  | Inbound | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564121 | Yes | UBE | 1269572 (11411), BXU545449 (14060) | BXU545543 14060 | 2 |  |  | Stock Quantity Synchronisation Errors | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/19/2019 | 6/18/2019 |  | 952 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-23 23:55 | Singh, Sunil Kumar | 56-F-EU-V-190612-S2LO076 | Error | Yes | Y |  |  | Retrofit not required | KTW2 |  |  | 56-F-EU-V-190612-S2LOV076A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564121P | No | UBE | 1277486 | 1277489 74193 | 4 |  |  | 3PL Stock Reconciliation pre-processor | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/25/2019 | 7/24/2019 |  | 953 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 08:16 | Vishnubhatla, Mithra | 56-F-EU-V-190723-S4LO039 |  | Yes | Yes |  |  |  | KTW4 |  |  | 56-F-EU-V-190723-S4LOV039A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564121PG | No | UBE | BXU513247 | BXU512852 104668 | 4 | 4 |  | GLAB Stock Reconciliation Pre-Processor | L3 Pass | 126 | Closed | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 06/19/2019 | 06/18/2019 |  | 954 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 08:20 | Vishnubhatla, Mithra | 56-F-EU-V-190611-S2LO040 |  | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190611-S2LOV40A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564121S | No | UBE | 1255076 (21228) BXU545447 | 1255077 21228 | 1 |  |  | JDE Item Location Snapshot | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/29/2019 | 5/29/2019 |  | 955 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 08:25 | Vishnubhatla, Mithra | 56-F-EU-V-190522-S1LO096 |  | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190522-S1LOV96A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564121SA | No | UBE |  |  | 999 |  |  | JDE Item Location Snapshot with MCU consolidation | Obsolete |  |  | FALSE | LNE2E |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 956 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [6 empty] | it's a inventory snapshot program, created for Baxaltato handle integration between Baxter and Arvato, it's an obsolete object | Obsolete |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564121X | No | UBE | 1249498 | 1267975 25310 | 3 |  |  | Bollini XML Export | L3 Pass |  |  | TRUE | LE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/9/2019 | 7/9/2019 |  | 957 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 08:29 | Vishnubhatla, Mithra | 56-F-EU-V-190701-S3LO003 | Export / XML | Yes | Y |  |  | Review E2E process exists | KTW4 |  |  | 56-F-EU-V-190701-S3LOV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564121XS | No | UBE | 1249498 | 22545 1250498 | 3 |  |  | Bollini XML Export - SFR | L3 Pass |  |  | TRUE | LE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 07/09/2019 | 07/08/2019 |  | 958 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 08:34 | Vishnubhatla, Mithra | 56-F-EU-V-190704-S3LO038 | Export / XML | Yes | Y |  |  | Reivew E2E sprocess exists | KTW4 |  |  | 56-F-EU-V-190704-S3LOV038A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564121Z3 | No | UBE | 1273864 (49095) | 1274189 49095 | 4 |  |  | 3PL Stock Reconciliation against Snapshot file | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/25/2019 | 7/24/2019 |  | 959 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-12 13:15 | Singh, Sunil Kumar | 56-F-EU-V-190723-S4LO013 |  | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190723-S4LOV013A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564121ZG | Yes | UBE |  |  | 4 |  |  | GLAB Stock Reconciliation | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/26/2019 | 7/25/2019 |  | 960 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-05 09:21 | Mughal, Abdul | 56-F-EU-V-190723-S4LO038 |  | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190723-S4LOV038A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564121ZP | No | UBE | 1269572 (11411) | 1269575 (11411) | 4 | 6 |  | Purge records from F564121Z | PPD Passed |  |  | TRUE | L | TRUE | Purge | ARO |  | L2 Not required | No KT, as Tested by user only in ICT |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/5/2019 | 8/2/2019 |  | 961 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-14 07:54 | ANAND, S | 56-F-EU-V-190801-S4AR011 |  | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190801-S4ARV011A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641410B | Yes | UBE | BXU546712 (25759) | BXU546898 25759 | 1 |  |  | Print Cycle Count Sheets - including empty locations | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/29/2019 | 5/29/2019 |  | 962 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 09:04 | Vishnubhatla, Mithra | 56-F-EU-V-190520-S1LO062 | Printer | Yes | Yes |  |  | Related UBE is T5641410B | KTW2 |  |  | 56-F-EU-V-190520-S1LOV062A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641410C | Yes | UBE | BXU546713 (26909) | BXU546899 26909 | 1 |  |  | Cycle Count Report - UKIE | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/29/2019 | 5/29/2019 |  | 963 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 09:08 | Vishnubhatla, Mithra | 56-F-EU-V-190528-S1LO125 | Report | Yes | Yes |  |  |  | KTW2 |  |  | 56-F-EU-V-190528-S1LO125A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641411 | No | UBE | 1250496 (22314), 1251754 (24167), 1251659 (24032) | 1251660 (24032), 1250497 (22314), 1251755 (24167) | 3 |  |  | Bollini Inventory Movements Extract | L3 Pass |  |  | TRUE | LE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/9/2019 | 7/8/2019 |  | 964 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-12 12:44 | Singh, Sunil Kumar | 56-F-EU-V-190703-S3LO030 |  | Yes | Y |  |  | Review E2E process exists | KTW4 |  |  | 56-F-EU-V-190703-S3LOV030A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641411E | No | UBE | 1248389 (21264) | 1249499 (21264) | 3 |  |  | Bollini Inventory Movements Exception Report | L3 Pass |  |  | TRUE | LE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/8/2019 | 7/5/2019 |  | 965 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-05 13:18 | Singh, Sunil Kumar | 56-F-EU-V-190702-S3LO024 | Report | Yes | Y |  |  | Review E2E process exists | KTW4 |  |  | 56-F-EU-V-190702-S3LOV24A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641421 | No | UBE | 1248389 (21264) | 1249499 (21264) | 3 |  |  | Bollini Extract from F4211 | L3 Pass | 196 | Open | TRUE | LE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/10/2019 | 7/9/2019 |  | 966 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-05 13:19 | Singh, Sunil Kumar | 56-F-EU-V-190708-S3LO080 |  | Yes | Y |  |  | Review E2E process exists | KTW4 |  |  | 56-F-EU-V-190708-S3LOV080A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641421E | No | UBE | 1248389 (21264) | 1249499 (21264) | 3 |  |  | Bollini Sales/Returns Exception Report | L3 Pass |  |  | TRUE | LE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/10/2019 | 7/09/2019 |  | 967 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-05 13:20 | Singh, Sunil Kumar | 56-F-EU-V-190709-S3LO082 | Report | Yes | Y |  |  | Review E2E process exists | KTW4 |  |  | 56-F-EU-V-190709-S3LOV082A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564142R | No | UBE | 1248389 (21264) | 1249499 (21264) | 2 |  |  | Reprocess F5641020 records for xref errors | L3 Pass |  |  | TRUE | LE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 968 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-05 13:21 | Singh, Sunil Kumar | 56-F-EU-V-190610-S2LO025 | Error | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190610-S2LOV25A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641800 | Yes | UBE | 1222844 (12360) 1230246 | 1224684 (12360) 1232195 13692 | 5 | 5 |  | Batch Recall Report - Full History | L3 Pass |  |  | TRUE | H |  | Quality | Logistics | Miruna Danes | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 24/05/2019 | 24/05/2019 |  | 969 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 09:13 | Vishnubhatla, Mithra | 56-F-EU-V-190515-S1LO019 | Report | Yes | Yes |  |  | Report is going on error as V56421UA view won’t work right now in UT.&nbsp; It’s a view over some Archive tables, and the Archive schemas are not in UT yet.&nbsp; The DBA is working on that.We can skip L1 and L2 testing. | KTQ1 |  |  | 56-F-EU-V-190515-S1LOV19A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56418C0 | Obsolete | UBE |  |  | 999 |  |  | WISE Lot and Location Master Conversion - UBE | Obsolete |  |  |  | L |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 970 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-12-05 07:03 | Singh, Sunil Kumar | [7 empty] | KTW6 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56418E2 | Yes | UBE |  |  | 999 |  |  | Flat File Lot Master Extract | Obsolete | [5 empty] | Quality | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 971 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642005 | No | UBE | 1250557 (21890) | 1250558 (21890) | 999 |  |  | Whse Automatic BA and BR UBE AP 16/10/2019 - unable to process the test as there is no inventory in WCS. We are currently unable to receive inventory into WCS so this is on hold until that issue is fixed. | Obsolete | 467 | closed | TRUE | HE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete | Refer email on 10th July - Abdul has received confirmation from Vikas that the R5642005 program calls integration therefore it needs to tested in CRP, so long as the UBE is not erroring, the L2 test should be passed. |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 972 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-12 06:53 | ANAND, S | 56-F-EU-V-190514-S1LO005 |  | Yes | Yes |  |  | waiting for integration to be availableBased on this test, we can conclude the system is working as desired without running the UBE R5642005. | KTW2 |  |  | 56-F-EU-V-190515-S1LOV05A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642015R | No | UBE | BXU546656 |  | 6 | 6 |  | Batch Reservation Error Records Deletion | PPD Passed | 136 | Closed | TRUE | LNE2E |  |  | ARO | Rakesh Kumar | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/18/2019 | 6/12/2019 |  | 973 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:12 | Joshi, Abhishek N | 56-F-EU-V-190611-S2LO063 | Error | No |  |  |  | Move to CRP | KTW2 |  |  | 56-F-EU-V-190611-S2LOV063A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564201L | No | UBE |  |  | 1 |  |  | Customer Label Print for Saudi | L3 Pass |  |  | TRUE | H |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 974 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:53 | Chiau, Liesbet | 56-F-EU-V-190515-S1LO014 | Printer | Yes | Yes |  |  |  | KTW2 |  |  | 56-F-EU-V-190515-S1LOV014A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642029 | Yes | UBE |  |  | 999 |  |  | Cross Border Identification | Obsolete | [5 empty] | Technical Services | Logistics | Mandy Corbett, Swetha M S, Thierry Kestens |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 975 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet |  | Cross Refer | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642030 | No | UBE | 1240722 (15527) | 1241039 (15527) | 6 |  |  | WCS Ship Note UBE | PPD Passed |  |  | TRUE | HE2E |  | Transportation | Logistics | Eric Destrebecq, Scott Weber, Puneet Sharma | L2 Not required | covered in KTT3 with process flow but no testing possible as no integration with WCS Witron |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/26/2019 | 7/25/2019 |  | 976 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 06:16 | ANAND, S | 56-F-EU-V-190724-S4LO044 |  | Yes | Y |  |  | waiting for integration to be available | KTT3 |  |  | 56-F-EU-V-190724-S4LOV044A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642034 | No | UBE |  |  | 4 |  |  | Pallet Tails Report - WCS | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/26/2019 | 7/25/2019 |  | 977 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-05 09:52 | De Brouwer, Peter | 56-F-EU-V-190725-S4LO052 | Report | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190725-S4LOV052A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642038 | No | UBE |  |  | 1 |  |  | Daily Sales Extract UBE | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/31/2019 | 5/30/2019 |  | 978 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:53 | Chiau, Liesbet | 56-F-EU-V-190529-S1LO135 |  | Yes | Yes |  |  |  | KTW1 |  |  | 56-F-EU-V-190529-S1LOV135A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642039 | No | UBE | 15524 1242045 |  | 1 |  |  | Truck Planning Purge program | PPD Passed |  |  | TRUE | L | TRUE | Purge | ARO |  | L2 Not required | No KT, as Tested by user only in ICT |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/31/2019 | 5/31/2019 |  | 979 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-25 04:29 | Vishnubhatla, Mithra | 56-F-EU-V-190529-S1AR001 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190529-S1ARV01A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642055G | Yes | UBE | BXU513247 (104668) | BXU512852 (104668) | 2 |  |  | GLAB Process Second Stage Order Creation | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/19/2019 | 6/18/2019 |  | 980 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 06:28 | ANAND, S | 56-F-EU-V-190611-S2LO045 |  | Yes |  |  |  |  | KTW3 |  |  | 56-F-EU-V-190611-S2LOV045A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642056 | No | UBE |  |  | 1 |  |  | Flate Rate Shipments | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 24/05/2019 | 24/05/2019 |  | 981 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-17 05:24 | Seputyte, Lina | 56-F-EU-V-190515-S1LO018 |  | Yes | Yes |  |  |  | KTW3 |  |  | 56-F-EU-V-190515-S1LOV18A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564211B | Yes | UBE | BXU545508, 1241776 (17980), 1249046 (22088), BXU546685 (23866), BXU546688 (20127), 1249046 (22088) 11538 | BXU537484, BXU546927 (20127), 1249047 (22088), BXU546931 (23866), BXU547619 (25431) | 4 |  |  | Populate EDI from Sales Order Dispatches | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/26/2019 | 7/25/2019 |  | 982 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 09:25 | Vishnubhatla, Mithra | 56-F-EU-V-190724-S4LO049 |  | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190724-S4LOV049A, 56-F-EU-V-190724-S4LOV049B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564211D | No | UBE |  |  | 1 |  |  | Daily Open Sales Report | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/31/2019 | 5/31/2019 |  | 983 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:53 | Chiau, Liesbet | 56-F-EU-V-190531-S1LO137 | Report | Yes | Y |  |  | done. Index verified. | KTW2 |  |  | 56-F-EU-V-190531-S1LOV137A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564211DP | No | UBE |  |  | 1 |  |  | Delivery Performance Report | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/31/2019 | 5/31/2019 |  | 984 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:53 | Chiau, Liesbet | 56-F-EU-V-190524-S1LO112 | Report | Yes | Yes |  |  | On Hold N/A for EMEA | na |  |  | 56-F-EU-V-190524-S1LOV112A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564211M | No | UBE |  |  | 1 |  |  | Monthly Open Sales Report | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/31/2019 | 5/31/2019 |  | 985 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:53 | Chiau, Liesbet | 56-F-EU-V-190529-S1LO128 | Report | Yes | Yes |  |  |  | KTW2 |  |  | 56-F-EU-V-190529-S1LO128A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564211R | No | UBE | 1248194 (21269) | 1248195 (21269) | 1 |  |  | Waiting for Shipment Report - By Route Code | L3 Pass |  |  | TRUE | MNE2E |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 986 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 07:04 | ANAND, S | 56-F-EU-V-190516-S1LO035 | Report | Yes | Yes |  |  |  | KTT4 |  |  | 56-F-EU-V-190516-S1LOV35A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564238 | No | UBE | BXU544776 (18535) | BXU546856 | 2 |  |  | Agreement number and prices report | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 06/18/2019 | 06/19/2019 |  | 987 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 09:36 | Joshi, Abhishek N | 56-F-EU-V-190618-S2LO110 | Report | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190618-S2LOV110A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564243 | No | UBE | BXU546661 |  | 2 |  |  | Sales Order vs Transfer Order Integrity | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | ARO | Jaisingh Jaiswar | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/19/2019 | 6/18/2019 |  | 988 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:08 | Joshi, Abhishek N | 56-F-EU-V-190618-S2LO101 |  | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190618-S2LOV101A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642500 | No | UBE |  |  | 2 |  |  | Ship Confirmation for Held Orders | L3 Pass |  |  | TRUE | ME2E |  | Technical Services | Logistics | Nuri Bilensoy | L2 Pass / Complete | Order lines not getting ship confirmed. R5642500 calls shipment confirmation program P4205 which is Sprint 2. Hence, object moved to Sprint 2 08/07/19 SM : After rework complete, L2 Completed. |  |  | Terry Greenard / Vikas Verma | VV-09/07-Code reviewed by Vikas after Rework Complete Status found | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/24/2019 | 5/24/2019 |  | 989 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-10 07:05 | BILENSOY, NURI | 56-F-EU-V-190516-S1LO003 |  | Yes | Yes |  |  |  | KTTS2 |  |  | 56-F-EU-V-190516-S1LOV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642501 | No | UBE |  |  | 1 |  |  | Complete Ship Confirmation for Held Orders | L3 Pass |  |  | TRUE | ME2E |  | Technical Services | Logistics | Mandy Corbett, Swetha M S, Thierry Kestens | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/24/2019 | 5/24/2019 |  | 990 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:53 | Chiau, Liesbet | 56-F-EU-V-190516-S1LO004 |  | Yes | Yes |  |  | Retrofit not required | KTTS2 |  |  | 56-F-EU-V-190516-S1LOV04A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642520 | Yes | UBE |  |  | 2 |  |  | Print Pick Slips - Czech | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/18/2019 | 6/17/2019 |  | 991 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 07:30 | ANAND, S | 56-F-EU-V-190614-S2LO092 | Printer | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190614-S2LOV92A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642520A | Yes | UBE | BXU546752 (21933), BXU546652 (24761), 1253947 (21933) 24142 24761 BXU546652 31682 | BXU547009 (5079), 1235893 (15839), BXU547408 (24142), BXU547410 (24272), BXU547007 (24761), 1255074 (25139)&nbsp; 24142&nbsp; BXU547408&nbsp; 25709 31682 | 2 |  |  | Manual Logistics WarehousePicklist UBE | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/18/2019 | 6/18/2019 |  | 992 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 03:50 | Vishnubhatla, Mithra | 56- F-EU-V-190618-S2LO108 |  | Yes | Y |  |  |  | KTW4 |  |  | 56- F-EU-V-190618-S2LOV108A,56- F-EU-V-190618-S2LOV108B,56- F-EU-V-190618-S2LOV108C | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642520B | No | UBE |  |  | 2 |  |  | Manual Logistics WarehousePicklist Controller | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/18/2019 | 6/17/2019 |  | 993 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:05 | Chiau, Liesbet | 56-F-EU-V-190612-S2LO075 |  | Yes |  |  |  | Retrofit not required | KTW4 |  |  | 56-F-EU-V-190612-S2LOV075A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642520C | Yes | UBE | BXU545779 (104749) | BXU549568 (104749) | 2 |  |  | APL Hard Commitment Pickslip | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 06/19/2019 | 06/18/2019 |  | 994 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-14 07:46 | ANAND, S | 56-F-EU-V-190611-S2LO039 |  | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190611-S2LOV39A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642599 | No | UBE | 1258017 (26923) | 1258019 (26923) | 5 |  |  | Replenishment Notification - Great Bear | L3 Pass |  |  | TRUE | LE2E |  | Procurement | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/19/2019 | 8/16/2019 |  | 995 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 08:45 | ANAND, S | 56-F-EU-V-190813-S5LO031 |  | Yes | Y |  |  | Review E2E process exists | KTW4 |  |  | 56-F-EU-V-190813-S5LOV031A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642599G | OBS | UBE |  |  | 999 |  |  | Replenishment Notification - Medolla | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 996 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643001 | No | UBE |  |  | 2 |  |  | Extract Receiving Repository Data | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/18/2019 | 6/18/2019 |  | 997 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:05 | Chiau, Liesbet | 56-F-EU-V-190610-S2LO022 |  | Yes | Yes |  |  |  | FCA2 |  |  | 56-F-EU-V-190610-S2LOV22A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643003 | No | UBE |  |  | 2 |  |  | Freight Cost Allocation - Inbound | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/25/2019 | 6/25/2019 |  | 998 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-12 08:58 | Destrebecq, Eric | 56-F-EU-V-240619-S2LO126 | Inbound | Yes | Y |  |  | VV-23/06 Moved to Sprint 2 as per request from Eric | FCA2 |  |  | 56-F-EU-V-240619-S2LOV126A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643005 | OBS | UBE |  |  | 999 |  |  | Receipt Re-Processing | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 999 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643006 | No | UBE |  |  | 4 |  |  | Invoice File Upload - Inbound | L3 Not Required |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/5/2019 | 8/2/2019 |  | 1000 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-08 03:22 | Destrebecq, Eric | 56-F-EU-V-190725-S4LO063 | Upload | Yes | Y |  |  | On Hold N/A for EMEA | na |  |  | 56-F-EU-V-190725-S4LOV063A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643008 | No | UBE | 1251991 (22486) | 1251992 (22486) | 4 |  |  | Receiving Count Sheet | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT , CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/26/2019 | 7/22/2019 |  | 1001 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 08:56 | ANAND, S | 56-F-EU-V-190723-S4LO036 |  | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190723-S4LOV036A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643009 | No | UBE | 1274586 |  | 3 |  |  | Interco Replenishment IN by Register | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/10/2019 | 7/10/2019 |  | 1002 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-12 13:23 | Singh, Sunil Kumar | 56-F-EU-V-190708-S3LO044 |  | Yes | Y |  |  |  | various |  |  | 56-F-EU-V-190708-S3LOV044A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643010 | No | UBE | 1274586 |  | 3 |  |  | Interco Replenishment IN by XLVEL | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/10/2019 | 7/9/2019 |  | 1003 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-12 13:37 | Singh, Sunil Kumar | 56-F-EU-V-190710-S3LO001 |  | Yes | Y |  |  |  | various |  |  | 56-F-EU-V-190710-S3LOV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643014 | Yes | UBE | 1253600 (24079) | 1253601 (24079) | 5 |  |  | Receipt Routing Worst Case Logic Report | L3 Pass |  |  | TRUE | H |  | Quality | Logistics | Pawel Oskroba | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 08/19/2019 | 08/16/2019 |  | 1004 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 08:59 | ANAND, S | 56-F-EU-V-190818-S5LO048 | Report | Yes | Y |  |  |  | KTQ2 |  |  | 56-F-EU-V-190818-S5LOV048A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643015 | No | UBE | 1272865 (23357) | 1272955 | 1 |  |  |  | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 05/29/2019 | 05/28/2019 |  | 1005 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 08:58 | Singh, Sunil Kumar | 56-F-EU-V-190523-S1LO102 | Report | Yes | Yes |  |  |  | KTW2 |  |  | 56-F-EU-V-190523-S1LOV102A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643016 | No | UBE |  |  | 2 |  |  | Freight Inbound Expense Report | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 1006 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-12 09:12 | weber, scott | 56-F-EU-V-190611-S2LO061 | Inbound / Report | Yes | Y |  |  |  | various |  |  | 56-F-EU-V-190611-S2LOV061A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564301P | No | UBE | BXU546664 |  | 6 |  |  | Purge Report F5643001 | PPD Passed |  |  | TRUE | L | TRUE | Purge | ARO | Cosmin Mutiu / Terry Greenard | L2 Not required | No KT, as Tested by user only in ICT |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/26/2019 | 8/26/2019 |  | 1007 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:08 | Joshi, Abhishek N | 56-F-EU-V-190819-S5AR001 | Report | Yes | Y |  |  | Yes, run on Scheduler 27/11/2019 |  |  |  | 56-F-EU-V-190819-S5ARV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564303A | No | UBE |  |  | 2 |  |  | Freight Cost Allocation by Supplier | L3 Not Required |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/11/2019 | 6/11/2019 |  | 1008 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:05 | Chiau, Liesbet | 56-F-EU-V-190610-S2LO006 |  | Yes | Y |  |  | On Hold N/A for EMEA | na |  |  | 56-F-EU-V-190610-S2LOV006A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564303B | No | UBE |  |  | 4 |  |  | Freight Cost Allocation by Item/ X-Level - INBOUND | L3 Not Required |  |  | TRUE | L |  | Transportation | Logistics | Puneet Sharma | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 1009 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-08 08:34 | Sharma, Puneet | 56-F-EU-V-190802-S4LO105 | Inbound | Yes | Y |  |  | On Hold N/A for EMEA | Na |  |  | 56-F-EU-V-190802-S4LOV105A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564303H | No | UBE |  | BXU516681 | 4 |  |  | Transfer Freight Cost Allocation History INBOUND | L3 Not Required |  |  | TRUE | L |  | Transportation | Logistics | Puneet Sharma | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/05/2019 | 8/02/2019 |  | 1010 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 09:44 | Joshi, Abhishek N | 56-F-EU-V-190802-S4LO106 | Inbound | Yes | Y |  |  | On Hold N/A for EMEA | na |  |  | 56-F-EU-V-190802-S4LOV106A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564303P | No | UBE | BXU546669 |  | 4 | 6 |  | Purge Freight Cost Allocation History INBOUND | PPD Passed |  |  | TRUE | L | TRUE | Purge | ARO |  | L2 Not required | No KT, as Tested by user only in ICT |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/6/2019 | 8/5/2019 |  | 1011 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:57 | Joshi, Abhishek N | 56-F-EU-V-190805-S4AR013 | Inbound | Yes | Y | [6 empty] | 56-F-EU-V-190805-S4ARV013A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643092 | Yes | UBE | 1258017 (26923) | 1258019 (26923) | 2 |  |  | Receipt Routing Notification - Great Bear | L3 Pass |  |  | TRUE | LE2E |  | Procurement | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/18/2019 | 6/18/2019 |  | 1012 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-12 07:06 | ANAND, S | 56-F-EU-V-190611-S2LOV044A |  | Yes | Y |  |  | Reivew E2E process exists | KTW2 |  |  | 56-F-EU-V-190611-S2LOV044A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643092A | Yes | UBE | BXU519115 (99566) | BXU548350 116536A | 2 |  |  | Receipt Routing Notification - AIP | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Leonard Dartois | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/18/2019 | 6/17/2019 |  | 1013 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-14 04:33 | Vishnubhatla, Mithra | 56-F-EU-V-190617-S2LO095 |  | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190617-S2LOV095A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643121 | No | UBE |  |  | 2 |  |  | Inventory Check Goods In Transit INV-6 | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Leonard Dartois | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/18/2019 | 6/17/2019 |  | 1014 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-12 09:23 | Dartois, Léonard | 56-F-EU-V-190614-S2LO088 |  | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190614-S2LOV088A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643121A | No | UBE | BXU546562 (15754) | 1255227 (25731) | 1 |  |  | Check for fully received OMs and send message to Siebel | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/29/2019 | 5/29/2019 |  | 1015 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-12 07:33 | ANAND, S | 56-F-EU-V-190521-S1LO090 |  | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190521-S1LOV090A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643121R | No | UBE |  |  | 6 |  |  | Pharma Report - based over F56CDNBL | L3 Pass |  |  | TRUE | LE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 9/3/2019 | 9/2/2019 |  | 1016 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-06 05:18 | Mughal, Abdul | 56-F-EU-V-190827-S6LO012 | Report | Yes |  |  |  | Review E2E process exists | KTW4 |  |  | 56-F-EU-V-190827-S6LOV012A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564312R | No | UBE |  |  | 2 |  |  | Customer Returns Report - Email XLS BIP | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Pawel Oskroba | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/17/2019 | 6/14/2019 |  | 1017 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:05 | Chiau, Liesbet | 56-F-EU-V-190614-S2LO091 | Report | Yes | Y |  |  |  | KTQ1 |  |  | 56-F-EU-V-190614-S2LOV91A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643500 | No | UBE | 1251991, 1235425 (13428), 1246751 (20709), BXU546045 (15079) | 1235427 (13428), 1255225 (25722) | 1 |  |  | Baxter Purchase Order Print - BIPublisher output | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 29/05/2019 | 29/05/2019 |  | 1018 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-12 07:46 | ANAND, S | 56-F-EU-V-190520-S1LO030 | Printer | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190520-S1LOV30A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5646011C | No | UBE |  | 1258338, 1258434 | 3 |  |  | Load Carton/Pallet info into F46011 from .csv file | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/2/2019 | 7/2/2019 |  | 1019 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 05:59 | Joshi, Abhishek N | 56-F-EU-V-190702-S3MD001 |  | Yes | Y | [6 empty] | 56-F-EU-V-190702-S3MDV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647006 | No | UBE |  |  | 2 |  |  | KfH CONPCK Preprocessor Report | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 19/06/18 | 19/06/18 |  | 1020 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:05 | Chiau, Liesbet | 56- F-EU-V-190618-S2LO106 | Report | Yes | Y |  |  |  | KTW6 |  |  | 56- F-EU-V-190618-S2LOV106A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647008 | No | UBE | 1272865 (23357) | 1272955 | 1 |  |  | Inbound Sales Order Errors Report | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete | email issue |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 1021 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 09:00 | Singh, Sunil Kumar | 56-F-EU-V-190515-S1LO009 | Error / Inbound | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190515-S1LOV09A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647010 | No | UBE | BXU519115 (99566) | BXU519116 (99566) | 2 |  |  | JDE Inbound PO Pre Processor | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete | Only to check program updating EDSP = P , sales order generation not required as discussed in scrum call on 21st june |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/17/2019 | 6/14/2019 |  | 1022 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-14 06:30 | ANAND, S | 56-F-EU-V-190611-S2LO070 | Inbound | Yes | Y |  |  | Retrofit not required | KTW3 |  |  | 56-F-EU-V-190611-S2LOV070A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647012 | No | UBE | BXU519115 (99566) | BXU547780 (99566) | 2 |  |  | JDE Inbound PO Post Processor | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 06/17/2019 | 06/17/2019 |  | 1023 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-14 06:36 | ANAND, S | 56-F-EU-V-190611-S2LO038 | Inbound | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190611-S2LOV38A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647013 | Yes | UBE | BXU514348 (108075F) |  | 4 |  |  | 3PL EDI Routing Pre Processor | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT , CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/26/2019 | 7/25/2019 |  | 1024 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 04:22 | Singh, Sunil Kumar | 56-F-EU-V-190722-S4LO007 |  | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190722-S4LOV007A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647014 | Yes | UBE | BXU514324 (108075A) | BXU514437 (108075) | 4 |  |  | 3PL EDI Receiving Pre Processor (F47071-2) | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete | As discussed in scrum call, PQOR will not be updated, instead UORG updated |  |  | Terry Greenard / Vikas Verma |  | TANKUT , CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 07/26/2019 | 07/25/2019 |  | 1025 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 06:42 | ANAND, S | 56-F-EU-V-190724-S4LO050 |  | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190724-S4LOV050A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647015 | Yes | UBE | BXU514348 (108075F), BXU514324 (108075A) | BXU514437 (108075F) | 4 |  |  | 3PL EDI Receiving Pre Processor (F43092Z1) | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/26/2019 | 7/25/2019 |  | 1026 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 06:48 | ANAND, S | 56-F-EU-V-190722-S4LO018 |  | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190722-S4LOV018A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647016 | yes | UBE |  |  | 999 |  |  | 3PL-ESL-LOG EDI Receiving Pre Processor (F43092Z1) | Obsolete |  |  |  | HE2E |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 1027 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-12 01:46 | Greenard, Terry | [7 empty] | KTW3 | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647017 | yes | UBE | BXU519888 (122435) | BXU520267 (122435) | 4 |  |  | 3PL EDI Purchase Order Receiving Post Processor (F47016/7) | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/26/2019 | 7/25/2019 |  | 1028 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 10:14 | ANAND, S | 56-F-EU-V-190723-S4LO040 |  | Yes | Yes |  |  |  | KTW4 |  |  | 56-F-EU-V-190723-S4LOV040A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647032 | Yes | UBE | 1278349 (11448), BXU546683 (17240), 1255653 (26102), 1276090 (73844) | 1255654 (26102), 1276091 (73844), BXU547440 (17240), BXU547551 (11448) | 4 |  |  | EDI Advanced Ship Notice Extraction | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/26/2019 | 7/25/2019 |  | 1029 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 10:02 | ANAND, S | 56-F-EU-V-190724-S4LO048 |  | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190724-S4LOV048A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647121A | Yes | UBE | BXU546347 (12503) | BXU547377 (12503) | 2 |  |  | JDE Inventory Upload | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 1030 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 08:59 | ANAND, S | 56-F-EU-V-190617-S2LO096 | Upload | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190617-S2LOV96A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647121B | Yes | UBE | BXU546347 (12503), 1231851 (13044) | 1231852 (13044), BXU547377 (12503) | 1 |  |  | Creation of Item/location records | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete | issue reported |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/28/2019 | 5/28/2019 |  | 1031 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 08:55 | ANAND, S | 56-F-EU-V-190527-S1LO114 |  | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190527-S1LO114A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647121C | Yes | UBE | 1274145 (50878) | 1274146 | 4 |  |  | EDI Product Activity Data Edit/Create - Extended | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/26/2019 | 7/25/2019 |  | 1032 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 10:59 | Singh, Sunil Kumar | 56-F-EU-V-190724-S4LO046 |  | Yes | Yes |  |  |  | KTW3 |  |  | 56-F-EU-V-190724-S4LOV046A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647121E | Yes | UBE | BXU519115 (99566), BXU518959 (99566) | BXU519114 (99566) | 4 | 4 |  | 3PL RSA IPA Pre-Processor | L3 Pass | 85 | Closed | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/17/2019 | 6/14/2019 |  | 1033 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 08:48 | ANAND, S | 56-F-EU-V-190611-S2LO060 |  | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190611-S2LOV060A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647121F | Yes | UBE | BXU514348 (108075C) | BXU514437 (108075) | 2 |  |  | 3PL IPA Pre-Processor with CLM Validation | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete | 18 July: MW BSL Status was blanked out erroneously which is now corrected. |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/17/2019 | 6/17/2019 |  | 1034 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 06:52 | ANAND, S | 56-F-EU-V-190611-S2LOV043A |  | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190611-S2LOV043A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647121X | No | UBE |  |  | 4 |  |  | Parts Consumption failed Repairing BP | L3 Pass |  |  | TRUE | ME2E |  | Technical Services | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/29/2019 | 7/26/2019 |  | 1035 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-07 08:32 | Corbett, Mandy | 56-F-EU-V-190801-S4LO094 |  | Yes | Y |  |  |  | KTTS2 |  |  | 56-F-EU-V-190801-S4LOV094A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647121Y | No | UBE |  |  | 4 |  |  | SRs failed due to Repairing BP Parts Consumption Problem | L3 Pass |  |  | TRUE | ME2E |  | Technical Services | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/29/2019 | 7/26/2019 |  | 1036 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-07 08:33 | Corbett, Mandy | 56-F-EU-V-190801-S4LO095 |  | Yes | Y |  |  |  | KTTS2 |  |  | 56-F-EU-V-190801-S4LOV095A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647121Z | No | UBE |  |  | 4 | 6 |  | EDI Product Activity Data Edit/Create with Email | L3 Pass |  |  | TRUE | ME2E |  | Technical Services | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/29/2019 | 7/26/2019 |  | 1037 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-07 08:33 | Corbett, Mandy | 56-F-EU-V-190725-S4LO065 |  | Yes | Y |  |  |  | KTTS2 |  |  | 56-F-EU-V-190725-S4LOV065A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647210 | Yes | UBE | 1222675, 1264842 (11672) | 1264843 (11672) | 2 |  |  | SAP Inventory Conversion | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 06/14/2019 | 06/14/2019 |  | 1038 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-12 09:42 | ANAND, S | 56-F-EU-V-190617-S2LO094 |  | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190617-S2LOV094A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647341 | Yes | UBE | 1253922 (24450), 1255649 (25984) | 1254243 (24450), BXU547001 (25984) | 2 |  |  | EMEA APS UBE Dependent on other programs from sprint 2 therefore moved this object from sprint 1 to sprint 2. | L3 Pass | 139 | Closed | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/31/2019 | 5/31/2019 |  | 1039 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 08:17 | ANAND, S | 56-F-EU-V-190517-S1LO056 |  | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190517-S1LOV56A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564735 | No | UBE | 1238862 (14849) |  | 4 |  |  | FFA EDI Table Generation - Manual Logistics Warehouseand WMS | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/29/2019 | 7/26/2019 |  | 1040 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-01 06:56 | Singh, Sunil Kumar | 56-F-EU-V-190729-S4LO071 |  | Yes | Y |  |  |  | KTS6 |  |  | 56-F-EU-V-190729-S4LOV071A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564736A | No | UBE | 1238862 (14849), BXU546232 (19778) | 1241629 (14849) | 4 |  |  | Freight Forwarder EDI Table Generation UBE | L3 Pass |  |  | TRUE | HNE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/29/2019 | 7/28/2019 |  | 1041 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-12 09:35 | ANAND, S | 56-F-EU-V-190724-S4OM019 |  | Yes | Y |  |  |  | KTS6 |  |  | 56-F-EU-V-190724-S4OMV019A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564736B | No | UBE |  |  | 4 |  |  | Freight Forwarder EDI Table Generation UBE-GLAB | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/29/2019 | 7/28/2019 |  | 1042 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-07 03:26 | weber, scott | 56-F-EU-V-190731-S4LO080 |  | Yes | Y |  |  |  | KTS6 |  |  | 56-F-EU-V-190731-S4LOV080A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564737 | No | UBE | 1242967 (18727) | 1242969 (18727) | 4 |  |  | EDI FFA Load Reference Data | L3 Pass |  |  | TRUE | ME2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/29/2019 | 7/26/2019 |  | 1043 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 09:41 | ANAND, S | 56-F-EU-V-190723-S4LO010 |  | Yes | Y |  |  |  | KTS6 |  |  | 56-F-EU-V-190723-S4LOV010A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564739 | No | UBE |  |  | 999 |  |  | EDI FFA Integrity Report | Obsolete |  |  |  | NA |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 1044 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet |  | Report | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564740 | No | UBE | 1238862 (14849) |  | 4 |  |  | Post Picking EDI FFA Generation | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT , CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 07/26/2019 | 07/25/2019 |  | 1045 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-01 06:58 | Singh, Sunil Kumar | 56-F-EU-V-190725-S4LO054 |  | Yes | Y |  |  |  | KTS6 |  |  | 56-F-EU-V-190725-S4LOV054A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564740G | No | UBE |  |  | 999 |  |  | GLAB: Post Picking EDI FFA Send without Generation | Obsolete |  |  |  | NA |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri |  |  |  | 1046 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564749 | No | UBE |  |  | 3 |  |  | Populate Paragon Outbound Load Planning File | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 07/11/2019 | 07/10/2019 |  | 1047 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-16 03:06 | weber, scott | 56-F-EU-V-190710-S3LO002 | Outbound | Yes | Y |  |  |  | KTT5 |  |  | 56-F-EU-V-190710-S3LOV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56474905 | No | UBE |  |  | 4 |  |  | EDI Invoice File Upload | L3 Not Required |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 08/05/2019 | 08/05/2019 |  | 1048 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-08 03:22 | Destrebecq, Eric | 56-F-EU-V-190802-S4LO153 | Upload | Yes | Y |  |  | On Hold N/A for EMEA | na |  |  | 56-F-EU-V-190802-S4LOV153A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564749S | No | UBE |  |  | 3 |  |  | Select Shipments for Paragon processing | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/11/2019 | 7/10/2019 |  | 1049 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-16 03:06 | weber, scott | 56-F-EU-V-190710-S3LO053 |  | Yes | Y |  |  | Retrofit not required | KTT5 |  |  | 56-F-EU-V-190710-S3LOV053A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649001 | No | UBE | 17987 | 17987 | 2 |  |  | Extract Shipping Repository Data | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/17/2019 | 6/14/2019 |  | 1050 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 04:21 | Singh, Sunil Kumar | 56-F-EU-V-190614-S2LO087 |  | Yes | Y |  |  |  | FCA OUT |  |  | 56-F-EU-V-190614-S2LOV087A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649002 | No | UBE |  |  | 3 | 3 |  | Automatic Journal Entry Creation UBE | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/16/2019 | 7/15/2019 |  | 1051 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-17 03:51 | Destrebecq, Eric | 56-F-EU-V-190715-S3LO097 |  | Yes | Y |  |  |  | FCA OUT |  |  | 56-F-EU-V-190715-S3LOV97A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649002D | No | UBE |  |  | 2 | 3 |  | Dummy - Automatic Journal Entry Creation UBE | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 06/13/2019 | 06/12/2019 |  | 1052 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-17 03:52 | Destrebecq, Eric | 56-F-EU-V-190611-S2LO067 |  | Yes | Y |  |  |  | FCA OUT |  |  | 56-F-EU-V-190611-S2VLO067A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649003 | No | UBE | 1240721 | 16249 1240744 | 1 |  |  | Print Packing List | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 05/31/2019 | 05/30/2019 |  | 1053 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-31 08:36 | Vishnubhatla, Mithra | 56-F-EU-V-190523-S1LO105 | Printer | Yes | Y |  |  |  | KTT3 |  |  | 56-F-EU-V-190523-S1LOV105A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649003G | No | UBE | BXU513247 |  | 4 |  |  | Print Packing List - GLAB | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT , CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/29/2019 | 7/26/2019 |  | 1054 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-31 07:54 | Vishnubhatla, Mithra | 56-F-EU-V-190725-S4LO055 | Printer | Yes | Y |  |  |  | KTT3 |  |  | 56-F-EU-V-190725-S4LOV055A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649005 | No | UBE |  |  | 4 |  |  | Freight Cost Allocation - Outbound | L3 Not Required |  |  | TRUE | L |  | Transportation | Logistics | Puneet Sharma | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 8/6/2019 | 8/5/2019 |  | 1055 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-08 08:35 | Sharma, Puneet | 56-F-EU-V-190802-S4LO109 | Outbound | Yes | Y |  |  | On Hold N/A for EMEA | FCA OUT |  |  | 56-F-EU-V-190802-S4LOV109A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649005A | No | UBE |  |  | 2 |  |  | Invoice File Upload | L3 Not Required |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/11/2019 | 6/11/2019 |  | 1056 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:05 | Chiau, Liesbet | 56-F-EU-V-190610-S2LO013 | Upload | Yes | Y |  |  | On Hold N/A for EMEA | na |  |  | 56-F-EU-V-190610-S2LOV013A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649005B | No | UBE |  |  | 6 |  |  | FCA - XML Invoice Upload | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete | Raised SR with Oracle 3-20972203691 (Severity 3) |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 9/4/2019 | 9/4/2019 |  | 1057 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-18 04:51 | Destrebecq, Eric | 56-F-EU-V-190828-S6LO020 | Upload /XML | Yes |  |  |  |  | various |  |  | 56-F-EU-V-190828-S6LOV020A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649005I | No | UBE |  |  | 4 |  |  | Freight Cost Allocation - Outbound | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Puneet Sharma | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/29/2019 | 7/28/2019 |  | 1058 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-07 04:39 | Sharma, Puneet | 56-F-EU-V-190723-S4LO041 | Outbound | Yes | Y |  |  |  | FCA2 |  |  | 56-F-EU-V-190723-S4LOV041A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649005I1 | No | UBE |  |  | 4 |  |  | Freight Cost Allocation - Outbound -Fine Tuned | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT , CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/29/2019 | 7/28/2019 |  | 1059 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-23 02:07 | Destrebecq, Eric | 56-F-EU-V-190725-S4LO051 | Outbound | Yes | Y |  |  |  | FCA2 |  |  | 56-F-EU-V-190725-S4LOV051A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649005I2 | No | UBE |  |  | 4 |  |  | Freight Cost Allocation - Outbound -Update F5649007 ASYNC | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/29/2019 | 8/23/2019 |  | 1060 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-23 05:48 | Gongati, Srinivasa | 56-F-EU-V-190726-S4LO029 | Outbound | Yes |  |  |  |  | FCA2 |  |  | 56-F-EU-V-190726-S4LOV029A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649005IO | No | UBE |  |  | 4 |  |  | Freight Cost Allocation - Outbound - IT - Optimized | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 07/29/2019 | 07/29/2019 |  | 1061 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-23 04:56 | Destrebecq, Eric | 56-F-EU-V-190726-S4LO028 | Outbound | Yes | Y |  |  |  | FCA2 |  |  | 56-F-EU-V-190726-S4LOV028A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649005O | No | UBE |  |  | 3 |  |  | Freight Cost Allocation - Outbound - Optimized | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 07/02/2019 | 07/02/2019 |  | 1062 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-10 03:55 | Destrebecq, Eric | 56-F-EU-V-190701-S3LO021 | Outbound | Yes | Y |  |  | VV-01/07-Moved to Sprint 3 as per the request from Eric | FCA OUT |  |  | 56-F-EU-V-190701-S3LOV021A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649005P | No | UBE |  |  | 2 |  |  | FCA - XML Invoice Purge Workfiles | PPD Passed |  |  | TRUE | L | TRUE | Purge | ARO |  | L2 Not required | No KT, as Tested by user only in ICT |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/24/2019 | 6/24/2019 |  | 1063 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-17 05:37 | Partanen, Aki | 56-F-EU-V-190619-S2AR001 | XML | Yes | Y | [6 empty] | 56-F-EU-V-190619-S2ARV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649007A | No | UBE |  |  | 2 |  |  | FCA Month End Closing Report - Summary Version | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/14/2019 | 6/13/2019 |  | 1064 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 07:03 | Prabhu, Varsha | 56-F-EU-V-190613-S2LO080 | Report | Yes |  |  |  |  | FCA OUT |  |  | 56-F-EU-V-190613-S2LOV80A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649007B | No | UBE |  |  | 2 |  |  | FCA Month End Closing Report-Detailed Version | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/14/2019 | 6/14/2019 |  | 1065 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:06 | Chiau, Liesbet | 56-F-EU-V-190610-S2LO035 | Report | Yes | Y |  |  |  | FCA OUT |  |  | 56-F-EU-V-190610-S2LOV035A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649007C | No | UBE | 1274586 |  | 4 |  |  | Inter Company Cost Allocation - OUTBOUND | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Puneet Sharma | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT , CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/30/2019 | 7/29/2019 |  | 1066 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 06:20 | Singh, Sunil Kumar | 56-F-EU-V-190722-S4LO028 | Outbound | Yes | Y |  |  |  | FCA OUT |  |  | 56-F-EU-V-190722-S4LOV028A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649007D | No | UBE | 1274586 |  | 4 |  |  | Inter Company Cost Allocation - OUTBOUND | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Puneet Sharma | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT , CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/30/2019 | 7/29/2019 |  | 1067 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-12 13:39 | Singh, Sunil Kumar | 56-F-EU-V-190729-S4LO066 | Outbound | Yes | Y |  |  |  | FCA OUT |  |  | 56-F-EU-V-190729-S4LOV066A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649009 | No | UBE | 1240753 (18459) | 1264176 | 1 |  |  | Transportation Planning Report | L3 Pass |  |  | TRUE | HNE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 5/31/2019 | 5/31/2019 |  | 1068 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 05:56 | Singh, Sunil Kumar | 56-F-EU-V-190521-S1LO089 | Report | Yes | Y |  |  |  | KTT4 |  |  | 56-F-EU-V-190521-S1LOV089A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649012 | No | UBE |  |  | 4 |  |  | FCA Freight Expense Accrual Report | L3 Pass | 229 | Close | TRUE | L |  | Transportation | Logistics | Puneet Sharma | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 7/30/2019 | 7/29/2019 |  | 1069 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-09 07:57 | Sharma, Puneet | 56-F-EU-V-190731-S4LO081 | Report | Yes | Y |  |  |  | FCA2 |  |  | 56-F-EU-V-190731-S4LOV081A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649015 | No | UBE | 1241980 (17899) | 1241982 (17899) | 2 |  |  | FCA Extraction Report | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/14/2019 | 6/13/2019 |  | 1070 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 09:55 | ANAND, S | 56-F-EU-V-190611-S2LO069 | Report | Yes | Y |  |  | Retrofit not required | FCA2 |  |  | 56-F-EU-V-190611-S2LOV069A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649015G | No | UBE |  |  | 2 |  |  | FCA Extraction Report with G/L Date | L3 Not Required |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:53 | Kishi, Sayuri | 6/28/2019 | 6/28/2019 |  | 1071 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:06 | Chiau, Liesbet | 56-F-EU-V-190618-S2LO111 | Report | Yes | Y |  |  | On Hold N/A for EMEA | na |  |  | 56-F-EU-V-190618-S2LOV111A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649017 | No | UBE |  |  | 2 |  |  | Delete Allocated + Linked Shipments from Invoice | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/14/2019 | 6/13/2019 |  | 1072 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:06 | Chiau, Liesbet | 56-F-EU-V-190611-S2LO036 |  | Yes | Y |  |  |  | FCA OUT |  |  | 56-F-EU-V-190611-S2LOV36A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649018 | No | UBE |  |  | 2 |  |  | FCA Analysis Report | L3 Not Required |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/11/2019 | 6/11/2019 |  | 1073 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:06 | Chiau, Liesbet | 56-F-EU-V-190610-S2LO012 | Report | Yes | Yes |  |  | On Hold N/A for EMEA | na |  |  | 56-F-EU-V-190610-S2LOV12A | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649019 | No | UBE |  |  | 4 |  |  | FCA Freight Expense Report | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Puneet Sharma | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/30/2019 | 7/29/2019 |  | 1074 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-07 06:27 | Sharma, Puneet | 56-F-EU-V-190725-S4LO053 | Report | Yes | Y |  |  |  | FCA2 |  |  | 56-F-EU-V-190725-S4LOV053A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564901P | No | UBE | BXU546664 |  | 6 |  |  | Purge Report F5649001 | PPD Passed |  |  | TRUE | L |  | Purge | ARO | Cosmin Mutiu / Terry Greenard | L2 Not required | No KT, as Tested by user only in ICT |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 9/13/2019 | 8/30/2019 |  | 1075 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:06 | Joshi, Abhishek N | 56-F-EU-V-190829-S6AR001 | Report | Yes | Yes |  |  | Yes, run on Scheduler 27/11/2019 |  |  |  | 56-F-EU-V-190829-S6ARV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649031 | No | UBE |  |  | 999 |  |  | Picker and Checker Report | Obsolete |  |  |  | NA |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1076 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet |  | Report | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649032 | Yes | UBE | BXU546547 (27084) | BXU547577 (27084) | 2 |  |  | Journey Sheet - UK and Ireland | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1077 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 06:49 | ANAND, S | 56-F-EU-V-190610-S2LO017 |  | Yes | Y |  |  |  | KTT5 |  |  | 56-F-EU-V-190610-S2LOV17A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649037 | No | UBE |  |  | 1 |  |  | Picking Instructions and Critical Customers Report | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1078 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:53 | Chiau, Liesbet | 56-F-EU-V-190515-S1LO013 | Report | Yes | Y |  |  |  | KTT5 |  |  | 56-F-EU-V-190515-S1LOV13A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649038 | No | UBE |  |  | 2 |  |  | Populate – Shipping Repository table | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/11/2019 | 6/11/2019 |  | 1079 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 07:02 | Sagar, Sanjay | 56-F-EU-V-190611-S2LO055 |  | Yes | Y |  |  |  | FCA2 |  |  | 56-F-EU-V-190611-S2LOV055A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649040 | No | UBE |  |  | 2 |  |  | FCA Link Shipments to Invoice | L3 Not Required |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/11/2019 | 6/11/2019 |  | 1080 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:06 | Chiau, Liesbet | 56-F-EU-V-190610-S2LO004 |  | Yes | Yes |  |  | On Hold N/A for EMEA | na |  |  | 56-F-EU-V-190610-S2LOV004A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649041 | No | UBE |  |  | 999 |  |  | Portugal Delivery Inquiry by Item X6 Level | Obsolete |  |  |  | NA |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1081 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet |  | Inquiry | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649042 | OBS | UBE |  |  | 999 |  |  | 3PL Send Order | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1082 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649042A | No | UBE |  |  | 4 |  |  | 3PL Send Order - Agility | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/30/2019 | 7/29/2019 |  | 1083 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-08 10:14 | Mughal, Abdul | 56-F-EU-V-190731-S4LO086 |  | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190731-S4LOV086A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649042C | No | UBE | BXU514348 (108075F) | 108075 BXU514437 | 4 |  |  | 3PL Send Order - CH - Galliker | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/30/2019 | 7/29/2019 |  | 1084 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 04:31 | Singh, Sunil Kumar | 56-F-EU-V-190723-S4LO011 |  | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190723-S4LOV011A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649042D | OBS | UBE |  |  | 999 |  |  | 3PL Send Order - DHL | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1085 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649042G | No | UBE | BXU513247 (104668) | BXU512849 (104668) | 4 |  |  | GLAB Send Order | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 07/30/2019 | 07/29/2019 |  | 1086 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 06:54 | ANAND, S | 56-F-EU-V-190729-S4LO070 |  | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190729-S4LOV070A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649042L | no | UBE | BXU517981 | 116536 | 4 |  |  | 3PL Send Order - ESL - Logista Pharma | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/30/2019 | 7/29/2019 |  | 1087 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-30 10:13 | Vishnubhatla, Mithra | 56-F-EU-V-190725-S4LO056 |  | Yes | Y |  |  | Retrofit Completed : Assigned 1 parameter in BSFN B4900900 RetrieveApproveShipmentPO | KTW3 |  |  | 56-F-EU-V-190725-S4LOV056A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649042M | No | UBE | 1277476 (70757) | 70757 | 4 |  |  | 3PL Send Order - Movianto | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/31/2019 | 7/30/2019 |  | 1088 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 02:52 | Singh, Sunil Kumar | 56-F-EU-V-190723-S4LO042 |  | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190723-S4LOV042A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649042P | OBS | UBE |  |  | 999 |  |  | 3PL Send Order - POLARSPEED | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1089 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649042U | OBS | UBE |  |  | 999 |  |  | 3PL Send Order - UNIPHAR | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1090 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649042V | OBS | UBE |  |  | 999 |  |  | 3PL Send Order - VOIGT | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1091 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649043 | OBS | UBE |  |  | 999 |  |  | 3PL Outbound Order Processor | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1092 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet |  | Outbound | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649043A | No | UBE | BXU521471 | 128328 | 4 |  |  | 3PL Outbound Order Processor - Agility | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT , CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/30/2019 | 7/29/2019 |  | 1093 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-30 08:52 | Vishnubhatla, Mithra | 56-F-EU-V-190729-S4LO067 | Outbound | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190729-S4LOV067A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649043C | No | UBE | BXU514348 (108075F) | BXU514437 (108075) | 4 |  |  | 3PL Outbound Order Processor - CH - Galliker | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT , CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/30/2019 | 7/29/2019 |  | 1094 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-05-26 08:43 | Singh, Sunil Kumar | 56-F-EU-V-190729-S4LO069 | Outbound | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190729-S4LOV069A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649043D | OBS | UBE |  |  | 999 |  |  | 3PL Outbound Order Processor - DHL | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1095 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet |  | Outbound | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649043G | Yes | UBE | BXU513247 (104668) | BXU512849 (104668) | 4 |  |  | GLAB Outbound Order Processor | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete | it is tested through R5649042G |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 07/30/2019 | 07/29/2019 |  | 1096 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 06:54 | ANAND, S | 56-F-EU-V-190729-S4LO029 | Outbound | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190729-S4LOV029A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649043L | no | UBE | BXU517981 | 116536 | 4 |  |  | 3PL Outbound Order Processor - ESL - Logista Pharma | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/31/2019 | 7/30/2019 |  | 1097 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-30 08:30 | Vishnubhatla, Mithra | 56-F-EU-V-190730-S4LO075 | Outbound | Yes |  |  |  |  | KTW3 |  |  | 56-F-EU-V-190730-S4LOV075A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649043M | No | UBE | 1277476 (70757) | 70757 | 4 |  |  | 3PL Outbound Order Processor - Movianto | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/31/2019 | 7/30/2019 |  | 1098 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 02:58 | Singh, Sunil Kumar | 56-F-EU-V-190729-S4LO068 | Outbound | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190729-S4LOV068A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649043P | no | UBE |  |  | 999 |  |  | 3PL Outbound Order Processor - POLARSPEED | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1099 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet |  | Outbound | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649043U | No | UBE |  |  | 999 |  |  | 3PL Outbound Order Processor - UNIPHAR | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1100 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet |  | Outbound | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649043V | No | UBE |  |  | 999 |  |  | 3PL Outbound Order Processor - VOIGT | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1101 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet |  | Outbound | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649044 | Yes | UBE |  |  | 999 |  |  | 3PL Ship Confirm Processor | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1102 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649044A | Yes | UBE | BXU519511 (128332) | 128332 | 4 |  |  | 3PL Ship Confirm Processor - Agility | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/31/2019 | 7/30/2019 |  | 1103 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 13:31 | Singh, Sunil Kumar | 56-F-EU-V-190731-S4LO082 |  | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190731-S4LOV082A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649044C | Yes | UBE | BXU514348 (108075F) | 108075 | 4 |  |  | 3PL CH - Galliker Ship Confirm Processor | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/31/2019 | 7/30/2019 |  | 1104 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 04:34 | Singh, Sunil Kumar | 56-F-EU-V-190731-S4LO056 |  | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190731-S4LOV056A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649044G | Yes | UBE | BXU513247 | 104668 | 4 |  |  | GLAB Ship Confirm Processor | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/31/2019 | 7/30/2019 |  | 1105 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-30 08:19 | Vishnubhatla, Mithra | 56-F-EU-V-190731-S4LO089 |  | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190731-S4LOV089A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649044L | Yes | UBE | BXU517981 | 116536 BXU517976 | 4 |  |  | 3PL-ESL - Logista Pharma Ship Confirm Processor | L3 Pass | 259 | Closed | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/31/2019 | 7/30/2019 |  | 1106 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-31 09:22 | Vishnubhatla, Mithra | 56-F-EU-V-190731-S4LO001 |  | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190731-S4LOV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649044M | Yes | UBE | 1277478 (70657) | 1277479 (70657) | 4 |  |  | 3PL Ship Confirm Processor - Movianto | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT , CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 07/31/2019 | 07/30/2019 |  | 1107 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 02:46 | Singh, Sunil Kumar | 56-F-EU-V-190730-S4LO074 |  | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190730-S4LOV074A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649044P | Yes | UBE |  |  | 999 |  |  | 3PL Polarspeed Ship Confirm Processor | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1108 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649044U | Yes | UBE |  |  | 999 |  |  | 3PL Uniphar Ship Confirm Processor | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1109 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649044V | Yes | UBE |  |  | 999 |  |  | 3PL Voigt Ship Confirm Processor | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1110 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649045 | No | UBE | BXU519888 (122435) | BXU519894 (122435) | 1 |  |  | Report to Email Delivery Instructions | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/31/2019 | 5/31/2019 |  | 1111 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 13:01 | Singh, Sunil Kumar | 56-F-EU-V-190524-S1LO108 | Report | Yes | Y |  |  |  | KTW5 |  |  | 56-F-EU-V-190524-S1LOV108A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649049 | No | UBE |  |  | 999 |  |  | Supplemental Database BI Report (F00092) | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1112 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet |  | Report | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564907A | No | UBE |  |  | 2 |  |  | Freight Cost Allocation by Customer | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/14/2019 | 6/14/2019 |  | 1113 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:06 | Chiau, Liesbet | 56-F-EU-V-190610-S2LO024 |  | Yes | Y |  |  |  | FCA2 |  |  | 56-F-EU-V-190610-S2LOV024A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564907B | No | UBE |  |  | 4 |  |  | Freight Cost Allocation by item/ X-Level-Outbound | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Puneet Sharma | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/31/2019 | 7/30/2019 |  | 1114 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-05 10:30 | Sharma, Puneet | 56-F-EU-V-190725-S4LO057 | Outbound | Yes | Y |  |  |  | FCA2 |  |  | 56-F-EU-V-190725-S4LOV057A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564907C | No | UBE |  |  | 4 |  |  | Inter Company Cost Allocation - OUTBOUND | L3 Not Required |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/6/2019 | 8/5/2019 |  | 1115 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-08 03:22 | Destrebecq, Eric | 56-F-EU-V-190805-S4LO115 | Outbound | Yes | Y |  |  | On Hold N/A for EMEA | na |  |  | 56-F-EU-V-190805-S4LOV115A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564907H | No | UBE |  |  | 4 |  |  | Transfer Freight Cost Allocation History OUTBOUND | L3 Not Required |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/6/2019 | 8/5/2019 |  | 1116 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-12 02:19 | Destrebecq, Eric | 56-F-EU-V-190801-S4LO001 | Outbound | Yes | Y |  |  | On Hold N/A for EMEA | na |  |  | 56-F-EU-V-190801-S4LOV001A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564907P | No | UBE | BXU546669 |  | 4 | 6 |  | Purge Freight Cost Allocation History OUTBOUND | PPD Passed |  |  | TRUE | L | TRUE | Purge | ARO |  | L2 Not required | No KT, as Tested by user only in ICT |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/7/2019 | 8/6/2019 |  | 1117 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:56 | Joshi, Abhishek N | 56-F-EU-V-190807-S4AR014 | Outbound | Yes | Y | [6 empty] | 56-F-EU-V-190807-S4ARV014A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564908 | Yes | UBE | 1277459 (75813) | 1278735 (75813) | 2 |  |  | Hazardous Goods Waybill by Shipment | L3 Pass |  |  | TRUE | HNE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/12/2019 | 6/12/2019 |  | 1118 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-09 05:58 | Singh, Sunil Kumar | 56-F-EU-V-190613-S2LO086 |  | Yes | Y |  |  |  | various2 |  |  | 56-F-EU-V-190613-S2LOV086A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564941A | No | UBE |  |  | 999 |  |  | LOAD LIST | Obsolete |  |  |  | NA |  | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1119 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564941B | No | UBE |  |  | 3 |  |  | LOAD LIST - Germany | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Puneet Sharma | L2 Pass / Complete | Except email funcationality testing completed this will be tested in L3 UT., Pl. refer R5600103 comments. |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/11/2019 | 7/11/2019 |  | 1120 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-23 05:01 | Chavan, Prasad | 56-F-EU-V-190708-S3LO079 |  | Yes | Y |  |  |  | KTT3 |  |  | 56-F-EU-V-190708-S3LOV079A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564941C | No | UBE |  |  | 3 |  |  | LOAD LIST | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Puneet Sharma | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/11/2019 | 7/10/2019 |  | 1121 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-24 08:53 | weber, scott | 56-F-EU-V-190704-S3LO039 |  | Yes | Y |  |  |  | KTT3 |  |  | 56-F-EU-V-190704-S3LOV39A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564941E | No | UBE |  |  | 3 |  |  | LOAD LIST - France | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 07/11/2019 | 07/10/2019 |  | 1122 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-24 09:10 | weber, scott | 56-F-EU-V-190708-S3LO046 |  | Yes | Y |  |  |  | KTT3 |  |  | 56-F-EU-V-190708-S3LOV046A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564948P | No | UBE | BXU546666 |  | 6 |  |  | Purge Report F5649004 and F5649008 | PPD Passed |  |  | TRUE | L |  | Purge | ARO | Cosmin Mutiu / Terry Greenard | L2 Not required | No KT, as Tested by user only in ICT |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 9/13/2019 | 9/12/2019 |  | 1123 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 07:24 | Joshi, Abhishek N | 56-F-EU-V-190903-S6AR003 | Report | Yes | Yes |  |  | Yes, run on Scheduler 27/11/2019 |  |  |  | 56-F-EU-V-190903-S6ARV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649500 | No | UBE |  |  | 1 |  |  | Batch Transportation Shipment Confirmation | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete | status not updating |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/31/2019 | 5/31/2019 |  | 1124 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:53 | Chiau, Liesbet | 56-F-EU-V-190517-S1LO046 |  | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190517-S1LOV46A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564950C | No | UBE | 1264552 (13747) |  | 1 |  |  | Copy Routing Entries from one branch plant to another | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 19/05/30 | 19/05/30 |  | 1125 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-01 06:23 | Singh, Sunil Kumar | 56-F-EU-V-190529-S1LO134 |  | Yes | Y |  |  | No retrofit required | KTT4 |  |  | 56-F-EU-V-190529-S1LOV134A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564950HP | No | UBE |  |  | 2 | 2 |  | Home Patients Route Pre-Planning Report | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/31/2019 | 5/30/2019 |  | 1126 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-15 04:39 | Gongati, Srinivasa | 56-F-EU-V-190527-S1LO118 | Report | Yes | Y |  |  | Retrofit not required | KTS6 |  |  | 56-F-EU-V-190527-S1LOV118A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564950HP1 | No | UBE |  |  | 2 | 2 |  | Home Patients Route Planning Report | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/31/2019 | 5/30/2019 |  | 1127 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:06 | Chiau, Liesbet | 56-F-EU-V-190529-S1LO132 | Report | Yes | Y |  |  | There is File path value Diff b/w PD812 and DV920 in BXEUFR01 version. However did not modify and moved for build as is(Confirmed by Robert) | KTS6 |  |  | 56-F-EU-V-190529-S1LOV132A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564950R | Yes | UBE | BXU546252 (111196) | BXU533965 (111196) | 1 |  |  | Copy Multiple Route Codes | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/3/2019 | 6/3/2019 |  | 1128 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-09 06:12 | Singh, Sunil Kumar | 56-F-EU-V-190529-S1LO111 |  | Yes | Y |  |  |  | KTT4 |  |  | 56-F-EU-V-190529-S1LOV111A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649603A | Yes | UBE | BXU545898, 1240716 (15523), BXU546542 (26842), 1240716 (28842) | 4955, BXU548237 (28842) | 4 |  |  | Direct Shipments WCS Send SH SP | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/5/2019 | 8/2/2019 |  | 1129 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 07:30 | ANAND, S | 56-F-EU-V-190725-S4LO061 |  | Yes | Y |  |  |  | KTT3 |  |  | 56-F-EU-V-190725-S4LOV061A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649UWF | No | UBE |  |  | 4 | 4 |  | Upload Invoices By Shipments - Validation File | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Puneet Sharma | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/12/2019 | 7/11/2019 |  | 1130 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-12 03:02 | Destrebecq, Eric | 56-F-EU-V-190709-S3LO084 | Upload | Yes | Y |  |  | waiting for R5649005I in sprint 4 | FCA2 |  |  | 56-F-EU-V-190709-S3LOV084A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R566111Z | Yes | UBE |  |  | 999 |  |  | Load F596111 From the Z File | Obsolete | [5 empty] | Technical Services | Logistics | Mandy Corbett, Swetha M S, Thierry Kestens |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1131 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R566111ZG | Yes | UBE | 1266473 | 22187 1266875 | 2 |  |  | Load Equipment Master F596111 from SAP | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/25/2019 | 6/24/2019 |  | 1132 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-31 10:11 | Vishnubhatla, Mithra | 56-F-EU-V-190624-S2LO129 |  | Yes | Y |  |  | Retrofitted for the F4102 Index change. In PD812 the BX LITM,MCU Index 13&nbsp; but in DV920 the Index was 17 .Hence retrofitted the object | KTTS5 |  |  | 56-F-EU-V-190624-S2LOV129A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R566112ZG | No | UBE | 1266473 (22187) | 1266875 (22187) | 2 | 5 |  | Equipment Conversion Error Report | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/14/2019 | 6/13/2019 |  | 1133 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 10:11 | ANAND, S | 56-F-EU-V-190613-S2LO059 | Error / Report | Yes | Y |  |  |  | KTTS5 |  |  | 56-F-EU-V-190613-S2LOV059A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5698009 | No | UBE |  |  | 4 |  |  | MILD Invoice PABACO Processor UBE | L3 Pass |  |  | TRUE | HE2E |  | Procurement | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/31/2019 | 7/30/2019 |  | 1134 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-08 03:01 | De Brouwer, Peter | 56-F-EU-V-190730-S4LO073 |  | Yes | Y |  |  | Reivew E2E process exists | KTW3 |  |  | 56-F-EU-V-190730-S4LOV073A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56AT42535 | No | UBE | 1251954 (21977) |  | 1 |  |  | Delivery Note Austria | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/24/2019 | 5/23/2019 |  | 1135 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 03:59 | Singh, Sunil Kumar | 56-F-EU-V-190515-S1LO25 |  | Yes | Yes |  |  | Retrofitted. Spec diff b/w PD812 & DV920 , the BSFN B0800750 is obseleted in DV920 .Hence used B96701 BSFN bcz if the String was found the returnFlag =zero in B0800750 and B96701 BSFN | KTT3 |  |  | 56-F-EU-V-190515-S1LV25A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56BX0014 | No | UBE |  |  | 999 |  |  | Pallet Labels - Zebra Printer Output - BeNeLux | Obsolete |  |  | TRUE | NA |  | Transportation | Logistics | Eric Destrebecq | L2 Not required |  |  |  | Terry Greenard / Vikas Verma | VV-12/08 - Changed from 999 to Sprint 5 as bsfn calling the ube is failing | Vikas Verma |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1136 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-28 10:27 | Chiau, Liesbet |  | Printer |  |  |  |  | obsolete, not required in EMEA | [7 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56BX42535 | No | UBE | 1263916 | 11215 1264408 | 3 |  |  | Delivery Note BeNeLux | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/12/2019 | 7/11/2019 |  | 1137 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-31 09:19 | Vishnubhatla, Mithra | 56-F-EU-V-190710-S3LO086 |  | Yes | Y |  |  |  | KTT3 |  |  | 56-F-EU-V-190710-S3LOV86A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56CALGN | No | UBE |  |  | 1 |  |  | Baxter Calendar Generation Based on Template | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/28/2019 | 5/28/2019 |  | 1138 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:53 | Chiau, Liesbet | 56-F-EU-V-190520-S1LO070 |  | Yes | Y |  |  | Move the object with Validation issue in 920 and 812 | KTT2 |  |  | 56-F-EU-V-190520-S1LOV70A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56CDNBL | No | UBE | 1260383 | 18020 1260385 | 4 |  |  | Populate/Refresh CDN Balance Table | L3 Pass |  |  | TRUE | H |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | VV-09/08 - Moved to Sprint 4 as per the discussion with Sameer for defect 233 | Vikas Verma |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/9/2019 | 8/8/2019 |  | 1139 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-31 09:15 | Vishnubhatla, Mithra | 56-F-EU-V-190808-S4LO124 |  | Yes |  |  |  | Retrofitted under sprint4. Refer defect 233. | KTW3 |  |  | 56-F-EU-V-190808-S4LOV124A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56CDNIT | No | UBE | BXU549758 |  | 6 |  |  | CDN Balance to F41021Integrity Check | L3 Pass | 313 | closed | TRUE | H |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 9/4/2019 | 9/3/2019 |  | 1140 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 04:08 | Joshi, Abhishek N | 56-F-EU-V-190827-S6LO006 |  | Yes | Yes |  |  |  | KTW3 |  |  | 56-F-EU-V-190827-S6LOV006A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56CH42535 | No | UBE | 1250045 (21992) | (21992) 1251617 | 3 |  |  | Delivery Note Switzerland | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/12/2019 | 7/11/2019 |  | 1141 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 07:52 | Singh, Sunil Kumar | 56-F-EU-V-190709-S3LO081 |  | Yes | Y |  |  |  | KTT3 |  |  | 56-F-EU-V-190709-S3LOV081A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56CONV | Yes | UBE | BXU545567 (11450) |  | 2 |  |  | ERP - Stock Conversion | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/14/2019 | 6/14/2019 |  | 1142 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 04:50 | Singh, Sunil Kumar | 56-F-EU-V-190614-S2LO001 |  | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190614-S2LO001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56CONV1 | Yes | UBE | 1275357 (67534) | BXU549013 (67534) | 5 |  |  | G2B Nordics - Conversion process between SAP-JDE | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/19/2019 | 8/19/2019 |  | 1143 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 07:38 | ANAND, S | 56-F-EU-V-190814-S5LO039 |  | Yes | Yes |  |  |  | KTW3 |  |  | 56-F-EU-V-190814-S5LOV039A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56CZ003R | No | UBE | BXU545316 |  | 4 |  |  | Reprint multiple Invoices from Legal Documents | L3 Pass | 232 |  | TRUE | HE2E |  | Order Management | OM | Swagatika Swain | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/27/2019 | 6/26/2019 |  | 1144 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 08:34 | Joshi, Abhishek N | 56-F-EU-V-190625-S2OM042 | Printer | Yes | Y |  |  | The invoice not appearing in Standard order try UA because of PO values of P4210 CZD0015 .we can’t see order in this version as sales update(status = 999) has been done for the Order has been moved to 999 status. |  |  |  | 56-F-EU-V-190625-S2OMV042A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56DE42535 | No | UBE | 1251956 | 1251989 22040 | 2 | 2 |  | Delivery Note Germany | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/25/2019 | 6/21/2019 |  | 1145 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-31 08:58 | Vishnubhatla, Mithra | 56-F-EU-V-190621-S1LO126 |  | Yes | Yes |  |  |  | KTT3 |  |  | 56-F-EU-V-190621-S1LOV126A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56E4211 | No | UBE |  |  | 2 |  |  | CZ csv extract F4211 | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/11/2019 | 6/11/2019 |  | 1146 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:06 | Chiau, Liesbet | 56-F-EU-V-190611-S2OM002 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190611-S2OMV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56ES42535 | No | UBE | 1235432 (15031) | 1235890 (15031) | 3 |  |  | Delivery Notes Print Spain | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/12/2019 | 7/12/2019 |  | 1147 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-07-24 03:35 | Singh, Sunil Kumar | 56-F-EU-V-190701-S3LO005 | Printer | Yes | Y |  |  |  | KTT3 |  |  | 56-F-EU-V-190701-S3LOV005A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FB040 | No | UBE |  |  | 6 |  |  | Sales Process Tracing by Customer | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Rafal Molas | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 9/3/2019 | 9/2/2019 |  | 1148 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-05 02:41 | MOLAS, RAFAL | 56-F-EU-V-190827-S6OM002 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6OMV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FBP190 | No | UBE |  |  | 999 |  |  | TOSC Sales Details | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1149 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FR42535 | No | UBE | 1256041 (25586) | 6013 1267974 | 3 |  |  | Delivery Note France | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/12/2019 | 7/11/2019 |  | 1150 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 10:28 | Singh, Sunil Kumar | 56-F-EU-V-190710-S3LO088 |  | Yes | Y |  |  |  | KTT3 |  |  | 56-F-EU-V-190710-S3LOV088A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FREDI | No | UBE |  |  | 1 |  |  | Freight Routing Flat File Import UBE | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/31/2019 | 5/31/2019 |  | 1151 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:53 | Chiau, Liesbet | 56-F-EU-V-190603-S1LO140 |  | Yes | Y |  |  |  | KTT4 |  |  | 56-F-EU-V-190603-S1LOV140A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRGEO | No | UBE | 1256936 (26046) | 1256937 (26046) | 3 |  |  | Freight Routing Upload - Geodis Calberson | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/15/2019 | 7/12/2019 |  | 1152 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 02:18 | Singh, Sunil Kumar | 56-F-EU-V-190708-S3LO076 | Upload | Yes | Y |  |  |  | KTT4 |  |  | 56-F-EU-V-190708-S3LOV076A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRINT | No | UBE | 1271317 (17787) | (17787) 1271319 | 3 |  |  | Freight forwarder Routing Upload - Integra2 | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/15/2019 | 7/14/2019 |  | 1153 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-02 13:10 | Singh, Sunil Kumar | 56-F-EU-V-190703-S3LO031 | Upload | Yes | Y |  |  |  | KTT4 |  |  | 56-F-EU-V-190703-S3LOV031A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FROUT | No | UBE |  |  | 3 |  |  | Freight Routing Upload UBE | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete | R56FROUT¦BXEUPL01 version promoted to 8.12 PD after spec merge, so the decision taken to take them up in R1, R2 etc. So tested R56FROUT using BXEU0001 version from fast path in DV 9.2 as it has same PO as R56FROUT¦BXEUPL01 version. |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/15/2019 | 7/12/2019 |  | 1154 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-17 05:36 | weber, scott | 56-F-EU-V-190715-S3LO092 | Upload | Yes | Y |  |  |  | KTT4 |  |  | 56-F-EU-V-190715-S3LOV092A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FULCD | No | UBE | BXU544575 (99298) |  | 3 |  |  | Fulcod Generator Report | L3 Pass |  |  | TRUE | L |  | MDM | MDM |  | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 07/08/2019 | 07/02/2019 |  | 1155 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-12 14:31 | Singh, Sunil Kumar | 56-F-EU-V-190702-S3MD021 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190702-S3MDV021A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56G0005 | Yes | UBE | 1268529 (23928) | 1268530 (23928) | 4 |  |  | Gambro: Create PO from SO - Direct Ship Process | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 08/14/2019 | 07/30/2019 |  | 1156 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 09:51 | Singh, Sunil Kumar | 56-F-EU-V-190731-S4LO078 |  | Yes | Yes |  |  |  | KTW3 |  |  | 56-F-EU-V-190731-S4LOV078A,56-F-EU-V-190731-S4LOV078B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56G0006 | Yes | UBE | 1268529 (23928) | 1268530 (23928) | 4 |  |  | Gambro: Lot Alignment UBE | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/1/2019 | 7/31/2019 |  | 1157 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 09:56 | Singh, Sunil Kumar | 56-F-EU-V-190731-S4LO090 |  | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190731-S4LOV090A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56G0041 | No | UBE |  |  | 999 |  |  | Gambro: Send JDE Stock Information to SAP | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1158 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56G0042 | OBS | UBE |  |  | 999 |  |  | Gambro: Send Receipt confirm from JDE to SAP | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1159 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56G0043 | OBS | UBE |  |  | 999 |  |  | Gambro: Send Load confirm from JDE to SAP | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1160 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56G0173 | No | UBE | 1259324 | 4523 | 4 |  |  | Gambro: GFS: Export Inventory Stock Level | L3 Pass |  |  | TRUE | ME2E |  | Technical Services | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/1/2019 | 7/31/2019 |  | 1161 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-30 07:56 | Vishnubhatla, Mithra | 56-F-EU-V-190730-S4LO072 | Export | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190730-S4LOV072A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56G0200 | Yes | UBE | 1266847 (17168) | 17168 | 4 |  |  | Gambro: GSQTS code Report | L3 Pass | 240 | Open | TRUE | L |  | Quality | Logistics | Miruna Danes | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/1/2019 | 7/31/2019 |  | 1162 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-18 09:41 | ANAND, S | 56-F-EU-V-190731-S4LO083 | Report | Yes | Y |  |  |  | KTQ4 |  |  | 56-F-EU-V-190731-S4LOV083A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56G43500 | No | UBE | 1260788 (3411) | 3411 | 4 |  |  | Gambro: PO Print to CSV | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/29/2019 | 7/28/2019 |  | 1163 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-01 07:44 | Singh, Sunil Kumar | 56-F-EU-V-190731-S4LO057 | Printer | Yes | Y |  |  |  | KTW1 |  |  | 56-F-EU-V-190731-S4LOV057A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56G4711 | Yes | UBE |  |  | 999 |  |  | Gambro GFS-JDE Interface Service Orders Pre-Processor | Obsolete | [5 empty] | Technical Services | Logistics | Mandy Corbett, Swetha M S, Thierry Kestens |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1164 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet |  | Interface | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56G4711W | No | UBE | BXU545935 | 103220 | 1 |  |  | GSP EDI Wrapper for EMEA | L3 Pass |  |  | TRUE | ME2E |  | Technical Services | Logistics | Mandy Corbett, Swetha M S, Thierry Kestens | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/31/2019 | 5/31/2019 |  | 1165 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-30 05:03 | Vishnubhatla, Mithra | 56-F-EU-V-190522-S1LO093 |  | Yes | Y |  |  |  | KTTS1 |  |  | 56-F-EU-V-190522-S1LOV93A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56G4713 | No | UBE |  |  | 999 |  |  | Inbound EDI order analysis | Obsolete |  |  |  | L |  | Technical Services | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1166 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet |  | Inbound | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56G6101 | Yes | UBE | 1258371 | 4102 | 2 |  |  | HWT: Export Equipment Master | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/25/2019 | 6/21/2019 |  | 1167 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-30 04:59 | Vishnubhatla, Mithra | 56-F-EU-V-190621-S1LO125 | Export | Yes | Yes |  |  |  | KTTS5 |  |  | 56-F-EU-V-190621-S1LOV125A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56G6102 | no | UBE |  |  | 2 | 6 |  | Retransmit Equipment Master Batches | L3 Pass | 141 | Closed | TRUE | L |  | Technical Services | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 06/14/2019 | 06/13/2019 |  | 1168 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-12 03:51 | Chiau, Liesbet | 56-F-EU-V-190611-S2LO057 |  | Yes | Y |  |  |  | KTTS5 |  |  | 56-F-EU-V-190611-S2LO057A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56GB42535 | No | UBE | 1258312 |  | 1 |  |  | Delivery Note - UK and Belfast | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/24/2019 | 5/24/2019 |  | 1169 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-09 05:24 | Singh, Sunil Kumar | 56-F-EU-V-190521-S1LO074 |  | Yes | Y |  |  |  | KTT3 |  |  | 56-F-EU-V-190521-S1LOV74A |  |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56HWT01 | No | UBE | 1278647 (82802) | 82802 | 4 | 4 |  | HWT Issue Resolution - Cardex Transactions | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/1/2019 | 7/31/2019 |  | 1170 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 03:16 | Singh, Sunil Kumar | 56-F-EU-V-190801-S4LO104 |  | Yes | Y |  |  |  | KTTS4 |  |  | 56-F-EU-V-190801-S4LOV104A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56HWT02 | No | UBE | 1278647 (82802) | 82802 | 4 | 4 |  | HWT Issue Resolution - Z File Processor | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/1/2019 | 7/31/2019 |  | 1171 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 03:16 | Singh, Sunil Kumar | 56-F-EU-V-190723-S4LO012 |  | Yes |  |  |  |  | KTTS4 |  |  | 56-F-EU-V-190723-S4LOV012A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56HWT03 | No | UBE |  |  | 999 | 4 |  | HWT Issue Resolution - SQL Updates | Obsolete |  |  |  | L |  | Technical Services | Logistics | Mandy Corbett, Swetha M S, Thierry Kestens |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1172 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56HWT04 | No | UBE | 1268647 (82802) | 82802 | 4 | 4 |  | Flag HWT Transactions as Baxter or Gambro | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 08/01/2019 | 07/30/2019 |  | 1173 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 03:19 | Singh, Sunil Kumar | 56-F-EU-V-190731-S4LO077 |  | Yes | Y |  |  |  | KTTS4 |  |  | 56-F-EU-V-190731-S4LOV077A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56HWT05 | No | UBE | 1278647 (82802) | 82802 | 4 | 4 |  | Determine whether a F56HWT01 record should be excluded | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/1/2019 | 7/31/2019 |  | 1174 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 03:21 | Singh, Sunil Kumar | 56-F-EU-V-190725-S4LO058 |  | Yes | Y |  |  |  | KTTS4 |  |  | 56-F-EU-V-190725-S4LOV058A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56HWT06 | No | UBE |  |  | 999 | 4 |  | Determine whether a F56HWT01 record is a stock record | Obsolete |  |  |  | L |  | Technical Services | Logistics | Mandy Corbett, Swetha M S, Thierry Kestens |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1175 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56HWT07 | No | UBE | 1278647 (82802) | 82802 | 4 | 4 |  | Delete Baxter Transactions from F596111 and F596108 | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/1/2019 | 7/31/2019 |  | 1176 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 03:23 | Singh, Sunil Kumar | 56-F-EU-V-190725-S4LO062 |  | Yes | Y |  |  |  | KTTS4 |  |  | 56-F-EU-V-190725-S4LOV062A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56HWT08 | No | UBE | 1278647 (82802) | 82802 1278736 | 4 | 4 |  | Reset Missing Cardex Transactions for Gambro | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/1/2019 | 7/31/2019 |  | 1177 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 03:25 | Singh, Sunil Kumar | 56-F-EU-V-190731-S4LO088 |  | Yes | Y |  |  |  | KTTS4 |  |  | 56-F-EU-V-190731-S4LOV088A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56HWT09 | No | UBE | 1278647 (82802) | 1278736 (82802) | 4 | 4 |  | Resequence Gambro Items/Lots that had missing transactions | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/01/2019 | 7/31/2019 |  | 1178 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 03:27 | Singh, Sunil Kumar | 56-F-EU-V-190731-S4LO076 |  | Yes | Y |  |  |  | KTTS4 |  |  | 56-F-EU-V-190731-S4LOV076A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56HWT10 | No | UBE |  |  | 999 | 4 |  | Remove From IT Cardex Transactions from F56HWT01 | Obsolete |  |  |  | L |  | Technical Services | Logistics | Mandy Corbett, Swetha M S, Thierry Kestens |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1179 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56HWT11 | No | UBE |  |  | 999 | 4 |  | Check that every X Y or Z type has a corresponding B I or G | Obsolete |  |  |  | L |  | Technical Services | Logistics | Mandy Corbett, Swetha M S, Thierry Kestens |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1180 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56HWT12 | No | UBE | 1278647 (82802) | 1278736 (82802) | 4 | 4 |  | Reset Exceptions on F56HWT01 from Backup | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 08/01/2019 | 08/31/2019 |  | 1181 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 03:29 | Singh, Sunil Kumar | 56-F-EU-V-190801-S4LO097 |  | Yes | Y |  |  |  | KTTS4 |  |  | 56-F-EU-V-190801-S4LOV097A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56HWT13 | Yes | UBE | 1278647 (82802) | 82802 1278636 | 4 | 4 |  | Update Ship To/Bill To Addresses in HWT | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/2/2019 | 8/1/2019 |  | 1182 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 03:30 | Singh, Sunil Kumar | 56-F-EU-V-190731-S4LO091 |  | Yes | Y |  |  |  | KTTS4 |  |  | 56-F-EU-V-190731-S4LOV091A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56HWT14 | No | UBE | 1278647 (82802) | 1278636 (82802) | 4 | 4 |  | Correct Dates and Country Codes on HWT | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/2/2019 | 8/1/2019 |  | 1183 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 03:33 | Singh, Sunil Kumar | 56-F-EU-V-190801-S4LO093 |  | Yes | Y |  |  |  | KTTS4 |  |  | 56-F-EU-V-190801-S4LOV093A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56HWT15 | No | UBE | 1278647 (82802) | 82802 | 4 | 4 |  | Set the UR01 flag on F596111Z | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/2/2019 | 8/1/2019 |  | 1184 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 03:37 | Singh, Sunil Kumar | 56-F-EU-V-190731-S4LO084 |  | Yes |  |  |  |  | KTTS4 |  |  | 56-F-EU-V-190731-S4LOV084A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56HWT16 | Yes | UBE |  |  | 999 | 4 |  | Load missing OUT records in workfile | Obsolete |  |  |  | L |  | Technical Services | Logistics | Mandy Corbett, Swetha M S, Thierry Kestens |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1185 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56HWT17 | Yes | UBE |  |  | 999 | 4 |  | Reset Cardex & Z-file for missing OUT records | Obsolete |  |  |  | L |  | Technical Services | Logistics | Mandy Corbett, Swetha M S, Thierry Kestens |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1186 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56HWT18 | No | UBE | BXU545935 | 103220 | 4 | 4 |  | Fix Reason Codes on F596111 | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/2/2019 | 8/1/2019 |  | 1187 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-30 04:10 | Vishnubhatla, Mithra | 56-F-EU-V-190802-S4LO107 |  | Yes | Y |  |  |  | KTTS4 |  |  | 56-F-EU-V-190802-S4LOV107A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56HWT19 | No | UBE | 1259324 | 4523 | 4 | 4 |  | Hardware Tracking Equipment & Spare Parts Integrity Report | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/2/2019 | 8/1/2019 |  | 1188 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-30 04:05 | Vishnubhatla, Mithra | 56-F-EU-V-190802-S4LO110 | Report | Yes | Y |  |  |  | KTTS4 |  |  | 56-F-EU-V-190802-S4LOV110A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56IE42535 | No | UBE | 1258312 |  | 4 |  |  | Delivery Note - IE | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/2/2019 | 8/1/2019 |  | 1189 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-09 05:34 | Singh, Sunil Kumar | 56-F-EU-V-190731-S4LO002 |  | Yes | Y |  |  |  | KTT3 |  |  | 56-F-EU-V-190731-S4LOV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56IE43500 | No | UBE | 1258312 |  | 4 |  |  | Baxter Purchase Order Print IE - BIPublisher output | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 08/02/2019 | 08/01/2019 |  | 1190 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-09 05:35 | Singh, Sunil Kumar | 56-F-EU-V-190731-S4LO079 | Printer | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190731-S4LOV079A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56IM173 | No | UBE | 1259324 | 4523 | 2 | 3 |  | Retrieve Cardex Records for Missing GSP Inventory | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/13/2019 | 6/12/2019 |  | 1191 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-30 04:03 | Vishnubhatla, Mithra | 56-F-EU-V-190611-S2LO068 |  | Yes | Y |  |  | Retrofit not required | KTTS5 |  |  | 56-F-EU-V-190611-S2LOV068A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56IN003 | No | UBE |  |  | 999 |  |  | Plasma Commision Invoice | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1192 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56IT42535 | No | UBE | 1248392 (21265) | 12057 | 4 |  |  | Delivery Note Italy | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Puneet Sharma | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/2/2019 | 8/1/2019 |  | 1193 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-05 13:24 | Singh, Sunil Kumar | 56-F-EU-V-190725-S4LO059 |  | Yes | Y |  |  | Error in BSFN "SearchForStringinString(B0800750)" Replaced the BSFN B0800750 with B5600014. | KTT3 |  |  | 56-F-EU-V-190725-S4LOV059A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56ND42535 | No | UBE | 1241414 (17921) |  | 5 |  |  | Delivery Note Nordics | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/2/2019 | 8/1/2019 |  | 1194 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-02 13:20 | Singh, Sunil Kumar | 56-F-EU-V-190731-S4LO087 |  | Yes | Y |  |  |  | KTT3 |  |  | 56-F-EU-V-190731-S4LOV087A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL0005 | No | UBE | 1273412 (12057) | 12057 | 1 |  |  | Delivery Notes Print | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics |  | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/24/2019 | 5/24/2019 |  | 1195 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-31 10:17 | Singh, Sunil Kumar | 56-F-EU-V-190514-S1LO021 | Printer | Yes | Y |  |  | done. Index verified. DS generated. L1 done. | KTT3 |  |  | 56-F-EU-V-190515-S1LOV021A |  |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL0007P | No | UBE | BXU546597 |  | 1 |  |  | Receipt Document (PZ) | L3 Pass |  |  | TRUE | LE2E |  | Warehouse | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/28/2019 | 5/28/2019 |  | 1196 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 04:31 | Joshi, Abhishek N | 56-F-EU-V-190517-S1LO049 |  | Yes | Y |  |  | Review E2E process exists | KTW2 |  |  | 56-F-EU-V-190517-S1LOV49A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL0014Z | No | UBE |  |  | 6 |  |  | Pallet Labels - Zebra Printer Output AP 23/10/2019 - in a test today, the label job was called by the integrations and zebra code generated by the UBE. AP 10/10/2019 - job is not called by the integrations when a shipment is processed in Swisslog for Blonie WH. | PPD Passed | 433 | Open | TRUE | HE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/5/2019 | 8/1/2019 |  | 1197 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-23 10:34 | Partanen, Aki | 56-F-EU-V-190801-S4LO092 | Printer | Yes |  |  |  | AP: Since integrations needed for the run, moving this object to CRP (L3 not required). | KTW1 |  |  | 56-F-EU-V-190801-S4LOV092A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL0020 | No | UBE | BXU550845 |  | 1 |  |  | Stock Documents Print | L3 Pass |  |  | TRUE | LE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/28/2019 | 5/27/2019 |  | 1198 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-23 04:56 | Joshi, Abhishek N | 56-F-EU-V-190523-S1LO101 | Printer | Yes | Y |  |  | Review E2E process exists | KTW2 |  |  | 56-F-EU-V-190523-S1LOV101A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL0033 | No | UBE | BXU548328 |  | 6 |  | CRP | Report for Cost Upload | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 9/3/2019 | 9/1/2019 |  | 1199 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 11:08 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI009 | Upload / Report | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV009A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL0035 | No | UBE | BXU548329 |  | 4 |  | CRP | Standard to Standard by Product | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/7/2019 | 8/6/2019 |  | 1200 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 11:09 | Joshi, Abhishek N | 56-F-EU-V-190802-S4FI090 |  | Yes | [7 empty] | 56-F-EU-V-190802-S4FIV090A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL0035A | No | UBE | BXU548331 |  | 4 |  | CRP | Standard to Standard Create Workfile | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 08/07/2019 | 08/06/2019 |  | 1201 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 11:12 | Joshi, Abhishek N | 56-F-EU-V-190806-S4FI101 |  | Yes | Y | [6 empty] | 56-F-EU-V-190806-S4FIV101A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL0040 | No | UBE | BXU550822 |  | 4 |  |  | Poland - Stock Documents Print | L3 Pass |  |  | TRUE | LE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/02/2019 | 8/01/2019 |  | 1202 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-20 07:17 | Joshi, Abhishek N | 56-F-EU-V-190801-S4LO096 | Printer | Yes | Y |  |  | Review E2E process exists | KTW4 |  |  | 56-F-EU-V-190801-S4LOV096A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL0045 | No | UBE |  |  | 2 |  |  | Returned Products Accepted | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Miruna Danes | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/13/2019 | 6/12/2019 |  | 1203 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:06 | Chiau, Liesbet | 56-F-EU-V-190610-S2LO034 |  | Yes | Yes |  |  |  | KTQ3 |  |  | 56-F-EU-V-190610-S2LOV34A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL0046 | No | UBE | BXU548581 |  | 2 |  |  | Returned Products Waiting | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Pawel Oskroba | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/13/2019 | 6/13/2019 |  | 1204 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 04:26 | Joshi, Abhishek N | 56-F-EU-V-190610-S2LO014 |  | Yes | Yes |  |  |  | KTQ3 |  |  | 56-F-EU-V-190610-S2LOV14A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL0048 | Yes | UBE |  | BXU547454 (13929) | 2 |  |  | Print Return Request | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Pawel Oskroba | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/11/2019 | 6/11/2019 |  | 1205 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 07:44 | ANAND, S | 56-F-EU-V-190611-S2LO046 | Printer | Yes | Y |  |  |  | KTQ4 |  |  | 56-F-EU-V-190611-S2LOV046A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL017 | No | UBE |  |  | 3 |  |  | Sales Proces Tracing by Product 2 | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Malatesh Ganiger | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/02/2019 | 7/01/2019 |  | 1206 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-18 06:26 | Ganiger, Malatesh | 56-F-EU-V-190701-S3OM003 |  | Yes | Y |  |  | Retrofit not required |  |  |  | 56-F-EU-V-190701-S3OMV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL42535 | No | UBE | 1267798 (26162) |  | 4 |  |  | Delivery Note - Poland | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 07/29/2019 | 07/29/2019 |  | 1207 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 06:13 | Singh, Sunil Kumar | 56-F-EU-V-190725-S4LO060 |  | Yes | Y |  |  |  | KTT3 |  |  | 56-F-EU-V-190725-S4LOV060A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PT42535 | No | UBE | 1232813 (13308) | 1233105 (13308) | 1 |  |  | Delivery Notes Print | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/28/2019 | 5/28/2019 |  | 1208 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-07-24 09:54 | Singh, Sunil Kumar | 56-F-EU-V-190521-S1LO088 | Printer | Yes | Y |  |  |  | KTT3 |  |  | 56-F-EU-V-190521-S1LOV088A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56R4703B | No | UBE |  |  | 1 |  |  | BO Release Report | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete | difficult to find data |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 28/05/2019 | 28/05/2019 |  | 1209 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:53 | Chiau, Liesbet | 56-F-EU-V-190516-S1LO029 | Report | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190516-S1LOV29A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56RU006 | Yes | UBE | BXU548597 19218 | 19218 BXU547609 | 5 |  |  | Russian - Inventory Check Goods In Transit INV-6 | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/19/19 | 8/16/19 |  | 1210 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 08:06 | ANAND, S | 56-F-EU-V-190812-S5LO014 |  | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190812-S5LOV014A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56RU015 | Yes | UBE | BXU546667 (49469) | 46469 | 5 |  |  | Russian Logistics WarehouseTORG15 Damaged Goods | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/19/2019 | 8/16/2019 |  | 1211 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 06:24 | Singh, Sunil Kumar | 56-F-EU-V-190814-S5LO053 |  | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190814-S5LOV053A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56RU019 | No | UBE | BXU548585 |  | 5 |  |  | Russian INV 3 Report | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/19/2019 | 8/16/2019 |  | 1212 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 05:26 | Joshi, Abhishek N | 56-F-EU-V-190814-S5LO051 | Report | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190814-S5LOV051A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56RU020 | No | UBE | 1267638 (19411) |  | 5 |  |  | Russian Logistics WarehouseReport - TORG13 | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/19/2019 | 8/19/2019 |  | 1213 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-05 07:35 | Singh, Sunil Kumar | 56-F-EU-V-190819-S5LO065 | Report | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190819-S5LOV065A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56RU029 | No | UBE | BXU548600 |  | 5 |  |  | Russia TORG29 Logistics WarehouseReport | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | CIZMECI,TANKUT |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/19/2019 | 8/16/2019 |  | 1214 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-20 06:34 | Joshi, Abhishek N | 56-F-EU-V-190814-S5LO047 | Report | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190814-S5LOV047A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56SLOG2 | Yes | UBE | BXU531854 (133080B) | BXU547397(133080B) | 3 |  |  | Serialisation Log Processor | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/15/2019 | 7/12/2019 |  | 1215 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-05-26 07:50 | Singh, Sunil Kumar | 56-F-EU-V-190710-S3LO051 |  | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190710-S3LOV051A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56SLOGE | No | UBE | BXU531854 (133080B) | 133080B | 3 |  |  | Serialised Log Error Reporting | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/15/2019 | 7/15/2019 |  | 1216 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-12 12:12 | Singh, Sunil Kumar | 56-F-EU-V-190715-S3LO091 | Error / Report | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190715-S3LOV091A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56SLOGP | No | UBE |  |  | 6 |  |  | Serialised Log Purge UBE | PPD Passed |  |  | TRUE | L |  | Purge | ARO | Cosmin Mutiu / Terry Greenard | L2 Not required | No KT, as Tested by user only in ICT |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/15/2019 | 7/14/2019 |  | 1217 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-12-23 09:08 | Greenard, Terry | 56-F-EU-V-190708-S3AR118 |  | Yes | Y |  |  | Works in PPD, records purged - report saved.There is a issue but it exists in 8.12 also |  |  |  | 56-F-EU-V-190708-S3ARV118A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56SPR01 | No | UBE |  |  | 3 |  |  | Sales in Specific Period Report | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Malatesh Ganiger | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 07/01/2019 | 07/01/2019 |  | 1218 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-18 06:27 | Ganiger, Malatesh | 56-F-EU-V-190701-S3OM010 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3OMV010A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56SPR03 | No | UBE |  |  | 3 |  |  | Sales by SBU, Item and Price Report | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Malatesh Ganiger | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/2/2019 | 7/1/2019 |  | 1219 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-18 05:24 | Ganiger, Malatesh | 56-F-EU-V-190628-S3OM002 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190628-S3OMV02A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56SPR04 | No | UBE |  |  | 3 |  |  | Sales by Customer (Total), Export to TXT-File | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Malatesh Ganiger | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 07/02/2019 | 07/02/2019 |  | 1220 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-28 06:18 | Ganiger, Malatesh | 56-F-EU-V-190701-S3OM009 | Export | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3OMV009A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56SPR05 | No | UBE | BXU544776 (18535) |  | 2 |  |  | Summary by Buyer | L3 Pass | 149 | Closed | TRUE | LNE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/13/2019 | 6/13/2019 |  | 1221 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 06:22 | Singh, Sunil Kumar | 56-F-EU-V-190610-S2LO023 |  | Yes | Yes |  |  |  | KTW5 |  |  | 56-F-EU-V-190610-S2LOV023A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56SPR07 | No | UBE |  |  | 3 |  |  | Sales in Specific Period Report - Buyer Summary | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Swagatika Swain | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1222 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-17 02:11 | Swain, Swagatika | 56-F-EU-V-190628-S3OM007 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190628-S3OMV007A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56SPR08 | No | UBE |  |  | 3 |  |  | Sales Statistic - Count of Documents by Buyer | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Swagatika Swain | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/2/2019 | 7/1/2019 |  | 1223 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-17 02:43 | Swain, Swagatika | 56-F-EU-V-190628-S3OM001 |  | Yes | Y | [6 empty] | 56-F-EU-V-190628-S3OMV01A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56SPR10 | No | UBE |  |  | 3 |  |  | Sales Statistic - Count of Documents by Trans. Originator | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Swagatika Swain | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/4/2019 | 7/3/2019 |  | 1224 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-17 03:23 | Swain, Swagatika | 56-F-EU-V-190701-S3OM017 |  | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3OMV017A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56SWEXT | Yes | UBE | BXU545567 (11450) |  | 5 |  |  | Inventory Conv Swisslog extract | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/20/2019 | 8/14/2019 |  | 1225 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 04:52 | Singh, Sunil Kumar | 56-F-EU-V-190814-S5LO041 |  | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190814-S5LOV041A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56X4701 | Yes | UBE | 1264519 | 12127 | 1 |  |  | Populate Inbound APS for Ownership Change | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Leonard Dartois | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1226 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-29 09:46 | Vishnubhatla, Mithra | 56-F-EU-V-190515-S1LO008 | Inbound | Yes | Y |  |  |  | KTW5 |  |  | 56-F-EU-V-190515-S1LOV08A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R574352A | No | UBE |  |  | 3 |  | CRP | PO Receipts - Currency Mismatch - Auto Reversal UBE | L3 Pass |  |  | TRUE | HNE2E | TRUE | Finance AP | Finance | Seray Golge | L2 Pass / Complete | Defect 183 is closed, R47071/Pssing for L2 since R47071 was ran succefully&nbsp; |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/10/2019 | 7/9/2019 |  | 1227 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-29 01:27 | Thippulla, sreekanth | 56-F-EU-V-190708-S3FI124 |  | Yes | Y | [6 empty] | 56-F-EU-V-190708-S3FIV124A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R57R0110 | Yes | UBE | BXU531264 39268 | BXU547463 (12961) | 1 |  |  | F4111 / F41021 Integrity | L3 Pass |  |  | TRUE | H |  | Warehouse | ARO | Malatesh Ganiger | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1228 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-20 08:16 | Vishnubhatla, Mithra | 56-F-EU-V-190515-S1LO026 |  | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190515-S1LOV026A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5841112 | No | UBE | BXU546697 |  | 1 |  | CRP | F41112 Database Output | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 28/05/2019 | 28/05/2019 |  | 1229 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 03:50 | Joshi, Abhishek N | 56-F-EU-V-190515-S1FI006 |  | Yes | Y | [6 empty] | 56-F-EU-V-190515-S1FIV06A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5841116 | No | UBE | BXU546948 |  | 1 |  | CRP | Slow movement inventories | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | 25/06: Reviewed Data issues-L3 Passed. L3 Failed due to data differences between 8.12 and 9.20 . Sent Details to Joanne | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 28-05-19 | 28-05-19 |  | 1230 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 03:56 | Joshi, Abhishek N | 56-F-EU-V-190517-S1FI013 |  | Yes | Y | [6 empty] | 56-F-EU-V-190517-S1FIV13A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5842520 | No | UBE | 1260383 (18020) | 18020 | 2 |  |  | Print Pick Slips - Russia | L3 Pass |  |  | TRUE | H2E2 |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/12/2019 | 6/12/2019 |  | 1231 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 05:03 | Singh, Sunil Kumar | 56-F-EU-V-190612-S2LO079 | Printer | Yes | Yes |  |  |  | KTW5 |  |  | 56-F-EU-V-190612-S2LOV079A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58435 | No | UBE | 1230527 (13303) | 13303 | 1 |  |  | Purchase Order Print - derived from R43500 | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 19/05/28 | 19/05/28 |  | 1232 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 05:25 | Singh, Sunil Kumar | 56-F-EU-V-190528-S1LO120 | Printer | Yes | Y |  |  | No retrofit required | KTW1 |  |  | 56-F-EU-V-190528-S1LOV120A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R587441003 | No | UBE |  |  | 1 |  |  | Item Transfer Note - RUS - 43 - 74R | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/28/2019 | 5/27/2019 |  | 1233 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:54 | Chiau, Liesbet | 56-F-EU-V-190520-S1LO066 |  | Yes | Y |  |  | Retrofit not required | KTW2 |  |  | 56-F-EU-V-190520-S1LOV66A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58EQL01 | Yes | UBE | 1230246 (13692) |  | 1 |  |  | Expired Quantity List | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Miruna Danes | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/28/2019 | 5/27/2019 |  | 1234 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 11:25 | Singh, Sunil Kumar | 56-F-EU-V-190527-S1LO116 |  | Yes | Y |  |  |  | KTQ1 |  |  | 56-F-EU-V-190527-S1LOV116A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58FBP070 | Yes | UBE | 1230246 (13692) | 13692 | 5 |  |  | Inventory Transactions History Report | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Pawel Oskroba | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/20/2019 | 8/19/2019 |  | 1235 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-18 07:44 | ANAND, S | 56-F-EU-V-190813-S5LO032 | Report | Yes | Y |  |  |  | KTQ3 |  |  | 56-F-EU-V-190813-S5LOV032A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58FBP200 | No | UBE |  |  | 5 |  |  | GIT Report | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Pawel Oskroba | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | CIZMECI,TANKUT |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 08/20/2019 | 08/19/2019 |  | 1236 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-30 07:01 | Oskroba, Pawel | 56-F-EU-V-190816-S5LO055 | Report | Yes | Y |  |  |  | KTQ4 |  |  | 56-F-EU-V-190816-S5LOV055A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58FBP240 | No | UBE | BXU546824 |  | 3 |  | CRP | Inventory Transactions History Logistic Report | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/10/2019 | 7/10/2019 |  | 1237 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 04:00 | Joshi, Abhishek N | 56-F-EU-V-190701-S3FI005 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3FIV005A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58ICR01B | No | UBE | BXU546244 |  | 3 |  |  | Item Cross Reference Print | L3 Pass | 166 | Closed | TRUE | LNE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/13/2019 | 6/12/2019 |  | 1238 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 05:23 | Joshi, Abhishek N | 56-F-EU-V-190611-S2LO078 | Cross Ref / Printer | Yes | Yes |  |  |  | KTW5 |  |  | 56-F-EU-V-190611-S2LOV078A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58IL002 | No | UBE |  |  | 2 |  |  | Inventory List - Hold/Qua/Ava | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Leonard Dartois | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/13/2019 | 6/13/2019 |  | 1239 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:06 | Chiau, Liesbet | 56-F-EU-V-190613-S2LO001 |  | Yes | Yes |  |  |  | KTW5 |  |  | 56-F-EU-V-190613-S2LO001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58ILE03 | No | UBE | BXU548595 |  | 2 |  |  | Inventory List - Export to TXT-File | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 06/13/2019 | 06/12/2019 |  | 1240 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 04:39 | Joshi, Abhishek N | 56-F-EU-V-190611-S2LO049 | Export | Yes | Yes |  |  | No Retrofit Required | KTW5 |  |  | 56-F-EU-V-190611-S2LO049A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58PL012 | Yes | UBE | 1230246 (13692) | 24753 | 2 |  |  | Inventory Movement Summary | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Pawel Oskroba | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/13/2019 | 6/13/2019 |  | 1241 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-18 07:47 | ANAND, S | 56-F-EU-V-190610-S2LO008 |  | Yes | Yes |  |  |  | KTQ4 |  |  | 56-F-EU-V-190610-S2LOV08A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58PL013 | Yes | UBE | 1230246 (13692) | 13692 | 2 |  |  | Track Change Lot Status | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Miruna Danes | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/13/2019 | 6/13/2019 |  | 1242 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-18 07:48 | ANAND, S | 56-F-EU-V-190611-S2LO037 |  | Yes | Yes |  |  |  | KTQ3 |  |  | 56-F-EU-V-190611-S2LOV037A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58PL014 | Yes | UBE | 1230246 (13692) | 13692 | 2 |  |  | QA Stock Report | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Pawel Oskroba | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/13/2019 | 6/13/2019 |  | 1243 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-18 07:49 | ANAND, S | 56-F-EU-V-190610-S2LO021 | Report | Yes | Yes |  |  |  | KTQ4 |  |  | 56-F-EU-V-190610-S2LOV021A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58PL016 | Yes | UBE | 1230246 (13692) | 1232195 | 3 |  |  | Sales Proces Tracing by Product | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Swagatika Swain | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1244 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 08:35 | ANAND, S | 56-F-EU-V-190701-S3OM001 |  | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3OMV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58PL018 | No | UBE | 1257988 (27008) | 27008 | 2 |  |  | Location Report | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Pawel Oskroba | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/12/2019 | 6/11/2019 |  | 1245 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-19 07:01 | ANAND, S | 56-F-EU-V-190611-S2LO033 | Report | Yes | Y |  |  |  | KTQ3 |  |  | 56-F-EU-V-190611-S2LOV033A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58PL019 | Yes | UBE | 1230246 (13692) | 19981 | 2 |  |  | Inventory Structure | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Pawel Oskroba | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/12/2019 | 6/12/2019 |  | 1246 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-18 07:50 | ANAND, S | 56-F-EU-V-190612-S2LO002 | [6 empty] | KTQ4 |  |  | 56-F-EU-V-190612-S2LO002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58R0072 | No | UBE |  |  | 999 | 6 |  | Purge EDI Inbound 945 Files Report | Obsolete |  |  | TRUE | L | TRUE | Purge | ARO | Cosmin Mutiu / Terry Greenard | L2 Not required | No KT, as Tested by user only in ICT |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/8/2019 | 8/7/2019 |  | 1247 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-17 09:09 | Greenard, Terry | 56-F-EU-V-190801-S4AR012 | Inbound / Report | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190801-S4ARV012A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58R0094 | No | UBE |  |  | 4 |  |  | EDI Product Activity Data Edit/Create | L3 Pass | 260 | WIP | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | Found Differences in the Code. Details attached in the mail | Nikit |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 08/06/2019 | 08/06/2019 |  | 1248 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-23 03:11 | Mughal, Abdul | 56-F-EU-V-190801-S4LO108 |  | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190801-S4LOV108A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58R43Z1I | No | UBE |  |  | 4 |  |  | Demand Solutions to JDE - Create Purchase Orders | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/6/2019 | 8/5/2019 |  | 1249 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-14 11:16 | Mughal, Abdul | 56-F-EU-V-190801-S4LO100 |  | Yes |  |  |  |  | KTW2 |  |  | 56-F-EU-V-190801-S4LOV100A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58R4730 | OBS | UBE |  |  | 999 |  |  | EDI 945 Preprocessor UBE | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1250 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58R47500 | OBS | UBE |  |  | 999 |  |  | Inbound Transaction Processor | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1251 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet |  | Inbound | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58R49500 | OBS | UBE |  |  | 999 |  |  | Batch Transportation Shipment Confirmation | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1252 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58SCM004 | No | UBE |  |  | 2 |  |  | List discrepancies in G/L Class and SBU | L3 Pass |  |  | TRUE | H |  | MDM | MDM |  | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/12/2019 | 6/11/2019 |  | 1253 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:06 | Chiau, Liesbet | 56-F-EU-V-190611-S2LO041 |  | Yes | Y | [6 empty] | 56-F-EU-V-190611-S2LOV041A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58SCM005 | No | UBE |  |  | 6 |  |  | List discrepancies in SBU Description | L3 Pass |  |  | TRUE | H |  | MDM | MDM |  | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 09/13/2019 | 09/12/2019 |  | 1254 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-13 03:37 | Icardo, Ana | 56-F-EU-V-190904-S6MD006 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190904-S6MDV006A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58SCM006 | No | UBE |  |  | 6 |  |  | Integrity Report - GLPT and SBU | L3 Pass |  |  | TRUE | H |  | MDM | MDM |  | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 9/13/2019 | 9/12/2019 |  | 1255 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-16 03:04 | Icardo, Ana | 56-F-EU-V-190910-S6MD008 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190910-S6MDV008A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5942323 | No | UBE |  |  | 999 |  |  | ARIBA - Work Order Extract | Obsolete | [5 empty] | Finance AP | Finance | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1256 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5942521A | OBS | UBE |  |  | 999 |  |  | Print Pick/Pack Slips by Load Number | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1257 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:14 | Chiau, Liesbet |  | Printer | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59437001 | No | UBE |  |  | 5 |  |  | Custom- Sales Order Purchase Order Generator | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/20/2019 | 8/20/2019 |  | 1258 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-27 02:32 | Mughal, Abdul | 56-F-EU-V-190814-S5LO040 |  | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190814-S5LOV040A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59604 | Yes | UBE | 1247143 | 12817,BXU545672 | 3 |  |  | Extraction of X-levels Hierarchy with MCC link | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/03/2019 | 7/02/2019 |  | 1259 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 10:40 | Joshi, Abhishek N | 56-F-EU-V-190702-S3MD018 |  | Yes | Y | [6 empty] | 56-F-EU-V-190702-S3MDV018A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R00303 | No | UBE |  |  | 3 |  |  | User Exception Table UBE | L3 Pass |  |  | TRUE | L |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 07/03/2019 | 07/03/2019 |  | 1260 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-15 03:26 | Barrera Perez, Carlos Manuel | 56- F-EU-V-190701-S3MD010 |  | Yes | Y | [6 empty] | 56- F-EU-V-190701-S3MDV010A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0066 | On Hold | UBE |  |  | 2 |  |  | Lot Master and Transaction Synchronize Report | L3 Not Required |  |  | TRUE |  |  | Technical Services | Logistics | Mandy Corbett, Swetha M S, Thierry Kestens | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/28/2019 | 6/28/2019 |  | 1261 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:06 | Chiau, Liesbet | 56-F-EU-V-190613-S2LO085 | Report | Yes | Yes |  |  | On Hold N/A for EMEA |  |  |  | 56-F-EU-V-190613-S2LOV085A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0067 | No | UBE |  |  | 2 | 3 |  | Customer List for FCA Report Customer No- Build Work File | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/12/2019 | 65/12/2019 |  | 1262 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:06 | Chiau, Liesbet | 56-F-EU-V-190610-S2LO007 | Report | Yes | Y |  |  |  | KTTS3 |  |  | 56-F-EU-V-190610-S2LOV07A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0074 | Yes | UBE |  |  | 5 |  |  | Extract Lot Master for Outbound Transaction Set 856 | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/20/2019 | 8/29/2019 |  | 1263 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-29 05:54 | Mughal, Abdul | 56-F-EU-V-190814-S5LO043 | Outbound | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190814-S5LOV043A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0109 | No | UBE |  |  | 1 | 2 |  | ASN Data Turnaround | L3 Pass | 55 | Closed | TRUE | HE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/28/2019 | 5/28/2019 |  | 1264 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-12 03:51 | Chiau, Liesbet | 56-F-EU-V-190524-S1LO111 |  | Yes | Yes |  |  |  | KTW2 |  |  | 56-F-EU-V-190524-S1LOV111A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0129 | no | UBE |  |  | 5 |  |  | Install/Swap Data from Siebel to Hardware Tracking System | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/22/19 | 8/19/19 |  | 1265 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-27 06:30 | BILENSOY, NURI | 56-F-EU-V-190812-S5LO015 |  | Yes | Y |  |  |  | KTTS5 |  |  | 56-F-EU-V-190812-S5LOV015A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0130 | On Hold | UBE |  |  | 2 |  |  | JDE and Hardware Tracking System Data Integrity Report | L3 Not Required |  |  | TRUE |  |  | Technical Services | Logistics | Mandy Corbett, Swetha M S, Thierry Kestens | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/28/2019 | 6/27/2019 |  | 1266 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:06 | Chiau, Liesbet | 56-F-EU-V-250619-S2LO138 | Report | Yes | Y |  |  | On Hold N/A for EMEA |  |  |  | 56-F-EU-V-250619-S2LOV138A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0145 | No | UBE |  |  | 2 |  |  | Customer List for FCA Rep with Serial Number - Building WF | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/12/2019 | 6/12/2019 |  | 1267 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:06 | Chiau, Liesbet | 56-F-EU-V-190610-S2LO020 |  | Yes | Y |  |  |  | KTTS5 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0146 | No | UBE |  |  | 2 | 3 |  | Customer List for FCA Report - Build Work File | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/12/2019 | 6/12/2019 |  | 1268 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:06 | Chiau, Liesbet | 56-F-EU-V-190610-S2LO018 | Report | Yes | Yes |  |  |  | KTTS3 |  |  | 56-F-EU-V-190610-S2LOV018A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0153 | No | UBE |  |  | 3 |  |  | ASN Outbound Creation Report | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/16/2019 | 7/15/2019 |  | 1269 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-23 08:18 | Mughal, Abdul | 56-F-EU-V-190716-S3LO001 | Outbound / Report | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190716-S3LOV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0184 | No | UBE |  |  | 5 |  |  | Sender Invoice to F59TRNST file | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | CIZMECI,TANKUT |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/20/2019 | 8/17/2019 |  | 1270 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-28 10:44 | Mughal, Abdul | 56-F-EU-V-190814-S5LO054 |  | Yes | Y |  |  |  | KTW1 |  |  | 56-F-EU-V-190814-S5LOV054A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0257 | No | UBE | BXU546703 |  | 3 |  | CRP | Cardex Extract | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Robbin/Florencia | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/10/2019 | 7/09/2019 |  | 1271 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 10:22 | Joshi, Abhishek N | 56-F-EU-V-190710-S3FI001 |  | Yes | Y | [6 empty] | 56-F-EU-V-190710-S3FIV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0269 | No | UBE |  |  | 3 |  |  | Repost - Failed WO Commitments | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 07/16/2019 | 07/15/2019 |  | 1272 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-23 08:46 | De Brouwer, Peter | 56-F-EU-V-190715-S3LO095 |  | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190715-S3LOV095A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0322 | Yes | UBE | 1259324 |  | 2 | 1 |  | JDE Cardex and HWT Work File Process Update | L3 Pass |  |  | TRUE | HE2E |  | Technical Services | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/21/2019 | 6/20/2019 |  | 1273 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-21 00:21 | Singh, Sunil Kumar | 56-F-EU-V-190620-S2LO119 |  | Yes | Y |  |  | Retrofit not required | KTTS5 |  |  | 56-F-EU-V-190620-S2LOV119A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0408 | No | UBE |  |  | 2 |  |  | FCA YTD Report | L3 Not Required |  |  | TRUE | L |  | Transportation | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/28/2019 | 6/27/2019 |  | 1274 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:06 | Chiau, Liesbet | 56-F-EU-V-250619-S2LO137 | Report | Yes | Y |  |  | On Hold N/A for EMEA | na |  |  | 56-F-EU-V-250619-S2LOV137A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0409 | No | UBE |  |  | 999 | 6 |  | FCA YTD Purge Report | Obsolete |  |  | TRUE | L |  | Purge | ARO | Cosmin Mutiu / Terry Greenard | L2 Not required | No KT, as Tested by user only in ICT |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1275 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-12-23 05:38 | Greenard, Terry | 56-F-EU-V-190624-S2AR001 | Report | Yes | Y |  |  | Global Object - Not run since 2017 |  |  |  | 56-F-EU-V-190624-S2ARV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0410 | Yes | UBE | BXU516652 (109164) |  | 1 |  |  | Populate F2F ASN Outbound | L3 Not Required |  |  | TRUE |  |  | Warehouse | Logistics | Abdul Mughal | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/31/2019 | 5/31/2019 |  | 1276 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 05:28 | Singh, Sunil Kumar | 56-F-EU-V-190521-S1LO075 | Outbound | Yes | Y |  |  | On Hold N/A for EMEA | KTW2 |  |  | 56-F-EU-V-190521-S1LOV75A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0411 | Yes | UBE |  |  | 999 |  |  | Custom Preprocessor F2F ASN Inbound | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1277 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Inbound | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0412 | No | UBE | BXU516652 (109164) |  | 3 |  |  | Foreign to Foreign Sourcing Report | L3 Not Required |  |  | TRUE |  |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/16/2019 | 7/15/2019 |  | 1278 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 05:29 | Singh, Sunil Kumar | 56-F-EU-V-190715-S3LO096 | Report | Yes | Y |  |  | On Hold N/A for EMEA | KTW3 |  |  | 56-F-EU-V-190715-S3LOV096A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0413 | No | UBE | BXU516652 (109164) | BXU546030 (109164) | 6 |  |  | Purge F2F Shipping workbench Data | PPD Passed |  |  | TRUE | L |  | Purge | ARO | Cosmin Mutiu / Terry Greenard | L2 Not required | No KT, as Tested by user only in ICT |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 9/16/2019 | 9/13/2019 |  | 1279 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-14 08:14 | ANAND, S | 56-F-EU-V-190829-S6AR002 |  | Yes | Yes |  |  | Works in PPD, no records in F5900300 | KTW2 |  |  | 56-F-EU-V-190829-S6ARV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0432 | No | UBE |  |  | 3 |  |  | Integrity Rep for Lot Proc Type btw PTC and Glb Itm Ms | L3 Pass |  |  | TRUE | L |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/3/2019 | 7/3/2019 |  | 1280 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-15 04:20 | Barrera Perez, Carlos Manuel | 56-F-EU-V-190702-S3MD020 |  | Yes | Y | [6 empty] | 56-F-EU-V-190702-S3MDV20A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0434 | No | UBE |  |  | 6 |  |  | Integrity Report for Sterilization | L3 Pass |  |  | TRUE | L |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 9/13/2019 | 9/12/2019 |  | 1281 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-13 04:04 | Icardo, Ana | 56-F-EU-V-190830-S6MD005 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190830-S6MDV005A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0441 | No | UBE |  |  | 999 |  |  | Integrity Record Count Report | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1282 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Report | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R41083 | Yes | UBE |  |  | 1 |  |  | Update Effective Lots - Lot Status Synchronization | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Miruna Danes | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/27/2019 | 5/27/2019 |  | 1283 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:54 | Chiau, Liesbet | 56-F-EU-V-190521-S1LO081 |  | Yes | Y |  |  |  | KTQ2 |  |  | 56-F-EU-V-190521-S1LOV81A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R47031 | No | UBE |  |  | 4 |  |  | EDI Shipping Notice Edit/Create | L3 Pass | 267 | WIP | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/6/2019 | 8/5/2019 |  | 1284 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-26 03:41 | Mughal, Abdul | 56-F-EU-V-190725-S4LO064 |  | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190725-S4LOV064A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74LI5 | No | UBE |  |  | 2 |  |  |  | L3 Not Required |  |  | TRUE |  |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/24/2019 | 6/26/2019 |  | 1285 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-11 00:06 | Verma, Vikas | 56-F-EU-V-190531-S1OL001 |  | Yes | Y | [6 empty] | 56-F-EU-V-190531-S1OLV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74ZD013 | No | UBE |  |  | 999 |  |  | Stock Documents Print | Obsolete |  |  | FALSE | L |  | Quality | Logistics |  | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/2/2019 | 6/24/2019 |  | 1286 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet | 56-F-EU-V-190624-S2LO130 | Printer | Yes |  |  |  | Clone created for this Std object as R5674ZD13 | KTQ3 |  |  | 56-F-EU-V-190624-S2LOV130A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642037 | Yes | APPL | BXU545779 (104749) |  | 3 |  |  | APL Shipment Feedback Recovery | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/16/2019 | 7/16/2019 |  | 1287 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 04:11 | Singh, Sunil Kumar | 56-F-EU-V-190702-S3LO027 |  | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190702-S3LOV027A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5643070 | Yes | APPL | BXU532396 (148542) | BXU532399 (148542) | 2 |  |  | Line Level Held Order Release | L3 Pass |  |  | TRUE | H |  | Quality | Logistics | Pawel Oskroba | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/12/2019 | 6/12/2019 |  | 1288 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 08:08 | ANAND, S | 56-F-EU-V-190610-S2LO032 |  | Yes | Y |  |  |  | KTQ4 |  |  | 56-F-EU-V-190610-S2LOV32A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5800002 | Yes | APPL |  |  | 5 |  |  | Lot Create/Update Error Log Application | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Pawel Oskroba | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/20/2019 | 8/19/2019 |  | 1289 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-26 11:07 | Oskroba, Pawel | 56-F-EU-V-190819-S5LO063 | Error | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190819-S5LOV063A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560010H | Yes | UBE | BXU546243 (145382) |  | 2 |  |  | JDE GME Receiving Label Print | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/12/2019 | 6/12/2019 |  | 1290 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 08:48 | Singh, Sunil Kumar | 56-F-EU-V-190610-S2LO010 | Printer | Yes | Yes |  |  |  | KTW5 |  |  | 56-F-EU-V-190610-S2LOV010A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560018IA | No | UBE |  |  | 3 |  |  | Statutory Intrastat Reporting Austria | L3 Pass |  |  | TRUE | LNE2E |  | warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/16/2019 | 7/15/2019 |  | 1291 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-26 04:34 | Mughal, Abdul | 56-F-EU-V-190708-S3LO078 | Report | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190708-S3LOV78A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560018SE | No | UBE |  | BXU545702 | 3 |  |  | Statutory Intrastat Reporting Swede | L3 Pass |  |  | TRUE | LNE2E |  | warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 07/16/2019 | 07/15/2019 |  | 1292 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 04:40 | Joshi, Abhishek N | 56-F-EU-V-190709-S3LO048 | Report | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190709-S3LOV048A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564121ZA | Yes | UBE | BXU545779 (104749) | BXU546016 (104749) | 3 |  |  | APL Stock Reconciliation | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/17/2019 | 7/16/2019 |  | 1293 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 04:12 | Singh, Sunil Kumar | 56-F-EU-V-190715-S3LO150 |  | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190715-S3LOV150A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564211SE | No | UBE | BXU532056 (139511) | BXU532059 (139511) | 3 |  |  | Export Compliance and Sales Authorization Send Email | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Leonard Dartois | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/17/2019 | 7/16/2019 |  | 1294 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 07:14 | ANAND, S | 56-F-EU-V-190628-S3LO006 | Export | Yes | Y |  |  |  | KTW6 |  |  | 56-F-EU-V-190628-S3LOV06A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642625 | No | UBE |  |  | 5 |  |  | Close Shipped Order Lines | L3 Pass |  |  | TRUE | LE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/20/2019 | 8/20/2019 |  | 1295 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-28 11:08 | Mughal, Abdul | 56-F-EU-V-190820-S5LO075 |  | Yes | Y |  |  | Review E2E process exists | KTW3 |  |  | 56-F-EU-V-190820-S5LOV075A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647342 | Yes | UBE | BXU545779 (104749) | 1267338 (104749) | 6 |  |  | EMEA OWC Conversion for Gemini | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 9/4/2019 | 9/3/2019 |  | 1296 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-14 07:44 | ANAND, S | 56-F-EU-V-190827-S6LO018 |  | Yes | Yes |  |  |  | KTW3 |  |  | 56-F-EU-V-190827-S6LOV018A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564736E | Yes | UBE |  |  | 999 |  |  | FM Logistics Report For Carrier | Obsolete |  |  |  | NA |  | Transportation | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1297 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Report | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649008 | No | UBE | BXU545779 (104749) |  | 1 |  |  | APL Shipment Feedback | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | VV-09/07 - Code reviewed by Vikas after the DC Link Object retrofitted | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/28/2019 | 5/28/2019 |  | 1298 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 04:17 | Singh, Sunil Kumar | 56-F-EU-V-190514-S1LO004 |  | Yes | Y |  |  | UBE depend on N5649009 which is on Hold status with comment "Dependent object BD3n4201(DSI) not found in DV920" | KTW3 |  |  | 56-F-EU-V-190514-S1LOV04A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56X4701B | Yes | UBE | BXU545779 (104749) | BXU548906 (104749) | 4 |  |  | Populate Inbound APS for Ownership Change | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/6/2019 | 8/5/2019 |  | 1299 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 08:00 | ANAND, S | 56-F-EU-V-190802-S4LO111 | Inbound | Yes |  |  |  |  | KTW2 |  |  | 56-F-EU-V-190802-S4LOV111A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5841123 | Yes | UBE |  |  | 4 | 4 |  | BRS to JDE For Released Lots | L3 Pass |  |  | TRUE | H |  | Quality | Logistics |  | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/17/2019 | 7/17/2019 |  | 1300 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-23 09:03 | Oskroba, Pawel | 56-F-EU-V-190704-S3LO001 |  | Yes | Y |  |  |  | KTQ4 |  |  | 56-F-EU-V-190704-S3LOV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58R0062 | No | UBE | BXU549859 |  | 6 |  |  | Purge BRS to JDE Interface - Batch Create and Status update | PPD Passed |  |  | TRUE | L |  | Purge | ARO | Cosmin Mutiu / Terry Greenard | L2 Not required | No KT, as Tested by user only in ICT |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/27/2019 | 8/27/2019 |  | 1301 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:43 | Joshi, Abhishek N | 56-F-EU-V-190819-S5AR002 | Interface | Yes | Y |  |  | Works in PPD, records processed - Report Saved |  |  |  | 56-F-EU-V-190819-S5ARV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58R0063 | No | UBE | BXU549859 |  | 6 |  |  | Purge Lot Create/Update Error Log Table | PPD Passed |  |  | TRUE | L |  | Purge | ARO | Cosmin Mutiu / Terry Greenard | L2 Not required | No KT, as Tested by user only in ICT |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/16/2019 | 7/15/2019 |  | 1302 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:42 | Joshi, Abhishek N | 56-F-EU-V-190716-S3AR001 | Error | Yes | Y |  |  | Works in PPD, no records to purge - Report Saved |  |  |  | 56-F-EU-V-190716-S3ARV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0059 | No | UBE |  |  | 3 |  |  | Export Direct Ship PO Outbound Post Processor | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/17/2019 | 7/16/2019 |  | 1303 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-19 05:55 | Mughal, Abdul | 56-F-EU-V-190712-S3LO089 | Export / Outbound | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190712-S3LOV089A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0135 | No | UBE |  |  | 5 |  |  | Acknowledgement Data Turnaround | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/21/2019 | 8/20/2019 |  | 1304 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-27 06:22 | Mughal, Abdul | 56-F-EU-V-190813-S5LO033 |  | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190813-S5LOV033A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R47071 | No | UBE |  |  | 5 |  |  | EDI Receiving Advice Edit/Create - Purchasing | L3 Pass |  |  | TRUE | HE2E |  | Procurement | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/23/2019 | 8/20/2019 |  | 1305 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-27 07:59 | Mughal, Abdul | 56-F-EU-V-190814-S5LO049 |  | Yes | Y |  |  |  | KTW2 |  |  | 56-F-EU-V-190814-S5LOV049A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R42520 | Yes | UBE |  |  | 1 |  |  | Print Pick Slips | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/23/2019 | 5/22/2019 |  | 1306 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:54 | Chiau, Liesbet |  | Printer | Yes | Y |  |  | No Retrofit Required | KTW5 |  |  | 56-F-EU-V-190517--BV0004A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0431 | no | UBE |  |  | 999 |  |  | FCA-XML Inbound Upload Report | Obsolete |  |  | FALSE | L |  | Transportation | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma | VV-06/09 - Obsoleted the object as there is no version in EUPD812 |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 09/17/2019 | 09/16/2019 |  | 1307 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-06 09:29 | Verma, Vikas | 56-F-EU-V-190906-S6LO049 | Upload / XML |  |  |  |  | On Hold N/A for EMEA | na |  |  | NA | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564302I | No | UBE | 1248867 (16629) | 1248868 (16629) | 1 |  |  | Import and Load Supplier Cross Ref NEW MODEL | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/28/2019 | 5/28/2019 |  | 1308 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 09:29 | ANAND, S | 56-F-EU-V-190527-S1LO113 | Cross Refer | Yes | Yes |  |  |  | KTW2 |  |  | 56-F-EU-V-190527-S1LO113A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0003 | No | UBE |  |  | 1 |  |  | Order Compliance Checking | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/28/2019 | 5/28/2019 |  | 1309 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:54 | Chiau, Liesbet | 56-F-EU-V-190520-S1LO069 |  | Yes | Y |  |  | data structure "DD3N4206" for BSFN "BD3N4206" is missinng in DV920 | KTW2 |  |  | 56-F-EU-V-190520-S1LOV69A, 56-F-EU-V-190520-S1LOV69B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P41024 | Yes | APPL | 1264895 | BXU548196 | 1 |  |  | Location Revisions | L3 Pass |  |  | TRUE | H |  | Quality | Logistics | Pawel Oskroba | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/22/2019 | 5/22/2019 |  | 1310 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-27 02:08 | Singh, Sunil Kumar | 56-F-EU-V-190514-S1LO002 | Revision | Yes | Yes |  |  | Retrofit completed | KTW5 |  |  | 56-F-EU-V-190514-S1LOV02A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4112 | Yes | APPL |  |  | 1 |  |  | Inventory Issues | L3 Pass |  |  | TRUE | H |  | Warehouse | Logistics | Grant Butler | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1311 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:54 | Chiau, Liesbet | 56-F-EU-V-190510-S1LO001 |  | Yes | Yes |  |  |  | KTW1 |  |  | 56-F-EU-V-190510-S1LOV01A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4113 | Yes | APPL |  |  | 1 |  |  | Inventory Transfers | L3 Pass |  |  | TRUE | H |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/22/2019 | 5/22/2019 |  | 1312 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:54 | Chiau, Liesbet | 56-F-EU-V-190514-S1LO009 |  |  | Y |  |  | Retrofit Completed. | KTW1 |  |  | 56-F-EU-V-190514-S1LOV09A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4114 | Yes | APPL |  |  | 1 |  |  | Inventory Adjustments | L3 Pass |  |  | TRUE | H |  | Warehouse | Logistics | Grant Butler | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/20/2019 | 5/20/2019 |  | 1313 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:54 | Chiau, Liesbet | 56-F-EU-V-190514-S1WD001 |  | Yes | Yes |  |  | Retrofit completed | KTW1 |  |  | 56-F-EU-V-190514-S1WDV01A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4116 | Yes | APPL |  |  | 1 |  |  | Item Reclassifications | L3 Pass |  |  | TRUE | H |  | Warehouse | Logistics | Grant Butler | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/22/2019 | 5/22/2019 |  | 1314 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:54 | Chiau, Liesbet | 56-F-EU-V-190517-S1LO058 |  | Yes | Yes |  |  |  | KTW1 |  |  | 56-F-EU-V-190517-S1LOV58A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P41202 | No | APPL |  |  | 1 |  |  | Item Availability | L3 Pass |  |  | TRUE | H |  | Warehouse | Logistics | Leonard Dartois | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/22/2019 | 5/20/2019 |  | 1315 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:54 | Chiau, Liesbet | 56-F-EU-V-190514-S1LO008 |  | Yes | Yes |  |  | 02/07 RK: L2 Pass , Retrofitted, Rework Required | KTW1 |  |  | 56-F-EU-V-190514-S1LOV08A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P554013T | Yes | APPL |  |  | 999 |  |  | QTS Supplier Item Restrictions - Maintenance | Obsolete |  |  | TRUE |  |  | Quality | Logistics | Miruna Danes, Douglas Roussel, Pawel Oskroba | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1316 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet | 56-F-EU-V-190610-S2LO002 | Maintenance | Yes | Yes |  |  |  | Obsolete |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P58ITM8B | Yes | APPL | 1258827, 1241561&nbsp;&nbsp; 1268724, 1268724 (21099) | 1258829 21099 1269069 | 2 |  |  | Item Search Returns Quantity E812 adapted | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/28/2019 | 5/28/2019 |  | 1317 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-12 02:59 | Singh, Sunil Kumar | 56-F-EU-V-190612-S2LO033 |  | Yes | Yes |  |  |  | KTW4 |  |  | 56-F-EU-V-190612-S2LOV33A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5801402 | No | UBE | BXU545092 |  | 1 |  |  | Mailing Labels by Address Number | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/24/2019 | 5/24/2019 |  | 1318 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 05:29 | Joshi, Abhishek N | 56-F-EU-V-190521-S1OM036 |  | Yes | Y | [6 empty] | 56-F-EU-V-190521-S1OM036A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5620652 | No | APPL |  |  | 3 |  |  | HS Code Maintenance | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/17/2019 | 7/15/2019 |  | 1319 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-17 07:11 | De Brouwer, Peter | 56-F-EU-V-190708-S3LO077 | Maintenance | Yes | Y |  |  |  | KTW4 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P58ITM8 | Yes | APPL | 12905 BXU549830 |  | 3 |  |  | Item Search Returns Quantity | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Leonard Dartois | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/18/2019 | 7/17/2019 |  | 1320 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 04:27 | Vishnubhatla, Mithra | 56-F-EU-V-190703-S3LO033 |  | Yes | Y |  |  |  | KTW4 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P58ITM8A | No | APPL | BXU549830 |  | 3 |  |  | Item Search Two Workfile Maintenance | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/18/2019 | 7/17/2019 |  | 1321 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 04:35 | Joshi, Abhishek N | 56-F-EU-V-190715-S3LO093 | Maintenance | Yes |  |  |  |  | KTW4 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P58ITM9 | No | APPL | BXU549830 |  | 3 |  |  | Item Search | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/18/2019 | 7/17/2019 |  | 1322 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 04:37 | Joshi, Abhishek N | 56-F-EU-V-190715-S3LO090 |  | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190715-S3LOV090A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564210C | Yes | APPL | 1253922 (104749) | 1254243 (24450) | 1 |  |  | Replenishment Item Level Setup | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/27/2019 | 5/27/2019 |  | 1323 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 07:22 | ANAND, S | 56-F-EU-V-190513-S1LO020 | Setup | Yes | Yes |  |  | done. Index verified. DS generated. L1 done. No Proc Option. | KTW1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5640ITM | No | APPL |  |  | 1 |  |  | Item Search Returns Quantity | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/20/2019 | 5/20/2019 |  | 1324 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:54 | Chiau, Liesbet | 56-F-EU-V-190515-S1LO033 |  | Yes | Yes |  |  | Restored par from PD812. Dependent on P4210 | KTW1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56HWT20 | No | UBE |  |  | 4 |  |  | Determine Source System for Equipment Orders | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 08/06/2019 | 08/05/2019 |  | 1325 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-15 03:03 | BILENSOY, NURI | 56-F-EU-V-190802-S4LO154 |  | Yes |  |  |  |  | KTTS5 |  |  | 56-F-EU-V-190802-S4LOV154A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P41016 | Yes | APPL | 1219895 | 11541, 1233005 | 1 |  |  | Item Description Translation | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/21/2019 | 5/21/2019 |  | 1326 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 10:31 | Joshi, Abhishek N | 56-F-EU-V-190513-S1MD007 |  | Yes | Yes |  |  | MDM-SupplyChain |  |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4104 | No | APPL |  | 1233005 | 1 |  |  | Item Cross Reference | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 05/23/2019 | 05/22/2019 |  | 1327 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 10:32 | Joshi, Abhishek N | 56-F-EU-V-190520-S1MD044 | Cross Refer | Yes | Yes |  |  | MDM-SupplyChain |  |  |  | 56-F-EU-V-190520-S1MDV44A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564188S | No | APPL | 1263246 | 1274708 | 1 |  |  | Item Branch Enrichment External Data File Search | L3 Not Required |  |  | FALSE | H |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1328 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 09:03 | Vishnubhatla, Mithra |  | SECURE | [12 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564189 | Yes | APPL | 1274706 1263246 | BXU547536, 1274708 | 1 |  |  | Item Branch Group Data Enrichment Matrix | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 completed |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/20/2019 | 5/20/2019 |  | 1329 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 09:03 | Vishnubhatla, Mithra | 56-F-EU-V-190516-S1MD027 |  | Yes | Yes |  |  | Retrofit Not Required | DEFECT ID: 73 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564190 | No | APPL | 1263246 | 1274708 | 1 |  |  | Item Branch Creation Group Maintenance | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/20/2019 | 5/20/2019 |  | 1330 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 09:04 | Vishnubhatla, Mithra | 56-F-EU-V-190516-S1MD029 | Maintenance | Yes | Yes |  |  | Retrofit Not Required | DEFECT ID: 60 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564191 | No | APPL | 1263246 | 1274708 | 1 |  |  | Item Branch Creation Group Detail Maintenance - Pyramid | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 05/20/2019 | 05/20/2019 |  | 1331 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 09:04 | Vishnubhatla, Mithra | 56-F-EU-V-190517-S1MD040 | Maintenance | Yes | Y |  |  | Retrofitted | DEFECT ID: 61 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564197 | Yes | APPL | 1274706 1263246 | BXU547537, 1274708 | 1 |  |  | Item Branch Enrichment Branch Plant Groups | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/20/2019 | 5/20/2019 |  | 1332 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 09:04 | Vishnubhatla, Mithra | 56-F-EU-V-190517-S1MD036 |  | Yes | Yes |  |  |  | DEFECT ID: 62 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564199 | Yes | APPL | 1274706 1233246 | BXU547538, 1274708 | 1 |  |  | Item Branch Enrichment Assignment Rule Definition | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 20/05/2019 | 20/05/2019 |  | 1333 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 09:05 | Vishnubhatla, Mithra | 56-F-EU-V-190514-S1MD006 |  | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564199S | No | APPL | 1263246 | 1274708 | 1 |  |  | Item Branch Enrichment Rule Search | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 20/05/2019 | 20/05/2019 |  | 1334 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 09:05 | Vishnubhatla, Mithra | 56-F-EU-V-190514-S1MD001 |  | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P55XREF | No | APPL |  |  | 4 |  |  | Maintain XPI Cross-Reference Tables | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/29/2019 | 7/26/2019 |  | 1335 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-07 10:40 | Icardo, Ana | 56-F-EU-V-190730-S4MD007 | Cross Ref / Maintenance | Yes | Y |  |  | The Depricated Feature Warning: pops when trying open the application design in DV920 and PD812. However the application validation is successful. |  |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5600150 | Yes | APPL | 1263246 5409 | 26229, BXU545915 | 1 |  |  | EMEA - MDM Replication Status Application | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 20/05/2019 | 20/05/2019 |  | 1336 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 08:57 | Vishnubhatla, Mithra | 56-F-EU-V-190514-S1MD011 |  | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564101 | Yes | APPL | 1263246 | 1271288, 1263247 | 1 |  |  | Item Master XE EMEA Version | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 20/05/2019 | 20/05/2019 |  | 1337 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 03:20 | Joshi, Abhishek N | 56-F-EU-V-190515-S1MD023 |  | Yes | Yes |  |  |  | DEFECT ID: 96 |  |  | 56-F-EU-V-190515-S1MDV23A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P569869H | Yes | APPL | 5409 1263246 | BXU545915 | 1 |  | S1 | MDM Replication - Approve Held Items | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 20-05-2019 | 20-05-2019 |  | 1338 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 08:58 | Vishnubhatla, Mithra | 56-F-EU-V-190515-S1MD021 |  | Yes | Yes | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P03013 | Yes | APPL | 1255078 (24459), BXU544578 (21524) | 1255083 (24459), BXU545131 | 1 |  |  | Customer Master | L3 Pass | 144 | Closed | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/23/2019 | 5/20/2019 |  | 1339 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-12 13:51 | Singh, Sunil Kumar | 56-F-EU-V-190517-S1MD037 |  | Yes | Y |  |  | MDM-SupplyChain | DEFECT ID: 114 |  |  | 56-F-EU-V-190517-S1MDV037A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P41026 | Yes | APPL | BXU544673 | BXU547540, 1241362 (16342) | 1 |  |  | Item Branch | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1340 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-29 23:58 | Singh, Sunil Kumar |  |  |  | Y |  |  | MDM-SupplyChain | DEFECT ID: 115 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600147 | Yes | UBE | 1263246 | BXU545915 | 3 |  |  | Baxter EMEA - MDM - Detailed Error Message Report | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 07/04/2019 | 07/03/2019 |  | 1341 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 08:58 | Vishnubhatla, Mithra | 56-F-EU-V-190701-S3MD012 | Error / Report | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3MDV012A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600154 | Yes | UBE | 1263246 | BXU545915 | 4 |  |  | EMEA - Holding Table for MDM Replication Purge Program | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/29/2019 | 7/26/2019 |  | 1342 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 08:59 | Vishnubhatla, Mithra | 56-F-EU-V-190725-S4MD002 |  | Yes | Y | [6 empty] | 56-F-EU-V-190725-S4MDV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600155 | Yes | UBE | 1263246 | BXU545915 | 4 |  |  | EMEA - MDM Replication Status/Error Purge Program | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | TANKUT , CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/29/2019 | 7/26/2019 |  | 1343 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 08:59 | Vishnubhatla, Mithra | 56-F-EU-V-190729-S4MD005 | Error | Yes | Y | [6 empty] | 56-F-EU-V-190729-S4MDV005A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600195 | Yes | UBE | 1263246 | 1263247 | 3 |  |  | Copy Item UOM F41002 from one BP to another BP V2 | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/4/2019 | 7/3/2019 |  | 1344 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 08:59 | Vishnubhatla, Mithra | 56-F-EU-V-190628-S3LO002 |  | Yes | Y | [6 empty] | 56-F-EU-V-190628-S3LOV02A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600196 | No | UBE | 1263246 | 1263247 | 3 |  |  | Copy UOM Defn F46011 from one Branch Plant to another V2 | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/4/2019 | 7/2/2019 |  | 1345 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 09:00 | Vishnubhatla, Mithra | 56-F-EU-V-190701-S3MD011 |  | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3MDV011A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600198 | No | UBE | 1263246 | 1263247 | 4 |  |  | Capture Item UOM F41002 deletions for update from GEMETRIC | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/30/2019 | 7/29/2019 |  | 1346 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 09:00 | Vishnubhatla, Mithra | 56-F-EU-V-190729-S4MD003 |  | Yes | Y | [6 empty] | 56-F-EU-V-190729-S4MDV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600199 | No | UBE | 1263246 | 1263247 | 4 |  |  | Capture Item UOM F46011 deletions for update from GEMETRIC | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/30/2019 | 7/29/2019 |  | 1347 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 09:00 | Vishnubhatla, Mithra | 56-F-EU-V-190731-S4MD009 |  | Yes | Y | [6 empty] | 56-F-EU-V-190731-S4MDV009A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5600157 | Yes | APPL | 1263246 |  | 1 |  |  | Maintain MDM Replication Filtering Table | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 19\05\20 | 19\05\20 |  | 1348 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 09:01 | Vishnubhatla, Mithra | 56-F-EU-V-190515-S1MD025 | Maintenance | Yes | Yes |  |  | No retrofit required |  |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P59059 | Yes | APPL |  |  | 2 |  |  | Test BSFN N5900110 Item validation Full prm | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 19\06\12 | 19\06\12 |  | 1349 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:06 | Chiau, Liesbet | 56-F-EU-V-190612-S2MD023 |  | Yes | Yes |  |  | No retrit required |  |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P55TC01 | No | APPL |  | BXU545672 | 4 |  |  | Migration Errors Inquiry | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/30/2019 | 7/29/2019 |  | 1350 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 10:43 | Joshi, Abhishek N | 56-F-EU-V-190725-S4MD001 | Error/Inquiry | Yes | [7 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P0150 | No | APPL |  |  | 1 |  |  | A/B - Org Structure Browse | L3 Pass |  |  | TRUE | L |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/22/2019 | 5/22/2019 |  | 1351 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:54 | Chiau, Liesbet | 56-F-EU-V-190514-S1MD010 |  | Yes | Y |  |  | Retrofit completed |  |  |  | 56-F-EU-V-190514-S1MDV10A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P55TC04 | No | APPL |  | BXU545672 | 4 |  |  | Part Integration Errors Inquiry | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/31/2019 | 7/30/2019 |  | 1352 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 10:43 | Joshi, Abhishek N | 56-F-EU-V-190730-S4MD008 | Error/Inquiry | Yes | Y | [6 empty] | 56-F-EU-V-190730-S4MDV008A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P594101Y | No | APPL |  | BXU545672 | 1 |  |  | EIM Y-Tables Inquiry | L3 Pass |  |  | TRUE | L |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/20/2019 | 5/20/2019 |  | 1353 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 10:44 | Joshi, Abhishek N | 56-F-EU-V-190516-S1MD033 | Inquiry | Yes | Y |  |  | Retrofit Not Required |  |  |  | 56-F-EU-V-190516-S1MDV33A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5603012C | No | UBE |  | 1248414 | 2 |  |  | Load F03012Z1from CSV - Front End | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/26/2019 | 6/25/2019 |  | 1354 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 04:11 | Joshi, Abhishek N | 56-F-EU-V-190611-S2MD024 |  | Yes | [7 empty] | 56-F-EU-V-190611-S2MDV024A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P560301W | No | APPL | BXU544578 (21524) | BXU545131 | 5 | 5 |  | Customer Master Workflow | L3 Pass | 144 | Closed | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/26/2019 | 6/26/2019 |  | 1355 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-12 13:50 | Singh, Sunil Kumar | 56-F-EU-V-190626-S2MD001 |  | Yes | Y |  |  |  | 'According to L3 Scrum call of July 8th with Vikas and Fatiha, we have decided to pass this script and test P560301W individually in Sprint 5 |  |  | 56-F-EU-V-190626-S2MDV01A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5601050 | Yes | UBE | BXU544579 (15217) | BXU545132 | 2 |  |  | Baxter Copy A/B Category Code to Customer Master | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/25/2019 | 6/26/2019 |  | 1356 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 09:57 | ANAND, S | 56- F-EU-V-190620-S2MD044 |  | Yes | Yes | [6 empty] | 56- F-EU-V-190620-S2MDV44A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5641001 | Yes | APPL | 1222675 | 1223173 | 4 |  |  | Class Temperature Retrieval Maintenance Program | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/7/2019 | 8/7/2019 |  | 1357 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-28 21:21 | Singh, Sunil Kumar | 56-F-EU-V-190807-S4LO001 | Maintenance | Yes | Y |  |  |  | KTT1 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560401ZF | No | UBE | BXU544580 (16037) | BXU545676 | 2 |  |  | Load F0401Z1Supplier Master Z-File from CSV - Front End | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/26/2019 | 6/26/2019 |  | 1358 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 09:48 | ANAND, S | 56-F-EU-V-190618-S2MD039 |  | Yes | Y | [6 empty] | 56-F-EU-V-190618-S2MDV39A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5614779 | No | UBE | BXU546670 |  | 6 |  |  | Item Branch Plant Validation Report | PPD Passed |  |  | TRUE | L | FALSE | ECC | ARO | Krista Vensever | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/16/2019 | 7/16/2019 |  | 1359 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:55 | Joshi, Abhishek N | 56-F-EU-V-190715-S3ARV003A | Report | Yes | Y |  |  | To be tested in CRP |  |  |  | 56-F-EU-V-190715-S3ARV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564102P | Yes | APPL | 1255769 | 1255770 | 1 |  |  | Item Branch Copy Application | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/20/2019 | 5/20/2019 |  | 1360 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-23 12:43 | Singh, Sunil Kumar | 56-F-EU-V-190514-S1MD019 |  | Yes | Y | [6 empty] | 56-F-EU-V-190514-S1MDV19A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564190S | No | APPL |  | 1274708 | 1 |  |  | Item Branch Creation Group Search | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/20/2019 | 5/20/2019 |  | 1361 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-14 05:14 | Singh, Sunil Kumar | 56-F-EU-V-190517-S1MD042 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564193 | No | APPL |  | 1274708 | 1 |  |  | Item Branch Creation Pyramid Enquiry | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/20/2019 | 5/20/2019 |  | 1362 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-14 05:14 | Singh, Sunil Kumar | 56-F-EU-V-190513-S1MD006 | Inquiry | Yes | Yes |  |  | done. Index verified. DS generated. No PO exists. L1 done. |  |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560101R | No | UBE | 1240624, BXU544564 | 17772, 1240625 | 2 |  |  | Related Address Book Numbers update | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/25/2019 | 6/24/2019 |  | 1363 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 07:06 | Joshi, Abhishek N | 56-F-EU-V-190618-S2MD040 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190618-S2MDV40A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560150I | No | UBE | BXU544564 |  | 2 |  |  | Upload csv file into Parent-Child Z-File | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/25/2019 | 6/25/2019 |  | 1364 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 07:06 | Joshi, Abhishek N | 56- F-EU-V-190620-S2MD046 | Upload | Yes | Yes | [6 empty] | 56- F-EU-V-190620-S2MDV046A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56AU200 | Yes | APPL | 1235591 1263246 | 15388, 1235592 | 3 |  |  | Audit Inquiry Item BP | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/4/2019 | 7/3/2019 |  | 1365 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 09:01 | Vishnubhatla, Mithra | 56-F-EU-V-190701-S3MD001 | Inquiry / Audit | Yes | Yes |  |  | Object depends on ‘N56AU200’ BSNF which is ‘On Hold’ due to build error in DV920. A41021 Table not found in DV920. |  |  |  | 56-F-EU-V-190701-S3MDV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56AU400 | Yes | APPL | 1263246 | 1235592 | 3 |  |  | Audit Enquiry - Address Book | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/5/2019 | 7/4/2019 |  | 1366 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 09:01 | Vishnubhatla, Mithra | 56- F-EU-V-190701-S3MD009 | Inquiry / Audit | Yes | Y | [6 empty] | 56- F-EU-V-190701-S3MDV009A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P560101Z | Yes | APPL | 1242968 (19282) | 19282, 1243037 | 2 |  |  | Batch Address Book For conversions | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/25/2019 | 6/24/2019 |  | 1367 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-18 07:16 | ANAND, S | 56-F-EU-V-210619-S2MD049 |  | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P560401Z | No | APPL | 1242968 (19282) | 1243037 | 2 |  |  | Batch Suppliers for conversions | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1368 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-18 07:16 | ANAND, S | 56-F-EU-V-190612-S2MD029 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56TC01 | No | APPL | 1242968 (19282) | 1243037 | 2 |  |  | Interco Z-Files Inquiry | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/24/2019 | 6/24/2019 |  | 1369 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-18 07:17 | ANAND, S | 56- F-EU-V-190620-S2MD045 | Inquiry | Yes | Y | [6 empty] | 56- F-EU-V-190620-S2MDV045A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P58AU100 | Yes | APPL | 1263246 | 1235592 | 3 |  |  | Audit Inquiry EIM | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/5/2019 | 7/4/2019 |  | 1370 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 09:02 | Vishnubhatla, Mithra | 56-F-EU-V-190702-S3MD017 | Inquiry / Audit | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900026 | Yes | APPL | BXU514993 | BXU545548 | 1 |  |  | Item Master Tag File Maintenance | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/20/2019 | 5/20/2019 |  | 1371 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-23 12:58 | Singh, Sunil Kumar | 56-F-EU-V-190514-S1MD014 | Maintenance | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5603010Z | no | UBE | 1242968 (19282) | 1243037 | 2 |  |  | Baxter - Customer Master Batch Upload | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/24/2019 | 6/24/2019 |  | 1372 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-18 07:17 | ANAND, S | 56-F-EU-V-210619-S2MD048 | Upload | Yes | [7 empty] | 56-F-EU-V-210619-S2MDV048A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600042 | No | UBE | BXU544581 37807 | BXU545135 | 4 |  |  | EIM Regenerate X-levels/MCU/BU from SRP6 | L3 Pass |  |  | TRUE | L |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/31/2019 | 7/30/2019 |  | 1373 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 07:25 | ANAND, S | 56-F-EU-V-190729-S4MD004 |  | Yes | Y | [6 empty] | 56-F-EU-V-190729-S4MDV004A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641002C | No | UBE |  | 1258338, 1258434 | 3 |  |  | Load UoM conversions into F41002 from .csv file | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/5/2019 | 7/4/2019 |  | 1374 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 05:59 | Joshi, Abhishek N | 56-F-EU-V-190702-S3MD016 |  | Yes | Y | [6 empty] | 56-F-EU-V-190702-S3MDV16A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5600013 | No | APPL | 1247918 | 1247919 | 6 |  |  | EDI Customer Inquiry | L3 Pass |  |  | TRUE | MNE2E |  | EDI Order Management | eCommerce | Aidan Scally | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1375 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-29 02:59 | Vishnubhatla, Mithra | 56-F-EU-V-190610-S2ED001 | Inquiry | Yes | Yes |  |  |  | KTEDI7 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5600121 | No | APPL |  | 1253946 | 2 |  |  | Customer XREF | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1376 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 06:26 | Joshi, Abhishek N | 56-F-EU-V-190611-S2MD020 |  | Yes | Y |  |  |  | DEFECT ID: 125 |  |  | 56-F-EU-V-190611-S2MDV020A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P560150 | No | APPL |  |  | 999 |  |  | A/B - Parent Org Structure Browse | Obsolete |  |  |  | H |  | MDM | MDM | Tom Hoste | (Blank) |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1377 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5603014 | No | APPL |  | 1253946 | 2 |  |  | Basis/Bill To Maintenance | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/24/2019 | 6/23/2019 |  | 1378 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 06:26 | Joshi, Abhishek N | 56-F-EU-V-190620-S2MD047 | Maintenance | Yes | [7 empty] | 56-F-EU-V-190620-S2MDV047A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5603012 | Yes | APPL |  | 1253946 | 2 |  |  | Patient/Ship To Maintenance | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1379 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 06:27 | Joshi, Abhishek N | 56-F-EU-V-190611-S2MD017 | Maintenance | Yes | Y | [6 empty] | 56-F-EU-V-190611-S2MDV17A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56PDO | No | APPL |  | BXU545917 | 2 |  |  | Product Design Owner Maintenance (PDO) | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/12/2019 | 6/12/2019 |  | 1380 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 06:44 | Joshi, Abhishek N | 56-F-EU-V-190612-S2MD002 | Maintenance | Yes | Yes | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5659002 | No | UBE | BXU544617 |  | 1 |  |  | Mass Updte F59002 status | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/21/2019 | 5/21/2019 |  | 1381 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 06:25 | Joshi, Abhishek N | 56-F-EU-V-190514-S1MD018 |  | Yes | Yes |  |  | done. Index verified. L1 done. |  |  |  | 56-F-EU-V-190515-S1MDV018A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56010Z | No | APPL |  |  | 999 |  |  | Revise Pre – Address Book Records | Obsolete | [5 empty] | Technical Services | Logistics | Mandy Corbett, Swetha M S, Thierry Kestens |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1382 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P560101B | No | APPL | BXU545397 | BXU547458 | 2 |  |  | EMEA Enhanced Address Book Search | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/27/2019 | 6/25/2019 |  | 1383 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 04:26 | Joshi, Abhishek N | 56- F-EU-V-190618-S2OM039 |  | Yes | Yes | [6 empty] | 56- F-EU-V-190618-S2OMV39A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5600176 | No | APPL | BXU544618 |  | 4 |  |  | MDM Conversion Reference Enquiry | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/31/2019 | 7/30/2019 |  | 1384 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 06:26 | Joshi, Abhishek N | 56-F-EU-V-190731-S4MD010 | Inquiry | Yes | Y | [6 empty] | 56-F-EU-V-190731-S4MDV010A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560401Z1 | No | UBE | 1229478 | 1233852 | 2 |  |  | Supplier Master Category Code General Update | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/21/2018 | 6/21/2018 |  | 1385 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 06:53 | Joshi, Abhishek N | 56-F-EU-V-190612-S2MD028 |  | Yes | [7 empty] | 56-F-EU-V-190612-S2MDV028A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600176 | No | UBE | BXU544618 |  | 1 |  |  | MDM Conversion Reference Upload | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/21/2019 | 5/21/2019 |  | 1386 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 06:26 | Joshi, Abhishek N | 56-F-EU-V-190514-S1MD015 | Upload | Yes | Yes |  |  | Related PO T5600176 |  |  |  | 56-F-EU-V-190514-S1MDV015A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5530Z1A | No | APPL | BXU544620 |  | 2 |  |  | Review Bank Transit Number Batch File | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1387 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 06:28 | Joshi, Abhishek N | 56-F-EU-V-190612-S2MD004 |  | Yes | [7 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R563012Z2 | Yes | UBE | 1229478 | 1233852 | 2 |  |  | AB-CM Tag File Mass Update | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 06/21/2019 | 06/20/2019 |  | 1388 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 06:54 | Joshi, Abhishek N | 56-F-EU-V-190613-S2MD031 |  | Yes | Y | [6 empty] | 56-F-EU-V-190613-S2MDV31A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5646010 | No | APPL |  |  | 4 |  |  | Upload Data to F46010 | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/1/2019 | 7/31/2019 |  | 1389 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-19 05:33 | Barrera Perez, Carlos Manuel | 56-F-EU-V-190731-S4MD011 | Upload | Yes | Y | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564101D | Yes | UBE | 1235436 | 1235442 | 1 |  |  | Integrate Alternate Description into F4101D | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/21/2019 | 5/21/2019 |  | 1390 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-23 12:58 | Singh, Sunil Kumar | 56-F-EU-V-190516-S1MD035 |  | Yes | Y | [6 empty] | 56-F-EU-V-190516-S1MD035A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560100Z1 | No | UBE | BXU546237 | BXU545522 | 2 |  |  | Upload Customer Contact Details F0111, F0115, F01151 | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/20/2019 | 6/19/2019 |  | 1391 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 07:08 | Joshi, Abhishek N | 56-F-EU-V-190611-S2MD018 | Upload | Yes | [7 empty] | 56-F-EU-V-190611-S2MD018A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564101Z2 | Yes | UBE | 1229495 | 13039, 1230564 | 1 |  |  | Item Category Code General Update | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/21/2019 | 5/21/2019 |  | 1392 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 07:16 | Joshi, Abhishek N | 56-F-EU-V-190516-S1MD031 |  | Yes | Yes |  |  | No Retrofit Required |  |  |  | 56-F-EU-V-190516-S1MDV31A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564102D | No | UBE |  |  | 999 |  |  | Create Item Branch Rcds from Item Master - Data Conversion | Obsolete |  |  |  | H |  | MDM | MDM | Tom Hoste | (Blank) |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1393 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 03:05 | Greenard, Terry | [6 empty] | Carlos, Objects to Obsolete | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564102R | No | UBE | 1229495 | 1230564 | 5 |  |  | Item Branch Plant Conversion - Restamp CMCG with Entity | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/12/2019 | 8/9/2019 |  | 1394 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 07:17 | Joshi, Abhishek N | 56-F-EU-V-190812-S5MD005 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5MDV005A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564102Z2 | Yes | UBE | 1229495 |  | 1 |  |  | Mass Upload of Item Tag File and Item BP tag File | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/21/2019 | 5/21/2019 |  | 1395 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-09 02:51 | Singh, Sunil Kumar | 56-F-EU-V-190516-S1MD030 | Upload | Yes | Y |  |  | Retrofit Not Required |  |  |  | 56-F-EU-V-190516-S1MDV30A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564182 | Yes | UBE |  | R564182, 1274708 | 1 |  |  | Item Branch Creation Audit Report | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/11/2019 | 6/10/2019 |  | 1396 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 01:50 | Joshi, Abhishek N | 56-F-EU-V-190506-S1MD045 | Audit / Report | Yes | Yes |  |  |  | DEFECT ID: 54 |  |  | 56-F-EU-V-190506-S1MDV45A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641826 | No | UBE | 1229495 | 1230564 | 3 |  |  | Item Branch Duplication - Batch Selection -Report Generation | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/9/2019 | 7/5/2019 |  | 1397 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 08:32 | Joshi, Abhishek N | 56-F-EU-V-190701-S3MD013 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3MDV013A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564183 | Yes | UBE |  | 1274708 | 1 |  |  | Automated Item Branch Mass Creation | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/4/2019 | 6/3/2019 |  | 1398 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-14 05:15 | Singh, Sunil Kumar | 56-F-EU-V-190517-S1MD039 |  | Yes | Yes |  |  |  | DEFECT ID: 70 |  |  | 56-F-EU-V-190517-S1MDV39A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564184 | No | UBE | 1274706 (69256) |  | 1 |  |  | Extract Item Branch Conversion Set Up Data to CSV | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/21/2019 | 5/21/2019 |  | 1399 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 07:03 | ANAND, S | 56-F-EU-V-190517-S1MD038 |  | Yes | Y |  |  |  | L3 DEFECT ID: 9 |  |  | 56-F-EU-V-190517-S1MDV038A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564185 | Yes | UBE | 1274706 69256 | 69256 | 1 |  |  | Load the Item Branch Conversion Set Up Tables | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 21/05/2019 | 21/05/2019 |  | 1400 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 07:04 | ANAND, S | 56-F-EU-V-190514-S1MD007 |  | Yes | Y |  |  |  | L3 DEFECT ID: 7 |  |  | 56-F-EU-V-190514-S1MDV01A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564188 | Yes | UBE | 1274706 69256 | BXU547535 | 1 |  |  | Load the Item Branch Enrichment External Data Table F564188 | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 21/05/2019 | 21/05/2019 |  | 1401 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 07:05 | ANAND, S | 56-F-EU-V-190514-S1MD002 |  | Yes | Y |  |  |  | L3 DEFECT ID: 6 |  |  | 56-F-EU-V-190514-S1MDV02A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564192 | Yes | UBE | 1274706 69256 |  | 1 |  |  | Load the Item Branch Creation Field Enrichment Table F564192 | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 21/05/2019 | 21/05/2019 |  | 1402 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 07:05 | ANAND, S | 56-F-EU-V-190514-S1MD013 |  | Yes | Y | [6 empty] | 56-F-EU-V-190515-S1MDV013A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564194 | Yes | UBE | 1274706 69256 |  | 1 |  |  | Item Branch Creation and Enrichment | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 21/05/2019 | 21/05/2019 |  | 1403 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 07:06 | ANAND, S | 56-F-EU-V-190515-S1MD024 |  | Yes | Y |  |  |  | DEFECT ID: 95 |  |  | 56-F-EU-V-190515-S1MDV24A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564195 | Yes | UBE | 1274706 69256 |  | 1 |  |  | Item Branch Creation and Enrichment - By Process Group | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 21-05-2019 | 21-05-2019 |  | 1404 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 07:06 | ANAND, S | 56-F-EU-V-190515-S1MD022 |  | Yes | Y |  |  |  | DEFECT ID: 96 |  |  | 56-F-EU-V-190515-S1MDV22A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564195Z1I | Yes | UBE | 1274706 69256 |  | 1 |  |  | Item Branch Creation Inbound Unedited Transaction Processor | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 19\06\06 | 19\05\21 |  | 1405 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 07:06 | ANAND, S | 56-F-EU-V-190516-S1MD032 | Inbound | Yes | Y | [6 empty] | 56-F-EU-V-190516-S1MDV032A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R563012Z1 | Yes | UBE | 1279962 | BXU545600 | 3 |  |  | Category Code General Update | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/8/2019 | 7/5/2019 |  | 1406 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-23 13:06 | Singh, Sunil Kumar | 56-F-EU-V-190705-S3MD024 |  | Yes | Y | [6 empty] | 56-F-EU-V-190705-S3MDV24A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900028 | Yes | APPL | 1253816 | 21774, 1253946 | 3 |  |  | Address Book Tag File Maintenance | L3 Pass | 170 | Closed | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/16/2019 | 7/15/2019 |  | 1407 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 06:28 | Joshi, Abhishek N | 56-F-EU-V-190708-S3MD028 | Maintenance | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900029 | Yes | APPL |  |  | 2 |  |  | Customer Master Tag File Maintenance | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/26/2019 | 6/25/2019 |  | 1408 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:07 | Chiau, Liesbet | 56-F-EU-V-190625-S2MD004 | Maintenance | Yes | Y |  |  | VV- 25/06 - Moved to Sprint 2 as per approval from Palenzuela, Jose Luis |  |  |  | N/A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900084 | No | APPL |  |  | 999 |  |  | Maintenance Application for UOM cross reference data | Obsolete |  |  |  | H |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1409 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 03:03 | Greenard, Terry |  | SECURE |  |  |  |  | Carlos, Objects to Obsolete |  |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900096 | No | APPL | 1256301 | 1256302 | 5 |  |  | Address Number Search By Company/Cat Code | L3 Pass |  |  | TRUE | L |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/12/2019 | 8/12/2019 |  | 1410 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-14 04:38 | Singh, Sunil Kumar | 56-F-EU-V-190812-S5MD002 |  | Yes | Yes | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R569869H | Yes | UBE | BXU544577 (13149) | BXU545915 | 3 |  |  | EMEA - Holding Table for MDM Replication Report | L3 Pass | 181 | Closed | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/8/2019 | 7/7/2019 |  | 1411 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 09:52 | ANAND, S | 56-F-EU-V-190708-S3MD025 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190708-S3MDV025A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56G101Z | Yes | UBE | 1278350 89975 | 89975, 1278738 | 2 |  |  | GSP: Address Book Batch Upload | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 06/20/2019 | 06/20/2019 |  | 1412 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 06:35 | ANAND, S | 56-F-EU-V-190612-S2MD027 | Upload | Yes | Y | [6 empty] | 56-F-EU-V-190612-S2MDV027A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56G301Z | Yes | UBE | 1278350 (89975) | 1278738 | 2 |  |  | GSP - Customer Master Batch Upload | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1413 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 06:35 | ANAND, S | 56-F-EU-V-190612-S2MD006 | Upload | Yes | [7 empty] | 56-F-EU-V-190612-S2MDV006A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56R0049B | No | UBE |  |  | 2 |  |  | BSM Vendor Create Request - EMEA | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/26/2019 | 6/25/2019 |  | 1414 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:07 | Chiau, Liesbet | 56-F-EU-V-190612-S2MD030 |  | Yes | Y |  |  | DSI BSFN BD3N0011 dependent object |  |  |  | 56-F-EU-V-190612-S2MDV030A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56R0049W | No | UBE |  |  | 2 |  |  | Process Vendor Contacts Requests - EMEA | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/19/2019 | 6/19/2019 |  | 1415 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:07 | Chiau, Liesbet | 56-F-EU-V-190611-S2MD013 |  | Yes | Y | [6 empty] | 56-F-EU-V-190611-S2MDV13A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P597601 | No | APPL |  |  | 999 |  |  | Recall - Customer Address Number/Group Maintenance | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1416 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Maintenance | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P597603 | No | APPL |  |  | 999 |  |  | Blocked Customer Maintainance | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1417 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Maintenance | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P597606 | Yes | APPL |  |  | 999 |  |  | Recall Request Maintenance | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1418 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Maintenance | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R594101T | Yes | UBE |  | 1233005 | 3 |  |  | Item Master Update Notification Batch Job | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/8/2019 | 7/8/2019 |  | 1419 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 10:32 | Joshi, Abhishek N | 56-F-EU-V-190708-S3MD026 |  | Yes | Y | [6 empty] | 56-F-EU-V-190708-S3MDV026A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R4101Z1I | OBS | UBE |  |  | 999 |  |  | Item Master Unedited Transactions Inbound Processor | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | (Blank) |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1420 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Inbound |  |  |  |  | MDM-SupplyChain | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59TC0410 | No | UBE |  | BXU545672 | 3 |  |  | EIM: Retrieval MILD Sites per product from MILD Global Part | L3 Not Required |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Not required | No KT needed. Test in CRP |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/8/2019 | 7/7/2019 |  | 1421 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 10:45 | Joshi, Abhishek N |  |  | Yes | Y | [6 empty] | 56-F-EU-V-190628-S3MDV03A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0049B | No | UBE |  |  | 2 |  |  | BSM Vendor Create Request | L3 Not Required |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/19/2019 | 6/19/2019 |  | 1422 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:22 | Barrera Perez, Carlos Manuel | 56-F-EU-V-190613-S2MD032 | SECURE | Yes | Yes |  |  | Report Did not validate due to DSI BSFN-BD3N00011 |  |  |  | 56-F-EU-V-190613-S2MDV032A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P594112 | No | APPL |  |  | 1 |  |  | European Item Master & Grouping Matrix Inquiry | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/20/2019 | 5/20/2019 |  | 1423 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:54 | Chiau, Liesbet | 56-F-EU-V-190514-S1MD016 | Inquiry | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P01012 | Yes | APPL |  |  | 1 | 2 |  | Address Book | L3 Pass | 118 | Closed | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/22/2019 | 5/20/2019 | 5/20/2019 | 1424 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-21 04:23 | Verma, Vikas | 56-F-EU-V-190513-S1MD008 | [5 empty] | Retrofit Completed | According to L3 Scrum call of July 8th with Vikas and Fatiha, we have decided to pass this script and test P5900028 in Sprint 3 and P5900096 individually in Sprint 5 |  |  | 56-F-EU-V-190513-S1MDV08A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P0101S | No | APPL |  |  | 5 |  |  | Address Book Master Search | L3 Pass |  |  | TRUE | L |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/21/2019 | 5/21/2019 |  | 1425 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 10:33 | Barrera Perez, Carlos Manuel | 56-F-EU-V-190510-S1MD002 |  | Yes | Y |  |  | Dependencies: P5900096 Sprint 5; P5900097 Sprint 2; P5900098 Sprint 2 | According to L3 Scrum call of July 8th with Vikas and Fatiha, we have decided to pass this script and test P5900096 individually in Sprint 5 |  |  | 56-F-EU-V-190510-S1MDV02 | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P0101SL | No | APPL |  |  | 5 |  |  | Address Book Long Search | L3 Pass |  |  | TRUE | L |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/23/2019 | 5/22/2019 |  | 1426 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 10:33 | Barrera Perez, Carlos Manuel | 56-F-EU-V-190513-S1MD005 |  | Yes | Y |  |  | MDM-SupplyChain - Dependant View in 56-F-EU-V-190415-S0FN033.Retrofit Completed. Dependencies: P5900096 Sprint 5; P5900097 Sprint 2; P5900098 Sprint 2 | 5 According to L3 Scrum call of July 8th with Vikas and Fatiha, we have decided to pass this script and test P5900096 individually in Sprint 5 |  |  | NA | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4101 | Yes | APPL |  |  | 1 |  |  | Item Master | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/4/2019 | 5/20/2019 |  | 1427 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:54 | Chiau, Liesbet | 56-F-EU-V-190510-S1MD003 |  | Yes | Y |  |  | MDM-SupplyChain |  |  |  | 56-F-EU-V-190510-S1FIV02A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P41016W | No | APPL |  | 1233005 | 1 |  |  | Item Master Alternative Description File | L3 Pass |  |  | TRUE | L |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/21/2019 | 5/21/2019 |  | 1428 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 10:33 | Joshi, Abhishek N | 56-F-EU-V-190514-S1MD012 |  | Yes | Y |  |  | Retrofitted |  |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560101Z1 | Yes | UBE | 1248413 | 15087, 1248414 | 2 |  |  | Address Book Batch Upload - New version | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | Retrofit not required | Saiteja |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 11/06/2019 | 11/06/2019 |  | 1429 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 04:11 | Joshi, Abhishek N | 56-F-EU-V-190611-S2MD014 | Upload | Yes | Yes |  |  | MDM-SupplyChain |  |  |  | 56-F-EU-V-190611-S2MDV014A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P55XREFA | Yes | APPL | 190730 BXU550074 |  | 4 |  |  | Maintain XPI Cross-Reference Tables Mk II | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/1/2019 | 7/31/2019 |  | 1430 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-28 04:24 | Vishnubhatla, Mithra | 56-F-EU-V-190730-S4MD006 | Cross Ref / Maintenance | Yes | Y | [6 empty] | N/A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560101Z | No | UBE |  | 1248414 | 3 |  |  | Mass Update Address & Whos Who Data | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/9/2019 | 7/8/2019 |  | 1431 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 04:11 | Joshi, Abhishek N | 56-F-EU-V-190709-S3MD001 |  | Yes | Y | [6 empty] | 56-F-EU-V-190709-S3MDV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P560101T | Yes | APPL | 1229478 | 1233852 | 3 |  |  | Maintenance of the table F560101T | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 07/09/2019 | 07/08/2019 |  | 1432 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 06:54 | Joshi, Abhishek N | 56-F-EU-V-190708-S3MD032 | Maintenance | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560101C | No | UBE |  | 1248414 | 2 |  |  | Load F0101Z2 from CSV - Front End | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/19/2019 | 6/19/2019 |  | 1433 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 04:30 | Joshi, Abhishek N | 56-F-EU-V-190618-S2MD037 |  | Yes | Y | [6 empty] | 56-F-EU-V-190618-S2MDV037A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564102 | Yes | APPL | 1240512 (16342) | 1241632, BXU545352 (20175) | 1 |  |  | Maintain Baxter Item Branch Tag File (RAQA) | L3 Pass |  |  | TRUE | H |  | Quality | Logistics | Pawel Oskroba | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/20/2019 | 5/20/2019 |  | 1434 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-18 08:00 | ANAND, S | 56-F-EU-V-190516-S1MD026 | Maintenance | Yes | Y |  |  | Retrofit Not Required | KTQ3 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900027 | Yes | APPL |  |  | 1 |  |  | Item Branch Tag File Maintenance | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/20/2019 | 5/20/2019 |  | 1435 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:55 | Chiau, Liesbet | 56-F-EU-V-190516-S1MD028 | Maintenance | Yes | Y |  |  | Retrofit Not Required |  |  |  | NA | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P55009 | No | APPL | BXU546671 |  | 2 |  |  | ECC calendar maintenance | PPD Passed |  |  | TRUE |  | FALSE | ECC | ARO | Ravi / Cosmin | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1436 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:14 | Joshi, Abhishek N | 56-F-EU-V-190624-S2AR004 | Maintenance | Yes | Y |  |  | VV-23/06- Moved to Sprit 2 as per request from Ravi |  |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P55010 | No | APPL |  |  | 4 | 6 | CRP | ECC Audit Trail Inquiry | PPD Passed |  |  | TRUE | L | TRUE | ECC | ARO | Ravi | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/9/2019 | 8/8/2019 |  | 1437 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 06:00 | Thapa, Ravi Pratap | 56-F-EU-V-190801-S4AR013 | Inquiry / Audit | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P00092 | No | APPL |  |  | 1 |  |  | Supplemental Data | L3 Pass |  |  | TRUE | L |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/22/2019 | 5/21/2019 |  | 1438 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 06:46 | Prabhu, Varsha | 56-F-EU-V-190510-S1MD004 |  | Yes | Y |  |  | MDM-SupplyChain |  |  |  | 56-F-EU-V-190510-S1MDV04A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5530Z1 | No | APPL | BXU544568 |  | 2 |  |  | Review Bank Transit Number Batch File | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 06/20/2019 | 06/19/2019 |  | 1439 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 06:21 | Joshi, Abhishek N | 56-F-EU-V-190611-S2MD019 |  | Yes |  |  |  | While testing Web exception error is encountered, same is the behaviour with EUDV812 |  |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564101E | No | UBE | 1253598 | 1253599 | 3 |  |  | Mass update of Item Z File - multiple columns | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/09/2019 | 7/08/2019 |  | 1440 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-23 13:12 | Singh, Sunil Kumar | 56-F-EU-V-190708-S3MD029 |  | Yes | Y |  |  | Retrofit not required |  |  |  | 56-F-EU-V-190708-S3MDV029A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5695001 | Yes | UBE | BXU546668 (12878) | BXU547462 (12878) | 6 |  |  | 21CFR Report - AB Set with Custom CFRUID | PPD Passed |  |  | TRUE | L |  | 21CFR | ARO | Cosmin Mutiu / Terry Greenard | L2 Not required | No KT, as Tested by user only in ICT |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/16/2019 | 7/15/2019 |  | 1441 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-14 07:30 | ANAND, S | 56-F-EU-V-190710-S3AR002 | 21CFR / Report | Yes | Y |  |  | Run a number of times by Users in PPD |  |  |  | 56-F-EU-V-190710-S3ARV02A, 56-F-EU-V-190710-S3ARV02B |  |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56007 | No | APPL | 1235433 (15273) | BXU548179 | 4 |  |  | Inquiry F59007 | L3 Pass |  |  | TRUE |  |  | MDM | MDM |  | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/2/2019 | 8/1/2019 |  | 1442 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 06:53 | ANAND, S | 56-F-EU-V-190731-S4MD012 | Inquiry | Yes | Y | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59601 | No | UBE | 1258235 |  | 3 |  |  | EBX: Integrity Report for Item Master F4101:FTK4101 | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/9/2019 | 7/9/2019 |  | 1443 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-09 05:37 | Singh, Sunil Kumar | 56-F-EU-V-190708-S3MD030 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190708-S3MDV030A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59602 | No | UBE | 1258235 |  | 3 |  |  | EBX : Integrity F4104 to FTK4104 | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/10/2019 | 7/09/2019 |  | 1444 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-09 05:37 | Singh, Sunil Kumar | 56-F-EU-V-190704-S3MD023 |  | Yes | Y | [6 empty] | 56-F-EU-V-190704-S3MDV23A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59603 | No | UBE | 1258235 |  | 3 |  |  | EBX: Integrity - FTK4101 to F4104 | L3 Pass | 184 | Closed | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/10/2019 | 7/9/2019 |  | 1445 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-09 05:38 | Singh, Sunil Kumar | 56-F-EU-V-190704-S3MD022 |  | Yes | Y | [6 empty] | 56-F-EU-V-190704-S3MDV022A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P55XREF1 | Yes | APPL |  | BXU545601 | 4 |  |  | Maintain XPI Cross-Reference Tables (new) | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/2/2019 | 8/1/2019 |  | 1446 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-23 13:17 | Singh, Sunil Kumar | 56-F-EU-V-190801-S4MD013 | Cross Ref / Maintenance | Yes | [7 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564101T | Yes | APPL | 1229495 | 1230564 | 3 |  |  | Maintenance of the table F574101T | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/10/2019 | 7/9/2019 |  | 1447 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 08:33 | Joshi, Abhishek N | 56-F-EU-V-190628-S3MD006 | Maintenance | Yes | Y | [6 empty] | 56-F-EU-V-190628-S3MDV06A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564102T | No | APPL | 1242968 (19282) | 1243037 | 3 |  |  | Inquiry over F574101T | L3 Pass |  |  | TRUE | L |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/10/2019 | 7/8/2019 |  | 1448 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-18 07:18 | ANAND, S | 56-F-EU-V-190708-S3MD031 | Inquiry | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5695001 | Yes | APPL |  | BXU545602 | 3 |  |  | AB Audit Maintenance | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/11/2019 | 7/11/2019 |  | 1449 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-23 08:28 | Singh, Sunil Kumar | 56-F-EU-V-190701-S3MD002 | Maintenance / Audit | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL0012 | No | UBE | BXU546939 |  | 5 |  | CRP | Update G/L Class in F41021 | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/22/2019 | 8/22/2019 |  | 1450 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 11:03 | Joshi, Abhishek N | 56-F-EU-V-190822-S5FI032 |  | Yes | Y | [6 empty] | 56-F-EU-V-190822-S5FIV032A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560101T | Yes | UBE | 1229478 | 1233852 | 3 |  |  | Address Book Mass Update Notification | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/11/2019 | 7/10/2019 |  | 1451 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 06:57 | Joshi, Abhishek N | 56-F-EU-V-190710-S3MD037 |  | Yes | Y | [6 empty] | 56-F-EU-V-190710-S3MDV037A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5603021 | No | UBE | 1235431 (13646) | 1235437 (13646) | 2 |  |  | Upload Customer Ship to X-REF | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/18/2019 | 6/18/2019 |  | 1452 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 06:43 | ANAND, S | 56-F-EU-V-190618-S2MD001 | Upload | [8 empty] | 56-F-EU-V-190618-S2MD001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0078 | Yes | UBE | BXU549662 (123865) |  | 3 |  |  | Item Master/Branch Sync Report | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/11/2019 | 7/10/2019 |  | 1453 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 10:06 | ANAND, S | 56-F-EU-V-190703-S3MD021 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190703-S3MDV021A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0142 | Yes | UBE | BXU549662 |  | 3 |  |  | Item Branch Country/Local Sync Report | L3 Pass | 207 | Closed | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/18/2019 | 7/10/2019 |  | 1454 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 10:16 | ANAND, S | 56-F-EU-V-190702-S3MD019 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190702-S3MDV19A,56-F-EU-V-190702-S3MDV19B,56-F-EU-V-190702-S3MDV19C,56-F-EU-V-190702-S3MDV19D,56-F-EU-V-190702-S3MDV19E,56-F-EU-V-190702-S3MDV19F,56-F-EU-V-190702-S3MDV19I,56-F-EU-V-190702-S3MDV19J | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0151 | Yes | UBE | BXU549662 |  | 3 |  |  | Item Master / Item Branch Tag File Synchronization Report | L3 Pass | 211 | Closed | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/12/2019 | 7/11/2019 |  | 1455 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 10:24 | ANAND, S | 56-F-EU-V-190710-S3MD036 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190710-S3MD036,56-F-EU-V-190710-S3MDV036A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0170 | Yes | UBE | BXU549662 |  | 1 |  |  | Item Branch Tag Sync | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/21/2019 | 5/21/2019 |  | 1456 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 10:20 | ANAND, S | 56-F-EU-V-190516-S1MD034 |  | Yes | Y |  |  | Retrofit Not Required |  |  |  | 56-F-EU-V-190516-S1MDV34A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0171A | No | UBE |  |  | 999 |  |  | Item Branch UoM Sync | Obsolete |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/21/2019 | 5/20/2019 |  | 1457 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 03:04 | Greenard, Terry | 56-F-EU-V-190515-S1MD020 | SECURE | Yes | Y |  |  | Unit Testing not done as L2 testing was not required Carlos, Objects to Obsolete 06/08/2019 |  |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0258 | No | UBE |  |  | 999 |  |  | Copy UOM Defn F46011 From One BP to another | Obsolete |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/12/2019 | 7/11/2019 |  | 1458 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 03:03 | Greenard, Terry | 56-F-EU-V-190709-S3MD034 | SECURE | Yes | Y |  |  | R59R0258 report contains no versions in PD812 but still the report needs to deployed to DV920 as its a Global object (Confirmed the details in email&nbsp; on 7/11/2019)Carlos, Objects to Obsolete 06/08/2019 |  |  |  | N/A | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0428 | No | UBE |  |  | 5 |  |  | MDM Controlled Item Check | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/13/2019 | 8/12/2019 |  | 1459 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-29 07:01 | Barrera Perez, Carlos Manuel | 56-F-EU-V-190812-S5MD006 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5MDV006A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P584101D | Yes | APPL | BXU544675 | BXU545603 | 1 |  |  | Item Alternate Description Maintenance | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/20/2019 | 5/17/2019 |  | 1460 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-24 04:45 | Vishnubhatla, Mithra | 56-F-EU-V-190517-S1MD039 | Maintenance | Yes | Y | [6 empty] | 56-F-EU-V-190517-S1MDV39A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564101P | No | APPL | BXU544624 |  | R2 |  |  | Maintain Item Packaging Data Tag File | PPD Passed |  |  | TRUE | H | TRUE | MDM | MDM | Carlos Barrera | L2 Pass / Complete | Not promoted to Production yet! |  |  | Terry Greenard / Vikas Verma | VV:08/11 Object moved to R2 from R3, As per request from Sandhya | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 08/11/2019 | 07/11/2019 |  | 1461 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 02:04 | Joshi, Abhishek N | 56-F-EU-V-191108-R2MD002 | Maintenance | Yes | Yes |  |  |  | R1 Script created |  |  | 56-F-EU-V-191108-R2MDV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P563002 | TBD (in Dev. Not in PD) | APPL | BXU544624 |  | R3 |  |  | Bill of Material Revisions - EMEA Functionality | PPD Passed |  |  | TRUE | L | TRUE | MDM | MDM | Tom Hoste | L2 Pass / Complete | Not Promoted to Production Yet! |  |  | Terry Greenard / Vikas Verma | VV-25-10, Moved to R3 VV-18/09 - Move to R2 as object still not avialable in PD812 | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 11/18/2019 | 11/15/2019 |  | 1462 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 06:31 | Joshi, Abhishek N | 56-F-EU-V-191108-R3MD002 | Revision | Yes | Yes |  |  | Restored PAR from PD812. | KT unplanned |  |  | 56-F-EU-V-191108-R3MDV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642047 | No | UBE | BXU549678 |  | 3 |  |  | OWC Item & Costs Integrity Report | L3 Not Required |  |  | TRUE | L |  | Order Management | OM | John Whalley | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma | VV-25/10, This was wrongly move to R2, chnged it back to 3 | Vikas Verma |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/17/2019 | 7/16/2019 |  | 1463 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 02:13 | Joshi, Abhishek N | 56-F-EU-V-190711-S3AR120 | Report | Yes | Y |  |  | To be tested in CRP |  |  |  | 56-F-EU-V-190711-S3ARV120A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0055 | No | UBE |  |  | 5 |  |  | Inactive Customer Analysis | L3 Pass |  |  | TRUE | L |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 08/13/2019 | 08/12/2019 |  | 1464 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-11 05:59 | Icardo, Ana | 56-F-EU-V-190812-S5MD013 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5MDV013A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R590421 | No | UBE |  |  | 4 |  |  | ECC: Month End Closing | L3 Pass |  |  | TRUE |  |  | ECC | ARO | Ravi / Cosmin | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 07/26/2019 | 07/25/2019 |  | 1466 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-20 03:08 | Thapa, Ravi Pratap | 56-F-EU-V-190724-S4AR001 |  | Yes | Y | [6 empty] | 56-F-EU-V-190724-S4ARV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59061 | No | UBE | BXU546671 |  | 4 |  |  | ECC: download Actual MFG cost file to csv | L3 Pass |  |  | TRUE |  |  | ECC | ARO | Ravi / Cosmin | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/22/2019 | 7/22/2019 |  | 1467 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:36 | Joshi, Abhishek N | 56-F-EU-V-190722-S4AR006 | Download | Yes | Y | [6 empty] | 56-F-EU-V-190722-S4ARV006A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59062 | No | UBE | BXU546671 |  | 4 |  |  | ECC: Download budget cost to csv | L3 Pass |  |  | TRUE |  |  | ECC | ARO | Ravi / Cosmin | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/23/2019 | 7/22/2019 |  | 1468 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:35 | Joshi, Abhishek N | 56-F-EU-V-190722-S4AR001 | Download | Yes | Y | [6 empty] | 56-F-EU-V-190722-S4ARV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59065 | No | UBE | BXU546671 |  | 4 |  |  | ECC: UOM Changed | L3 Pass |  |  | TRUE |  |  | ECC | ARO | Ravi / Cosmin | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 07/23/2019 | 07/22/2019 |  | 1469 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:35 | Joshi, Abhishek N | 56-F-EU-V-190722-S4AR005 |  | Yes | [7 empty] | 56-F-EU-V-190722-S4ARV005A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59076 | No | UBE | BXU546671 |  | 4 |  |  | ECC: Budget Rollover #1: Archive & remove Actual cost | L3 Pass |  |  | TRUE |  |  | ECC | ARO | Ravi / Cosmin | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/23/2019 | 7/22/2019 |  | 1470 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:34 | Joshi, Abhishek N | 56-F-EU-V-190722-S4AR003 |  | Yes | Y | [6 empty] | 56-F-EU-V-190722-S4ARV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59077 | No | UBE | BXU546671 |  | 4 |  |  | ECC: Upload Currency from F560015 | L3 Pass |  |  | TRUE |  |  | ECC | ARO | Ravi / Cosmin | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/24/2019 | 7/23/2019 |  | 1471 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:33 | Joshi, Abhishek N | 56-F-EU-V-190723-S4AR009 | Upload | Yes | Yes | [6 empty] | 56-F-EU-V-190723-S4ARV009A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P590005A | No | APPL | BXU544630 |  | 3 |  |  | Maintain Country Codes by System | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/12/2019 | 7/11/2019 |  | 1472 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 07:10 | Joshi, Abhishek N | 56-F-EU-V-190710-S3MD035 | Maintenance | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900153 | No | APPL |  |  | 5 |  |  | XUDI - Object Processing Control File Application | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/14/2019 | 8/13/2019 |  | 1473 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-13 03:10 | Icardo, Ana | 56-F-EU-V-190812-S5MD010 |  | Yes | Yes | [6 empty] | NA | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900385 | No | APPL |  |  | 6 |  |  | Email Configuration Application | PPD Passed |  |  | TRUE | L |  | ARO | ARO | Terry Greenard | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/26/2019 | 8/23/2019 |  | 1474 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-12-19 02:45 | Greenard, Terry | 56-F-EU-V-190820-S5CNC002 |  | Yes | Y |  |  | Works in PPD, no records to view in table |  |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P590407 | No | APPL |  |  | 5 |  |  | BSM Vendor Create Inquiry | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/14/2019 | 8/13/2019 |  | 1475 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-26 05:55 | Barrera Perez, Carlos Manuel | 56-F-EU-V-190812-S5MD008 | Inquiry | Yes | Yes | [6 empty] | NA | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P590407B | No | APPL |  |  | 5 |  |  | BSM Vendor Bank Accounts Requests | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/14/2019 | 8/13/2019 |  | 1476 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-26 05:55 | Barrera Perez, Carlos Manuel | 56-F-EU-V-190813-S5MD013 |  | Yes | Yes | [6 empty] | NA | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P590407W | No | APPL |  |  | 5 |  |  | BSM Vendor Contacts Requests | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/14/2019 | 8/13/2019 |  | 1477 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-26 05:55 | Barrera Perez, Carlos Manuel | 56-F-EU-V-190812-S5MD009 |  | Yes | Yes | [6 empty] | NA | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P594113 | No | APPL | BXU546671 |  | 4 |  |  | ECC Filter Criteria Maintenance | PPD Passed |  |  | TRUE |  | FALSE | ECC | ARO | Ravi / Cosmin | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/24/2019 | 7/23/2019 |  | 1478 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:33 | Joshi, Abhishek N | 56-F-EU-V-190723-S4AR007 | Maintenance | Yes | Yes | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0430 | No | UBE |  |  | 5 |  |  | Refresh LE vs Transactional BranchPlant. | L3 Pass |  |  | TRUE | L |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 08/16/2019 | 08/15/2019 |  | 1479 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-11 02:30 | Icardo, Ana | 56-F-EU-V-190816-S5MD022 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190816-S5MDV022A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0433 | No | UBE |  |  | 5 |  |  | IR - Compare PTC GTIN and Conversion Factor with ETPD BP | L3 Pass |  |  | TRUE | L |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/16/2019 | 8/14/2019 |  | 1480 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-05 03:09 | Barrera Perez, Carlos Manuel | 56-F-EU-V-190813-S5MD017 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190813-S5MDV017A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0435 | No | UBE |  |  | 5 |  |  | IR - for DUNS Number between PTC and JDE | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma |  | CIZMECI,TANKUT |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/16/2019 | 8/14/2019 |  | 1481 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-09 06:47 | Icardo, Ana | 56-F-EU-V-190812-S5MD011 |  | Yes | Y | [6 empty] | 56-F-EU-V-190812-S5MDV011A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0436 | No | UBE |  |  | 5 |  |  | Integrity Rep for Lot Proc Type btw PTC and Branch/Plants | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/16/2019 | 8/14/2019 |  | 1482 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-09 06:15 | Icardo, Ana | 56-F-EU-V-190813-S5MD014 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190813-S5MDV014A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0438 | No | UBE |  |  | 5 |  |  | Integrity Report for Sterilization between PTC and Branch Pl | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 08/18/2019 | 08/26/2019 |  | 1483 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-11 03:48 | Icardo, Ana | 56-F-EU-V-190816-S5MD023 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190816-S5MDV023A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P0004A | Yes | APPL |  |  | 1 |  |  | BSM UDC Extract maintenance | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 05/29/2019 | 05/28/2019 |  | 1484 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:55 | Chiau, Liesbet |  | Maintenance | Yes | Y |  |  | Retrofit Not Required |  |  |  | 56-F-EU-V-190516-IV0001A,56-F-EU-V-190516-IV0001B,56-F-EU-V-190516-IV0001C,56-F-EU-V-190516-IV0001D,56-F-EU-V-190516-IV0001E | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P590004E | No | APPL |  |  | 999 |  |  | User Defined Codes | Obsolete |  |  | FALSE | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma | VV-14/08 - Based on Terry suggestion, put on hold until Carlos is back |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1485 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-05 02:28 | Barrera Perez, Carlos Manuel | [6 empty] | Object tested from ET to EU. No need to bring it to EMEA. Included on MDM EMEA test tracker. |  |  |  |  | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P590004F | No | APPL |  |  | 999 |  |  | User Defined Code Alternate Descriptions | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1486 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-10 03:40 | Verma, Vikas |  | SECURE |  |  |  |  | VV-10/07 - Obsoleted the object as does not find in 8.12 |  |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900174 | No | APPL |  |  | 999 |  |  | Master Maintenance Application | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma | VV-27/08 - Obsoleted as per discussion with Terry |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1487 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-27 03:28 | Verma, Vikas |  | SECURE | [9 empty] | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900181 | No | APPL |  |  | 999 |  |  | Address Book Mass Upload | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1488 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 02:38 | Greenard, Terry |  | SECURE |  |  |  |  | Carlos, REMOVE FROM THE TRACKER. NOT NEEDED IN EMEA |  |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900182 | No | APPL |  |  | 999 |  |  | Customer Master Upload | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1489 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 02:38 | Greenard, Terry |  | SECURE |  |  |  |  | Carlos, REMOVE FROM THE TRACKER. NOT NEEDED IN EMEA |  |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900183 | No | APPL |  |  | 999 |  |  | Vendor Master Mass upload | Obsolete |  |  |  | H |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1490 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 02:39 | Greenard, Terry |  | SECURE |  |  |  |  | Carlos, REMOVE FROM THE TRACKER. NOT NEEDED IN EMEA |  |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900184 | No | APPL |  |  | 999 |  |  | Supplemental Data Mass Upload | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1491 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 02:40 | Greenard, Terry |  | SECURE |  |  |  |  | Carlos, REMOVE FROM THE TRACKER. NOT NEEDED IN EMEA |  |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900185 | No | APPL |  |  | 999 |  |  | Item Restrictions Mass Upload | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1492 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 02:42 | Greenard, Terry |  | SECURE |  |  |  |  | Carlos, REMOVE FROM THE TRACKER. NOT NEEDED IN EMEA |  |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5901020 | No | APPL |  |  | 999 |  |  | JDE to Address Validation S/W - Overridden Addresses | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1493 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 02:42 | Greenard, Terry |  | SECURE |  |  |  |  | Carlos, REMOVE FROM THE TRACKER. NOT NEEDED IN EMEA |  |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5901021 | No | APPL |  |  | 999 |  |  | Customer Master | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1494 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 02:43 | Greenard, Terry |  | SECURE |  |  |  |  | Carlos, REMOVE FROM THE TRACKER. NOT NEEDED IN EMEA |  |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5903013 | No | APPL |  |  | 999 |  |  | Customer Master | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1495 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 02:44 | Greenard, Terry |  | SECURE |  |  |  |  | Carlos, REMOVE FROM THE TRACKER. NOT NEEDED IN EMEA |  |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5903014 | No | APPL |  |  | 999 |  |  | Basis/Bill To Maintenance | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1496 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 02:30 | Greenard, Terry |  | SECURE |  |  |  |  | Carlos , REMOVE FROM THE TRACKER. NOT NEEDED IN EMEA |  |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5941306 | No | APPL |  |  | 999 |  |  | Echelon and Item/BP Application | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1497 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 02:47 | Greenard, Terry |  | SECURE |  |  |  |  | Carlos, REMOVE FROM THE TRACKER. NOT NEEDED IN EMEA |  |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P59BDWRD | No | APPL |  |  | 999 |  |  | BAX Word Search | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1498 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 02:47 | Greenard, Terry |  | SECURE |  |  |  |  | Carlos, REMOVE FROM THE TRACKER. NOT NEEDED IN EMEA |  |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P59MD011 | No | APPL |  |  | 999 |  |  | MDM Integrated Comparison Request Maintenance | Obsolete |  |  | FALSE | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma | VV-14/08 - Based on Terry suggestion, put on hold until Carlos is back |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1499 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-05 02:30 | Barrera Perez, Carlos Manuel |  | Maintenance |  |  |  |  | Object tested from ET to EU. No need to bring it to EMEA. Included on MDM EMEA test tracker. |  |  |  |  | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P59MD012 | No | APPL |  |  | 999 |  |  | MDM Integrated Application | Obsolete |  |  | FALSE | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma | VV-14/08 - Based on Terry suggestion, put on hold until Carlos is back |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1500 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-05 02:30 | Barrera Perez, Carlos Manuel | [6 empty] | Object tested from ET to EU. No need to bring it to EMEA. Included on MDM EMEA test tracker. |  |  |  |  | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P59MD09 | No | APPL |  |  | 1 |  |  | Pull Master Application | L3 Not Required |  |  | TRUE | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT needed. Global object not modified in EMEA. To test in UAT (Integration requiered) |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/20/2019 | 5/20/2019 |  | 1501 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:55 | Chiau, Liesbet | 56-F-EU-V-190517-S1MD035 |  | Yes | Y | [6 empty] | N/A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5900029 | No | UBE |  |  | 999 |  |  | Custom Item Branch Duplication | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1502 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 02:48 | Greenard, Terry |  | SECURE |  |  |  |  | Carlos, REMOVE FROM THE TRACKER. NOT NEEDED IN EMEA |  |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5900385 | No | UBE |  |  | 999 |  |  | UBE to trigger Email with attachment | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1503 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 02:52 | Greenard, Terry |  | SECURE |  |  |  |  | Carlos, REMOVE FROM THE TRACKER. NOT NEEDED IN EMEA |  |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R594104 | No | UBE |  |  | 999 |  |  | Store GTIN in X-ref Table (F4104) | Obsolete |  |  | FALSE | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma |  | VV-14/08 - Based on Terry suggestion, put on hold until Carlos is back |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1504 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-05 02:31 | Barrera Perez, Carlos Manuel | [6 empty] | Object tested from ET to EU. No need to bring it to EMEA. Included on MDM EMEA test tracker. |  |  |  |  | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5941826 | No | UBE |  |  | 999 |  |  | Item Branch Duplication - Batch Selection | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1505 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 02:53 | Greenard, Terry |  | SECURE |  |  |  |  | Carlos, REMOVE FROM THE TRACKER. NOT NEEDED IN EMEA |  |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R595901 | No | UBE |  |  | 999 |  |  | Control Condition Integrity Check Report | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1506 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 02:53 | Greenard, Terry |  | SECURE |  |  |  |  | Carlos, REMOVE FROM THE TRACKER. NOT NEEDED IN EMEA |  |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59MD98AA | No | UBE |  |  | 999 |  |  | MDM AB Replication Monitoring Report | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1507 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 02:54 | Greenard, Terry |  | SECURE |  |  |  |  | Carlos, REMOVE FROM THE TRACKER. NOT NEEDED IN EMEA |  |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59MD98IA | No | UBE |  |  | 999 |  |  | MDM Item Replication Audit Report | Obsolete |  |  | FALSE | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma | VV-14/08 - Based on Terry suggestion, put on hold until Carlos is back |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1508 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-05 02:31 | Barrera Perez, Carlos Manuel |  | Audit / Report |  |  |  |  | Object tested from ET to EU. No need to bring it to EMEA. Included on MDM EMEA test tracker. |  |  |  |  | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59MD98UA | No | UBE |  |  | 999 |  |  | MDM UDC Replication Audit Report | Obsolete |  |  | FALSE | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma | VV-14/08 - Based on Terry suggestion, put on hold until Carlos is back |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1509 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-05 02:31 | Barrera Perez, Carlos Manuel |  | Audit / Report |  |  |  |  | Object tested from ET to EU. No need to bring it to EMEA. Included on MDM EMEA test tracker. |  |  |  |  | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0156 | No | UBE |  |  | 999 |  |  | Address Validation report called from R59R0156A | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1510 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 02:55 | Greenard, Terry |  | SECURE |  |  |  |  | Carlos, REMOVE FROM THE TRACKER. NOT NEEDED IN EMEA |  |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0156A | No | UBE |  |  | 999 |  |  | JDE to Address Validation S/W - Validate/Overidden Address | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1511 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 02:55 | Greenard, Terry |  | SECURE |  |  |  |  | Carlos, REMOVE FROM THE TRACKER. NOT NEEDED IN EMEA |  |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0174 | No | UBE |  |  | 999 |  |  | Item Master Trigger Error Details | Obsolete |  |  | TRUE | L | TRUE | MDM | MDM | Carlos Barrera | (Blank) | 19/11/2019 BC : Need data from SME, informed Carlos. No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma | VV:08/11 Object moved to R2 from R3, As per request from Sandhya | Nikit Sharma |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 10/22/2019 | 10/21/2019 |  | 1512 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-13 00:07 | Naik, Prashant | 56-F-EU-V-191021-R2MD001 | Error | Yes | Y |  |  | Unable to test the report as Table F594101G and View V594101G are on hold due to existing behavior in 812 and report contains only XBX version |  |  |  | N/A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0259 | No | UBE |  |  | 999 |  |  | Supplement Data Inbound Processor UBE | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1513 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 02:56 | Greenard, Terry |  | SECURE |  |  |  |  | Carlos, REMOVE FROM THE TRACKER. NOT NEEDED IN EMEA |  |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0338 | No | UBE |  |  | 999 |  |  | AB Mass Maintenance | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1514 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 02:58 | Greenard, Terry |  | SECURE |  |  |  |  | Carlos, REMOVE FROM THE TRACKER. NOT NEEDED IN EMEA |  |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0342 | No | UBE |  |  | 999 |  |  | Batch Address Book Mass Upload | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1515 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 02:58 | Greenard, Terry |  | SECURE |  |  |  |  | Carlos, REMOVE FROM THE TRACKER. NOT NEEDED IN EMEA |  |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0343 | No | UBE |  |  | 999 |  |  | Batch Customer Master Upload | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1516 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 02:58 | Greenard, Terry |  | SECURE |  |  |  |  | Carlos, REMOVE FROM THE TRACKER. NOT NEEDED IN EMEA |  |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0344 | No | UBE |  |  | 999 |  |  | Vendor Master Mass Upload | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1517 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 02:58 | Greenard, Terry |  | SECURE |  |  |  |  | Carlos, REMOVE FROM THE TRACKER. NOT NEEDED IN EMEA |  |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0345 | No | UBE |  |  | 999 |  |  | Batch Supplemental Data Mass Upload | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1518 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 02:58 | Greenard, Terry |  | SECURE |  |  |  |  | Carlos, REMOVE FROM THE TRACKER. NOT NEEDED IN EMEA |  |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0346 | No | UBE |  |  | 999 |  |  | Batch Item Restrictions Mass Upload | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1519 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 02:58 | Greenard, Terry |  | SECURE |  |  |  |  | Carlos, REMOVE FROM THE TRACKER. NOT NEEDED IN EMEA |  |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R41001A | TBD | UBE |  |  | 999 |  |  | Flat File import to staging table | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | (Blank) | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1520 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-21 10:34 | Greenard, Terry | [11 empty] | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R41001B | Yes | UBE |  |  | 999 |  |  | Import from staging tables to standard JDE tables | Obsolete |  |  |  | H |  | MDM | MDM | Tom Hoste | (Blank) | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1521 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-21 10:34 | Greenard, Terry | [11 empty] | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R41001C | TBD | UBE |  |  | 999 |  |  | Import from staging tables to standard JDE tables-Sort ITM | Obsolete |  |  | FALSE | L |  | MDM | MDM | Tom Hoste | (Blank) | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/21/2019 | 8/21/2019 |  | 1522 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-21 10:35 | Greenard, Terry | 56-F-EU-V-190814-S5MD020 | [9 empty] | 56-F-EU-V-190814-S5MDV020A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59RMD01 | No | UBE |  |  | 999 |  |  | MDM Integrated Request Process | Obsolete |  |  | FALSE | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma | VV-14/08 - Based on Terry suggestion, put on hold until Carlos is back |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1523 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-05 02:32 | Barrera Perez, Carlos Manuel | [6 empty] | Object tested from ET to EU. No need to bring it to EMEA. Included on MDM EMEA test tracker. |  |  |  |  | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59RMD02 | No | UBE |  |  | 999 |  |  | MDM Integrated Request Comparison Report | Obsolete |  |  | FALSE | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma | VV-14/08 - Based on Terry suggestion, put on hold until Carlos is back |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1524 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-05 02:32 | Barrera Perez, Carlos Manuel |  | Report |  |  |  |  | Object tested from ET to EU. No need to bring it to EMEA. Included on MDM EMEA test tracker. |  |  |  |  | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59RMD02W | No | UBE |  |  | 999 |  |  | MDM Integrated Request Comparison Report - Wrapper | Obsolete |  |  | FALSE | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma | VV-14/08 - Based on Terry suggestion, put on hold until Carlos is back |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1525 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-05 02:32 | Barrera Perez, Carlos Manuel |  | Report |  |  |  |  | Object tested from ET to EU. No need to bring it to EMEA. Included on MDM EMEA test tracker. |  |  |  |  | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59RMD04 | No | UBE |  |  | 999 |  |  | Display Processed Request Information | Obsolete |  |  | FALSE | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma | VV-14/08 - Based on Terry suggestion, put on hold until Carlos is back |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1526 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-05 02:33 | Barrera Perez, Carlos Manuel | [6 empty] | Object tested from ET to EU. No need to bring it to EMEA. Included on MDM EMEA test tracker. |  |  |  |  | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59RMD05 | No | UBE |  |  | 999 |  |  | Process MDM Requests | Obsolete |  |  | FALSE | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma | VV-14/08 - Based on Terry suggestion, put on hold until Carlos is back |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1527 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-05 02:33 | Barrera Perez, Carlos Manuel | [6 empty] | Object tested from ET to EU. No need to bring it to EMEA. Included on MDM EMEA test tracker. |  |  |  |  | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0392 | No | UBE |  |  | 999 |  |  | F4104.XRT Cross Reference Update Program | Obsolete |  |  | FALSE | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma | VV-14/08 - Based on Terry suggestion, put on hold until Carlos is back |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1528 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-05 02:33 | Barrera Perez, Carlos Manuel |  | Cross Refer |  |  |  |  | Object tested from ET to EU. No need to bring it to EMEA. Included on MDM EMEA test tracker. |  |  |  |  | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59SWAP | No | UBE |  |  | 999 |  |  | Item Auto Swap Process for GEMETRIC and GEIMPERIAL | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | (Blank) | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1529 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-31 01:20 | Greenard, Terry | [11 empty] | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P40131 | TBD | APPL |  |  | 999 |  |  | Order Processing Cross Ref | Obsolete |  |  | TRUE | L |  | MDM | MDM | Tom Hoste | (Blank) | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma | VV-02/08 As per discussion with BSL and Baxter Obsoleted the objects as not retrofit is required | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/15/2019 | 7/12/2019 |  | 1530 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-02 02:21 | Verma, Vikas | NA | Cross Refer | Yes | Y |  |  | No Retrofit Required |  |  |  | NA | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P41003 | No | APPL |  |  | 1 |  |  | Unit of Measure Conversion - Std | L3 Pass |  |  | TRUE | L |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1531 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-12-05 06:53 | Singh, Sunil Kumar |  |  | Yes | Yes |  |  | No Retrofit required |  |  |  |  | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4108 | Yes | APPL |  |  | 1 |  |  | Lot Master This is the standard JDE Lot Master application which should be used only for inquiry purposes, as there is no Lot Status Security implemented. The application security should not allow add/change options for the users in PROD. | L3 Not Required |  |  | TRUE | L |  | Quality | Logistics |  | L2 Not required | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/28/2019 | 5/27/2019 |  | 1532 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:55 | Chiau, Liesbet |  |  | Yes | Y |  |  | Retrofit Not Required |  |  |  | 56-F-EU-V-190516- -BV0003A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P41829 | TBD | APPL |  |  | 999 |  |  | P41829 | Obsolete |  |  | TRUE | L |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma | VV-02/08 As per discussion with BSL and Baxter Obsoleted the objects as not retrofit is required | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/12/2019 | 7/11/2019 |  | 1533 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-02 02:22 | Verma, Vikas | N/A |  | Yes | Y |  |  | No Retrofit required |  |  |  | 56-F-EU-V-190711-IV0001A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900151 | No | APPL |  |  | 999 |  |  | Global Object | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Test needed, Global object to secure |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1534 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 02:58 | Greenard, Terry |  | SECURE |  |  |  |  | Carlos, REMOVE FROM THE TRACKER. NOT NEEDED IN EMEA |  |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56BIP02 | No | APPL | BXU545834 | BXU546786 | 6 |  |  |  | L3 Pass |  |  | TRUE | MNE2E |  | IXOS Archive | eCommerce | Linda Kenny | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/26/2019 | 8/23/2019 |  | 1535 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 07:32 | Joshi, Abhishek N | 56-F-EU-V-190820-S5EC002 |  | Yes | Y |  |  |  | NoKT |  |  | 56-F-EU-V-190820-S5ECV002A,56-F-EU-V-190820-S5ECV002B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56BIP04 | No | APPL | BXU549624 | BXU546797 | 6 |  |  | IXOS E-mails | L3 Pass |  |  | TRUE | MNE2E |  | IXOS Archive | eCommerce | Linda Kenny | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/26/2019 | 8/23/2019 |  | 1536 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 02:35 | Joshi, Abhishek N | 56-F-EU-V-190820-S5EC009 |  | Yes | Y |  |  |  | NoKT |  |  | 56-F-EU-V-190820-S5ECV009A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56BIP05 | No | APPL |  | BXU546798 | 5 |  |  | IXOS ShipTo Email Exclusion | L3 Pass |  |  | TRUE | MNE2E |  | IXOS Archive | eCommerce | Linda Kenny | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/27/2019 | 8/26/2019 |  | 1537 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-21 06:03 | Joshi, Abhishek N | 56-F-EU-V-190820-S5EC006 |  | Yes | Y |  |  |  | NoKT |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56BIP06 | No | APPL |  | BXU546808 | 5 |  |  | IXOS Contact Information | L3 Pass |  |  | TRUE | MNE2E |  | IXOS Archive | eCommerce | Linda Kenny | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/27/19 | 8/26/19 |  | 1538 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-21 06:34 | Joshi, Abhishek N | 56-F-EU-V-190819-S5EC004 |  | Yes | Y |  |  |  | NoKT |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56BIP07 | No | APPL | BXU549594 | BXU546810 | 5 |  |  | IXOS Set Email Hold Code | L3 Pass |  |  | TRUE | MNE2E |  | IXOS Archive | eCommerce | Linda Kenny | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/28/2019 | 8/27/2019 |  | 1539 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 02:57 | Joshi, Abhishek N | 56-F-EU-V-190819-S5EC005 |  | Yes | Y |  |  |  | NoKT |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P58AU005 | No | APPL | BXU550485 |  | 4 |  |  | Manual Price Override Audit Inquiry | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/22/2019 | 7/19/2019 |  | 1540 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 03:19 | Joshi, Abhishek N | 56-F-EU-V-190722-S4OM001 | Inquiry / Audit | Yes | Yes |  |  | Retrofit not required |  |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P58IN010 | No | APPL |  |  | 999 |  |  | Edelivery Workfile | Obsolete |  |  |  | ME2E |  | Transportation | Logistics | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1541 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-05 05:26 | Greenard, Terry | [7 empty] | NA | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P58IN011 | No | APPL | BXU550677 |  | 6 |  |  | Edelivery Customer Setup | L3 Pass |  |  | TRUE | MNE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 9/4/2019 | 9/3/2019 |  | 1542 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-20 06:40 | Joshi, Abhishek N | 56-F-EU-V-190827-S6LO005 | Setup | Yes | Y |  |  |  | various |  |  | 56-F-EU-V-190827-S6LOV005A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900010 | No | APPL |  |  | 2 |  |  | Product Allocation Standard Preference Upload | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/11/2019 | 6/10/2019 |  | 1543 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:07 | Chiau, Liesbet | 56-F-EU-V-190611-S2OM016 | Upload | Yes | Y | [6 empty] | 56-F-EU-V-190611-S2OMV16A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900021 | No | APPL | 1247918 (21698) |  | 6 |  |  | Customer XREF Extension | L3 Pass |  |  | TRUE | HE2E |  | EDI Order Management | eCommerce | Aidan Scally | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 9/5/2019 | 9/5/2019 |  | 1544 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-20 07:37 | ANAND, S | 56-F-EU-V-190828-S6EC001 |  | Yes |  |  |  |  | KTEDI2 |  |  | 56-F-EU-V-190828-S6VEC001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900040 | No | APPL |  |  | 2 |  |  | Frozen Billing Advanced Preference Upload Applicaion | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/11/2019 | 6/10/2019 |  | 1545 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:07 | Chiau, Liesbet | 56-F-EU-V-190610-S2OM012 | Upload | Yes | Y | [6 empty] | 56-F-EU-V-190610-S2OMV012A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900053 | Yes | APPL |  |  | 1 |  |  | Inventory Sourcing Preference Upload Application | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 22/05/2019 | 22/05/2019 |  | 1546 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-12-05 06:47 | Singh, Sunil Kumar | 56-F-EU-V-190515-S1OM019 | Upload | Yes | Y | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900132 | No | APPL | 1240673 241 | BXU546801 | 2 |  |  | EDI 850 Inbound Staging Tables | L3 Pass |  |  | TRUE | LNE2E |  | EDI Order Management | eCommerce | Linda Kenny | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/25/2019 | 6/24/2019 |  | 1547 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-21 05:13 | Vishnubhatla, Mithra | 56-EU-V-190617-S2OM034 | Inbound | Yes | Y |  |  |  | KTEDI5 |  |  | 56-EU-V-190617-S2OMV034A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900133 | No | APPL |  | BXU546803 | 2 |  |  | Staging Table - Header | L3 Pass |  |  | TRUE | LNE2E |  | EDI Order Management | eCommerce | Linda Kenny | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1548 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-21 06:16 | Joshi, Abhishek N | 56-F-EU-V-190617-S2OM036 |  | Yes | Y |  |  |  | KTEDI5 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900134 | No | APPL |  | BXU546804 | 2 |  |  | Staging Table - Detail | L3 Pass |  |  | TRUE | LNE2E |  | EDI Order Management | eCommerce | Linda Kenny | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1549 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-21 06:18 | Joshi, Abhishek N | 56-F-EU-V-190617-S2OM035 |  | Yes | Y |  |  |  | KTEDI5 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900135 | No | APPL |  | BXU546805 | 2 |  |  | Detail - Tag File Application | L3 Pass |  |  | TRUE | LNE2E |  | EDI Order Management | eCommerce | Linda Kenny | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 06/19/2019 | 06/19/2019 |  | 1550 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-21 06:22 | Joshi, Abhishek N | 56-F-EU-V-190612-S2ED003 |  | Yes | Y |  |  |  | KTEDI5 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900136 | No | APPL |  | BXU546806 | 2 |  |  | Detail Text | L3 Pass |  |  | TRUE | LNE2E |  | EDI Order Management | eCommerce | Linda Kenny | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 06/18/2019 | 06/17/2019 |  | 1551 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-21 06:26 | Joshi, Abhishek N | 56-F-EU-V-190612-S2MO072 | Text | Yes | Y |  |  |  | KTEDI5 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900141 | No | APPL |  | BXU546807 | 2 |  |  | Header Text | L3 Pass |  |  | TRUE | LNE2E |  | EDI Order Management | eCommerce | Linda Kenny | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 12/096/19 | 12/06/19 |  | 1552 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-21 06:31 | Joshi, Abhishek N | 56-F-EU-V-190610-S2OM007 | Text | Yes | Y |  |  |  | KTEDI5 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900147 | No | APPL |  | BXU546812 | 1 |  |  | EDI 850 Inbound Error Control | L3 Pass |  |  | TRUE | LNE2E |  | EDI Order Management | eCommerce | Linda Kenny | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/24/2019 | 5/24/2019 |  | 1553 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-21 06:56 | Joshi, Abhishek N | 56-F-EU-V-190520-S1ED003 | Error / Inbound | Yes | Y |  |  | Retrofit Not Required | KTEDI5 |  |  | 56-F-EU-V-190520-S1EDV03A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900149 | No | APPL |  |  | 3 |  |  | Advanced preference upload maps | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 07/03/2019 | 07/02/2019 |  | 1554 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-09 06:50 | Kamatham, Deepika | 56- F-EU-V-190701-S3OM011 | Upload | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900150 | No | APPL |  |  | 4 |  |  | Generic Advanced Preference Upload | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete | L3 - waiting for R59R0253 deployed to UT |  |  | Terry Greenard / Vikas Verma |  | Saieja |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/3/2019 | 7/3/2019 |  | 1555 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 06:04 | Deveen, Genevive | 56-F-EU-V-190628-S3OM008 | Upload | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R47002C | No | UBE |  |  | 999 |  |  | Inbound Flat File Conversion | Obsolete | 216 |  | TRUE | L |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete | L3 testing - need access to \\DEFRE1WIN903.AWS.BAXTER.COM=> KSR000009172004; INC000001226663 (workaround) + defect # 216 |  |  | Terry Greenard / Vikas Verma | VV-02/08 As per discussion with BSL and Baxter Obsoleted the objects as not retrofit is required | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/15/2019 | 7/14/2019 |  | 1556 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-02 02:23 | Verma, Vikas | NA | Inbound | Yes | Y |  |  | UBE Doesnot require retrofit as PD812 and DV920 specs are same,only version project created . |  |  |  | 56-F-EU-V-190711-BV0383A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4072 | No | APPL | BXU545316 |  | 3 |  |  | Price Adjustment Detail Revisions | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Malithara, George Manuval | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/4/2019 | 7/3/2019 |  | 1557 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 08:35 | Joshi, Abhishek N | 56-F-EU-V-190704-S3OM077 | Revision | Yes | Y | [6 empty] | 56-F-EU-V-190704-S3OMV077A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600128 | No | UBE |  |  | 999 |  |  | Italy Athena JDE Reconciliation | Obsolete | [5 empty] | EDI Order Management | eCommerce | Aidan Scally |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1558 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0050 | No | UBE |  | BXU546793 | 4 |  |  | EDI Inbound preprocessor | L3 Pass |  |  | TRUE | HE2E |  | EDI Order Management | eCommerce | Aidan Scally | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/29/2019 | 7/28/2019 |  | 1559 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-21 05:52 | Joshi, Abhishek N | 56-F-EU-V-190725-S4EC002 | Inbound | Yes |  |  |  |  | KTEDI1 |  |  | 56-F-EU-V-190725-S4ECV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0245 | No | UBE |  |  | 6 | 1 |  | EDI 850 Inbound Pre-processor Revisions | L3 Pass |  |  | TRUE | ME2E |  | Technical Services | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth, Thippulla |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 9/4/2019 | 9/3/2019 |  | 1560 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-12 07:30 | BILENSOY, NURI | 56-F-EU-V-190827-S6LO003 | Revision / Inbound | Yes | Yes |  |  |  | KTTS5 |  |  | 56-F-EU-V-190827-S6LOV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56BIP02M | No | UBE | BXU546082 | BXU546799 | 6 |  |  | Create new Customer E-mails for IXOS | L3 Not Required |  |  | TRUE | MNE2E |  | IXOS Archive | eCommerce | Linda Kenny | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 9/13/2019 | 9/12/2019 |  | 1561 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 07:51 | Joshi, Abhishek N | 56-F-EU-V-190906-S6EC003 |  | Yes | Yes |  |  | To be tested in CRP | NoKT |  |  | 56-F-EU-V-190906-S6ECV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56BIP09 | No | UBE | BXU545843 | BXU546791 | 6 |  |  | IXOS Integrity - Full Report | L3 Pass |  |  | TRUE | MNE2E |  | IXOS Archive | eCommerce | Linda Kenny | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 9/16/2019 | 9/13/2019 |  | 1562 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 07:46 | Joshi, Abhishek N | 56-F-EU-V-190903-S6EC002 | Report | Yes | Yes |  |  |  | NoKT |  |  | 56-F-EU-V-190903-S6ECV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647121 | No | UBE | 1235434, BXU545265 | 15746 | 2 |  |  | Consignment Order Processing | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/11/2019 | 6/11/2019 |  | 1563 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 05:33 | Joshi, Abhishek N | 56-F-EU-V-190610-S2OM013 |  | Yes | Y |  |  | Retrofit not required |  |  |  | 56-F-EU-V-190610-S2OMV013A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P38010 | No | APPL | BXU545418 | BXU547085, BXU547090 | 2 |  |  | Agreement Master | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | John Whalley | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/12/2019 | 6/11/2019 |  | 1564 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 03:09 | Joshi, Abhishek N | 56-F-EU-V-190610-S2OM011 |  | Yes | Y | [6 empty] | 56-F-EU-V-190610-S2OMV11A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P38011 | No | APPL | BXU545418 | BXU547085 | 2 |  |  | Agreement Quantities | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/12/2019 | 6/11/2019 |  | 1565 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 03:09 | Joshi, Abhishek N | 56-F-EU-V-190611-S2OM017 |  | Yes | Y | [6 empty] | 56-F-EU-V-190611-S2OMV17A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P38200W | No | APPL | BXU547349 |  | 3 |  |  | Agreement Selection Window | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/8/2019 | 7/7/2019 |  | 1566 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 05:20 | Joshi, Abhishek N | 56-F-EU-V-190708-S3OM082 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P40051 | Yes | APPL |  | BXU548943 (13238) | 2 |  |  | Work with Return Material Authorization | L3 Not Required |  |  | TRUE |  |  | Warehouse | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1567 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 06:42 | ANAND, S | 56-F-EU-V-190611-S2LO081 | [5 empty] | On Hold N/A for EMEA |  |  |  | 56-F-EU-V-190611-S2LOV081A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P400511 | Yes | APPL |  | BXU544710 | 3 |  |  | Return Material Authorization Revisions | L3 Not Required |  |  | TRUE |  |  | Warehouse | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/12/2019 | 7/09/2019 |  | 1568 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-09 06:10 | Singh, Sunil Kumar | 56-F-EU-V-190708-S3LO042 | Revision |  | Y |  |  | On Hold N/A for EMEA |  |  |  | 56-F-EU-V-190708-S3LOV42A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P40071 | No | APPL | BXU545383 | BXU547034 | 1 | 6 |  | Customer Group Preferences | L3 Not Required |  |  | TRUE | HNE2E |  | Order Management | OM | John Whalley | L2 Not required | L3 awaiting UT9.2 AIP Connection (tested during CRP) |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/21/2019 | 5/21/2019 |  | 1569 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 03:07 | Joshi, Abhishek N | 56-F-EU-V-190510-S1OM001 |  | Yes | Y |  |  |  |  | UTS_P40071 |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P40073 | No | APPL |  |  | 1 | 2 |  | Preference Hierarchy | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | John Whalley | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/21/2019 | 5/21/2019 |  | 1570 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-17 04:31 | Seputyte, Lina | 56-F-EU-V-190513-S1OM004 |  | Yes | Y |  |  | Retrofit Completed |  |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P40304 | No | APPL | BXU545395 |  | 3 |  |  | Preference Profile End Use | L3 Pass | 216 |  | TRUE | HNE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete | L3 testing - need access to \\DEFRE1WIN903.AWS.BAXTER.COM=> KSR000009172004; INC000001226663 (workaround) + defect # 216 |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 07/09/2019 | 07/08/2019 |  | 1571 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 04:23 | Joshi, Abhishek N | 56-F-EU-V-190701-S3OM002 |  | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3OMV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P40306 | Yes | APPL |  |  | 999 |  |  | Preference Profile Inventory Commitment | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1572 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P40307 | Yes | APPL |  |  | 3 |  |  | Preference Profile Product Allocations | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 07/10/2019 | 07/08/2019 |  | 1573 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-17 07:21 | Kamatham, Deepika | 56-F-EU-V-190704-S3OM029 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P40315 | No | APPL |  |  | 3 |  |  | Preference Profile Invoice Cycling | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 07/10/2019 | 07/09/2019 |  | 1574 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-17 03:01 | Kamatham, Deepika | 56-F-EU-V-190705-S3OM003 |  | Yes | Y | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4071 | No | APPL |  |  | 1 |  |  | Price Adjustment Type | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | John Whalley | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 22-05-2019 | 20-05-2019 |  | 1575 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-17 04:33 | Seputyte, Lina | 56-F-EU-V-190510-S1OM002 |  | Yes | Y | [6 empty] | 56-F-EU-V-190510-S1OMV02A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P40ITM | No | APPL |  |  | 1 |  |  | Search & Select by Short Item Number | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/21/2019 | 5/20/2019 |  | 1576 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:55 | Chiau, Liesbet | 56-F-EU-V-190514-S1OM001 |  | Yes | Y |  |  | Retrofit completed |  |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P40ITM1 | No | APPL |  |  | 1 |  |  | Item Master Search & Select | L3 Pass |  |  | TRUE | L |  | Order Management | OM | John Whalley | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 19\05\20 | 19\05\20 |  | 1577 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:55 | Chiau, Liesbet | 56-F-EU-V-190516-S1OM002 |  | Yes | Yes | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P40LITM | No | APPL |  |  | 1 |  |  | Search & Select by Second Item Number | L3 Pass |  |  | TRUE | L |  | Order Management | OM | John Whalley | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 19\05\20 | 19\05\20 |  | 1578 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:55 | Chiau, Liesbet | 56-F-EU-V-190516-S1OM001 |  | Yes | Yes | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P41002 | No | APPL |  | 1233005 | 1 |  |  | Unit of Measure Conversions - Item | L3 Not Required |  |  | TRUE | L |  | MDM | MDM | Tom Hoste | L2 Not required | No KT needed. Test in CRP |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 05/20/2019 | 05/20/2019 |  | 1579 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 10:34 | Joshi, Abhishek N |  |  | Yes | Yes |  |  | 56-F-EU-V-190513-S1MD009 |  |  |  | 56-F-EU-V-190513-S1MDV09A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P41280 | Yes | APPL | 12444 BXU547350 |  | 1 |  |  | Lot Master Availability | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | John Whalley | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 5/21/2019 | 5/21/2019 |  | 1580 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-21 07:59 | Vishnubhatla, Mithra | 56-F-EU-V-190513-S1OM003 |  | Yes | Y |  |  | Retrofitted |  |  |  | 56-F-EU-V-190513-S1OMV03A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P42025 | No | APPL | BXU547351 |  | 2 |  |  | Sales Ledger Inquiry | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | John Whalley | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/13/2019 | 6/11/2019 |  | 1581 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 05:27 | Joshi, Abhishek N | 56-F-EU-V-190611-S2OM014 | Inquiry | Yes | Y | [6 empty] | 56-F-EU-V-190611-S2OMV014A,56-F-EU-V-190611-S2OMV014B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P42040 | No | APPL | 1219245 OM117 |  | 3 |  |  | Sales Order Speed Status Update | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/5/2019 | 7/4/2019 |  | 1582 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 06:28 | ANAND, S | 56-F-EU-V-190702-S3OM020 |  | Yes | Y | [6 empty] | 56-F-EU-V-190702-S3OMV020A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4205 | Yes | APPL | 1235608 | 1235888, 1276008 | 2 | 2 |  | Shipment Confirmation 18/9 - 64 bit testing completed | L3 Pass | 165 | Closed | TRUE | HE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 06/19/2019 | 06/17/2019 |  | 1583 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-27 02:11 | Singh, Sunil Kumar | 56-F-EU-V-190612-S2LO074 |  | Yes | Y |  |  |  | KTW6 |  |  | 56-F-EU-V-190612-S2LOV074A, 56-F-EU-V-190612-S2LOV074B, 56-F-EU-V-190612-S2LOV074C | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P42050 | No | APPL | BXU545407 | BXU547014 | 3 |  |  | Credit Check | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | John Whalley | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 07/12/2019 | 07/10/2019 |  | 1584 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 04:35 | Joshi, Abhishek N | 56-F-EU-V-190703-S3OM101 |  | Yes | Y | [6 empty] | 56-F-EU-V-190703-S3OMV101A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P42053 | Yes | APPL |  |  | 3 |  |  | Select Multiple Locations | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/18/2019 | 7/11/2019 |  | 1585 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-22 04:37 | Mughal, Abdul | 56-F-EU-V-190709-S3LO087 |  | Yes | Y |  |  |  | KTW4 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4210 | Yes | APPL | BXU545444 (60558), 1222473 (11402) | 1276496 (60558),1263371 (4099), BXU545241 (11402) | 3 | 3 |  | Sales Order Entry | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Seputyte Lina | L2 Pass / Complete | RC-3007:After rework completed for Def214,release number is appearing in grid detail of customer service inquiry.L2 Passed.Defect 201 - VR01 Not filled. VV-30/07 - Can you please test the object relataed to defect -214 |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 06/07/2019 | 05/20/2019 |  | 1586 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-07-24 05:36 | Singh, Sunil Kumar | 56-F-EU-V-190522-S1OM042 |  | Yes | Y |  |  | BD3N0011 missing in DV920, Processing option already promoted in Sprint0, 8.12 form W4210F and W4210I are now W4210I and W4210J in 9.2 respectively |  |  |  | 56-F-EU-V-190522-S1OM042A-R,56-F-EU-V-190522-S1OM042T-Z, 56-F-EU-V-190522-S1OM042AA - AD | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P421001 | No | APPL |  |  | 5 |  |  | Sales Order Header Reusable Subform | PPD Passed | 208 | Closed | TRUE | HE2E |  | Order Management | OM | Malataesh Ganiger | L2 Pass / Complete | L3 New Defect 208 / RC-1907 -Defect# 145 has been closed from Oracle SR SR 3-20500883091 |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/24/2019 | 6/20/2019 |  | 1587 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-10 08:46 | Bodin, Fatiha | 56-F-EU-V-190624-S2OM001 |  | Yes | Y |  |  | Passed in UAT (PPD) |  |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P421002 | Yes | APPL |  |  | 5 |  |  | Sales Order Detail Reusable Subform | L3 Pass | 208 | Closed | TRUE | HE2E |  | Order Management | OM | Jaisingh Jaiswar | L2 Pass / Complete | L3 New Defect 208 / LRC-1907 -Defect# 145 has been closed from Oracle&nbsp; SR SR 3-20500883091. L3 Testing completed with the pre condition that KITID on order lines should not be equal to Zero. |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 06/24/2019 | 06/10/2019 |  | 1588 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-29 09:11 | Jaiswar, Jaisingh | 56-F-EU-V-190531-S2OM001 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P421004 | Yes | APPL |  |  | 5 |  |  | Sales Order Availability Reusable Subform | L3 Pass | 208 | Closed | TRUE | HE2E |  | Order Management | OM | Jaisingh Jaiswar | L2 Pass / Complete | L3 New Defect 208 / RC-1907 -Defect# 145 has been closed from Oracle SR SR 3-20500883091 |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/2/2019 | 7/1/2019 |  | 1589 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-13 03:45 | Jaiswar, Jaisingh | 56-F-EU-V-190628-S3OM003 |  | Yes | Y | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P421007 | No | APPL |  |  | 5 |  |  | Sales Order Header Reusable Subform | L3 Pass | 208 | Closed | TRUE | HE2E |  | Order Management | OM | Jaisingh Jaiswar | L2 Pass / Complete | RC-1907 -Defect# 145 has been closed from Oracle SR #3-20500883091. L3 Testing completed with the pre condition that KITID on order lines should not be equal to Zero. |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/20/2019 | 6/19/2019 |  | 1590 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-29 09:12 | Jaiswar, Jaisingh | 56-F-EU-V-190612-S2OM024 |  | Yes | Y | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P42101 | Yes | APPL |  |  | 5 |  |  | Sales Order Entry | PPD Passed | 208 | Closed | TRUE | HE2E |  | Order Management | OM | Swagatika Swain | L2 Pass / Complete | L3 New Defect 208 / RC-1907 -Defect# 145 has been closed from Oracle SR# 3-20500883091 |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/28/2019 | 6/24/2019 |  | 1591 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-10 08:46 | Bodin, Fatiha | 56-F-EU-V-190627-S2OM001 |  | Yes | Y |  |  | Passed in UAT (PPD) |  |  |  | 56-F-EU-V-190627-S2OMV01A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P42117 | Yes | APPL | BXU545444 (60558), 1270935 (Global Document) | 1276496 (60558), 1255648 (Global Document) | 2 |  |  | Backorder Release | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Malatesh Ganiger | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 06/20/2019 | 06/11/2019 |  | 1592 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-09 05:34 | Singh, Sunil Kumar | 56-F-EU-V-190513-S2OM001 |  | Yes | Y | [6 empty] | 56-F-EU-V-190513-S2OMV01A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P43070 | Yes | APPL | BXU545405 (9876) | 25921, BXU546472, BXU546469, BXU547849 | 2 |  |  | Held Order Release | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/19/2019 | 6/17/2019 |  | 1593 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 03:43 | Vishnubhatla, Mithra | 56-F-EU-V-190618-S2OM037 |  | Yes | Y | [6 empty] | 56-F-EU-V-190618-S2OMV037A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4530 | No | APPL |  |  | 999 |  |  | Accelerated Pricing Resolution Engine Workbench | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1594 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4550 | No | APPL |  |  | 999 |  |  | Basket Master | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1595 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P47010 | Yes | APPL |  |  | 2 |  |  | Inbound EDI Order Inquiry | L3 Pass |  |  | TRUE | HE2E |  | EDI Order Management | eCommerce | Linda Kenny | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 06/14/2019 | 06/12/2019 |  | 1596 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:07 | Chiau, Liesbet |  | Inquiry / Inbound | Yes | Y |  |  | No Retrofit Required | KTEDI2 |  |  | 56-F-EU-V-190611-S2ED002 | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P47040 | No | APPL | BXU547420 |  | 2 |  | CRP | Inbound EDI Invoice Inquiry | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/17/2019 | 6/14/2019 |  | 1597 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 09:04 | Joshi, Abhishek N | 56-F-EU-V-190614-S2FI041 | Inquiry / Inbound | Yes | Y | [6 empty] | 56-F-EU-V-190614-S2FIV041A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P47046 | No | APPL | BXU545845 | BXU546784 | 2 |  |  | Outbound EDI Invoice Inquiry | L3 Pass |  |  | TRUE | HE2E |  | EDI Order Management | eCommerce | Linda Kenny | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/12/2019 | 6/12/2019 |  | 1598 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 07:49 | Joshi, Abhishek N | 56-F-EU-V-190611-S2OM022 | Inquiry / Outbound | Yes | Y |  |  |  | KTEDI7 |  |  | 56-F-EU-V-190611-S2OMV022A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P47070 | Yes | APPL | 1267636 (19294), BXU545170 (20682) | 1267640, BXU544769 | 2 |  |  | Inbound EDI Receiving Advice Inquiry | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/12/2019 | 6/11/2019 |  | 1599 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 07:37 | Singh, Sunil Kumar | 56-F-EU-V-190612-S2LO001 | Inquiry / Inbound | Yes | Y |  |  |  | KTW6 |  |  | 56-F-EU-V-190612-S2LO001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5540073 | No | APPL |  |  | 999 |  |  | Preference Hierarchy - Baxter | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1600 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P554106 | No | APPL |  |  | 999 |  |  | Baxter Base Price Revisions | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1601 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Revision | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P554106C | No | APPL |  |  | 999 |  |  | Work with Price Conversion Table | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1602 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5600112 | No | APPL |  |  | 3 |  |  | Swisspost Interface Recovery Application | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/18/2019 | 7/18/2019 |  | 1603 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-17 07:11 | weber, scott | 56-F-EU-V-190715-S3LO094 | Interface | Yes | Y |  |  |  | KTT4 |  |  | 56-F-EU-V-190715-S3LOV094A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5600122 | No | APPL | BXU545389 |  | 3 |  |  | Report Column Sequencing Application | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Jaisingh Jaiswar | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saieja |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/3/2019 | 7/4/2019 |  | 1604 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 02:10 | Joshi, Abhishek N | 56-F-EU-V-190701-S3OM019 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3OMV19A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5600130 | No | APPL |  |  | 999 |  |  | Preference Upload Control Data Maintenance | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1605 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Maintenance / Upload | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5640073 | No | APPL | BXU545378, BXU545410, BXU545792 | BXU546839, BXU547606 | 3 | 3 |  | Baxter Preference Hierarchy | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete | L3 - waiting for P564072 UT promotion |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1606 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 04:39 | Joshi, Abhishek N | 56-F-EU-V-190620-S2OM039 |  | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564016 | No | APPL | BXU545385, BXU545409 | BXU547611 | 3 |  |  | Work with Baxter Print Messages by Effective Date | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/4/2019 | 7/3/2019 |  | 1607 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 06:13 | Joshi, Abhishek N | 56-F-EU-V-190704-S3OM025 | Printer | Yes | Y | [6 empty] | 56-F-EU-V-190704-S3OMV25A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56403UM | No | APPL | BXU545800 |  | 4 |  |  | Buying Group Upload Maintenance | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete | L3 - waiting for R56403UP to be promoted to UT |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/22/2019 | 7/22/2019 |  | 1608 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 04:18 | Joshi, Abhishek N | 56-F-EU-V-190722-S4OM006 | Maintenance / Upload | Yes | Y | [6 empty] | 56-F-EU-V-190722-S4OMV006A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564072 | No | APPL | BXU545295 | BXU546835, BXU546826, BXU546843, BXU545386, BXU545394 | 2 |  |  | Baxter Price Adjustment Detail Revisions | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1609 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 03:05 | Joshi, Abhishek N | 56-F-EU-V-190612-S2OM002 | Revision | Yes | Y | [6 empty] | 56-F-EU-V-190612-S2OMV002A, 56-F-EU-V-190612-S2OMV002B, 56-F-EU-V-190612-S2OMV002C, 56-F-EU-V-190612-S2OMV002D, 56-F-EU-V-190612-S2OMV002E | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5640722 | No | APPL | BXU545285 | BXU547613 | 2 |  |  | Adjustment Type Quantity Breaks Iframe | L3 Not Required |  |  | TRUE | HNE2E |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte | L2 Not required | 0705 RK: As per confirmation mail from Piet ,marked L2 not rquired. No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1610 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 05:37 | Joshi, Abhishek N | 56-F-EU-V-190612-S2OM004 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564072F | No | APPL | BXU545285, BXU545272 | BXU547613, BXU547620 | 5 |  |  | IFrame Price Adjustment Detail Revisions | L3 Not Required |  |  | TRUE | HNE2E |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 8/22/2019 | 8/21/2019 |  | 1611 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-30 05:07 | Joshi, Abhishek N | 56-F-EU-V-190821-S5OM018 | Revision | Yes | Y | [6 empty] | 56-F-EU-V-190821-S5OMV018A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564073 | No | APPL | BXU545378 | BXU546839 | 3 |  |  | Baxter Free Goods Revisions | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/4/2019 | 7/3/2019 |  | 1612 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 02:32 | Joshi, Abhishek N | 56-F-EU-V-190703-S3OM024 | Revision | Yes | Y | [6 empty] | 56-F-EU-V-190703-S3OMV024A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564074 | No | APPL | BXU545272 | BXU547620 | 2 |  |  | Check Price and Availability iFrame | L3 Not Required |  |  | TRUE | HNE2E |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1613 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-30 05:07 | Joshi, Abhishek N | 56-F-EU-V-190612-S2OM003 |  | Yes | Y | [6 empty] | 56-F-EU-V-190612-S2OMV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564106 | No | APPL | 1260383 (18020) | 18020 | 1 |  |  | Price Protocol for Russia | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 19\05\22 | 19\05\22 |  | 1614 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-20 06:33 | ANAND, S | 56-F-EU-V-190516-S1OM003 |  | Yes | Yes | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642009 | No | APPL | 1242579 (17919) |  | 3 |  |  | Proforma Invoice Nordics | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saieja |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/4/2019 | 7/4/2019 |  | 1615 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-20 06:38 | ANAND, S | 56-F-EU-V-190703-S3OM023 |  | Yes | Y | [6 empty] | 56-F-EU-V-190703-S3OMV023A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642011 | Yes | APPL | 1248075 20207 |  | 4 |  |  | Process Master Compounding Orders | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 07/23/2019 | 07/22/2019 |  | 1616 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 09:53 | Vishnubhatla, Mithra | 56-F-EU-V-190722-S4OM002 |  | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642025 | No | APPL | 1235544 (15780) | 15780 | 2 |  |  | Sales Ledger Inquiry Iframe | L3 Not Required |  |  | TRUE | HNE2E |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/26/2019 | 6/25/2019 |  | 1617 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-20 07:46 | ANAND, S | 56-F-EU-V-190610-S2OM038 | Inquiry | Yes | Yes | [6 empty] | 56-F-EU-V-190610-S2OMV038A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642029 | No | APPL |  |  | 999 |  |  | Work with Address Information | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1618 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642041 | No | APPL | BXU545380 | BXU546851 | 6 |  |  | CIG Number Update JDE | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 9/3/2019 | 8/30/2019 |  | 1619 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 02:31 | Joshi, Abhishek N | 56-F-EU-V-190827-S6OM001 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6OMV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642050 | No | APPL | BXU545283 | BXU547532 | 2 |  |  | Credit Check - IFrame | L3 Not Required |  |  | TRUE | HNE2E |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/26/2019 | 6/26/2019 |  | 1620 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 04:49 | Joshi, Abhishek N | 56-F-EU-V-190619-S2OM038 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190619-S2OMV038A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642052 | No | APPL | BXU545401 |  | 2 |  |  | Sales Order Text | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1621 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 02:29 | Joshi, Abhishek N | 56-F-EU-V-190625-S2OM001 | Text | Yes | Yes | [6 empty] | 56-F-EU-V-190625-S2OMV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642058 | No | APPL |  | BXU547736 | 2 |  |  | MASS DEFAULT TEXT MESSAGES UPLOAD | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/24/2019 | 6/21/2019 |  | 1622 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-20 04:35 | Joshi, Abhishek N | 56-F-EU-V-190610-S2OM032 | Upload / Text | Yes | [7 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642110 | No | APPL |  |  | 3 |  |  | Contract Master Application | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/5/2019 | 7/5/2019 |  | 1623 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-18 02:15 | Kamatham, Deepika | 56-F-EU-V-190705-S3OM001 |  | Yes | Y | [6 empty] | 56-F-EU-V-190705-S3OMV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642111 | No | APPL |  |  | 3 |  |  | Contract Ledger Application | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 7/5/2019 | 7/4/2019 |  | 1624 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-22 05:05 | Kamatham, Deepika | 56-F-EU-V-190701-S3OM006 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564211A | No | APPL |  |  | 999 |  |  | Maintain RECADV Tag File to F4211 | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1625 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Maintenance | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564211S | No | APPL | BXU545300 |  | 2 |  |  | Sales Order Detail Speed Update | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | John Whalley | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1626 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 02:21 | Joshi, Abhishek N | 56-F-EU-V-190620-S2OM014 |  | Yes | [7 empty] | 56-F-EU-V-190620-S2OMV014A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564217I | No | APPL | BXU545382, BXU545396, BXU545296, BXU545391, BXU535601, BXU545096 | BXU546246 | 6 |  |  | Backorder Release - IFRAME | L3 Not Required |  |  | FALSE | HNE2E |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 9/13/2019 | 9/12/2019 |  | 1627 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 02:28 | Joshi, Abhishek N | 56-F-EU-V-190911-S6OM013 |  | Yes | [7 empty] | 56-F-EU-V-190911-S6OMV013A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564217U | No | APPL | BXU545382, BXU545396 |  | 2 |  |  | Uncommitted Order Release | L3 Pass | 154 | Closed | TRUE | HNE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete | RC:23/07/19 - After Rework completed L2 passed for defect# 154 .L3 - defect #154 |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 2/07/2018 | 27/06/2019 |  | 1628 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 02:19 | Joshi, Abhishek N | 56-F-EU-V-190613-S2OM029 |  | Yes | Y | [6 empty] | 56-F-EU-V-190613-S2OMV029A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564238 | No | APPL | BXU545419 |  | 2 |  |  | Agreements Quantities Maintenance | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri | 6/21/2019 | 6/20/2019 |  | 1629 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 04:31 | Joshi, Abhishek N | 56-F-EU-V-190614-S2OM032 | Maintenance | Yes | Y | [6 empty] | 56-F-EU-V-190614-S2OMV32A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642S02 | No | APPL |  |  | 999 |  |  | BX Sales Order Header Check | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1630 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5645001 | No | APPL | BXU545388 |  | 2 |  |  | Enquire on Buying Groups | L3 Pass |  |  | TRUE | L |  | Order Management | OM | John Whalley | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:54 | Kishi, Sayuri |  |  |  | 1631 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 02:15 | Joshi, Abhishek N | 56-F-EU-V-190620-S2OM013 |  | Yes | [7 empty] | 56-F-EU-V-190620-S2OMV013A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5645002 | No | APPL | BXU545444 (60558) | 1276496 (60558) | 3 | 3 |  | Additional Charges - Orders to be repriced | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete | RC -05/07 Defect # 148 remain open till oracle case(SR# SR 3-20477322981) sorted out |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 20/06/2019 | 20/06/2019 |  | 1632 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-09 05:28 | Singh, Sunil Kumar | 56-F-EU-V-190613-S2OM028 |  | Yes | Y | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5645003 | No | APPL | BXU545406 |  | 1 |  |  | Enquire on Customer Groups | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 5/22/2019 | 5/22/2019 |  | 1633 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 02:13 | Joshi, Abhishek N | 56-F-EU-V-190515-S1OM013 |  | Yes | [7 empty] | 56-F-EU-V-190515-S1OM013A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5645004 | No | APPL |  |  | 2 |  |  | Additional Charges setup table | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1634 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:08 | Chiau, Liesbet | 56-F-EU-V-190614-S2OM034 | Setup | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5645501 | No | APPL | BXU545286 |  | 2 |  |  | Pricing Workbench | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1635 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 05:51 | Joshi, Abhishek N | 56-F-EU-V-190619-S2OM012 |  | Yes | [7 empty] | 56-F-EU-V-190619-S2OMV012A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5645550 | No | APPL | BXU545286 | BXU547673 | 4 |  |  | F4072 Global Update Engine | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | John Whalley | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/23/2019 | 7/22/2019 |  | 1636 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 05:51 | Joshi, Abhishek N | 56-F-EU-V-190722-S4OM011 |  | Yes | Y | [6 empty] | 56-F-EU-V-190722-S4OMV011A, 56-F-EU-V-190722-S4OMV011B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5647401 | No | APPL |  |  | 4 |  |  | Eurydice Setup's Maintenance | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Mike Tarpey | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/23/2019 | 7/22/2019 |  | 1637 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-26 05:24 | Mike, Tarpey | 56-F-EU-V-190722-S4OM012 | Maintenance / Setup | Yes | Y | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5647430 | No | APPL |  |  | 4 |  |  | Datagon Pricing Interface Setup Application | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Mike Tarpey | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/23/2019 | 7/22/2019 |  | 1638 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-26 05:25 | Mike, Tarpey | 56-F-EU-V-190722-S4OM007 | Setup / Interface | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564749 | No | APPL |  | BXU546337 | 4 |  |  | Maintenance Application over F564749Z | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/07/2019 | 8/06/2019 |  | 1639 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-22 03:51 | Joshi, Abhishek N | 56-F-EU-V-190806-S4LO076 | Maintenance | Yes | Y |  |  |  | various |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5647499 | No | APPL |  |  | 4 |  |  | Datagon Pricing Interface Ledger Application | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Mike Tarpey | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 07/24/2019 | 07/23/2019 |  | 1640 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-26 05:25 | Mike, Tarpey | 56-F-EU-V-190722-S4OM013 | Interface | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56474Z1 | No | APPL |  |  | 4 |  |  | Eurydice Buying Group Table Maintenance | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Mike Tarpey | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/24/2019 | 7/23/2019 |  | 1641 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-26 05:26 | Mike, Tarpey | 56-F-EU-V-190723-S4OM015 | Maintenance | Yes | Y | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56474Z2 | No | APPL | BXU545441 |  | 4 |  |  | Eurydice Pricing Interface Maintenance Application | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Mike Tarpey | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 07/24/2019 | 07/23/2019 |  | 1642 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 08:53 | Joshi, Abhishek N | 56-F-EU-V-190723-S4OM014 | Maintenance / Interface | Yes | Yes | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56474Z3 | No | APPL |  |  | 4 |  |  | Datagon Pricing Interface Maintenance Application | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Mike Tarpey | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/24/2019 | 7/23/2019 |  | 1643 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-26 05:27 | Mike, Tarpey | 56-F-EU-V-190722-S4OM008 | Maintenance / Interface | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56BIP03 | No | APPL | BXU545844 | BXU546787 | 6 |  |  | IXOS Interest Claims | L3 Pass |  |  | TRUE | MNE2E |  | IXOS Archive | eCommerce | Linda Kenny | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/29/2019 | 7/28/2019 |  | 1644 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 07:47 | Joshi, Abhishek N | 56-F-EU-V-190731-S4EC003 |  | Yes |  |  |  |  | NoKT |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56EUV07 | No | APPL | BXU547482 |  | 1 |  | CRP | VAT - Invoice Print Messages byTax Rate Area cd TXA1 | L3 Pass |  |  | TRUE | HE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/3/2019 | 6/3/2019 |  | 1645 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 23:53 | Joshi, Abhishek N | 56-F-EU-V-190531-S1FI191 | Printer | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56ISTS | No | APPL | BXU545420 |  | 3 |  |  | Maintain Invoice Additional Documentation Status | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 07/05/2019 | 07/04/2019 |  | 1646 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 02:12 | Joshi, Abhishek N | 56-F-EU-V-190705-S3OM002 | Maintenance | Yes | Y | [6 empty] | 56-F-EU-V-190705-S3OMV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56LOCN | No | APPL | 1251176 (23915), 1277534 (80724) | 23915 | 2 |  |  | EMEA Location Search and Select | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | John Whalley | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 19/06/2019 | 19/06/2019 |  | 1647 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 08:15 | ANAND, S | 56-F-EU-V-190613-S2OM027 |  | Yes | Y | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5840073 | No | APPL | BXU549677 |  | 2 |  |  | Preference Hierarchy - Baxter | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/18/2019 | 6/18/2019 |  | 1648 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 04:57 | Joshi, Abhishek N | 56-F-EU-V-190611-S2OM019 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5840311 | No | APPL | BXU545792 |  | 2 |  |  | Preference Profile Price Code 1 | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/18/2019 | 6/18/2019 |  | 1649 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 04:39 | Joshi, Abhishek N | 56-F-EU-V-190613-S2OM030 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5842025 | No | APPL | BXU550541 | BXU547680 | 2 |  |  | Sales Ledger Message Box | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | John Whalley | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/18/2019 | 6/18/2019 |  | 1650 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-20 06:14 | Joshi, Abhishek N | 56-F-EU-V-190613-S2OM025 |  | Yes | Y |  |  | Calling from P4210 |  |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5874300 | No | APPL | BXU549789 | BXU547696 | 3 |  |  | Change Inv/Legal Doc Date and Re-Print Original docs | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/05/2019 | 7/04/2019 |  | 1651 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-27 05:25 | Joshi, Abhishek N | 56-F-EU-V-190704-S3OM027 | Printer | Yes | Y |  |  | Retrofit not required |  |  |  | 56-F-EU-V-190704-S3OMV027A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900018 | Yes | APPL |  |  | 1 |  |  | Export Drop Ship Orders | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 5/22/2019 | 5/22/2019 |  | 1652 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-17 04:59 | Seputyte, Lina | 56-F-EU-V-190517-S1OM032 | Export | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900041 | No | APPL |  |  | 2 |  |  | Sales Order Line Error Inquiry | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete | L3 - JAS error - Defect created - 26/06 defect closed |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/17/2019 | 6/17/2019 |  | 1653 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:08 | Chiau, Liesbet | 56-F-EU-V-190617-S2OM001 | Error/Inquiry | Yes | Y | [6 empty] | 56-F-EU-V-190617-S2OM001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900060 | No | APPL |  |  | 999 |  |  | Order Address | Obsolete |  |  | TRUE | L |  | Order Management | OM | Genevieve Deveen | L2 Not required | No KT, testing to be done in CRP / UAT / OQ -- L3 - awaiting P4210 UT promotion |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 5/22/2019 | 5/22/2019 |  | 1654 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet | 56-F-EU-V-190514-S1OM008 |  | No | Yes |  |  | done. Index verified. No Proc Option exists. L1 not req as this is stand alone sub form, VV-03/07 - Obsoleted as per reqeust from Lina |  |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900112 | No | APPL |  |  | 2 |  |  | Sales Order Line Error Inquiry | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 19\06\17 | 19\06\14 |  | 1655 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:08 | Chiau, Liesbet | 56-F-EU-V-190612-S2MO071 | Error/Inquiry | Yes | Y |  |  | No retrofit required |  |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900114 | No | APPL |  |  | 1 |  |  | Additional Error Management Form | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 5/22/2019 | 5/22/2019 |  | 1656 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:55 | Chiau, Liesbet | 56-F-EU-V-190514-S1OM009 | Error | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900116 | No | APPL |  |  | 2 |  |  | Additional Sales Order Line Error Revision | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/17/2019 | 6/17/2019 |  | 1657 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:08 | Chiau, Liesbet | 56-F-EU-V-190611-S2OM018 | Error / Revision | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900117 | No | APPL |  |  | 2 | 2 |  | Invoice Hold | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 5/22/2019 | 5/22/2019 |  | 1658 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:08 | Chiau, Liesbet | 56-F-EU-V-190515-S1OM018 |  | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900123 | No | APPL |  |  | 3 |  |  | Sales Order Upload Z-File Application | L3 Pass |  |  | TRUE | L |  | Order Management | OM | John Whalley | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/14/2019 | 6/14/2019 |  | 1659 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-17 08:17 | Choudhry, Rashmi | 56-F-EU-V-190611-S2OM005 | Upload | Yes | Y | [6 empty] | 56-F-EU-V-190611-S2OMV05A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900137 | Yes | APPL |  |  | 1 |  |  | Direct Ship Export Order | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 5/22/2019 | 5/22/2019 |  | 1660 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:55 | Chiau, Liesbet | 56-F-EU-V-190520-S1OM035 | Export | Yes | Y |  |  | No Retrofit Required |  |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900140 | No | APPL |  |  | 1 |  |  | Order Address Revisions | L3 Not Required |  |  | TRUE | L |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 5/22/2019 | 5/22/2019 |  | 1661 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:55 | Chiau, Liesbet | 56-F-EU-V-190516-S1OM026 | Revision | Yes | Yes |  |  | No Retrofit Required |  |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R4201P | Yes | UBE |  |  | 999 |  |  | Purge Sales Order Header (F4201) | Obsolete |  |  | TRUE | L |  | Purge | ARO | Cosmin Mutiu / Terry Greenard | L2 Not required | No KT, as Tested by user only in ICT |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/1/2019 | 6/28/2019 |  | 1662 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-14 04:05 | Greenard, Terry | 56-F-EU-V-190701-S3ARO001 |  | Yes | Y |  |  | To be tested in CRP |  |  |  | 56-F-EU-V-190701-S3AROV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R42118 | No | UBE |  |  | 3 |  |  | Backorder Release and Report | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Jaisingh Jaiswar | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 07/08/2019 | 07/05/2019 |  | 1663 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-24 10:05 | Jaiswar, Jaisingh | 56-F-EU-V-190704-S3OM078 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190704-S3OMV078A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R42565 | No | UBE | BXU545224 (R42565), BXU545293 | BXU545219 | 3 |  |  | Print Invoices | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | John Whalley | L2 Pass / Complete | RC:0508 - L2 Passed for R42565 |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 07/18/2019 | 07/09/2019 |  | 1664 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 04:25 | Joshi, Abhishek N | 56-F-EU-V-190709-S3OM032 | Printer |  | Y | [6 empty] | 6-F-EU-V-190709-S3OMV32A to 56-F-EU-V-190709-S3OMV32Z,56-F-EU-V-190709-S3OMV32AA to 56-F-EU-V-190709-S3OMV32AZ and 56-F-EU-V-190709-S3OMV32BA to 56-F-EU-V-190709-S3OMV32BN | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R42995 | No | UBE | 1255068, BXU545392 | 26047 | 3 |  |  | Repost Active Sales Orders | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/10/2019 | 7/09/2019 |  | 1665 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 04:52 | Joshi, Abhishek N | 56-F-EU-V-190709-S3OM103 |  | Yes | Y | [6 empty] | 56-F-EU-V-190709-S3OMV103A,56-F-EU-V-190709-S3OMV103B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R42996 | Yes | UBE | 1242053 (18531) | BXU547464 (18531) | 999 |  |  | Purge Detail to History | Obsolete |  |  | TRUE | L |  | Purge | ARO | Cosmin Mutiu / Terry Greenard | L2 Not required | No KT, as Tested by user only in ICT |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 07/12/2019 | 07/11/2019 |  | 1666 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-14 08:10 | ANAND, S | 56-F-EU-V-190705-S3AR117 |  | Yes | Y |  |  | To be tested in CRP |  |  |  | 56-F-EU-V-190705-S3ARV117A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R47031 | No | UBE |  | BXU547567 | 1 |  |  | EDI Shipping Notice Edit/Create | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 5/23/2019 | 5/23/2019 |  | 1667 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 09:18 | Joshi, Abhishek N | 56-F-EU-V-190522-S1OM043 |  | Yes | Y |  |  | EDI - AIP Connections | KTW5 |  |  | 56-F-EU-V-190522-S1OMV43A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R47032 | No | UBE | 1235429 13892 | BXU546085 | 1 |  |  | EDI Advanced Ship Notice Extraction | L3 Pass |  |  | TRUE | HE2E |  | EDI Order Management | eCommerce | Linda Kenny | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 5/24/2019 | 5/23/2019 |  | 1668 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-21 06:42 | Vishnubhatla, Mithra | 56-F-EU-V-190515-S1ED001 |  | Yes | Yes |  |  |  | KTEDI6 |  |  | 56-F-EU-V-190515-S1ED001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R47121 | No | UBE |  | BXU546023 | 1 |  |  | EDI Product Activity Data Edit/Create | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 05/31/2019 | 05/31/2019 |  | 1669 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 09:23 | Joshi, Abhishek N | 56-F-EU-V-190531-S1OM046 |  |  | Y |  |  | Retrofit not required. Object is removed from project. Versions are retrofitted. | KTTS5 |  |  | 56-F-EU-V-190531-S1OMV046A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5547121 | No | UBE | 1235434 (15746) | 1236016 (15746) | 3 |  |  | EDI Product Activity Data Edit/Create | L3 Pass |  |  | TRUE | M |  | Quality | Logistics | Miruna Danes | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/8/2019 | 7/5/2019 |  | 1670 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 06:22 | ANAND, S | 56-F-EU-V-190705-S3OM081 |  | Yes | Y | [6 empty] | 56-F-EU-V-190705-S3OMV81A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600034 | No | UBE | 1251756, BXU545289, BXU545384, BXU545389 | 22888, 1251758 | 1 |  |  | Backorder Report - CSV | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 5/24/2019 | 5/24/2019 |  | 1671 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 02:10 | Joshi, Abhishek N | 56-F-EU-V-190516-S1OM028 | Report | Yes | Y |  |  | No retrofit required |  |  |  | 56-F-EU-V-190516-S1OMV28A, 56-F-EU-V-190516-S1OMV28B, 56-F-EU-V-190516-S1OMV28C | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600039 | No | UBE | 1243631 (15932), BXU545828 |  | 2 |  |  | Update Sourcing Branch Plant Preference - Non Stock Lines | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/11/2019 | 6/11/2019 |  | 1672 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 10:46 | Joshi, Abhishek N | 56-F-EU-V-190611-S2OM015 |  | Yes | Y | [6 empty] | 56-F-EU-V-190611-S2OMV015A,56-F-EU-V-190611-S2OMV015A,56-F-EU-V-190611-S2OMV015C | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600098 | No | UBE | BXU545379 |  | 1 |  |  | Consignment Orders Report | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 5/24/2019 | 5/23/2019 |  | 1673 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 01:59 | Joshi, Abhishek N | 56-F-EU-V-190521-S1OM037 | Report | Yes | Y |  |  | Retrofit Not Required |  |  |  | 56-F-EU-V-190521-S1OMV37A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560018Z1 | No | UBE |  | BXU546886 | 4 | 4 |  | Generate Customs Data for Sales | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 08/07/2019 | 08/06/2019 |  | 1674 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 04:40 | Joshi, Abhishek N | 56-F-EU-V-190709-S3LO084 |  | Yes | Y |  |  |  | various2 |  |  | 56-F-EU-V-190709-S3LOV084A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560045 | No | UBE | BXU545412 |  | 1 |  |  | Details of Patient Charges Report | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 5/24/2019 | 5/24/2019 |  | 1675 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 01:57 | Joshi, Abhishek N | 56-F-EU-V-190517-S1OM031 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190517-S1OMV031A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5618534 | No | UBE |  |  | 1 |  |  | Sales Process Tracing by Customer-With Reason Code | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 24/05/2019 | 24/05/2019 |  | 1676 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:55 | Chiau, Liesbet | 56-F-EU-V-190515-S1OM014 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190515-S1OMV14A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5618571 | No | UBE |  |  | 1 |  |  | Sales Order With Route Code | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 5/23/2019 | 5/23/2019 |  | 1677 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:55 | Chiau, Liesbet | 56-F-EU-V-190515-S1OM012 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190515-S1OMV012A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5620280 | No | UBE | BXU545270 |  | 1 |  |  | Monthly Sales by Patient | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 23/05/2019 | 23/05/2019 |  | 1678 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 01:55 | Joshi, Abhishek N | 56-F-EU-V-190515-S1OM017 |  | Yes | Y | [6 empty] | 56-F-EU-V-190515-S1OMV17A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5624346 | No | UBE | BXU545806 |  | 2 |  |  | Sales Proces Tracing by Product-Russia | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/14/2019 | 6/14/2019 |  | 1679 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 10:54 | Joshi, Abhishek N | 56-F-EU-V-190611-S2OM020 |  | Yes | Yes |  |  | Related PO T58PL016 |  |  |  | 56-F-EU-V-190611-S2OMV020A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5640304M | No | UBE | BXU545798 |  | 4 | 4 |  | Buying Group Maintenance | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 23-05-19 | 23-05-19 |  | 1680 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 01:52 | Joshi, Abhishek N | 56-F-EU-V-190515-S1OM015 | Maintenance | Yes | Y | [6 empty] | 56-F-EU-V-190515-S1OMV15A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5640722 | No | UBE | BXU545802 |  | 1 |  |  | Advanced Pricing Download | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 5/23/2019 | 5/23/2019 |  | 1681 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 01:51 | Joshi, Abhishek N | 56-F-EU-V-190514-S1OM005 | Download | Yes | Yes |  |  | No Retrofit Required |  |  |  | 56-F-EU-V-190514-S1OMV005A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564072E | No | UBE | BXU545410 | BXU546835 | 1 |  |  | Extend Contract Price | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 5/23/2019 | 5/23/2019 |  | 1682 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 02:40 | Joshi, Abhishek N | 56-F-EU-V-190516-S1OM004 |  | Yes | Y |  |  | Retrofit not required |  |  |  | 56-F-EU-V-190516-S1OMV04A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564072X | No | UBE |  | BXU546228, BXU545813 | 1 |  |  | Price Expiration Report | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 5/23/2019 | 5/23/2019 |  | 1683 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 01:49 | Joshi, Abhishek N | 56-F-EU-V-190515-S1OM016 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190515-S1OMV16A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642003 | No | UBE | BXU545408 | BXU547699 | 1 |  |  | MOH Tender Report for Saudi | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 5/23/2019 | 5/23/2019 |  | 1684 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 05:52 | Joshi, Abhishek N | 56-F-EU-V-190517-S1OM033 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190517-S1OMV33A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564201RC | No | UBE | BXU545267 |  | 2 |  |  | Reason code copy from sales order header to detail | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | John Whalley | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 06/14/2019 | 06/14/2019 |  | 1685 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 01:45 | Joshi, Abhishek N | 56-F-EU-V-190611-S2OM021 |  | Yes | [7 empty] | 56-F-EU-V-190611-S2OMV21A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642024 | No | UBE | BXU545273 |  | 1 |  |  | Reset Rebate Summary by MSD | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 5/23/2019 | 5/23/2019 |  | 1686 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 01:43 | Joshi, Abhishek N | 56-F-EU-V-190514-S1OM023 |  | Yes | Yes |  |  | done. Index verified. L1 done. |  |  |  | 56-F-EU-V-190515-S1OMV023A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642026 | No | UBE | BXU545273 |  | 2 |  |  | Order Hold UBE | L3 Pass | 127 | Closed | TRUE | L |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/13/19 | 6/13/19 |  | 1687 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 01:43 | Joshi, Abhishek N | 56-F-EU-V-190610-S2OM009 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190610-S2OMV09A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642049 | No | UBE | 1264937 | 9247 | 4 |  |  | Compounding Mass Order Line Cancellation | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/25/2019 | 7/24/2019 |  | 1688 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-28 06:02 | Vishnubhatla, Mithra | 56-F-EU-V-190723-S4OM016 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190723-S4OMV016A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642055 | Yes | UBE | 1277534 (80724) | 80724 | 4 |  |  | MILD Process Second Stage Order Creation | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/25/2019 | 7/24/2019 |  | 1689 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 10:03 | ANAND, S | 56-F-EU-V-190724-S4OM018 |  | Yes | Y | [6 empty] | 56-F-EU-V-190724-S4OMV018A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642058 | No | UBE |  |  | 2 | 2 |  | DEFAULT TEXT MESSAGES UPLOAD PROCESSOR UBE | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 5/23/2019 | 5/23/2019 |  | 1690 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:08 | Chiau, Liesbet | 56-F-EU-V-190515-S1OM020 | Upload / Text | Yes | Y | [6 empty] | 56-F-EU-V-190515-S1OMV020A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642110 | No | UBE |  |  | 3 |  |  | PPT invoices debits and credits processing | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/8/2019 | 7/5/2019 |  | 1691 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-18 02:29 | Kamatham, Deepika | 56-F-EU-V-190704-S3OM079 |  | Yes | Y | [6 empty] | 56-F-EU-V-190704-S3OMV79A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642116 | No | UBE | BXU545822 |  | 3 |  |  | Set Local Print Flag - F4211 | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 07/08/2019 | 07/05/2019 |  | 1692 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 01:42 | Joshi, Abhishek N | 56-F-EU-V-190701-S3OM018 | Printer | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3OMV018A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564211Q | No | UBE | BXU545298, BXU545801, BXU545827 |  | 3 |  |  | Price Protocol for Russia | L3 Pass | 246 |  | TRUE | HE2E |  | Order Management | OM | Jaisingh Jaiswar | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | 8/8/2019 - BIP is mapped to the constants with Russian script, So passing the code Review. Defect#246 created. | Devi Krishnan |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/9/2019 | 7/8/2019 |  | 1693 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 01:39 | Joshi, Abhishek N | 56-F-EU-V-190516-S1OM025 |  | Yes | Yes |  |  | Retrofitted the objects as it was unable to generate the XML when № was present in the constants.Hence removed № Character from the Constants in VO |  |  |  | 56-F-EU-V-190516-S1OM025A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642120 | No | UBE |  |  | 3 |  |  | PPT Service report processing | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/9/2019 | 7/8/2019 |  | 1694 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-18 05:01 | Kamatham, Deepika | 56-F-EU-V-190628-S3OM004 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190628-S3OMV04A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642130 | No | UBE |  |  | 3 |  |  | PPT Depreciation processing | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/9/2019 | 7/8/2019 |  | 1695 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-22 05:26 | Kamatham, Deepika | 56-F-EU-V-190708-S3OM083 |  | Yes | Y | [6 empty] | 56-F-EU-V-190708-S3OMV083A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642140 | No | UBE |  |  | 3 |  |  | PPT Spare Parts Direct Shipment processing | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/10/2019 | 7/10/2019 |  | 1696 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-23 03:33 | Kamatham, Deepika | 56-F-EU-V-190701-S3OM005 |  | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3OMV005A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642277 | No | UBE | BXU545266 |  | 1 |  |  | Custom UBE for Payment Term Update | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 5/23/2019 | 5/23/2019 |  | 1697 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 01:32 | Joshi, Abhishek N | 56-F-EU-V-190520-S1OM034 |  | Yes | Y |  |  | Retrofit Not Required |  |  |  | 56-F-EU-V-190520-S1OMV34A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642565CO | No | UBE | BXU545794 |  | 3 |  |  | BAXTER Invoice Consolidation Pre-Processor | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete | L3 - waiting for R42565 |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/15/2019 | 7/08/2019 |  | 1698 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 10:58 | Joshi, Abhishek N | 56-F-EU-V-190710-S3OM106 |  | Yes | Y | [6 empty] | 56-F-EU-V-190710-S3OMV106A--to--56-F-EU-V-190710-S3OMV106Z,56-F-EU-V-190710-S3OMV106AA-to--56-F-EU-V-190710-S3OMV106AN | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642565FX | No | UBE | BXU549922 |  | 3 |  |  | Print Invoices - EUFX | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | John Whalley | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/10/2019 | 7/09/2019 |  | 1699 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-30 05:13 | Joshi, Abhishek N | 56-F-EU-V-190709-S3OM104 | Printer | Yes | Yes | [6 empty] | 56-F-EU-V-190709-S3OMV104A,56-F-EU-V-190709-S3OMV104B,56-F-EU-V-190709-S3OMV104C,56-F-EU-V-190709-S3OMV104D,56-F-EU-V-190709-S3OMV104E | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642997 | No | UBE | BXU545803 |  | 2 |  |  | Generate Replacement Order Lines | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/13/2019 | 6/13/2019 |  | 1700 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 01:27 | Joshi, Abhishek N | 56-F-EU-V-190610-S2OM006 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190610-S2OMV006A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5645001 | No | UBE |  |  | 4 |  |  | Additional Charges - Orders to be repriced | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/25/2019 | 7/24/2019 |  | 1701 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-05 02:12 | Deveen, Genevive | 56-F-EU-V-190725-S4OM019 |  | Yes | Y | [6 empty] | 56-F-EU-V-190725-S4OMV019A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5645015 | No | UBE |  |  | 4 |  |  | Additional Charges consolidation UBE | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/26/2019 | 7/25/2019 |  | 1702 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-31 08:55 | Deveen, Genevive | 56-F-EU-V-190723-S4OM017 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190723-S4OMV017A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649700 | No | UBE | BXU545808 |  | 3 |  |  | Baxter Cycle Billing Program | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/11/2019 | 7/10/2019 |  | 1703 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 10:03 | Joshi, Abhishek N | 56-F-EU-V-190703-S3OM021 |  | Yes | Y | [6 empty] | 56-F-EU-V-190703-S3OMV021A,56-F-EU-V-190703-S3OMV021B,56-F-EU-V-190703-S3OMV021C,56-F-EU-V-190703-S3OMV021D,56-F-EU-V-190703-S3OMV021E | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649701 | No | UBE | BXU545818 | 23928 | 3 |  |  | Synchronize Scheduled Invoice for Non Stock | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/11/2019 | 7/10/2019 |  | 1704 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-28 05:54 | Vishnubhatla, Mithra | 56-F-EU-V-190703-S3OM022 |  | Yes | Y | [6 empty] | 56-F-EU-V-190703-S3OMV022A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R565013 | No | UBE | BXU545806 |  | 1 |  |  | Sales reports by Product /Customer with markup | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 5/23/2019 | 5/23/2019 |  | 1705 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 10:53 | Joshi, Abhishek N | 56-F-EU-V-190516-S1OM027 | Report | Yes | Yes |  |  | No Retrofit Required |  |  |  | 56-F-EU-V-190516-S1OMV27A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56AT42565 | No | UBE | BXU545794 |  | 3 |  |  | Print Invoices Austria | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete | L3 - waiting for R42565 |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/11/2019 | 7/10/2019 |  | 1706 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 10:59 | Joshi, Abhishek N | 56-F-EU-V-190709-S3OM084 | Printer | Yes | Y | [6 empty] | 56-F-EU-V-190709-S3OMV084A, 56-F-EU-V-190709-S3OMV084B, 56-F-EU-V-190709-S3OMV084C | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56BIP02E | No | UBE | BXU545846 | BXU546811 | 6 | 6 |  | Customer Invoice Email Error Report | L3 Not Required |  |  | TRUE | MNE2E |  | IXOS Archive | eCommerce | Linda Kenny | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Saieja |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/2/2019 | 7/1/2019 |  | 1707 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 07:53 | Joshi, Abhishek N | 56-F-EU-V-190701-S3EC001 | Error / Report | Yes | Y |  |  | To be tested in CRP | NoKT |  |  | 56-F-EU-V-190701-S3ECV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56BIP04 | No | UBE | BXU545836 | BXU546800 | 6 |  |  | Send Invoices by E-mail to Customer | L3 Not Required |  |  | TRUE | HE2E |  | IXOS Archive | eCommerce | Linda Kenny | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Sreekanth, Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/17/2019 | 9/17/2019 |  | 1708 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 07:36 | Joshi, Abhishek N | 56-F-EU-V-190730-S4EC001 |  | Yes | Yes |  |  | To be tested in CRP | NoKT |  |  | 56-F-EU-V-190730-S4ECV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56BX42565 | No | UBE | 1240730 (17394), BXU531854 (133080B) | 1241782 (17394) | 3 |  |  | Print Invoices BeNeLux | L3 Pass | 209 |  | TRUE | HE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/12/2019 | 7/11/2019 |  | 1709 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 08:20 | ANAND, S | 56-F-EU-V-190710-S3OM033 | Printer | Yes | Y | [6 empty] | 56-F-EU-V-190710-S3OMV033A, 56-F-EU-V-190710-S3OMV033B, 56-F-EU-V-190710-S3OMV033C, 56-F-EU-V-190710-S3OMV033D, 56-F-EU-V-190710-S3OMV033E | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56CH42565 | No | UBE | 1251322 (21733) | 1251990 | 3 |  |  | Print Invoices Switzerland | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | John Whalley | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/12/2019 | 7/12/2019 |  | 1710 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-18 06:41 | ANAND, S | 56-F-EU-V-190708-S3OM031 | Printer | Yes | Y |  |  | Error in BSFN "SearchForStringinString(B0800750)" Replaced the BSFN B0800750 with B5600014. |  |  |  | 56-F-EU-V-190703-S3OMV031A, 56-F-EU-V-190703-S3OMV031B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56DE42565 | No | UBE | 1250527 (21734) |  | 3 |  |  | Print Invoices Germany | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Rafal Molas | L2 Pass / Complete | L3 - waiting for R42565 |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/12/2019 | 7/11/2019 |  | 1711 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 09:01 | ANAND, S | 56-F-EU-V-190712-S3OM001 | Printer | Yes | Y | [6 empty] | 56-F-EU-V-190712-S3OMV001A,56-F-EU-V-190712-S3OMV002A,56-F-EU-V-190712-S3OMV003A,56-F-EU-V-190712-S3OMV004A,56-F-EU-V-190712-S3OMV005A,56-F-EU-V-190712-S3OMV006A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56ES42565 | No | UBE | BXU545828 (13702) | BXU545855 (13702) | 3 |  |  | Print Invoices Spain | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | John Whalley | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/15/2019 | 7/12/2019 |  | 1712 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-07-27 02:51 | Singh, Sunil Kumar | 56-F-EU-V-190710-S3OM105 | Printer | Yes | Yes | [6 empty] | 56-F-EU-V-190710-S3OMV105A,56-F-EU-V-190710-S3OMV105B,56-F-EU-V-190710-S3OMV105C,56-F-EU-V-190710-S3OMV105D,56-F-EU-V-190710-S3OMV105E,56-F-EU-V-190710-S3OMV105F,56-F-EU-V-190710-S3OMV105G | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FR42565 | No | UBE | 1255898 (25827) |  | 3 |  |  | Trade Invoices France | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | John Whalley | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 07/19/2019 | 07/12/2019 |  | 1713 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 08:27 | ANAND, S | 56-F-EU-V-190712-S3OM036 |  | Yes | Y | [6 empty] | 56-F-EU-V-190712-S3OMV036A, 56-F-EU-V-190712-S3OMV036B ,56-F-EU-V-190712-S3OMV036C | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56GB42565 | No | UBE | BXU545825 |  | 3 |  |  | Print Trade Invoices GB/IE | L3 Pass | 255 |  | TRUE | HE2E |  | Order Management | OM | Rafal Molas | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/19/2019 | 7/12/2019 |  | 1714 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 10:41 | Joshi, Abhishek N | 56-F-EU-V-190711-S3OM108 | Printer | Yes | Y |  |  | Retrofit not required |  |  |  | 56-F-EU-V-190711-S3OMV108A,B,C,D,E,F,G,H,I,J,K. | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56IT42565 | No | UBE | BXU545413 |  | 3 |  |  | Print Invoices Italy | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | John Whalley | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/16/2019 | 7/16/2019 |  | 1715 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 05:54 | Joshi, Abhishek N | 56-F-EU-V-190704-S3OM028 | Printer | Yes | Yes | [6 empty] | 56-F-EU-V-190704-S3OMV028A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56NO42001 | No | UBE | 1242579 (17919) | 17919 | 3 |  |  | Proforma Invoice Nordics | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/16/2019 | 7/15/2019 |  | 1716 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-20 06:38 | ANAND, S | 56-F-EU-V-190710-S3OM034 |  | Yes | Y | [6 empty] | 56-F-EU-V-190710-S3OMV34A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL0003 | No | UBE | BXU545416, BXU545409 | BXU547611 | 3 |  |  | Invoice Print - Baxter Poland | L3 Pass | 250 |  | TRUE | HE2E |  | Order Management | OM | Rafal Molas | L2 Pass / Complete | L3 - waiting for R42565 |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item | Poland | 2019-05-02 12:55 | Kishi, Sayuri | 7/16/2019 | 7/15/2019 |  | 1717 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 06:14 | Joshi, Abhishek N | 56-F-EU-V-190709-S3OM085 | Printer | Yes | [7 empty] | 56-F-EU-V-190709-S3OMV085A,56-F-EU-V-190709-S3OMV085B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL0037B | No | UBE |  |  | 999 |  |  | Sales Order Detail Export | Obsolete |  |  |  | OBS |  | Order Management | OM | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1718 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Export | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL011 | No | UBE |  |  | 1 |  |  | Customer List | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 5/23/2019 | 5/23/2019 |  | 1719 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:55 | Chiau, Liesbet | 56-F-EU-V-190517-S1OM030 |  | Yes | Y | [6 empty] | 56-F-EU-V-190517-S1OMV030A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL016 | No | UBE |  |  | 1 |  |  | Sales Proces Tracing by Product | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 23/05/2019 | 23/05/2019 |  | 1720 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:55 | Chiau, Liesbet | 56-F-EU-V-190514-S1OM004 |  | Yes | Y | [6 empty] | 56-F-EU-V-190514-S1OMV04A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56R0197 | No | UBE | BXU545821 |  | 1 | 1 |  | Transfer Price Data-Inbound Processor UBE (EMEA) | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | John Whalley | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1721 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 10:26 | Joshi, Abhishek N | 56-F-EU-V-190514-S1OM003 | Inbound | Yes | Y | [6 empty] | 56-F-EU-V-190514-S1OMV03A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56SA42565 | No | UBE | 1273347, BXU545438 |  | 5 |  |  | Print Invoices Saudi Arabia | L3 Not Required |  |  | TRUE | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte | L2 Not required | RC:2708 - L2 not required as per attached mail communication |  |  | Terry Greenard / Vikas Verma | VV-12/08 - Chnaged Sprint from 999 to 5 as objct is called by the Plug and Play NER which is crashing at the run time | Vikas Verma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1722 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 06:06 | Joshi, Abhishek N |  | Printer | [9 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56X4201 | OBS | UBE |  |  | 999 |  |  | Populate IPA from Sales Orders Report | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1723 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Report | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5874R3030 | No | UBE | 1260383 (18020), BXU545276,BXU545805 |  | 3 |  |  | Print Invoice - Russia - SOP/AR - 74R | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/17/2019 | 7/16/2019 |  | 1724 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 10:30 | Joshi, Abhishek N | 56-F-EU-V-190715-S3OM110 | Printer | Yes | Yes |  |  | B5608730 -Business function created in DV920 copy of B0800730 |  |  |  | 56-F-EU-V-190715-S3OMV110A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58CZ001 | No | UBE | 1266617 (20217), BXU545316 | BXU547744 | 3 |  |  | CZ: Print Invoice per Order | L3 Pass | 209 |  | TRUE | HE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete | . |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/17/2019 | 7/16/2019 |  | 1725 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 08:35 | Joshi, Abhishek N | 56-F-EU-V-190701-S3OM016 | Printer | Yes | Y | [6 empty] | 56-F-EU-V-190701-S3OMV16A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58CZ010 | No | UBE | 1266617 (20217), BXU545415, BXU545414 | BXU547740, BXU547745, BXU547746 | 4 |  |  | CZ: Invoice Baxter Czech | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/26/2019 | 7/25/2019 |  | 1726 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 05:59 | Joshi, Abhishek N | 56-F-EU-V-190711-S3OM107 |  | Yes | Yes |  |  | Retrofit was done in Sprint3 |  |  |  | 56-F-EU-V-190711-S3OMV107A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58CZ020 | No | UBE | 1266617 (20217), BXU545415, BXU545414 | BXU547740, BXU547745, BXU547756 | 3 |  |  | CZ: Consolidated Invoice Baxter Czech | L3 Pass | 257 | R42565 CZD0010 (also used for consolidation invoicing in CZ) needs also proc opt 6 change to blank and data selection fix (defect 257) | TRUE | HE2E |  | Order Management | OM | Rafal Molas | L2 Pass / Complete | RC:0208-L3 can be continue ,PO changes available in UT920.Defect 224 closed |  |  | Terry Greenard / Vikas Verma |  | TANKUT CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/18/2019 | 7/17/2019 |  | 1727 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 06:00 | Joshi, Abhishek N | 56-F-EU-V-190704-S3OM001 |  | Yes | Y | [6 empty] | 56-F-EU-V-190704-S3OMV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5947021 | No | UBE |  |  | 1 |  |  | EDI 855/860 Custom Inbound Processor | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 5/31/2019 | 5/30/2019 |  | 1728 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:55 | Chiau, Liesbet | 56-F-EU-V-190515-S1OM024 | Inbound | Yes | Y |  |  | Retrofit Not Required | KTW6 |  |  | 56-F-EU-V-190515-S1OMV24A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0018 | No | UBE |  |  | 2 | 2 |  | Product Allocation Standard Preference Upload | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 23-05-2019 | 23-05-2019 |  | 1729 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 07:11 | Sagar, Sanjay | 56-F-EU-V-190515-S1OM011 | Upload | Yes | Y | [6 empty] | 56-F-EU-V-190515-S1OMV011A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0051 | no | UBE |  | BXU546813 | 6 |  |  | EDI Inbound Postprocessor | L3 Pass |  |  | TRUE | HE2E |  | EDI Order Management | eCommerce | Linda Kenny | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/30/2019 | 7/29/2019 |  | 1730 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-21 06:59 | Joshi, Abhishek N | 56-F-EU-V-190731-S4EC004 | Inbound | Yes | Y |  |  | Retrofited.Using B4208490 in replacement of B4208280. | KTEDI1 |  |  | 56-F-EU-V-190731-S4ECV004A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0237 | No | UBE | BXU545935 | 103220 | 1 |  |  | Siebel Inbound Pre-Processor | L3 Pass |  |  | TRUE | ME2E |  | Technical Services | Logistics | Mandy Corbett, Swetha M S, Thierry Kestens | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 05/23/2019 | 05/21/2019 |  | 1731 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-29 07:16 | Vishnubhatla, Mithra | 56-F-EU-V-190517-S1LO052 | Inbound | Yes | Y |  |  |  | KTTS2 |  |  | 56-F-EU-V-190517-S1LOV52A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900012 | No | APPL |  |  | 1 |  |  | Sales Order Compliance Date & Licensing Information | L3 Not Required |  |  | TRUE | L |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 5/22/2019 | 5/22/2019 |  | 1732 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:55 | Chiau, Liesbet | 56-F-EU-V-190517-S1OM029 |  | Yes | Yes | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5695004 | Yes | UBE | BXU546668 (12878) | BXU547465 (22440) | 1 |  |  | New 21CFR Report - A4072 | PPD Passed |  |  | TRUE | L | TRUE | 21CFR | ARO | Cosmin Mutiu / Terry Greenard | L2 Not required | No KT, as Tested by user only in ICT |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 22/05/2019 | 22/05/2019 |  | 1733 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-14 07:24 | ANAND, S | 56-F-EU-V-190514-S1MD010 | 21CFR / Report | Yes | Y | [6 empty] | 56-F-EU-V-190514-S1MDV04A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56CUST | No | APPL | BXU545263 |  | 4 |  |  | Maintain the file of Invoicing Data Customers | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1734 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 06:01 | Joshi, Abhishek N | 56-F-EU-V-190725-S4OM020 | Maintenance | Yes | Y | [6 empty] | 56-F-EU-V-190725-S4OMV020A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56U142565 | No | UBE | BXU545287 |  | 4 |  |  | BHSA Deemed Invoices / Moves / Credits / Debits | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/26/2019 | 7/25/2019 |  | 1735 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 10:23 | Joshi, Abhishek N | 56-F-EU-V-190722-S4OM009 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190722-S4OMV009A,56-F-EU-V-190722-S4OMV009B,56-F-EU-V-190722-S4OMV009C,56-F-EU-V-190722-S4OMV009D,56-F-EU-V-190722-S4OMV009E | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56SAB104 | No | UBE | BXU545808, BXU545797 |  | 3 |  |  | SAB104 Shipped Not Invoiced OrderLines | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/18/2019 | 7/17/2019 |  | 1736 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 10:18 | Joshi, Abhishek N | 56- F-EU-V-190716-S3OM110 |  | Yes | Y | [6 empty] | 56- F-EU-V-190716-S3OMV110A,56- F-EU-V-190716-S3OMV110B,56- F-EU-V-190716-S3OMV110C | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PT42565 | No | UBE | BXU545287, BXU545264 | BXU547770, BXU545829, | 6 |  |  | Print Invoices Portugal | L3 Not Required | 327 | Closed | TRUE | HE2E |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte | L2 Pass / Complete | RC:2009 -Portuguese Localization is working fine in DV920 but defect 327 created for digital signature. |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/18/2019 | 7/17/2019 |  | 1737 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-07-24 09:58 | Singh, Sunil Kumar | 56-F-EU-V-190709-S3OM102 | Printer | Yes | Y | [6 empty] | 56-F-EU-V-190709-S3OMV102A,56-F-EU-V-190709-S3OMV102B,56-F-EU-V-190709-S3OMV102C | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56U242565 | No | UBE | BXU545297 |  | 4 |  |  | BHSA Intercompany Invoices / Credits / Debits notes | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/29/2019 | 7/26/2019 |  | 1738 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 10:14 | Joshi, Abhishek N | 56-F-EU-V-190722-S4OM010 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190722-S4OMV010A to 56-F-EU-V-190722-S4OMV010U | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56ND42565 | No | UBE | BXU531854 (133080B), BXU545816, BXU545299 |  | 3 |  |  | Print Invoices Nordics | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | John Whalley | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/19/2019 | 7/17/2019 |  | 1739 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 10:11 | Joshi, Abhishek N | 56-F-EU-V-190708-S3OM030 | Printer | Yes | Y | [6 empty] | 56-F-EU-V-190708-S3OMV030A,56-F-EU-V-190708-S3OMV030B,56-F-EU-V-190708-S3OMV030C,56-F-EU-V-190708-S3OMV030D,56-F-EU-V-190708-S3OMV030E,56-F-EU-V-190708-S3OMV030F,56-F-EU-V-190708-S3OMV030G,56-F-EU-V-190708-S3OMV030H | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564209A | No | UBE |  |  | 1 |  |  | Held Order Report - PDF Output | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1740 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:55 | Chiau, Liesbet | 56-F-EU-V-190514-S1OM002 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190514-S1OMV02A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56SB42565 | No | UBE | BXU545438 | BXU547778 | 3 |  |  | Saudi Arabia Invoice with VAT | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | John Whalley | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/19/2019 | 7/18/2019 |  | 1741 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 06:06 | Joshi, Abhishek N | 56-F-EU-V-190704-S3OM026 |  | Yes | Y | [6 empty] | 56-F-EU-V-190704-S3OMV026A,56-F-EU-V-190704-S3OMV026B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600053 | No | UBE |  |  | 4 |  |  | Daily Sales Update Report for Saudi | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT , CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 07/29/2019 | 07/26/2019 |  | 1742 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-05 11:53 | Kamatham, Deepika | 56-F-EU-V-190725-S4OM021 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190725-S4OMV021A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641024N | No | UBE | BXU545027 |  | 4 |  |  | JDE to JDE – Ico Return (Non Transfer Order Credit Note) | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/30/2019 | 7/29/2019 |  | 1743 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 10:06 | Joshi, Abhishek N | 56-F-EU-V-190731-S4OM001 |  | Yes | Y | [6 empty] | 56-F-EU-V-190731-S4OMV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641024 | No | UBE | BXU545027 | BXU537485 | 4 |  |  | JDE to JDE – Interco Return (Credit Order) | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT , CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 07/30/2019 | 07/29/2019 |  | 1744 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 10:06 | Joshi, Abhishek N | 56-F-EU-V-190729-S4OM022 |  | Yes | Y | [6 empty] | 56-F-EU-V-190729-S4OMV022A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642565A | No | UBE | BXU545271 | BXU547091 | 2 |  |  | Order Acknowledgement Report | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1745 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 03:11 | Joshi, Abhishek N | 56-F-EU-V-190611-S2OM023 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190611-S2OMV023A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564217M | No | APPL | BXU545398 | BXU547523 | R1 |  |  | Uncommitted Order Release_Multiple Records | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Venkateswaran Murugesan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | VV-02/08- Moved to R1 as object not yet promoted to EUPD812 | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/23/2019 | 9/20/2019 |  | 1746 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 05:18 | Joshi, Abhishek N | 56-F-EU-V-190920-R1OM003 |  | Yes | Y | [6 empty] | 56-F-EU-V-190920-R1OMV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642118 | No | UBE | BXU545279 |  | R1 |  |  | Backorder Release and Report | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Meltem Cetinkus | L2 Pass / Complete | Moved from S2 to R1 to give time to incorporate CRQ153890 |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/25/2019 | 9/24/2019 |  | 1747 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 05:00 | Joshi, Abhishek N | 56-F-EU-V-190610-S2OM008 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190610-S2OMV08A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647040 | No | UBE | BXU545436 | BXU547219 | 4 |  |  | MFGPro Hospira Invoice interface | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Rafal Molas | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/31/2019 | 7/30/2019 |  | 1748 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 03:15 | Joshi, Abhishek N | 56-F-EU-V-190731-S4OM028 | Interface | Yes | Y | [6 empty] | 56-F-EU-V-190731-S4OMV028A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647041 | No | UBE | BXU545436 | BXU547219 | 4 |  |  | MFGPro Hospira Invoice interface - Export | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/1/2019 | 7/31/2019 |  | 1749 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 03:15 | Joshi, Abhishek N | 56-F-EU-V-190731-S4OM025 | Export / Interface | Yes | [7 empty] | 56-F-EU-V-190731-S4OMV025A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0307 | No | UBE |  |  | R1 |  |  | APS Sourcing New UBE | L3 Not Required |  |  | TRUE | HNE2E |  | Order Management | OM | Venkateswaran Murugesan | L2 Not required | 09/26 RK: As per todays mail " Retrofit Not Required" Reassigned from S2 to R1 as dependency with R59R0308 |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/25/2019 | 9/24/2019 |  | 1750 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-15 03:34 | Seputyte, Lina | 56-F-EU-V-190611-S2OM028 |  | Yes | Y |  |  | Testing will be done in CRP |  |  |  | 56-F-EU-V-190611-S2OMV028A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0308 | No | UBE |  |  | R1 |  |  | R59R0307 Load Balance Report | L3 Not Required |  |  | TRUE | HNE2E |  | Order Management | OM | Venkateswaran Murugesan | L2 Not required | 09/26 RK: As per todays mail " Retrofit Not Required" |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1751 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-15 03:36 | Seputyte, Lina |  | Report |  |  |  |  | L.S 15/10 - Testing will be done in VV-26/09 - Changed the status L2 not required as per the request from Rajendra.Kharole, VV-24/06- Object Pormoted to EUPD812 on 23-March, It&nbsp; is moved to R1 Specification not found in both envi. (EUPD812 and DV920) |  |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0309 | No | UBE |  |  | R1 |  |  | APS Sourcing Location From E1 to AP New UBE | L3 Not Required |  |  | TRUE | HNE2E |  | Order Management | OM | Genevieve Deveen | L2 Not required | 09/26 RK: As per todays mail " Retrofit Not Required" move from S1 to R1 due to dependencies with R59R0308 |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1752 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-15 03:29 | Seputyte, Lina | 56-F-EU-V-190611-S2OM028 |  | Yes | Y |  |  | VV-26/09 - Changed the status L2 not required as per the request from Rajendra.Kharole, Specifications not found in dv and pd |  |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0310 | No | UBE |  |  | R1 |  |  | R59R0309 Load Balance Report | L3 Not Required |  |  | TRUE | HNE2E |  | Order Management | OM | Genevieve Deveen | L2 Not required | 09/26 RK: As per todays mail " Retrofit Not Required" move from S1 to R1 due to dependencies with R59R0308 |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 5/22/2019 | 5/22/2019 |  | 1753 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-15 03:30 | Seputyte, Lina | 56-F-EU-V-190611-S2OM028 | Report | Yes | Y |  |  | VV-26/09 - Changed the status L2 not required as per the request from Rajendra.Kharoleno L1&nbsp; unit testing required .Got the par from DV812. 09/20/2019: Status updated to 'No Retrofit Required' from 'L3 Not Required'. Object does not exist in EUPD812. |  |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R4101W | No | UBE |  |  | 999 |  |  | Item Master Data from E1 to APS PDP | Obsolete | [5 empty] | Warehouse | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1754 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-23 03:32 | Greenard, Terry | [6 empty] | On Hold N/A for EMEA |  |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R4280W | No | UBE |  |  | 999 |  |  | Sales Order Data from E1 to APS | Obsolete | [5 empty] | Warehouse | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1755 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-27 02:02 | Greenard, Terry | [6 empty] | On Hold N/A for EMEA |  |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R4282W | No | UBE |  |  | 999 |  |  | Sales Order Sourcing Data from E1 to APS | Obsolete | [5 empty] | Warehouse | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1756 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-27 02:04 | Greenard, Terry | [6 empty] | On Hold N/A for EMEA |  |  |  |  | TRUE |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59RMCU4 | No | UBE |  |  | 5 |  |  | Sourcing - Advance Planning Systems (APS) Demantra | L3 Not Required |  |  | TRUE |  |  | Warehouse | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/29/2019 | 8/29/2019 |  | 1757 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-02 07:12 | Dartois, Léonard | 56-F-EU-V-190827-S5LO083 |  | Yes | Yes |  |  | On Hold N/A for EMEA |  |  |  | N/A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5640071X | No | UBE |  |  | 999 |  |  | Cycle billing info DACH data F40071 | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1758 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647011 | Yes | UBE | 1259735 (4302), BXU545404 (101690), BXU545411 (13583)&nbsp; BXU545291 15093 9474 BXU545278 | 4302, 1231062, BXU547105, BXU547208, BXU547012 | 4 | 1 |  | EDI Inbound Purchase Order Edit And Create | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | John Whalley | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/1/2019 | 7/31/2019 |  | 1759 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 03:33 | Vishnubhatla, Mithra | 56-F-EU-V-190805-S4OM038 | Inbound | Yes | Y | [6 empty] | 56-F-EU-V-190805-S4OMV038A, 56-F-EU-V-190805-S4OMV038B, 56-F-EU-V-190805-S4OMV038C, 56-F-EU-V-190805-S4OMV038D, 56-F-EU-V-190805-S4OMV038E, 56-F-EU-V-190805-S4OMV038F, 56-F-EU-V-190805-S4OMV038G | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0188 | No | UBE |  |  | 3 |  |  | SO Z-file processing for Forex Sales | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/19/2019 | 7/18/2019 |  | 1760 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-18 07:48 | Deveen, Genevive | 56-F-EU-V-190715-S3OM037 |  | Yes | Y | [6 empty] | 56-F-EU-V-190715-S3OMV037A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5600042 | Yes | APPL | 1280832 (110889) | BXU515739 | 6 |  |  | Temperature Route Override – Rule | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Venkateswaran Murugesan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/4/2019 | 9/4/2019 |  | 1761 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 08:29 | ANAND, S | 56-F-EU-V-190829-S6OM006 |  | Yes | [8 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5638010 | No | APPL |  |  | 999 |  |  | Agreement Master Custom | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1762 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0253 | No | UBE |  |  | 4 |  |  | Generic Advanced Preference Upload UBE | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/2/2019 | 8/1/2019 |  | 1763 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 06:04 | Deveen, Genevive | 56-F-EU-V-190731-S4OM026 | Upload | Yes | Y | [6 empty] | 56-F-EU-V-190731-S4OMV026A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P57PRECS | No | APPL | 1250527 (21734) |  | 5 |  |  | Work with Preferential Origin Summary File About (Ctrl+Shift+J) Help Item Help Skip Navigation Links | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/12/2019 | 8/09/2019 |  | 1764 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 08:59 | ANAND, S | 56-F-EU-V-190812-S5OM001 |  | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647202 | No | UBE | 1230252 13583 | 13583 | 5 |  |  | EdI Inbound processor | L3 Pass |  |  | TRUE | HE2E |  | EDI Order Management | eCommerce | Aidan Scally | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT , CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/31/2019 | 7/30/2019 |  | 1765 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-21 06:46 | Vishnubhatla, Mithra | 56-F-EU-V-190723-S4EC001 | Inbound | Yes | Y |  |  |  | KTEDI1 |  |  | 56-F-EU-V-190723-S4ECV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647203 | No | UBE | 13583 1230252 |  | 5 |  |  | EdI Inbound post-processor | L3 Pass |  |  | TRUE | HE2E |  | EDI Order Management | eCommerce | Aidan Scally | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 07/31/2019 | 07/30/2019 |  | 1766 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-21 06:47 | Vishnubhatla, Mithra | 56-F-EU-V-190730-S4OM023 | Inbound | Yes | Y |  |  |  | KTEDI1 |  |  | 56-F-EU-V-190730-S4OMV023A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647204 | No | UBE | 1230252 13583 |  | 4 |  |  | EdI Inbound error post-processor | L3 Pass |  |  | TRUE | HE2E |  | EDI Order Management | eCommerce | Aidan Scally | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/1/2019 | 7/31/2019 |  | 1767 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-21 07:34 | Vishnubhatla, Mithra | 56-F-EU-V-190802-S4EC005 | Error / Inbound | Yes | Y |  |  |  | KTEDI1 |  |  | 56-F-EU-V-190802-S4ECV005A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647047 | Yes | UBE | 1241441 | 1241867 | 4 |  |  | EDI Order response (Nordics) | L3 Pass |  |  | TRUE | HE2E |  | EDI Order Management | eCommerce | Aidan Scally | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT , CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/1/2019 | 7/31/2019 |  | 1768 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-29 03:22 | Vishnubhatla, Mithra | 56-F-EU-V-190731-S4EC001 |  | Yes | Y |  |  |  | KTEDI3 |  |  | 56-F-EU-V-190731-S4ECV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R47042 | No | UBE | 1235429 | 15856 1235896 | 3 |  |  | EDI Invoice data generation | L3 Pass |  |  | TRUE | HE2E |  | EDI Order Management | eCommerce | Aidan Scally | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/11/2019 | 7/5/2019 |  | 1769 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 05:46 | Vishnubhatla, Mithra | 56-F-EU-V-190703-S3ED001 |  | Yes | Y |  |  |  | KTEDI4 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R47011 | No | UBE | 1271368 |  | 1 |  |  | EDI Inbound Purchase Order Edit/Create | L3 Pass |  |  | TRUE | HE2E |  | EDI Order Management | eCommerce | Aidan Scally | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 5/23/2019 | 5/22/2019 |  | 1770 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-21 07:14 | Vishnubhatla, Mithra | 56-F-EU-V-190516-S1ED002 | Inbound | Yes | Y |  |  |  | KTEDI4 |  |  | 56-F-EU-V-190516-S1EDV02A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R47018 | No | UBE |  |  | 6 | 6 |  | EDI Purchase Order Inbound Purge | L3 Pass |  |  | TRUE | LNE2E |  | EDI Technical | eCommerce | Aidan Scally | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/15/2019 | 7/14/2019 |  | 1771 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-04 03:50 | Kenny, Linda | NA | Inbound | Yes | Y |  |  | No Retrofit Required | NoKT |  |  | 56-F-EU-V-190711-BV0382A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R47019 | Yes | UBE |  |  | 999 |  |  | EDI Purchase Order Outbound Purge | Obsolete |  |  | TRUE | L |  | Purge | ARO | Cosmin Mutiu / Terry Greenard | L2 Not required | No KT, as Tested by user only in ICT |  |  | Terry Greenard / Vikas Verma | VV-02/08 As per discussion with BSL and Baxter Obsoleted the objects as not retrofit is required | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/16/2019 | 7/12/2019 |  | 1772 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-02 02:24 | Verma, Vikas | NA | Outbound | Yes | Y | [6 empty] | 56-F-EU-V-190712-BV1061A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R47021 | No | UBE |  |  | 1 |  |  | EDI Inbound P.O. Acknowledgment | L3 Pass |  |  | TRUE | LNE2E |  | EDI Order Management | eCommerce | Aidan Scally | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 5/31/2019 | 5/30/2019 |  | 1773 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:55 | Chiau, Liesbet |  | Inbound | Yes | Y |  |  | Retrofit Not Required | KTEDI7 |  |  | 56-F-EU-V-190516- -BV0002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R47029 | No | UBE |  |  | 6 | 6 |  | EDI P.O. Acknowledgment Outbound Purge | L3 Pass |  |  | TRUE | LNE2E |  | EDI Technical | eCommerce | Aidan Scally | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/16/2019 | 7/16/2019 |  | 1774 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-12-05 06:53 | Singh, Sunil Kumar |  | Outbound | Yes | Y |  |  |  | NoKT |  |  | 56-F-EU-V-190705-BV0379A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R47038 | OBS | UBE |  |  | 999 |  |  | EDI Shipping Notice Inbound Purge | Obsolete | [5 empty] | EDI Technical | eCommerce | Aidan Scally |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1775 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Inbound | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R47048 | No | UBE |  |  | 6 | 6 |  | EDI Invoice Inbound Purge | L3 Pass |  |  | TRUE | LNE2E |  | EDI Technical | eCommerce | Aidan Scally | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/16/2019 | 7/8/2019 |  | 1776 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-04 03:17 | Kenny, Linda |  | Inbound | Yes | Y |  |  | Retrofit not required.Added one version. | NoKT |  |  | 56-F-EU-V-190708-BV0380A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R47049 | No | UBE |  |  | 999 | 6 |  | EDI Invoice Outbound Purge | Obsolete |  |  | TRUE | LNE2E |  | EDI Technical | eCommerce | Aidan Scally | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma | No Retrofit required and No Custom version present- VV-02/08 As per discussion with BSL and Baxter Obsoleted the objects as not retrofit is required | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/17/2019 | 7/16/2019 |  | 1777 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-02 02:25 | Verma, Vikas | N/A | Outbound | Yes | Y |  |  |  | NoKT |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R47078 | No | UBE |  |  | 999 | 6 |  | EDI Receiving Advice Inbound Purge | Obsolete |  |  | TRUE | LNE2E |  | EDI Technical | eCommerce | Aidan Scally | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma | VV-02/08 As per discussion with BSL and Baxter Obsoleted the objects as not retrofit is required | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/17/2019 | 7/15/2019 |  | 1778 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-02 02:26 | Verma, Vikas | NA | Inbound | Yes | Y |  |  |  | NoKT |  |  | 56-F-EU-V-190710-BV1062 | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R47128A | No | UBE |  |  | 999 |  |  | EDI Product Activity Data Inbound Purge | Obsolete |  |  | TRUE | L |  | Purge | ARO | Cosmin Mutiu / Terry Greenard | L2 Not required | No KT, as Tested by user only in ICT |  |  | Terry Greenard / Vikas Verma | VV-02/08 As per discussion with BSL and Baxter Obsoleted the objects as not retrofit is required | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 07/17/2019 | 07/16/2019 |  | 1779 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-02 02:26 | Verma, Vikas | N/A | Inbound | Yes | Y |  |  | Retrofit does not require. There is no difference between EUPS812 and EUPD812. Version project is created for custom versions promotions & deployment. |  |  |  | 56-F-EU-V-190711-BV0381A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R47129A | OBS | UBE |  |  | 999 |  |  | EDI Product Activity Data Outbound Purge | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1780 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Outbound | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R47131 | OBS | UBE |  |  | 999 |  |  | EDI Inbound Purchase Order Change | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1781 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Inbound | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R47138 | No | UBE |  |  | 1 |  |  | EDI P.O. Change Inbound Purge | PPD Passed |  |  | TRUE | L | TRUE | Purge | ARO | Cosmin Mutiu / Terry Greenard | L2 Not required | No KT, as Tested by user only in ICT |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 05/30/2019 | 05/29/2019 |  | 1782 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-14 07:59 | Greenard, Terry |  | Inbound | Yes | Y |  |  | Retrofit Not Required |  |  |  | 56-F-EU-V-190516- -BV0001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5942INV | OBS | APPL |  |  | 999 |  |  | EDIControlFileMaintenance | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1783 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Maintenance | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5947200 | OBS | APPL |  |  | 999 |  |  | EDIErrorLogDetails | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1784 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Error | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647071 | Yes | UBE | BXU545508, 1267638 (19411), 1240731 (17485), 1254960 (25177), 1264923 (23046)&nbsp;&nbsp; 1267638 19738 25248 BXU547385 | BXU537484, 1240751 (17485), 1254962 (25177), 1258737 (25953), BXU547387 (26326), BXU547386 (26095), BXU547385 (25248), BXU547384 (23046), BXU547383 (19738) 25248 1267638 | 1 | 2 |  | EDIReceivingAdviceEdit/Create-Purchasing-Poland | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Leonard Dartois | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1785 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 04:20 | Vishnubhatla, Mithra | 56-F-EU-V-190603-S1OM047 |  | Yes | Y |  |  |  | KTW3 |  |  | 56-F-EU-V-190603-S1OMV047A, 56-F-EU-V-190603-S1OMV047B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58R47121 | OBS | UBE |  |  | 999 |  |  | EDIProductActivityDataEdit/Create | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1786 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58R4713 | OBS | UBE |  |  | 999 |  |  | EDI945BatchPreProcessorReport-CANADA | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1787 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Report | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59470411 | OBS | UBE |  |  | 999 |  |  | EDIInboundInvoice/MatchPreprocessor | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1788 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Inbound | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59470412 | OBS | UBE |  |  | 999 |  |  | EDIInboundInvoice/MatchtoP.O.Edit/Create | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1789 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Inbound | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5947049 | OBS | UBE |  |  | 999 |  |  | EDIInvoiceOutboundPurge | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1790 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Outbound | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0198 | No | UBE |  |  | 6 |  |  | EDI850StagingTablePurge | L3 Pass |  |  | TRUE | LNE2E |  | EDI Technical | eCommerce | Aidan Scally | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/2/2019 | 8/1/2019 |  | 1791 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-04 03:34 | Kenny, Linda | 56-F-EU-V-190802-S4EC006 |  | Yes |  |  |  |  | NoKT |  |  | 56-F-EU-V-190802-S4ECV006A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0228 | OBS | UBE |  |  | 999 |  |  | EDISucessfullyProcessedFlagUpdateReport-CostZfile | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1792 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Report | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0229 | OBS | UBE |  |  | 999 |  |  | EDISucessfullyProcessedFlagUpdateReport-PriceZfile | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1793 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Report | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900042 | No | APPL | 1215392 | BXU546796 | 5 |  |  | Unit of Measure Extension | L3 Pass |  |  | TRUE | MNE2E |  | EDI Order Management | eCommerce | Linda Kenny | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/13/2019 | 8/12/2019 |  | 1794 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-21 05:43 | Vishnubhatla, Mithra | 56-F-EU-V-190813-S5OM007 |  | Yes | Yes |  |  |  | KTEDI2 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56TC0101Z | Yes | UBE |  | 1248414 | 2 |  |  | Load F0101Z2 ,Z-File from CSV - Front End | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/18/2019 | 6/18/2019 |  | 1795 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 04:31 | Joshi, Abhishek N | 56-F-EU-V-190611-S2MD016 |  | Yes | [7 empty] | 56-F-EU-V-190611-S2MDV16A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56TC0401Z | Yes | UBE | BXU545676 | 16037, BXU545676 | 2 |  |  | Load F0401Z1Supplier Master Z-File from CSV - Front End | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/18/2019 | 6/18/2019 |  | 1796 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 10:57 | Joshi, Abhishek N | 56-F-EU-V-190612-S2MD026 |  | Yes | Y | [6 empty] | 56-F-EU-V-190612-S2MDV026A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R04010Z | Yes | UBE | R5601ZP3 | 13041, BXU545605 | 1 |  |  | Load F0401 | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 5/29/2019 | 5/28/2019 | R5601ZP5 | 1797 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 05:02 | Joshi, Abhishek N | 56-F-EU-V-190527-S1MD001 |  | Yes | Yes |  |  | Retrofit Completed. | DEFECT ID: 122 |  |  | 56-F-EU-V-190527-S1MDV01A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R573B551 | No | UBE | BXU546015 |  | 999 | 6 |  | Update Receipts Register From Electronic Input - EURO | Obsolete |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Not required | Waiting to have integration before testing |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 09/03/2019 | 09/02/2019 |  | 1798 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 00:52 | Joshi, Abhishek N | 56-F-EU-V-190705-S2FI001 |  | Yes | Y |  |  | to be tested in CRP |  |  |  | 56-F-EU-V-190705-S2FIV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56032000 | No | UBE | BXU545713 |  | 2 |  | CRP | Driver - AutoCash Upload Bank Statement File (SWIFT MT940) | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/18/2019 | 6/17/2019 |  | 1799 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 01:46 | Joshi, Abhishek N | 56-F-EU-V-190625-S2FI059 | Upload |  | Y |  |  | Abhishek Deshmukh,dependent object R57032002 is on hold |  |  |  | 56-F-EU-V-190625-S2FIV059A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5696700 | Yes | APPL | 1272691 | 1272878 | 6 |  |  | CC Repository Maintenance (Restricted) | L3 Not Required |  |  | TRUE | H |  | Validation | Validation | Sunil Kumar / Vinod | L2 Not required | no KT, testing during CRP |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/13/2019 | 9/13/2019 |  | 1800 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-07 06:28 | Singh, Sunil Kumar | 56-F-EU-V-190912-S6VA012 | Maintenance | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5696701 | Yes | APPL |  | 1272878 | 6 |  |  | Critical Configuration Batch Maintenance | L3 Not Required |  |  | TRUE | H |  | Validation | Validation | Sunil Kumar / Vinod | L2 Not required | no KT, testing during CRP |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/13/2019 | 9/12/2019 |  | 1801 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-07 06:30 | Singh, Sunil Kumar | 56-F-EU-V-190903-S6VA004 | Maintenance | Yes | Yes | [6 empty] | 56-F-EU-V-190903-S6VAV004A |  |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5696720 | Yes | APPL | 1272691 | 1272878 | 6 |  |  | Critical Configuration Batch Enquiry | L3 Not Required |  |  | TRUE | H |  | Validation | Validation | Sunil Kumar / Vinod | L2 Not required | no KT, testing during CRP |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/13/2019 | 9/12/2019 |  | 1802 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-07 06:57 | Singh, Sunil Kumar | 56-F-EU-V-190904-S6VA004 | Inquiry | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5696721 | Yes | APPL | 1272691 |  | 6 |  |  | Critical Configuration Data Enquiry | L3 Not Required |  |  | TRUE | H |  | Validation | Validation | Sunil Kumar / Vinod | L2 Not required | no KT, testing during CRP |  |  | Terry Greenard / Vikas Verma |  | Sreekanth, Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 09/13/2019 | 09/13/2019 |  | 1803 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-07 06:58 | Singh, Sunil Kumar | 56-F-EU-V-190909-S6VA007 | Inquiry | Yes | Yes | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5696722 | Yes | APPL | 1272691 | 1272878 | 6 |  |  | Critical Configuration Batch Snapshot Enquiry | L3 Not Required |  |  | TRUE | H |  | Validation | Validation | Sunil Kumar / Vinod | L2 Not required | no KT, testing during CRP |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 09/16/2019 | 09/13/2019 |  | 1804 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-07 07:01 | Singh, Sunil Kumar | 56-F-EU-V-190906-S6VA006 | Inquiry | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5696750 | Yes | APPL | 1272691 | 1272878 | 6 |  |  | Critical Configuration Type Definition | L3 Not Required |  |  | TRUE | H |  | Validation | Validation | Sunil Kumar / Vinod | L2 Not required | no KT, testing during CRP |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/16/2019 | 9/13/2019 |  | 1805 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-07 07:02 | Singh, Sunil Kumar | 56-F-EU-V-190910-S6VA010 |  | Yes | Yes | [6 empty] | N/A |  |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5696751 | Yes | APPL | 1272691 | 1272878 | 6 |  |  | Critical Configuration Stream Properties Maintenance | L3 Not Required |  |  | TRUE | H |  | Validation | Validation | Sunil Kumar / Vinod | L2 Not required | no KT, testing during CRP |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/16/2019 | 9/13/2019 |  | 1806 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-07 07:03 | Singh, Sunil Kumar | 56-F-EU-V-190830-S6VA002 | Maintenance | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5696752 | Yes | APPL | 1272691 | 1272878 | 6 |  |  | Critical Configuration Approval Route Maintenance | L3 Not Required |  |  | TRUE | H |  | Validation | Validation | Sunil Kumar / Vinod | L2 Not required | no KT, testing during CRP |  |  | Terry Greenard / Vikas Verma |  | Sreekanth, Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/16/2019 | 9/15/2019 |  | 1807 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-07 06:57 | Singh, Sunil Kumar | 56-F-EU-V-190909-S6VA008 | Maintenance | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5696753 | No | APPL |  | 1272878 | 6 |  |  | Approval Route Search | L3 Not Required |  |  | TRUE | H |  | Validation | Validation | Sunil Kumar / Vinod | L2 Not required | no KT, testing during CRP |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/17/2019 | 9/16/2019 |  | 1808 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-07 04:29 | Singh, Sunil Kumar | 56-F-EU-V-190912-S6VA012 |  | Yes | Yes | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5696754 | Yes | APPL |  | 1272878 | 6 |  |  | Search Configuration Type Table Fields | L3 Not Required |  |  | TRUE | H |  | Validation | Validation | Sunil Kumar / Vinod | L2 Not required | no KT, testing during CRP |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/17/2019 | 9/16/2019 |  | 1809 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-07 04:28 | Singh, Sunil Kumar | 56-F-EU-V-190910-S6VA011 |  | Yes | Yes | [6 empty] | N/A |  |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5696755 | Yes | APPL | 1272691 | 1272878 | 6 |  |  | Critical Configuration Type Definition Search | L3 Not Required |  |  | TRUE | H |  | Validation | Validation | Sunil Kumar / Vinod | L2 Not required | no KT, testing during CRP |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/17/2019 | 9/16/2019 |  | 1810 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-07 04:19 | Singh, Sunil Kumar | 56-F-EU-V-190830-S6VA003 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5696756 | Yes | APPL | 1272691, | 1272878 | 6 |  |  | Critical Configuration Maintain Table Data Selection | L3 Not Required |  |  | TRUE | H |  | Validation | Validation | Sunil Kumar / Vinod | L2 Not required | no KT, testing during CRP |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/17/2019 | 9/16/2019 |  | 1811 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-07 04:14 | Singh, Sunil Kumar | 56-F-EU-V-190912-S6VA013 | Maintenance | Yes | Yes | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5696799 | Yes | APPL | 1272691 | 1272878 | 6 |  |  | Critical Configuration Batch Header Audit Enquiry | L3 Not Required |  |  | TRUE | H |  | Validation | Validation | Sunil Kumar / Vinod | L2 Not required | no KT, testing during CRP |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/18/2019 | 9/17/2019 |  | 1812 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-06 09:36 | Singh, Sunil Kumar | 56-F-EU-V-190904-S6VA005 | Inquiry / Audit | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5696700 | Yes | UBE | 1272691 | 1272878 | 6 |  |  | Compare Critical Config Repository to selected data sources | L3 Not Required |  |  | TRUE | H |  | Validation | Validation | Sunil Kumar / Vinod | L2 Not required | no KT, testing during CRP |  |  | Terry Greenard / Vikas Verma |  | Sreekanth, Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 09/18/2019 | 09/18/2019 |  | 1813 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-06 09:35 | Singh, Sunil Kumar | 56-F-EU-V-190909-S6VA009 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190909-S6VAV009A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5696760 | Yes | UBE |  | 1272878 | 6 |  |  | Compare Generic JDE Table contents to CC Repository | L3 Not Required |  |  | TRUE | H |  | Validation | Validation | Sunil Kumar / Vinod | L2 Not required | no KT, testing during CRP |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/18/2019 | 9/17/2019 |  | 1814 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-06 09:11 | Singh, Sunil Kumar | 56-F-EU-V-190906-S6VA001 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190906-S6VAV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5696790 | No | UBE |  | 1272878 (40601) | 6 |  |  | Load CC Repository based on CC Type | L3 Not Required |  |  | TRUE | H |  | Validation | Validation | Sunil Kumar / Vinod | L2 Not required | no KT, testing during CRP |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/18/2019 | 9/17/2019 |  | 1815 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-06 09:10 | Singh, Sunil Kumar | 56-F-EU-V-190830-S6VA001 |  | Yes | Y | [6 empty] | 56-F-EU-V-190830-S6VAV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R550018 | No | UBE | BXU549465 |  | 6 | 6 | CRP | Italian Intra Community VAT Reporting | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Manuel Touyaa | L2 Pass / Complete | Have issue with DS values, waiting for input |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/3/2019 | 9/2/2019 |  | 1816 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 02:52 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI040 | Report | Yes | [7 empty] | 56-F-EU-V-190827-S6FIV040A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5503B01F | No | UBE | BXU550359 |  | 5 |  | CRP | Open Invoice Stats by invoice year | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/22/2019 | 8/21/2019 |  | 1817 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 04:02 | Joshi, Abhishek N | 56-F-EU-V-190819-S5FI116 |  | Yes | Y | [6 empty] | 56-F-EU-V-190819-S5FIV116A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5503B01G | No | UBE | BXU550362 |  | 5 |  | CRP | Open Invoice Stats by invoice year (CC11) | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | CIZMECI,TANKUT |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/22/2019 | 8/21/2019 |  | 1818 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 04:04 | Joshi, Abhishek N | 56-F-EU-V-190813-S5FI052 |  | Yes | Y | [6 empty] | 56-F-EU-V-190813-S5FIV052A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5512G61 | No | UBE | BXU549464 |  | 6 |  | CRP | Movement Accounts Report | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/3/2019 | 8/30/2019 |  | 1819 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 02:54 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI021 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV021A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5530Z1E | No | UBE | BXU548809 |  | 6 |  | CRP | Suppliers without Bank Information | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 08/30/2019 | 08/29/2019 |  | 1820 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 04:49 | Joshi, Abhishek N | 56-F-EU-V-190830-S6FI115 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190830-S6FIV115A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRAP02 | No | UBE | BXU548810 |  | 6 |  | CRP | A/P Payment History Detail Report | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Constanza Frade Dolesor | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/3/2019 | 8/30/2019 |  | 1821 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 04:53 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI004 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV004A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRAP21 | No | UBE | BXU548811 |  | 6 |  | CRP | A/P Unrealized Gain/Loss Report | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Constanza Frade Dolesor | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/3/2019 | 9/3/2019 |  | 1822 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 04:56 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI030 | Report | Yes | [7 empty] | 56-F-EU-V-190827-S6FIV030A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRAP25 | No | UBE | BXU550372 |  | 6 |  | CRP | Reset Voucher Pay Status | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Constanza Frade Dolesor | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/03/2019 | 9/03/2019 |  | 1823 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 06:06 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI051 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV051A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRAP35 | No | UBE | BXU549325 |  | 6 |  | CRP | Swiss VAT Reporting - Accounts Payable | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/3/2019 | 9/2/2019 |  | 1824 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 02:56 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI018 | Report |  | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV018A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRAP36 | No | UBE | BXU549326 |  | 6 | 6 | CRP | Swiss VAT AP Report in local CCY | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Robbin/Florencia | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/3/2019 | 9/3/2019 |  | 1825 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 05:01 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI031 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV031A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRAP71 | No | UBE | BXU550453 |  | 6 |  | CRP | Supplier Turnover by Document (Detail) | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Constanza Frade Dolesor | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/3/2019 | 9/2/2019 |  | 1826 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 06:08 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI001 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRAR21 | No | UBE | BXU549450 |  | 6 |  | CRP | A/R Gains/Losses Report | L3 Pass | 309 |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/3/2019 | 9/2/2019 |  | 1827 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 05:05 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI041 | Report | Yes | [7 empty] | 56-F-EU-V-190827-S6FIV041A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRAR24 | No | UBE | BXU548346 |  | 6 |  | CRP | Swiss VAT Reporting - Accounts Receivable | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Robbin/Florencia | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/3/2019 | 9/3/2019 |  | 1828 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 07:12 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI020 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV020A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRAR2A | No | UBE | BXU549328 |  | 6 |  | CRP | As Of VAT on Open A/R Invoices | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/4/2019 | 9/3/2019 |  | 1829 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 05:11 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI042 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV042A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRAR51 | No | UBE |  |  | 5 |  | CRP | Find Matching Credit Note | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/22/2019 | 8/19/2019 |  | 1830 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-28 15:54 | Fematt, Robbin | 56-F-EU-V-190819-S5FI108 |  | Yes | Y | [6 empty] | 56-F-EU-V-190819-S5FIV108A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRCB15 | No | UBE | BXU550364 |  | 2 |  | CRP | Autocash Exception Report | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/18/2019 | 6/17/2019 |  | 1831 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 04:05 | Joshi, Abhishek N | 56-F-EU-V-190610-S2FI003 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190610-S2FIV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRCB18 | No | UBE | BXU548736 |  | 2 |  | CRP | Deutsche Bank Cash Application Report | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/17/2019 | 6/17/2019 |  | 1832 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 09:04 | Joshi, Abhishek N | 56-F-EU-V-190613-S2FI036 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190613-S2FI036A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRCB18F | No | UBE | BXU547667 |  | 2 |  | CRP | Deutsche Bank Cash Application Report - Original | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/17/2019 | 6/17/2019 |  | 1833 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 04:59 | Joshi, Abhishek N | 56-F-EU-V-190614-S2FI040 | Report | Yes | Y |  |  | PO- T55FRCB18 already deployed in other project - 56-F-EU-V-190613-S2FI036 |  |  |  | 56-F-EU-V-190614-S2FIV040A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRDSOC | No | UBE | BXU548717 |  | 6 |  | CRP | DSO by Collection Manager | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/04/2019 | 9/04/2019 |  | 1834 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 09:05 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI054 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV054A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRDSOD | No | UBE | BXU548717 |  | 6 |  | CRP | DSO by Division | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/4/2019 | 9/3/2019 |  | 1835 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 09:07 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI007 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV007A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRDSOE | No | UBE | BXU548717 |  | 6 |  | CRP | DSO by Entity (Summary) | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/4/2019 | 9/3/2019 |  | 1836 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 09:07 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI032 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV032A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRDSOP | No | UBE | BXU548717 |  | 6 |  | CRP | DSO by Parent | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/3/2019 | 9/2/2019 |  | 1837 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 09:08 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI002 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRDSOX2 | No | UBE | BXU548833 |  | 6 |  | CRP | Driver for DSO | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/4/2019 | 9/3/2019 |  | 1838 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 03:57 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI043 |  | Yes | Y | [6 empty] | 56-F-EU-V-190827-S6FIV043A , 56-F-EU-V-190827-S6FIV043B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FREX01 | No | UBE | BXU550454 |  | 6 |  | CRP | F0411 line paid but amount still open | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/4/2019 | 9/3/2019 |  | 1839 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 06:11 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI027 |  | Yes | Y | [6 empty] | 56-F-EU-V-190827-S6FIV027A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FREX03 | No | UBE | BXU549451 |  | 6 |  | CRP | Batches Out of Balance | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/4/2019 | 9/3/2019 |  | 1840 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 05:15 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI029 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV029A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FREX06 | No | UBE | BXU549452 |  | 6 |  | CRP | F0011 Batch Header Posted, F0911 Not Posted | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Robbin/Florencia | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/4/2019 | 9/3/2019 |  | 1841 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 05:46 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI048 |  | Yes | Y | [6 empty] | 56-F-EU-V-190827-S6FIV048A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FREX07 | No | UBE | BXU549453 |  | 6 |  | CRP | V Batches different by offset | L3 Pass | 321 | Closed | TRUE | LNE2E |  | Finance GL | Finance | Robbin/Florencia | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 09/03/2019 | 09/02/2019 |  | 1842 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 05:57 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI014 | CRP | Yes | Yes |  |  |  | 6 |  |  | 56-F-EU-V-190827-S6FIV014A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FREX08 | No | UBE | BXU548738 |  | 6 |  | CRP | IB Batches different by offset | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth, Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/4/2019 | 9/3/2019 |  | 1843 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 08:04 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI022 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV022A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FREX09 | No | UBE | BXU548739 |  | 6 |  | CRP | F03B11 Line Received But Amount Still Open | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/4/2019 | 9/3/2019 |  | 1844 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 08:06 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI055 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV055A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FREX10 | No | UBE | BXU548740 |  | 6 |  | CRP | Batches Posted in F0011 and Not Posted in F03B11 | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/4/2019 | 9/3/2019 |  | 1845 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 09:08 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI010 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV010A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FREX100 | No | UBE | BXU548345 |  | 6 |  | CRP | F0911 DETAIL TO BATCH HEADER | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Robbin/Florencia | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/04/2019 | 9/04/2019 |  | 1846 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 07:17 | Joshi, Abhishek N | 56-F-EU-V-190828-S6FI074 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190828-S6FIV074A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FREX11 | No | UBE | BXU550456 |  | 6 |  | CRP | F0411 - Batch Header Posted, Detail Unposted | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/04/2019 | 9/04/2019 |  | 1847 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 06:41 | Joshi, Abhishek N | 56-F-EU-V-190828-S6FI075 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190828-S6FIV075A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FREX12 | No | UBE | BXU550454 |  | 6 |  | CRP | Payments Different in F0411 and F0414 | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/4/2019 | 9/3/2019 |  | 1848 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 06:22 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI005 |  | Yes | [7 empty] | 56-F-EU-V-190827-S6FIV005A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FREX13 | No | UBE | BXU550457 |  | 6 |  | CRP | Payments Different in F0911 and F0414 | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/3/2019 | 9/2/2019 |  | 1849 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 06:26 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI008 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV008A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FREX14 | No | UBE | BXU549454 |  | 6 |  | CRP | F0911 detail But No Batch Header | L3 Pass | 450 |  | TRUE | LNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/4/2019 | 9/3/2019 |  | 1850 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 06:00 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI033 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV033A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FREX15 | No | UBE | BXU549455 |  | 6 |  | CRP | Invalid Posting Key on Obj - Recurring | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1851 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 06:03 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI045 |  | Yes | [7 empty] | 56-F-EU-V-190827-S6FIV045A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FREX16A | No | UBE | BXU547569 |  | 6 |  | CRP | Inactive BUs used by Indexed Allocations | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/4/2019 | 9/3/2019 |  | 1852 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 07:18 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI028 |  | Yes | Y | [6 empty] | 56-F-EU-V-190827-S6FIV028A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FREX16C | No | UBE | BXU547580 |  | 6 |  | CRP | Inactive BUs used by Recurring Allocations | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/4/2019 | 9/2/2019 |  | 1853 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 07:22 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI037 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV037A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FREX19 | No | UBE | BXU550458 |  | 6 |  | CRP | AP Logging Report Reconciled to GL | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/5/2019 | 9/4/2019 |  | 1854 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 06:28 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI023 | Report | Yes | [7 empty] | 56-F-EU-V-190827-S6FIV023A,B,C,D | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FREX21 | No | UBE | BXU549456 |  | 6 |  | CRP | Check VAT on AP (F0411) records | L3 Pass | 311 |  | TRUE | LNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/5/2019 | 9/4/2019 |  | 1855 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 06:05 | Joshi, Abhishek N | 56-F-EU-V-190828-S6FI089 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190828-S6FIV089A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FREX27 | No | UBE | BXU548742 |  | 6 |  | CRP | Batches Posted in F0011 and Not Posted in F03B14 | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/5/2019 | 9/4/2019 |  | 1856 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 09:11 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI013 |  | Yes | Y | [6 empty] | 56-F-EU-V-190827-S6FIV013A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FREX28 | No | UBE | BXU549457 |  | 6 |  | CRP | Transactions w/o Account Master | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Robbin/Florencia | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/5/2019 | 9/4/2019 |  | 1857 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 06:09 | Joshi, Abhishek N | 56-F-EU-V-190827-S6049 | CRP | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6V049A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FREX2B | No | UBE | BXU548812 |  | 6 |  | CRP | F0411 Where Perod NE GL Date | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/5/2019 | 9/5/2019 |  | 1858 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 04:57 | Joshi, Abhishek N | 56-F-EU-V-190828-S6FI083 |  | Yes | [7 empty] | 56-F-EU-V-190828-S6FIV083A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FREX2C | No | UBE | BXU548741 |  | 6 |  | CRP | F03B11 Where Perod NE GL Date | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/05/2019 | 9/05/2019 |  | 1859 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 09:11 | Joshi, Abhishek N | 56-F-EU-V-190828-S6FI076 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190828-S6FIV076A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FREX30C | No | UBE | BXU547727 |  | 6 |  | CRP | PO Differences - F4311 not in F43121 | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 09/06/2019 | 09/04/2019 |  | 1860 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 07:25 | Joshi, Abhishek N | 56-F-EU-V-190830-S6FI116 |  | Yes | Y | [6 empty] | 56-F-EU-V-190830-S6FIV116A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FREX50 | No | UBE | BXU550473 |  | 6 |  | CRP |  | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/5/2019 | 9/4/2019 |  | 1861 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 09:13 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI034 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV034A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRFA09 | No | UBE | BXU549459 |  | 6 |  | CRP | Print Work Order Cost Summary | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/5/2019 | 9/4/2019 |  | 1862 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 07:38 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI011 | Printer | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV011A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRFA10 | No | UBE | BXU549460 |  | 6 |  | CRP | Capex Tracking Report | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/5/2019 | 9/5/2019 |  | 1863 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 07:40 | Joshi, Abhishek N |  | Report | Yes | Yes |  |  | 56-F-EU-V-190829-S6FI099 |  |  |  | 56-F-EU-V-190829-S6FIV099A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL05 | No | UBE | BXU549462 |  | 6 |  | CRP | Expense by Responsibility - Transaction Listing | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/5/2019 | 9/4/2019 |  | 1864 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 09:28 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI052 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV052A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL06 | No | UBE | BXU549463 |  | 6 |  | CRP | Expense by Responsibility - Summary | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/5/2019 | 9/4/2019 |  | 1865 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 07:41 | Joshi, Abhishek N | 56-F-EU-V-190829-S6FI103 |  | Yes | Y | [6 empty] | 56-F-EU-V-190829-S6FIV103A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL09 | No | UBE | BXU549244 |  | 6 |  | CRP | Expense by Responsibility - Transaction Listing | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/5/2019 | 9/2/2019 |  | 1866 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 07:43 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI044 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV044A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL101 | No | UBE | BXU547584 |  | 6 |  | CRP | Data Analysis from F0911 CSV - All Periods | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/5/2019 | 9/4/2019 |  | 1867 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 07:30 | Joshi, Abhishek N | 56-F-EU-V-190829-S6FI095 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190829-S6FIV095A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL102 | No | UBE | BXU548344 |  | 6 |  | CRP | DATA ANALYSIS FROM F0911 CSV WITH GRANTS ALL PERIODS | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 09/05/2019 | 09/04/2019 |  | 1868 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 07:32 | Joshi, Abhishek N | 56-F-EU-V-190828-S6FI078 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190828-S6FIV078A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL110 | No | UBE | BXU547585 |  | 6 |  | CRP | Capex Tracking Report | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/5/2019 | 9/4/2019 |  | 1869 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 07:36 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI024 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190827-S6FIV024A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL14 | No | UBE | BXU549245 |  | 6 |  | CRP | Zero Amounts of Period | L3 Pass | 312 |  | TRUE | LNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/5/2019 | 9/4/2019 |  | 1870 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 07:45 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI056 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV056A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL3F | No | UBE | BXU549246 |  | 6 |  | CRP | GL Reconciliation | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Manuel Touyaa | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/5/2019 | 9/4/2019 |  | 1871 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 07:46 | Joshi, Abhishek N | 56-F-EU-V-190829-S6FI106 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190829-S6FIV106A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL41 | No | UBE | BXU549254 |  | 6 |  | CRP | UK VAT Partial Exemption report - CSV Extract | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/5/2019 | 9/5/2019 |  | 1872 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 08:07 | Joshi, Abhishek N | 56-F-EU-V-190828-S6FI088 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190828-S6FIV088A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL61 | No | UBE | BXU549247 |  | 6 |  | CRP | P&L by BU Category Code 7 | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Manuel Touyaa | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/05/2019 | 9/05/2019 |  | 1873 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 08:09 | Joshi, Abhishek N | 56-F-EU-V-190828-S6FI077 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190828-S6FIV077A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL62 | No | UBE | BXU549248 |  | 6 |  | CRP | GL 3 Ledger (AA-UG-UL) YTD | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Manuel Touyaa | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 09/06/2019 | 09/05/2019 |  | 1874 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 09:45 | Joshi, Abhishek N | 56-F-EU-V-190830-S6FI117 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190830-S6FIV117A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL63 | No | UBE | BXU549249 |  | 6 |  | CRP | Monthly BS & PL | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/6/2019 | 9/6/2019 |  | 1875 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 08:10 | Joshi, Abhishek N | 56-F-EU-V-190828-S6FI069 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190828-S6FIV069A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL68 | No | UBE | BXU549250 |  | 6 |  | CRP | Sales Information by Division | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/6/2019 | 9/5/2019 |  | 1876 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 08:13 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI025 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV025A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL70 | No | UBE | BXU549252 |  | 6 |  | CRP | Hyperion Download | L3 Pass | 345 | Closed | TRUE | HNE2E |  | Finance GL | Finance | Manuel Touyaa | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/6/2019 | 9/5/2019 |  | 1877 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 08:18 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI057 | Download | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV057A, 56-F-EU-V-190827-S6FIV057B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL72 | No | UBE | BXU549234 |  | 6 |  | CRP | Hyperion Download Consolidation | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/6/2019 | 9/5/2019 |  | 1878 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 08:21 | Joshi, Abhishek N | 56-F-EU-V-190828-S6FI079 | Download | Yes | Yes | [6 empty] | 56-F-EU-V-190828-S6FIV079A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL73 | No | UBE | BXU549171 |  | 6 |  | CRP | IR & UK VAT Reports A/P Detail and Summary | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/6/2019 | 9/5/2019 |  | 1879 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 08:26 | Joshi, Abhishek N | 56-F-EU-V-190828-S6FI090 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190828-S6FIV090A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL75 | No | UBE | BXU549231 |  | 6 |  | CRP | Copy BUCatCode 26 to AccountCatCode 23 | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/6/2019 | 9/5/2019 |  | 1880 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 09:50 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI036 |  | Yes | Y | [6 empty] | 56-F-EU-V-190827-S6FIV036A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL80 | No | UBE | BXU549232 |  | 6 |  | CRP | Cost Centre Trend Report | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/6/2019 | 9/6/2019 |  | 1881 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 09:52 | Joshi, Abhishek N | 56-F-EU-V-190829-S6FI100 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190829-S6FIV100A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL81 | No | UBE | BXU549233 |  | 6 |  | CRP | Trial Balance by Foreign Currency | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/6/2019 | 9/6/2019 |  | 1882 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 08:30 | Joshi, Abhishek N | 56-F-EU-V-190829-S6FI104 |  | Yes | Y | [6 empty] | 56-F-EU-V-190829-S6FIV104A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL83 | No | UBE | BXU549235 |  | 6 |  | CRP | Account & Business Unit Master - csv format | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/06/2019 | 9/06/2019 |  | 1883 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 08:31 | Joshi, Abhishek N | 56-F-EU-V-190829-S6FI101 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190829-S6FIV101A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL85 | No | UBE | BXU549236 |  | 6 |  | CRP | Data Analysis CSV - F0901/F0000/F0902 | L3 Pass | 316 | Closed | TRUE | LNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 09/09/2019 | 09/06/2019 |  | 1884 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 09:55 | Joshi, Abhishek N | 56-F-EU-V-190830-S6FI118 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190830-S6FIV118A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL90 | No | UBE | BXU549237 |  | 6 |  | CRP | CO NEQ KCO Reconcilation Report | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/6/2019 | 9/5/2019 |  | 1885 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 08:41 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI035 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV035A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL91 | No | UBE | BXU549238 |  | 6 |  | CRP | Update F0011 Batch Status | L3 Pass | 329 |  | TRUE | LNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/6/2019 | 9/6/2019 |  | 1886 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 08:43 | Joshi, Abhishek N | 56-F-EU-V-190828-S6FI059 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190828-S6FIV059A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL92 | No | UBE | BXU549239 |  | 6 |  | CRP | Fast Running GL Integrity Reports | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 09/11/2019 | 09/05/2019 |  | 1887 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 08:45 | Joshi, Abhishek N | 56-F-EU-V-190830-S6FI119 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190830-S6FIV119A, | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FXDSOA | No | UBE | BXU548721 |  | 6 |  | CRP | Flexible DSO UBE | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete | 27/08 Output shared for confirmation |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/22/2019 | 8/21/2019 |  | 1888 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 09:17 | Joshi, Abhishek N | 56-F-EU-V-190813-S5FI061 |  | Yes | Y | [6 empty] | 56-F-EU-V-190813-S5FIV061A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600009 | No | UBE |  |  | 999 |  |  | Job Queue Activate / Inactivate | Obsolete | [5 empty] | CNC | CNC | Rob Zande | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma | VV-29/08 - Obsoleted as per confirmation from Rob and BSL |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1889 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-29 08:04 | Verma, Vikas | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560015 | No | UBE | BXU549093 |  | 6 |  | CRP | Automatic Update Finance Currency Rates | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/6/2019 | 9/5/2019 |  | 1890 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 09:57 | Joshi, Abhishek N | 56-F-EU-V-190830-S6FI108 |  | Yes | Y | [6 empty] | 56-F-EU-V-190830-S6FIV108A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600151 | No | UBE | BXU549093 |  | 6 |  | CRP | Automatic Update Finance Currency Rates - TC | L3 Pass | 337 |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/6/2019 | 9/5/2019 |  | 1891 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 09:59 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI038 |  | Yes | Y | [6 empty] | 56-F-EU-V-190827-S6FIV038A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600152 | No | UBE | BXU549093 |  | 6 |  | CRP | Automatic Update Finance Currency Rates to F0015 | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/6/2019 | 9/4/2019 |  | 1892 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 09:58 | Joshi, Abhishek N | 56-F-EU-V-190828-S6FI080 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190828-S6FIV080A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600153 | No | UBE | BXU549093 |  | 6 |  | CRP | Automatic Update Finance Currency Restatement Rates to F1113 | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/6/2019 | 9/5/2019 |  | 1893 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 10:56 | Joshi, Abhishek N | 56-F-EU-V-190830-S6FI109 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190830-S6FIV109A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5601ZP3 | No | UBE | BXU544679 |  | 6 |  |  | Purge Address Book Batch file - F0101Z2 (Del) | L3 Pass |  |  | TRUE | L |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/16/2019 | 9/15/2019 |  | 1894 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 06:39 | Joshi, Abhishek N | 56-F-EU-V-190912-S6MD009 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190912-S6MDV009A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5601ZP5 | No | UBE |  |  | 6 |  |  | Purge Customer Batch file - F03012Z1 (Del) | L3 Pass |  |  | TRUE | L |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/16/2019 | 9/16/2019 |  | 1895 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-17 05:57 | Icardo, Ana | 56-F-EU-V-190912-S6MD010 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190912-S6MDV010A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5601ZP7 | No | UBE | BXU544564 |  | 6 |  |  | Purge Supplier Batch file - F0401Z1 (Del) | L3 Pass |  |  | TRUE | L |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth, Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/17/2019 | 9/16/2019 |  | 1896 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 06:44 | Joshi, Abhishek N | 56-F-EU-V-190909-S6MD007 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190909-S6MDV007A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5601ZP9 | No | UBE | BXU544680 |  | 6 |  |  | Purge Bank Upload Batch file - F5530Z1 (Del) | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/17/2019 | 9/17/2019 |  | 1897 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 06:46 | Joshi, Abhishek N | 56-F-EU-V-190916-S6MD011 | Upload | Yes | Y | [6 empty] | 56-F-EU-V-190916-S6MDV011A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56030008 | No | UBE | BXU548723 |  | 6 |  | CRP | Citibank Receipts Netting Upload to F03B13Z1 | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 09/18/2019 | 09/17/2019 |  | 1898 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 08:07 | Joshi, Abhishek N | 56-F-EU-V-190819-S5FI113 | Upload | Yes | Y | [6 empty] | 56-F-EU-V-190819-S5FIV113A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560301 | No | UBE | BXU548724 |  | 5 |  | CRP | Credit Limit Extraction From F03012 and F0101 | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/22/2019 | 8/22/2019 |  | 1899 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 08:09 | Joshi, Abhishek N | 56-F-EU-V-190814-S5FI075 |  | Yes | Y | [6 empty] | 56-F-EU-V-190814-S5FIV075A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56032001 | No | UBE | BXU548718 |  | 2 |  | CRP | AutoCash - Table Converter | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 03/07/2019 | 03/07/2019 |  | 1900 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 08:11 | Joshi, Abhishek N | 56-F-EU-V-190611-S2FI019 |  | Yes | Y |  |  | Abhishek Deshmukh,dependent object R57032002 is on hold |  |  |  | 56-F-EU-V-190611-S2FIV19A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56032010 | No | UBE | BXU548718, BXU550198 |  | 2 |  | CRP | CH - Driver - AutoCash Upload UBS Bank File (BESR) | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 17-06-2019 | 17-06-2019 |  | 1901 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 09:19 | Joshi, Abhishek N | 56-F-EU-V-190626-S2FI059 | Upload | Yes | Y | [6 empty] | 56-F-EU-V-190626-S2FIV059A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56032011 | No | UBE | BXU548718 |  | 2 |  | CRP | AutoCash Upload Bank Statement File (BESR - CH) - TC | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/14/2019 | 6/14/2019 |  | 1902 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 08:12 | Joshi, Abhishek N | 56-F-EU-V-190610-S2FI009 | Upload | Yes | Y | [6 empty] | 56-F-EU-V-190610-S2FIV009A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5603B01A | No | UBE | BXU549241 |  | 3 |  | CRP | Realised and unrealised F/X Gains/Losses - Summary Print | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Robbin/Florencia | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saieja |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 1/7/2019 | 1/7/2019 |  | 1903 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 10:57 | Joshi, Abhishek N | 56-F-EU-V-190701-S3FI070 | Printer | Yes | Y |  |  | VV-28/06 - Moved to Sprint 3 as per request from Luigi |  |  |  | 56-F-EU-V-190701-S3FIV070A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5604571 | No | UBE | BXU548813 |  | 3 |  | CRP | A/P Auto Payments - Print Driver (Netting) | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 06/28/2019 | 06/27/2019 |  | 1904 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 05:01 | Joshi, Abhishek N |  | Printer | Yes | Y |  |  | PG 22/07: awaiting deployment of P5604571 |  |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5604576 | No | UBE | BXU548814 |  | 3 |  | CRP | A/P Auto Payment Register (Netting) | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saieja |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 06/28/2019 | 06/27/2019 |  | 1905 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 05:02 | Joshi, Abhishek N | 56-F-EU-V-190626-S3FI021 |  | Yes | Y |  |  | PG 22/07: awaiting deployment of P5604571 |  |  |  | 56-F-EU-V-190626-S3FIV021A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560513 | No | UBE |  |  | 5 |  |  | NSF Automation from BANSTA format | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/22/2019 | 8/21/2019 |  | 1906 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-30 02:52 | Alvargonzalez, Francisco | 56-F-EU-V-190814-S5FI082 |  | Yes | Y | [6 empty] | 56-F-EU-V-190814-S5FIV082A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560902C | No | UBE | BXU549240 |  | 6 |  | CRP | Balance Ledger Copy | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Robbin/Florencia | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 09/06/2019 | 09/05/2019 |  | 1907 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 11:19 | Joshi, Abhishek N | 56-F-EU-V-190828-S6FI081 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190828-S6FIV081A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560902Z | No | UBE | BXU549242 |  | 6 |  | CRP | Zero Out F0902 Beginning Balance | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/6/2019 | 9/5/2019 |  | 1908 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 08:46 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI026 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV026A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560911 | No | UBE |  |  | 6 |  | CRP | CSV download of F0911 and F0901 | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/6/2019 | 9/5/2019 |  | 1909 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-15 04:29 | Felitto, Gregory | 56-F-EU-V-190827-S6FI058 | Download | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV058A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560911C | No | UBE | BXU549243 |  | 6 |  | CRP | GL - CSV Summary by Co/Doc type | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/6/2019 | 9/5/2019 |  | 1910 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 11:21 | Joshi, Abhishek N | 56-F-EU-V-190828-S6FI091 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190828-S6FIV091A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R561201 | No | UBE |  |  | 6 |  | CRP | Fixed Asset for Germany | L3 Pass |  |  | TRUE | HNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/9/2019 | 9/9/2019 |  | 1911 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-15 06:05 | Slaby, Libor | 56-F-EU-V-190828-S6FI084 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190828-S6FIV084A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5612G99 | No | UBE |  |  | 999 |  |  | Upload Leased Hardware Transactions from WISE | Obsolete | [5 empty] | Finance FA | Finance | Libor Slaby |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1912 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Upload | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56150Z1 | No | UBE | BXU544564 |  | 6 |  |  | Upload Parent Address Book Numbers | L3 Pass |  |  | TRUE | L |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saieja |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/2/2019 | 7/2/2019 |  | 1913 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 07:12 | Joshi, Abhishek N | 56-F-EU-V-010719-S2MD050 | Upload | Yes | Y | [6 empty] | 56-F-EU-V-010719-S2MD050A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56150ZP | No | UBE | BXU546238 |  | 6 |  |  | Purge Parent Upload Batch file - F56150Z1 (Del) | L3 Pass |  |  | TRUE | L |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 09/04/2019 | 09/03/2019 |  | 1914 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 07:04 | Joshi, Abhishek N | 56-F-EU-V-190827-S6MD003 | Upload | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6MDV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5618276 | No | UBE |  |  | 6 |  | CRP | Held Sales Order Report | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth, Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/9/2019 | 9/6/2019 |  | 1915 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-08 08:35 | BAYINDIR, AYSE | 56-F-EU-V-190830-S6FI126 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190830-S6FIV126A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R563B5002E | No | UBE | BXU546032 |  | 4 |  | CRP | BAXTER ECEMEA Statement Print | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/7/2019 | 8/6/2019 |  | 1916 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-08 00:42 | Joshi, Abhishek N | 56-F-EU-V-190731-S4FI069 | Printer | Yes | Y | [6 empty] | 56-F-EU-V-190731-S4FIV069A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564300 | No | UBE | BXU550821 |  | 6 |  |  | Intrastat Arrivals | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1917 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-20 07:16 | Joshi, Abhishek N | 56-F-EU-V-190827-S6LO015 |  | Yes | Yes |  |  |  | KTW4 |  |  | 56-F-EU-V-190827-S6LOV015A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564301A | No | UBE |  |  | 999 |  |  | Intrastat - Refresh of F56VATA | Obsolete | [5 empty] | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1918 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564302 | No | UBE | BXU550844 |  | 6 |  |  | Intrastat Report | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/4/2019 | 9/3/2019 |  | 1919 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-23 04:54 | Joshi, Abhishek N | 56-F-EU-V-190827-S6LO008 | Report | Yes | Yes |  |  |  | KTW4 |  |  | 56-F-EU-V-190827-S6LOV008A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564308 | No | UBE | BXU549986 |  | 4 |  | CRP | Maximo JDE / GRN invoice extract | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/7/2019 | 8/6/2019 |  | 1920 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 03:46 | Joshi, Abhishek N | 56-F-EU-V-190731-S4FI075 |  | Yes | [7 empty] | 56-F-EU-V-190731-S4FIV075A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564310 | No | UBE | BXU549994 |  | 4 |  | CRP | Interface SPRING/SAPA to JDE | L3 Pass | 251 |  | TRUE | HE2E |  | Finance AP | Finance | Keith Haxton | L2 Pass / Complete | As per Keith mail-There are no records uploaded for the same batch numbers where TORG = SPRING_INT.Perhaps this is to be expected as R5643101 is in sprint 6 and we will need to be tested again once approved in that sprint.For now please pass the test. |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/7/2019 | 8/6/2019 |  | 1921 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 03:46 | Joshi, Abhishek N | 56-F-EU-V-190805-S4FI096 | Interface | Yes | [7 empty] | 56-F-EU-V-190805-S4FIV096A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643100 | No | UBE | BXU550010 |  | 4 |  | CRP | Import Text File SPRING/SAPA to F5643100 | L3 Pass | 251 |  | TRUE | HE2E |  | Finance AP | Finance | Keith Haxton | L2 Pass / Complete | As per Keith mail-There are no records uploaded for the same batch numbers where TORG = SPRING_INT.Perhaps this is to be expected as R5643101 is in sprint 6 and we will need to be tested again once approved in that sprint.For now please pass the test. |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/7/2019 | 8/6/2019 |  | 1922 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 03:51 | Joshi, Abhishek N | 56-F-EU-V-190807-S4FI100 | Text | Yes | [7 empty] | 56-F-EU-V-190807-S4FIV100A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647071F | No | UBE | BXU548815 |  | 4 |  | CRP | Process set of 500 records F47071 (JDB9900600 error) | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/7/2019 | 8/6/2019 |  | 1923 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 05:06 | Joshi, Abhishek N | 56-F-EU-V-190806-S4FI099 | Error | Yes | Yes | [6 empty] | 56-F-EU-V-190806-S4FIV099A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5674001 | No | UBE | BXU551100 |  | 2 |  | CRP | Baxter Withholding Tax Certification - Italy | L3 Pass | 163 | Closed | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1924 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-04-02 06:48 | Joshi, Abhishek N | 56-F-EU-V-190611-S2FI024 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190611-S2FIV024A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56912AR | No | UBE | BXU549744 |  | 5 |  | CRP | Calculate new factor | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/22/19 | 8/21/19 |  | 1925 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 11:23 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI028 |  | Yes | Y | [6 empty] | 56-F-EU-V-190812-S5FIV028A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56BR901 | No | UBE |  |  | R4 |  | CRP | P2P - BBR - Account iface LOAD F56BR901 | L3 Pass |  |  | TRUE |  | TRUE | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete | HR01/20 Passed as per the new test script |  |  | Terry Greenard / Vikas Verma | VV:06/12 As per reqeuest from Peter, Sprint to R4 from 999 | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 12/09/2019 | 12/06/2019 |  | 1926 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-13 08:34 | Gilthorpe, Peter | 56-F-EU-V-191206-R4FI002 |  | Yes | [7 empty] | 56-F-EU-V-191206-R4FIV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56CRAPX | No | UBE |  |  | 999 |  |  | Concur Interface - Amex/PCard Reg Extract | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1927 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Interface | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56CREXG | No | UBE |  |  | 999 |  |  | Concur Interface - Exchange Rate Extract to File | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1928 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Interface | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56CRMCU | No | UBE |  |  | 999 |  |  | Concur Interface - Business Unit Extraction | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1929 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Interface | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56EDIREC | No | UBE | BXU548816 |  | 4 |  | CRP | Receipts EDI Error Report | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/7/2019 | 8/6/2019 |  | 1930 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 05:07 | Joshi, Abhishek N | 56-F-EU-V-190801-S4FI006 | Error / Report | Yes | Y | [6 empty] | 56-F-EU-V-190801-S4FIV006A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FF001 | No | UBE | BXU548719 |  | 3 |  | CRP | Converting Farmafactoring file to FF workfile(F56FFUI1) | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/11/2019 | 7/10/2019 |  | 1931 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 09:22 | Joshi, Abhishek N | 56-F-EU-V-190709-S3FI154 |  | Yes | Y |  |  | R56FF001 report is called from R56FF001A report |  |  |  | 56-F-EU-V-190709-S3FIV154A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FF001A | No | UBE | BXU548719 |  | 3 |  | CRP | Driver Farmafactoring Upload | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/11/2019 | 7/10/2019 |  | 1932 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 09:25 | Joshi, Abhishek N | 56-F-EU-V-190710-S3FI161 | Upload | Yes | Y | [6 empty] | 56-F-EU-V-190710-S3FIV161A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FF002 | No | UBE | BXU548726 |  | 3 |  | CRP | Upload FF workfile(F56FFUI1) to F03B13Z1 and Report | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/11/2019 | 7/11/2019 |  | 1933 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 09:25 | Joshi, Abhishek N | 56-F-EU-V-190708-S3FI123 | Upload / Report | Yes | Y | [6 empty] | 56-F-EU-V-190708-S3FIV123A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRAP124 | No | UBE | BXU546846 |  | 6 |  | CRP | Spain VAT Reporting - Accounts Payable | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/9/2019 | 9/6/2019 |  | 1934 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 09:08 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI059 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV059A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRAP130 | No | UBE |  |  | 6 |  | CRP | Update UBE for AVMP - With Credit Notes | L3 Pass | 358 | Open | TRUE | HNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/9/2019 | 9/6/2019 |  | 1935 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-23 08:53 | GOLGE, SERAY | 56-F-EU-V-190827-S6FI015 |  | Yes | Y | [6 empty] | 56-F-EU-V-190827-S6FIV015A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRAP132 | No | UBE |  |  | 6 |  | CRP | CBR Manual Report | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/9/2019 | 9/6/2019 |  | 1936 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-06 10:27 | Touyaa, Manuel | 56-F-EU-V-190829-S6FI097 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190829-S6FIV097A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRAP141 | No | UBE | BXU549988 |  | 6 |  | CRP | Finance Reporting AP Ledger | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Constanza Frade Dolesor | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/9/2019 | 9/9/2019 |  | 1937 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 04:48 | Joshi, Abhishek N | 56-F-EU-V-190830-S6FI124 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190830-S6FIV124A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRAP142 | No | UBE | BXU549989 |  | 6 |  | CRP | Finance Reporting AP Payments | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Constanza Frade Dolesor | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/9/2019 | 9/9/2019 |  | 1938 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 05:57 | Joshi, Abhishek N | 56-F-EU-V-190909-S6FI119 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190909-S6FIV119A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRAP143 | No | UBE | BXU549990 |  | 6 |  | CRP | Finance Reporting AP Ledger ICO | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Constanza Frade Dolesor | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/09/2019 | 9/09/2019 |  | 1939 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 06:00 | Joshi, Abhishek N | 56-F-EU-V-190829-S6FI105 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190829-S6FIV105A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRAP144 | No | UBE |  |  | 6 |  | CRP | Financial Reporting - AP Ledger Refunds | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Constanza Frade Dolesor | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 09/09/2019 | 09/06/2019 |  | 1940 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-08 10:49 | Frade Dolesor, Constanza | 56-F-EU-V-190905-S6FI117 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190905-S6FIV117A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRAP148 | No | UBE | BXU548320 |  | 6 |  | CRP | Finance Reporting AP Logging | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Constanza Frade Dolesor | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/9/2019 | 9/6/2019 |  | 1941 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 04:15 | Joshi, Abhishek N | 56-F-EU-V-190903-S6FI038 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190903-S6FIV038A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRAP149 | No | UBE | BXU548321 |  | 6 |  | CRP | Finance Reporting Open GRNs | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Constanza Frade Dolesor | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/9/2019 | 9/8/2019 |  | 1942 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 04:18 | Joshi, Abhishek N | 56-F-EU-V-190828-S6FI060 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190828-S6FIV060A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRAP63 | No | UBE | BXU550459 |  | 6 |  | CRP | IRPF Report (withholding tax report) | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/9/2019 | 9/8/2019 |  | 1943 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 06:31 | Joshi, Abhishek N | 56-F-EU-V-190830-S6FI111 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190830-S6FIV111A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRAR127 | No | UBE | BXU546705 |  | 6 |  | CRP | Spain VAT Reporting - Accounts Recieveable Canary Island | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/9/2019 | 9/8/2019 |  | 1944 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 09:25 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI039 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV039A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRAR130 | No | UBE | BXU548322 |  | 5 |  | CRP | Finance Reporting ICO A/R Ledger | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/26/2019 | 8/26/2019 |  | 1945 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 06:43 | Joshi, Abhishek N | 56-F-EU-V-190826-S5FI030 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190826-S5FIV030A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRAR132 | No | UBE | BXU546007 |  | 5 |  | CRP | A/R Details with Aging - Detail only CSV | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/26/2019 | 8/26/2019 |  | 1946 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 06:45 | Joshi, Abhishek N | 56-F-EU-V-190819-S5FI112 |  | Yes | Y | [6 empty] | 56-F-EU-V-190819-S5FIV112A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRAR133 | No | UBE | BXU548323 |  | 5 |  | CRP | Finance Reporting Trade A/R Ledger | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 08/26/2019 | 08/23/2019 |  | 1947 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 06:46 | Joshi, Abhishek N | 56-F-EU-V-190821-S5FI029 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190821-S5FIV029A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRAR134 | No | UBE | BXU548324 |  | 5 |  | CRP | Financial Reporting - Cash Receipts on F03B13 FY/PN | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/26/2019 | 8/23/2019 |  | 1948 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 06:48 | Joshi, Abhishek N | 56-F-EU-V-190814-S5FI087 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190814-S5FIV087A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRFA15 | No | UBE | BXU550773 |  | 6 |  | CRP | De/Re - Activation of CPAs - PDF output | L3 Pass |  |  | TRUE | HNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete | Issue is fixed now. L2 defect 332 is closed. |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/9/2019 | 9/8/2019 |  | 1949 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-24 04:50 | Joshi, Abhishek N | 56-F-EU-V-190828-S6FI082 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190828-S6FIV082A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRFA16 | No | UBE | BXU549321 |  | 6 |  | CRP | Identify Invalid CPAs/Projects - CSV output | L3 Pass |  |  | TRUE | HNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/9/2019 | 9/6/2019 |  | 1950 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 02:41 | Joshi, Abhishek N | 56-F-EU-V-190830-S6FI110 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190830-S6FIV110A , 56-F-EU-V-190830-S6FIV110B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRFA18 | No | UBE | BXU550774 |  | 6 |  | CRP | Financial Reporting - Asset Master | L3 Pass |  |  | TRUE | LNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 09/09/2019 | 09/06/2019 |  | 1951 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-24 04:51 | Joshi, Abhishek N | 56-F-EU-V-190829-S6FI102 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190829-S6FIV102A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRFA20 | No | UBE | BXU550864 |  | 6 |  | CRP | Financial Reporting - Asset Transfer | L3 Pass |  |  | TRUE | LNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth, Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/9/2019 | 9/6/2019 |  | 1952 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-24 04:52 | Joshi, Abhishek N | 56-F-EU-V-190903-S6FI131 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190903-S6FIV131A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRGL118 | No | UBE | BXU544975 |  | 6 |  | CRP | GL to VAT posting UBE | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/9/2019 | 9/6/2019 |  | 1953 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 09:32 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI060 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV060A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRGL124 | No | UBE | BXU544972 |  | 6 |  | CRP | VAT Control Report | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/9/2019 | 9/6/2019 |  | 1954 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 06:36 | Joshi, Abhishek N | 56-F-EU-V-190829-S6FI098 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190829-S6FIV098A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRGL15 | No | UBE | BXU549737 |  | 6 |  | CRP | Ledger Clear down report for F0911 | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/9/2019 | 9/9/2019 |  | 1955 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 08:49 | Joshi, Abhishek N | 56-F-EU-V-190909-S6FI120 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190909-S6FIV120A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRGL96 | No | UBE | BXU549742 |  | 6 |  | CRP | Ledger Entry Report - CSV Extract | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/09/2019 | 9/09/2019 |  | 1956 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 08:51 | Joshi, Abhishek N | 56-F-EU-V-190830-S6FI121 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190830-S6FIV121A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56GETPD02 | No | UBE | BXU545550 |  | 1 |  | CRP | GetPaid - Text File creature UBE ARCUST | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Vijey Sesha | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 19/05/30 | 19/05/30 |  | 1957 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 04:25 | Joshi, Abhishek N | 56-F-EU-V-190530-S1FI019 | Text | Yes | Yes |  |  | No retrofit required |  |  |  | 56-F-EU-V-190530-S1FIV019A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56GETPD03 | No | UBE | BXU545550 |  | 1 |  | CRP | GetPaid ARCASH build programs (F56ARCSH) | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Vijey Sesha | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/03/2019 | 5/31/2019 |  | 1958 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 04:27 | Joshi, Abhishek N | 56-F-EU-V-190529-S1FI036 |  | Yes | Yes |  |  | Retrofit not required |  |  |  | 56-F-EU-V-190529-S1FIV036A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56GETPD05 | No | UBE | BXU545550 |  | 1 |  | CRP | GetPaid - Text File creature UBE ARMAST | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Vijey Sesha | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/3/2019 | 5/31/2019 |  | 1959 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 04:28 | Joshi, Abhishek N | 56-F-EU-V-190529-S1FI065 | Text | Yes | Yes |  |  | There is File path value Diff b/w PD812 and DV920 in few versions. However did not modify and moved for build as is(Confirmed by Robert) |  |  |  | 56-F-EU-V-190529-S1FIV65A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56GETPD06 | No | UBE | BXU545550 |  | 1 |  | CRP | GetPaid - Text File creature UBE ARCASH | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Vijey Sesha | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/03/2019 | 6/03/2019 |  | 1960 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 04:28 | Joshi, Abhishek N | 56-F-EU-V-190530-S1FI187 | Text | Yes | Y | [6 empty] | 56-F-EU-V-190530-S1FIV187A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56GETPD07 | No | UBE | BXU545550 |  | 1 |  | CRP | GetPaid - Text File creature UBE AREXTI | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Vijey Sesha | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/4/2019 | 6/3/2019 |  | 1961 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 04:29 | Joshi, Abhishek N | 56-F-EU-V-190530-S1FI184 | Text | Yes | Y | [6 empty] | 56-F-EU-V-190530-S1FIV184A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56GETPD08 | No | UBE | BXU545550 |  | 1 |  | CRP | GetPaid - Text File creature UBE ARTRAN | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Vijey Sesha | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/3/2019 | 6/3/2019 |  | 1962 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 04:30 | Joshi, Abhishek N | 56-F-EU-V-190528-S1FI014 | Text | Yes | Yes | [6 empty] | 56-F-EU-V-190528-S1FIV014A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56GETPD09 | No | UBE | BXU546010 |  | 1 |  |  | Update F03012 with F03B11 Last Inv and Last Paid Dates | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Nithya Ramachandran | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/3/2019 | 6/3/2019 |  | 1963 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 06:52 | Joshi, Abhishek N | 56-F-EU-V-190530-S1FI067 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190530-S1FI067A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56GL119A | No | UBE | BXU549740 |  | 6 |  | CRP | Balance Trimestral de Sumas y Saldos | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/10/2019 | 9/10/2019 |  | 1964 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 08:57 | Joshi, Abhishek N | 56-F-EU-V-190828-S6FI085 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190828-S6FIV085A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56KP001 | No | UBE | BXU550729 |  | 6 |  | CRP | KPI Control Driver | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/10/2019 | 9/9/2019 |  | 1965 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-23 02:30 | Joshi, Abhishek N | 56-F-EU-V-190903-S6FI134 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190903-S6FIV134A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56KP03A | No | UBE | BXU550730 |  | 6 |  | CRP | KPI Aging - Reviewed by company | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/10/2019 | 9/9/2019 |  | 1966 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-23 02:31 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI061 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV061A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56TEREB | No | UBE | BXU549547 |  | 6 |  | CRP | Rebill Extract Report for T&E | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/10/2019 | 9/9/2019 |  | 1967 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 11:25 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI016 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV016A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R57032WK | No | UBE | BXU548720 |  | 2 |  | CRP | TEST VERSION - Bank Receipting Debit/Credits Workfile Report | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 13-06-2019 | 13-06-2019 |  | 1968 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 08:14 | Joshi, Abhishek N | 56-F-EU-V-190611-S2FI002 | Report | Yes | Y |  |  | Dependent on R56032000 ,R57032002 and these are on hold as they are dependent on DSI objects |  |  |  | 56-F-EU-V-190611-S2FIV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5703B421C | No | UBE | BXU550351 |  | 5 |  | CRP | A/R Details with Aging - By Parent Number | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/26/2019 | 8/23/2019 |  | 1969 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 04:00 | Joshi, Abhishek N | 56-F-EU-V-190819-S5FI109 |  | Yes | Y | [6 empty] | 56-F-EU-V-190819-S5FIV109A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5703B426 | No | UBE | BXU549546 |  | 6 |  | CRP | A/R Gains/Losses Report - Accounts Validation | L3 Pass | 364 | CLOSED | TRUE | HNE2E |  | Finance GL | Finance | Lokesh Reddy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/10/2019 | 9/9/2019 |  | 1970 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 11:28 | Joshi, Abhishek N | 56-F-EU-V-190903-S6FI132 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190903-S6FIV132A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5704425 | No | UBE | BXU549544 |  | 6 |  | CRP | A/P Unrealized Gain/Loss Report - AAI Validation | L3 Pass | 355 | CLOSED: This issue exists in 8.12 as well and this will not be fixed as part of upgrade. | TRUE | HNE2E |  | Finance GL | Finance | Lokesh Reddy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/10/2019 | 9/10/2019 |  | 1971 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 01:17 | Joshi, Abhishek N | 56-F-EU-V-190904-S6FI139 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190904-S6FIV139A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5704ITL | No | UBE | BXU545362 |  | 6 |  | CRP | Italian Statutory Reporting - Upload to F0911Z1 (RF) | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth, Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/10/2019 | 9/10/2019 |  | 1972 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 05:21 | Joshi, Abhishek N | 56-F-EU-V-190910-S6FI122 | Upload / Report | Yes | Yes | [6 empty] | 56-F-EU-V-190910-S6FIV122A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5704ITLB | No | UBE | BXU545362 |  | 6 |  | CRP | Italian Stat Reporting - Upload F0911Z1 (URRF) | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/10/2019 | 9/10/2019 |  | 1973 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 05:23 | Joshi, Abhishek N | 56-F-EU-V-190903-S6FI129 | Upload / Report | Yes | Y | [6 empty] | 56-F-EU-V-190903-S6FIV129A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R57099B | No | UBE | BXU549545 |  | 6 |  | CRP | Sequential Number Report - Tax File | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Lokesh Reddy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 09/10/2019 | 09/09/2019 |  | 1974 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 01:19 | Joshi, Abhishek N | 56-F-EU-V-190905-S6FI118 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190905-S6FIV118A,56-F-EU-V-190905-S6FIV118B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5712002 | No | UBE | BXU550349 |  | 6 |  | CRP | Asset Report Writer: Additions and Retirements - Cust | L3 Pass |  |  | TRUE | LNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/10/2019 | 9/9/2019 |  | 1975 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 02:43 | Joshi, Abhishek N | 56-F-EU-V-190903-S6FI039 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190903-S6FIV039A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5712411 | No | UBE | BXU549323 |  | 6 |  | CRP | Depreciation Schedule - CSV version | L3 Pass | 314 | Closed | TRUE | HNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth, Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/10/2019 | 9/9/2019 |  | 1976 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 02:44 | Joshi, Abhishek N | 56-F-EU-V-190829-S6FI093 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190829-S6FIV093A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5712435 | No | UBE | BXU549324 |  | 6 |  | CRP | Account Reconciliation(Customised) for CSV output | L3 Pass |  |  | TRUE | LNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/10/2019 | 9/10/2019 |  | 1977 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 02:46 | Joshi, Abhishek N | 56-F-EU-V-190904-S6FI144 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190904-S6FIV144A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R573B5002 | No | UBE | BXU548727 |  | 4 |  | CRP | BAXTER - Dublin / Localized Statement Print | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/8/2019 | 8/7/2019 |  | 1978 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 08:17 | Joshi, Abhishek N | 56-F-EU-V-190802-S4FI086 | Printer | Yes | [7 empty] | 56-F-EU-V-190802-S4FIV086A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R573B5002A | No | UBE | BXU545541 |  | 4 |  | CRP | BAXTER - Localized Statement Print | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/8/2019 | 8/7/2019 |  | 1979 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 05:28 | Joshi, Abhishek N | 56-F-EU-V-190729-S4FI054 | Printer | Yes | [7 empty] | 56-F-EU-V-190729-S4FIV054A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R573B5002B | No | UBE | BXU545541 |  | 4 |  | CRP | BAXTER - Statements MICROGEN | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/8/2019 | 8/7/2019 |  | 1980 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 05:30 | Joshi, Abhishek N | 56-F-EU-V-190731-S4FI065 |  | Yes | [7 empty] | 56-F-EU-V-190731-S4FIV065A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R573B5002C | No | UBE | BXU545541 |  | 4 |  | CRP | BAXTER - BENELUX / Localized Statement Print | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/8/2019 | 8/7/2019 |  | 1981 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 05:31 | Joshi, Abhishek N | 56-F-EU-V-190731-S4FI066 | Printer | Yes | [7 empty] | 56-F-EU-V-190731-S4FIV066A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R573B5002I | No | UBE | BXU5455541 |  | 4 |  | CRP | BAXTER - Italy - Statement Print | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 08/07/19 | 08/08/19 |  | 1982 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 05:31 | Joshi, Abhishek N | 56-F-EU-V-190801-S4FI002 | Printer | Yes | [7 empty] | 56-F-EU-V-190801-S4FIV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R573B5005 | No | UBE | BXU548728 |  | 4 |  | CRP | A/R Statement Print Driver - Customized | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/08/2019 | 8/02/2019 |  | 1983 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 08:19 | Joshi, Abhishek N | 56-F-EU-V-190802-S4FI084 | Printer | Yes | [7 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5774079 | No | UBE |  |  | 999 |  |  | Invoice Control Report | Obsolete | [5 empty] | Finance AR | Finance | Francisco Alvargonzalez |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1984 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Report | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R57AR001 | No | UBE | BXU548730 |  | 2 |  | CRP | Update Authorized Users for Receipts | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1985 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 09:27 | Joshi, Abhishek N | 56-F-EU-V-190612-S2FI030 |  | Yes | [7 empty] | 56-F-EU-V-190612-S2FIV030A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R60A4BX11 | No | UBE |  |  | 6 |  | CRP | Commission Detail - 08426 | L3 Not Required |  |  | TRUE | HNE2E |  | Finance External | Finance | Izaskun Ajuria | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1986 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-06 07:11 | Ajuria, Izaskun | [7 empty] | NoKT |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R6211G02 | No | UBE | BXU551087 |  | 6 |  | CRP | CTA Report France & Italy | L3 Not Required |  |  | TRUE | HNE2E |  | Finance GL | Finance | Greg Felitto | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1987 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-04-02 06:08 | Joshi, Abhishek N |  | Report | [9 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R6213G03 | No | UBE | BXU551089 |  | 6 |  | CRP | MV Beginning Balance Creation (Proof ) | L3 Not Required |  |  | TRUE | HNE2E |  | Finance GL | Finance | Libor Slaby | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1988 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-04-02 06:10 | Joshi, Abhishek N | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R6213G05 | No | UBE | BXU551090 |  | 6 |  | CRP | Supplemental Account Year Ending Closing(Proof) | L3 Not Required |  |  | TRUE | HNE2E |  | Finance GL | Finance | Libor Slaby | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1989 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-04-02 06:12 | Joshi, Abhishek N | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R6213G06 | No | UBE | BXU551091 |  | 6 |  | CRP | BIO CTA Account Year End Closing (Proof) | L3 Not Required |  |  | TRUE | HNE2E |  | Finance GL | Finance | Libor Slaby | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1990 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-04-02 06:15 | Joshi, Abhishek N | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R6213G08 | No | UBE | BXU551095 |  | 6 |  | CRP | Integrity Supplemental accts & Assets - AA ledger | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Libor Slaby | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1991 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-04-02 06:18 | Joshi, Abhishek N | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R6213G12 | No | UBE | BXU551096 |  | 6 |  | CRP | Supplemental Account Report By Company | L3 Not Required |  |  | TRUE | LNE2E |  | Finance GL | Finance | Gregory Felitto | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1992 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-04-02 06:20 | Joshi, Abhishek N |  | Report | [9 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55093021B | No | UBE |  |  | 5 |  |  | Indexed Comps Compute And Print Report code categorie | L3 Not Required |  |  | TRUE | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/29/2019 | 8/29/2019 |  | 1993 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-04 03:40 | Haxton, Keith | 56-F-EU-V-190821-S5FI028 | Printer / Report | Yes | Yes |  |  |  | NoKT |  |  | 56-F-EU-V-190821-S5FIV028A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FEC014 | No | UBE |  |  | 5 |  |  | FEC - Sequential Number Generation Process V3 | L3 Not Required |  |  | FALSE | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 08/26/2019 | 08/23/2019 |  | 1994 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-03 02:02 | Haxton, Keith | 56-F-EU-V-190821-S5FI030 |  | Yes |  |  |  |  | NoKT |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FEC05 | No | UBE |  |  | 5 |  |  | Construction balance par tiers | L3 Not Required |  |  | TRUE | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/29/2019 | 8/28/2019 |  | 1995 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-04 03:40 | Haxton, Keith | 56-F-EU-V-190814-S5FI090 |  | Yes | Y |  |  |  | NoKT |  |  | 56-F-EU-V-190814-S5FIV090A |  |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56AN8EX | OBS | APPL |  |  | 999 |  |  | All Round file to exclude AN8's from specific processes | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1996 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56150Z1 | No | APPL | BXU544671 |  | 6 |  |  | Baxter - Address Organization Structure Master Upload File | L3 Pass |  |  | TRUE | L |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/3/2019 | 9/2/2019 |  | 1997 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 07:14 | Joshi, Abhishek N | 56-F-EU-V-190827-S6MD001 | Upload | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5703BZ1 | No | APPL | BXU548731 |  | 6 |  | CRP | Invoice Transaction Error Application | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/10/2019 | 9/9/2019 |  | 1998 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 09:29 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI062 | Error | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV062A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P6213G01 | No | APPL | BXU549543 |  | 6 |  | CRP | Revise Supplemental Account Mapping | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Libor Slaby | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 1999 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 01:21 | Joshi, Abhishek N | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P55FEC04 | No | APPL |  |  | 6 |  |  | FEC Setup by Company - V4 | L3 Not Required |  |  | TRUE | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/18/2019 | 9/17/2019 |  | 2000 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-10 09:50 | Haxton, Keith | 56-F-EU-V-190903-S6FI128 | Setup | Yes | Yes |  |  |  | NoKT |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56030 | No | APPL | BXU548732 |  | 6 |  | CRP | Maintain F56030 | L3 Pass |  |  | FALSE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth, Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/10/2019 | 9/10/2019 |  | 2001 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 09:32 | Joshi, Abhishek N | 56-F-EU-V-190910-S6FI123 | Maintenance | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P55GL001 | No | APPL | BXU549554 |  | 6 |  | CRP | Maintenance of Grants | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Robbin/Florencia | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/11/2019 | 9/11/2019 |  | 2002 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 01:23 | Joshi, Abhishek N | 56-F-EU-V-190828-S6FI086 | Maintenance | Yes | Yes | [6 empty] | 56-F-EU-V-190828-S6FIV086A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P561201 | No | APPL | BXU549319 |  | 6 |  | CRP | Update Unit/Serial nbr without check on Duplicates | L3 Pass |  |  | TRUE | HNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth, Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/11/2019 | 9/10/2019 |  | 2003 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 02:49 | Joshi, Abhishek N | 56-F-EU-V-190904-S6FI136 |  | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56CRTZ1 | No | APPL |  |  | 999 |  |  | Concur Interface - Payments z-file Maintenance | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2004 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Maintenance / Interface | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56TETAX | No | APPL |  |  | 999 |  |  | Travel&Expense Tax Control | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2005 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5709215 | No | APPL | BXU549745 |  | 6 |  | CRP | Trial Balance by Subledger | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/11/2019 | 9/10/2019 |  | 2006 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 08:59 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI063 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV063A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P55TC02 | No | APPL |  |  | 999 |  |  | Integrity DM errors Inquiry | Obsolete |  |  |  | H |  | MDM | MDM | Tom Hoste | (Blank) |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2007 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-05 05:27 | Greenard, Terry |  | Error/Inquiry | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P560015 | No | APPL | BXU549548 |  | 6 |  | CRP | Work with Automatic Updated Finance Currency Rates | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/11/2019 | 9/10/2019 |  | 2008 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 01:25 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI017 |  | Yes | Y | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P570411 | No | APPL |  |  | 999 |  |  | A/P Standard Voucher Entry - Baxter | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2009 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P570411Z | No | APPL |  |  | 999 |  |  | A/P Batch Voucher Entry | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2010 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5604431 | No | APPL |  |  | 999 |  |  | Value Date Modification(TMS) | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2011 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564322 | No | APPL | BXU549747 |  | 6 |  | CRP | Invoice Tolerance Rules for approval (Target) | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/11/2019 | 9/10/2019 |  | 2012 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-05 06:49 | Joshi, Abhishek N | 56-F-EU-V-190904-S6FI135 |  | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P570411A | No | APPL |  |  | 999 |  |  | A/P Standard Voucher Entry - REF | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2013 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P570413M | No | APPL |  |  | 999 |  |  | A/P Manual Payments - Customized | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2014 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56P2P02 | No | APPL | BXU548850 |  | 6 |  | CRP | PCARD user Maintenance | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth, Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/11/2019 | 9/11/2019 |  | 2015 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 06:47 | Joshi, Abhishek N | 56-F-EU-V-190910-S6FI124 | Maintenance | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P574310 | No | APPL |  |  | 999 |  |  | Purchase Orders - Baxter | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2016 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56PPV | No | APPL | BXU550356 |  | 6 |  | CRP | PPV Output Table Review | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/11/2019 | 9/10/2019 |  | 2017 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 05:47 | Joshi, Abhishek N | 56-F-EU-V-190910-S6FI149 |  | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56032B | No | APPL | BXU548733 |  | 2 |  | CRP | MT940 GVO codes by Country - Maintenance | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | Retrofit not required | Saiteja |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 13/06/2019 | 13/06/2019 |  | 2018 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 09:33 | Joshi, Abhishek N | 56-F-EU-V-190611-S2FI028 | Maintenance | Yes | Yes | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5641002 | No | APPL |  |  | 999 |  |  | UOM conversion used in Baxter EDI interface | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2019 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Interface | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5703B22 | No | APPL | BXU548734 |  | 5 |  |  | Delinquency Fee Review | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 08/08/2019 | 08/07/2019 |  | 2020 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 08:25 | Joshi, Abhishek N | 56-F-EU-V-190807-S4FI104 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P57AR004 | No | APPL | BXU550578 |  | 3 |  | CRP | Cash Discount FY | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saieja |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2021 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 01:07 | Joshi, Abhishek N | 56-F-EU-V-190625-S3FI015 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56GL113 | No | APPL | BXU549551 |  | 6 |  | CRP | Italian Fiscal Reporting - Maintain Account Classification | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/11/2019 | 9/11/2019 |  | 2022 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 01:28 | Joshi, Abhishek N | 56-F-EU-V-190903-S6FI133 | Maintenance / Report | Yes | Yes | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56KP011 | No | APPL | BXU551097 |  | 6 |  | CRP | Maintain KPI Types | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth, Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 09/11/2019 | 09/10/2019 |  | 2023 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-04-02 06:40 | Joshi, Abhishek N | 56-F-EU-V-190905-S6FI119 | Maintenance | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56KP021 | No | APPL | BXU551099 |  | 6 |  | CRP | KPI Balances Maintenance | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/11/2019 | 9/10/2019 |  | 2024 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-04-02 06:42 | Joshi, Abhishek N | 56-F-EU-V-190903-S6FI040 | Maintenance | Yes | Yes |  |  | No difference b/w properties for Company field size but the feild was shrinked when tested in IE browser during L2 testing. Hence the width of Company field in Header for P56KP021_W56KP021A was increased |  |  |  | 56-F-EU-V-190903-S6FIV040A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P570411B | No | APPL |  |  | 999 |  |  | A/P Standard Voucher Entry - VESR | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2025 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56PCTAX | No | APPL |  |  | 999 |  |  | P Card Travel&Expense Tax Control | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2026 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P560411A | No | APPL |  |  | 999 |  | CRP | F0411 Custom Updates | Obsolete |  |  | TRUE | LNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | PG 10/10: This application was retrofitted to 9.2 and promoted to PPD. However the users have now confirmed that it is not used and not required in production. | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/20/2019 | 9/11/2019 |  | 2027 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-10 02:36 | Gilthorpe, Peter | 56-F-EU-V-190829-S6FI096 |  | Yes | Y | [6 empty] | 56-F-EU-V-190829-S6FI096A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5747070 | No | APPL |  |  | 999 |  |  | Inbound EDI Receiving Advice Inquiry - Customized | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2028 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Inquiry / Inbound | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5748201 | No | APPL |  |  | 999 |  |  | Work With Work Orders 57 | Obsolete |  |  | TRUE | LNE2E |  | Finance FA | Finance | Finance | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | VV-23/09 - Obsoleted as per Joanne's request | Bargavi |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/11/2019 | 9/10/2019 |  | 2029 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-23 05:46 | Verma, Vikas | 56-F-EU-V-190910-S6FI153 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190910-S6FIV153A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56GL112 | No | APPL | BXU549552 |  | 6 |  | CRP | Italian Fiscal Reporting - Maintain Classification Types | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/11/2019 | 9/10/2019 |  | 2030 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 01:29 | Joshi, Abhishek N | 56-F-EU-V-190830-S6FI112 | Maintenance / Report | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P55FRAPE | No | APPL |  |  | 999 |  |  | Error Codes For Interface Reports | Obsolete |  |  |  | HNE2E |  | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2031 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-05 05:26 | Greenard, Terry |  | Error / Interface | [9 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56051A | No | APPL | BXU548735 |  | 5 |  |  | NSF BANSTA Message Maintenance | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/26/2019 | 8/26/2019 |  | 2032 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 08:28 | Joshi, Abhishek N | 56-F-EU-V-190820-S5FI128 | Maintenance | Yes | Yes | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5612G95 | No | APPL |  |  | 999 |  |  | Leased Hardware Interface Transactions | Obsolete | [5 empty] | Finance FA | Finance | Libor Slaby |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2033 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Interface | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5603B10 | No | APPL |  |  | 999 |  |  | Standard Receipt Entry - Cutomised | Obsolete | [5 empty] | Finance AR | Finance | Francisco Alvargonzalez |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2034 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P574310A | No | APPL |  |  | 999 |  |  | Purchase Orders - Baxter | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2035 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56TXA1E | No | APPL | BXU550732 |  | 6 |  | CRP | TXA1 codes for EDI Vat Logic FINTRNEDI (F56TXA1E) | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/11/2019 | 9/10/2019 |  | 2036 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-23 02:33 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI046 |  | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56912 | No | APPL | BXU549549 |  | 6 |  | CRP | Maintain Allocations Setup File Splitout | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/11/2019 | 8/30/2019 |  | 2037 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 01:31 | Joshi, Abhishek N | 56-F-EU-V-190828-S6FI092 | Maintenance / Setup | Yes | Yes | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5703B10 | No | APPL |  |  | 999 |  |  | Standard Receipts Entry | Obsolete | [5 empty] | Finance AR | Finance | Francisco Alvargonzalez |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2038 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P55FRC14 | No | APPL |  |  | 999 |  |  | AB# to EXCLUDE from Securitisation Extract | Obsolete | [5 empty] | Finance AR | Finance | Francisco Alvargonzalez |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2039 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5641061 | No | APPL |  |  | 999 |  |  | Review Supplier Price/Catalog Batch Upload File | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2040 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Upload | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56PCERR | No | APPL |  |  | 999 |  |  | Travel&Entertainment Error Control for PCard | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2041 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:15 | Chiau, Liesbet |  | Error | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564301 | No | APPL | 1240712 (18324) | BXU547015, BXU547015 | 6 |  |  | Intrastat Arrivals Maintenance | L3 Pass | 300 | Open | TRUE | L |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/5/2019 | 9/4/2019 |  | 2042 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 05:44 | Singh, Sunil Kumar | 56-F-EU-V-190827-S6LO009 | Maintenance | Yes | Yes |  |  | Form Load Warning: when trying to open the application in design mode in DV920 and PD812 but there is not spec difference DV920 and PD812 | KTW4 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56912AR | No | APPL | BXU549542 |  | 6 |  | CRP | Maintain Currencies per Doc Type & Nbr | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/11/2019 | 9/10/2019 |  | 2043 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 01:32 | Joshi, Abhishek N | 56-F-EU-V-190903-S6FI127 | Maintenance | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56EDIGL | No | APPL |  |  | 999 |  |  | EDI GL Account Defaults - Maintain F56EDIGL | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2044 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet |  | Maintenance | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P57SGJ0 | No | APPL | BXU549550 |  | 6 |  | CRP | Work with 'Submit Group Jobs' | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 09/10/2019 | 09/09/2019 |  | 2045 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 01:35 | Joshi, Abhishek N | 56-F-EU-V-190830-S6FI123 |  | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56KP100 | No | APPL | BXU547436 |  | 6 |  | CRP | AB# to EXCLUDE from KPI for non p2P compliant vouchers | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/11/2019 | 9/11/2019 |  | 2046 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 00:36 | Joshi, Abhishek N | 56-F-EU-V-190904-S6FI140 |  | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56032 | No | APPL | BXU548720 |  | 2 |  | CRP | MT940 Cross Reference - GL Bank Account | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/13/2019 | 6/13/2019 |  | 2047 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 08:32 | Joshi, Abhishek N | 56-F-EU-V-190610-S2FI015 | Cross Refer | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P55FRDSO | No | APPL | BXU548717 |  | 6 |  | CRP | Inquiry on F553B16 | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete | Passing after discussion 11/09 |  |  | Terry Greenard / Vikas Verma |  | Sreekanth, Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/11/2019 | 9/10/2019 |  | 2048 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 09:35 | Joshi, Abhishek N | 56-F-EU-V-190904-S6FI137 | Inquiry | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P55HYCOA | No | APPL | BXU549553 |  | 6 |  | CRP | Hyperion COA Maintenance | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/11/2019 | 9/10/2019 |  | 2049 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 01:38 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI064 | Maintenance | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56P2P01 | No | APPL |  |  | 999 |  |  | P2P Address Book Ariba Maintenance | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2050 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet |  | Maintenance | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P04012 | Yes | APPL |  | 1256302 | 1 |  |  | Supplier Master | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 5/20/2019 | 5/20/2019 |  | 2051 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-16 03:42 | Joshi, Abhishek N | 56-F-EU-V-190510-S1MD001 |  | Yes | Y |  |  | Retrofit Completed |  |  |  | 56-F-EU-V-190510-S1MDV01A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P076311 | No | APPL |  |  | 999 |  |  | Manager Self Service Leave Review | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | (Blank) |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2052 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P1113 | No | APPL |  |  | 999 |  |  | Currency Restatement Rates | Obsolete | [5 empty] | Finance GL | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2053 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P31P100 | No | APPL |  |  | 999 |  |  | Project Quotes | Obsolete | [5 empty] | Finance | Finance | Luigi Amorini |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2054 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P47120 | Yes | APPL | BXU545171 (147828) | BXU531266 | 2 |  |  | EDI Product Activity Data Inquiry - Inbound | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2055 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 08:55 | Singh, Sunil Kumar | 56-F-EU-V-190611-S2LO003 | Inquiry / Inbound | Yes | Y |  |  |  | KTW4 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5600072 | No | APPL | BXU547134 |  | 5 |  | CRP | Adjustment Control Maintenance Application | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/26/2019 | 8/25/2019 |  | 2056 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-05 05:54 | Joshi, Abhishek N | 56-F-EU-V-190819-S5FI117 | Maintenance | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P560010 | OBS | APPL |  |  | 999 |  |  | Maintain UBE Version Last Run Date and Time | Obsolete | [5 empty] | CNC | CNC | Rob Zande | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2057 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet |  | Maintenance | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5600105 | Yes | APPL | 1250897 (22485) | 1250898 | 5 |  |  | ITP From Branch Security Application | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/21/2019 | 8/20/2019 |  | 2058 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 08:20 | Singh, Sunil Kumar | 56-F-EU-V-190816-S5LO057 |  | Yes | Y |  |  |  | KTW4 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5601001 | No | APPL | 1250527 (21734) |  | 5 |  |  | Maintain Transaction Originator Info | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/13/2019 | 8/12/2019 |  | 2059 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 08:59 | ANAND, S | 56-F-EU-V-190812-S5OM005 | Maintenance | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P563012Z | Yes | APPL | 1242968 (19282) | 1243037 | 5 |  |  | Batch Customers for conversions | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | CIZMECI,TANKUT |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/26/2019 | 8/25/2019 |  | 2060 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-18 07:18 | ANAND, S | 56-F-EU-V-190813-S5MD015 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5641800 | yes | APPL | 1222844 | 1224684 12360 | 5 |  |  | Batch Recall Data Selection Maintenance App | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Douglas Roussel | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/21/2019 | 8/20/2019 |  | 2061 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 06:26 | Vishnubhatla, Mithra | 56-F-EU-V-190819-S5LO067 | Maintenance | Yes | Y |  |  |  | KTQ3 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642117 | OBS | APPL |  |  | 999 |  |  | Backorder Release - BAXTER | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2062 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5647491 | No | APPL |  |  | 5 |  |  | Maintenance Application Cost Description | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/21/2019 | 8/21/2019 |  | 2063 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-26 02:28 | Destrebecq, Eric | 56-F-EU-V-190821-S5LO077 | Maintenance | Yes | Y |  |  |  | FCA OUT |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5698001 | No | APPL | 1240727, BXU545221 | 1239326 | 5 |  |  | E1 Transaction Logging | L3 Not Required |  |  | TRUE | HE2E |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/20/2019 | 8/19/2019 |  | 2064 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 08:44 | Joshi, Abhishek N | 56-F-EU-V-190814-S5OM011 |  | Yes | Y | [6 empty] | 56-F-EU-V-190814-S5OMV011A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5698002 | yes | APPL | BXU545216 (13329), BXU545224 (R42565) | BXU545186, BXU545219 | 5 |  |  | Interface Version XREF Maintenance | L3 Not Required |  |  | TRUE | HE2E |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/21/2019 | 8/21/2019 |  | 2065 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 10:29 | ANAND, S | 56-F-EU-V-190816-S5OM015 | Maintenance / Interface | Yes | Y | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5698004 | Yes | APPL | 1235645, 1240725 (16555) | 1235851, 1241634 (16555) | 5 |  |  | Manual ASN RTE Re-sends | L3 Pass |  |  | TRUE | H |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 08/21/2019 | 08/20/2019 |  | 2066 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 10:36 | ANAND, S | 56-F-EU-V-190820-S5LO077 |  | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190820-S5LOV077V | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5698005 | No | APPL | BXU545225 |  | 5 |  |  | BX RTE Filtering Set-Up | L3 Not Required |  |  | TRUE | HE2E |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/21/2019 | 8/20/2019 |  | 2067 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 08:42 | Joshi, Abhishek N | 56-F-EU-V-190814-S5OM012 |  | Yes | Y | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5698006 | No | APPL |  | BXU546794 | 5 | 1 |  | Integration Email Handler Maintenance | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Pawel Oskroba | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/21/2019 | 8/20/2019 |  | 2068 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 04:32 | Joshi, Abhishek N | 56-F-EU-V-190816-S5LO059 | Maintenance | Yes | Y |  |  |  | KTQ3 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5698008 | No | APPL |  |  | 6 |  |  | Heartbeat Monitor | PPD Passed |  |  | TRUE |  |  | CNC | CNC | Rob Zande | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/27/2019 | 8/26/2019 |  | 2069 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-29 11:24 | Zande, Robert | 56-F-EU-V-190820-S5CNC001 |  | Yes | Y |  |  | To Be Tested in CRP |  |  |  | 56-F-EU-V-190820-S5CNCV01A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5698018 | No | APPL |  |  | 5 |  |  | Integration RTE Cross-Reference | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 08/13/2019 | 08/12/2019 |  | 2070 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-26 03:48 | Deveen, Genevive | 56-F-EU-V-190812-S5OM003 | Cross Refer | Yes | Yes |  |  |  | KTW4 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5698040 | No | APPL | 1240719 | 1241778 | 5 |  |  | Baxter E-mails | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | CIZMECI,TANKUT |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/16/2019 | 8/15/2019 |  | 2071 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-27 08:32 | Singh, Sunil Kumar | 56-F-EU-V-190812-S5OM006 |  | Yes | Y | [6 empty] | 56-F-EU-V-190812-S5OMV006A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5698044 | No | APPL | 1240719, BXU545290, BXU545441 | 1241778 | 5 |  |  | Baxter E-mail Constants | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/19/2019 | 8/16/2019 |  | 2072 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 08:52 | Joshi, Abhishek N | 56-F-EU-V-190813-S5OM010 | Constant | Yes | Yes | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P569862 | No | APPL | BXU544631 | BXU545915 | 6 |  |  | Table Master Business Function Maintenance | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/26/2019 | 8/23/2019 |  | 2073 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 07:16 | Joshi, Abhishek N | 56-F-EU-V-190819-S5MD023 | Maintenance | Yes | Y | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56AU100 | Yes | APPL |  |  | 999 |  |  | Audit Inquiry GSQTS | Obsolete |  |  |  | H |  | MDM | MDM | Tom Hoste | (Blank) |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2074 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet |  | Inquiry / Audit | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56AU500 | No | APPL | 1235591 15388 | 1235592 (15388) | 6 |  |  | Cost Audit Inquiry | PPD Passed |  |  | TRUE | L | FALSE | ECC | ARO | Krista Vensever | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/28/2019 | 8/27/2019 |  | 2075 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 08:19 | Vishnubhatla, Mithra | 56-F-EU-V-190820-S5AR003 | Inquiry / Audit | Yes | Y |  |  | To be tested in CRP |  |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56AU600 | Yes | APPL |  | 1235592 | 5 |  |  | Audit Inquiry - Grouping Matrix | L3 Pass | 292 | CLOSED | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma | Yes | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/27/2019 | 8/26/2019 |  | 2076 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 04:38 | Joshi, Abhishek N | 56-F-EU-V-190821-S5MD028 | Inquiry / Audit | Yes | [7 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56BIP08 | No | APPL |  | BXU546809 | 5 |  |  | IXOS Intercompany Invoice User Access | L3 Pass |  |  | TRUE | MNE2E |  | IXOS Archive | eCommerce | Linda Kenny | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/28/2019 | 8/27/2019 |  | 2077 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-21 06:46 | Joshi, Abhishek N | 56-F-EU-V-190821-S5EC010 |  | Yes | Yes |  |  |  | NoKT |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56FF102 | No | APPL | BXU547433 |  | 3 |  | CRP | Maintain the FF Outbounding file F56FF11 | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saieja |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/28/2019 | 6/27/2019 |  | 2078 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 04:52 | Joshi, Abhishek N | 56-F-EU-V-260619-S3FI019 | Maintenance / Outbound | Yes | Y | [6 empty] | 56-F-EU-V-260619-S3FIV019A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56G4710 | No | APPL | 1265996 (19831) | 19831 1265997 | 5 |  |  | Gambro: Inbound EDI Order Inquiry | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/21/2019 | 8/20/2019 |  | 2079 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 09:51 | Vishnubhatla, Mithra | 56-F-EU-V-190814-S5LO042 | Inquiry / Inbound | Yes | Y |  |  |  | KTTS5 |  |  | 56-F-EU-V-190814-S5LOV042A; 56-F-EU-V-190814-S5LOV042B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56QACTR | Yes | APPL | 1268950 (22814), 1268144 (21022), 1266540 (14885) | 1269067 & 1269168 (22814 & 21022) | 6 |  |  | QA Control Table Maintenance Application | L3 Not Required |  |  | TRUE | H |  | Validation | Validation | Sunil Kumar / Vinod | L2 Not required | no KT, testing during CRP |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/26/2019 | 8/22/2019 |  | 2080 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-19 10:29 | Singh, Sunil Kumar | 56-F-EU-V-190813-S5VA001 | Maintenance | Yes | Y |  |  | Validation QAC reports |  |  |  | 56-F-EU-V-190813-S5VAV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56QASCH | Yes | APPL | 1269576 | 1269578 | 6 |  |  | Critical Processing Options Search | L3 Not Required |  |  | TRUE | H |  | Validation | Validation | Sunil Kumar / Vinod | L2 Not required | no KT, testing during CRP |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/27/2019 | 8/27/2019 |  | 2081 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-31 09:16 | Singh, Sunil Kumar | 56-F-EU-V-190826-S5VA002 |  | Yes | Yes |  |  | Validation QAC reports |  |  |  | 56-F-EU-V-190826-S5VAV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900121 | No | APPL |  |  | 5 |  |  | In-Transit System Setup Information | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/21/2019 | 8/20/2019 |  | 2082 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-02 03:29 | De Brouwer, Peter | 56-F-EU-V-190819-S5LO068 | Setup | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190819-S5LOV068A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900146 | Yes | APPL |  |  | 1 | 1 |  | Object Processing Control File Application | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Srini Bojanapally |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2083 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:56 | Chiau, Liesbet | 56-F-EU-V-190514-S1LO003 |  | Yes | Y |  |  |  | KTW4 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900176 | Yes | APPL | 1235591, BXU549869 (22837) | 15388&nbsp; 1235592 22837 BXU547708 | 5 |  |  | Audit Inquiry New GSQTS | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Miruna Danes | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/21/2019 | 8/20/2019 |  | 2084 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 07:36 | ANAND, S | 56-F-EU-V-190813-S5LO030 | Inquiry / Audit | Yes | Yes |  |  |  | KTQ3 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P59002A | Yes | APPL | 1230479 | 13771, 1230568 | 2 |  |  | Maintain Item Selective Subscription | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/12/2019 | 6/12/2019 |  | 2085 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 09:58 | Joshi, Abhishek N | 56-F-EU-V-190612-S2MD025 | Maintenance | Yes | Yes | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5998001 | No | APPL | BXU550803 | BXU548832 | 5 |  |  | RTE Recovery Application | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/22/2019 | 8/21/2019 |  | 2086 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-20 06:42 | Joshi, Abhishek N | 56-F-EU-V-190816-S5LO056 |  | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190816-S5LOV056A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P59MD11 | No | APPL |  |  | 6 |  |  | Maintain Templates | PPD Passed |  |  | TRUE | L |  | ARO | ARO | Terry Greenard | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/28/2019 | 8/28/2019 |  | 2087 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-12-19 02:47 | Greenard, Terry | 56-F-EU-V-190827-S5CNC003 | Maintenance | Yes | Yes |  |  | Works in PPD, I can view the records |  |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P7430031 | No | APPL | BXU548624 |  | 5 |  | CRP | Reprint Legal Documents - COMM - 03B | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 08/26/2019 | 08/23/2019 |  | 2088 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 05:26 | Joshi, Abhishek N | 56-F-EU-V-190820-S5FI121 | Printer | Yes | Y | [6 empty] | 56-F-EU-V-190820-S5FIV121A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600010 | Yes | UBE | 1222666 |  | R1 |  |  | JDE WMS Receiving Label Print | PPD Passed | 403 |  | TRUE |  |  | Procurement | Logistics |  | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2089 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-25 04:59 | Vishnubhatla, Mithra | 56-F-EU-V-191008-R1LO032 | Printer | Yes |  |  |  | 08/10/19 TG -Mistakenly Obsoleted readded to Tracker |  |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5603012I | No | UBE | BXU549673 |  | 2 |  |  | Customer Master VAT Integrity | L3 Pass | 134 | Closed | TRUE | HNE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete | L3 - defect #134 closed |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2090 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 02:14 | Joshi, Abhishek N | 56-F-EU-V-190611-S2OM003 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190611-S2OMV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600170 | OBS | UBE |  |  | 999 |  |  | Integrity report to identify Shared products | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | (Blank) |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2091 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet |  | Report | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641052 | Yes | UBE | BXU545270 | 26297, BXU546104 | 6 |  | CRP | Baxter AG B4one - Inventory extract | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/12/2019 | 9/12/2019 |  | 2092 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-05 01:45 | Joshi, Abhishek N | 56-F-EU-V-190828-S6FI087 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190828-S6FIV087A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600191 | Yes | UBE | 1263246 | 1263247 | 3 |  |  | EMEA Item integrity report item –F46011-F41002 | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/15/2019 | 7/12/2019 |  | 2093 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 09:02 | Vishnubhatla, Mithra | 56-F-EU-V-190715-S3MD001 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190715-S3MDV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600194 | Yes | UBE | 1263246 | 1263247 | 3 |  |  | EMEA Item integrity report item –F4101 | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 07/16/2019 | 07/12/2019 |  | 2094 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 09:02 | Vishnubhatla, Mithra | 56-F-EU-V-190712-S3MD038 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190712-S3MDV038A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560902P | No | UBE |  |  | 999 |  |  | Populate F0902 from Coupa Text File | Obsolete |  |  | FALSE | HNE2E |  | Finance GL | Finance | Joanne Byrne |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2095 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-05 05:28 | Greenard, Terry |  | Text | [9 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564104IR | No | UBE | 1255080 | BXU547860 | 3 |  |  | National Number Integrity : Report | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/15/2019 | 7/12/2019 |  | 2096 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-09 05:53 | Joshi, Abhishek N | 56-F-EU-V-190712-S3MD039 | Report | Yes | Y |  |  | Retrofit not required |  |  |  | 56-F-EU-V-190712-S3MDV039A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56EQL02 | Yes | UBE | BXU531848 | 148540 BXU532520 | 6 |  |  | Expired Quantity List | L3 Pass | 323 | Closed | TRUE | L |  | Quality | Logistics | Miruna Danes | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth, Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/5/2019 | 9/4/2019 |  | 2097 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-31 07:47 | Vishnubhatla, Mithra | 56-F-EU-V-190827-S6LO004 |  | Yes |  |  |  |  | KTQ3 |  |  | 56-F-EU-V-190827-S6LOV004A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600116 | No | UBE | BXU549738 |  | 6 |  | CRP | Generate F56006 Global structures (X-levels) from F59XLVLS | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Lokesh Reddy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/12/2019 | 9/11/2019 |  | 2098 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 01:42 | Joshi, Abhishek N | 56-F-EU-V-190904-S6FI138 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190904-S6FIV138A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56ARCHI1 | No | UBE |  |  | 999 |  |  | ARCHIBUS - Chart of Accounts Extract | Obsolete |  |  |  | HNE2E |  | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2099 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R03B429A | No | UBE |  |  | 999 |  |  | Currency Detail - Foreign and Domestic | Obsolete | [5 empty] | Finance AR | Finance | Francisco Alvargonzalez |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2100 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R03B429B | No | UBE |  |  | 999 |  |  | Currency Detail - Aging | Obsolete | [5 empty] | Finance AR | Finance | Francisco Alvargonzalez |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2101 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R03B702 | No | UBE | BXU545723 |  | 999 |  |  | A/R to G/L Receipts Integrity by Batch | Obsolete |  |  | FALSE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez |  |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 06/25/2019 | 06/24/2019 |  | 2102 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 03:03 | Joshi, Abhishek N | 56-F-EU-V-190624-S2FI128 |  | Yes | Y |  |  | Object missing in 9.2, Cloned R5603B702 in 8.12 then restored PAR in 9.2 , VV-01/07- Obsoleted the object by oracle, so created R5603B702 as cloned as request from Luigi |  |  |  | 56-F-EU-V-190624-S2FIV128A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R04571 | No | UBE |  |  | 999 |  |  | A/P Auto Payments - Print Driver | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2103 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet |  | Printer |  |  |  |  | Obsolete the 8.12 version and test 9.12 version | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R097021 | No | UBE | BXU548618 |  | 2 |  | CRP | Transaction w/o Account Master | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Robbin/Florencia | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/11/2019 | 6/11/2019 |  | 2104 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 05:54 | Joshi, Abhishek N | 56-F-EU-V-190610-S2FI006 |  | Yes | Y | [6 empty] | 56-F-EU-V-190610-S2FIV006A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R553B11 | No | UBE | BXU547665 |  | 2 |  | CRP | Payment Terms Vs Payment Received | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/13/2019 | 6/12/2019 |  | 2105 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 05:34 | Joshi, Abhishek N | 56-F-EU-V-190610-S2FI017 |  | Yes | Yes |  |  | Retrofit not required |  |  |  | 56-F-EU-V-190610-S2FIV017A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL82 | No | UBE | BXU548342 |  | 5 |  | CRP | Data Analysis CSV - F0006 | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/26/2019 | 8/26/2019 |  | 2106 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 10:00 | Joshi, Abhishek N | 56-F-EU-V-190819-S5FI107 |  | Yes | Y | [6 empty] | 56-F-EU-V-190819-S5FIV107A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600063 | No | UBE | BXU547605 |  | 4 |  | CRP | Purge Account Reconciliation Workfiles | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/8/2019 | 8/7/2019 |  | 2107 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 04:11 | Joshi, Abhishek N | 56-F-EU-V-190805-S4FI094 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190805-S4FIV094A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600085 | No | UBE |  |  | 5 |  |  | Account Card, RuAccount RU70 | L3 Not Required |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Not required | No KT, test in E2E |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/29/2019 | 8/28/2019 |  | 2108 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-04 03:41 | Haxton, Keith | 56-F-EU-V-190820-S5FI127 |  | Yes | Y |  |  |  | No KT |  |  | 56-F-EU-V-190820-S5FIV127A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5603001F | No | UBE | BXU545709 |  | 5 |  | CRP | Annual Customer Credit Review Report – 18,12,6 months | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/27/2019 | 8/27/2019 |  | 2109 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 01:20 | Joshi, Abhishek N | 56-F-EU-V-190820-S5FI124 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190820-S5FIV124A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5603005 | No | UBE | BXU544716 |  | 5 |  | CRP | DB Payment Confirmation Upload | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 08/28/2019 | 08/27/2019 |  | 2110 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 01:33 | Joshi, Abhishek N | 56-F-EU-V-190821-S5FI031 | Upload | Yes | Y | [6 empty] | 56-F-EU-V-190821-S5FIV031A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5603006 | No | UBE | BXU544716 |  | 5 |  | CRP | IXOS Validation and Payment ID Update | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/27/2019 | 8/26/2019 |  | 2111 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 01:36 | Joshi, Abhishek N | 56-F-EU-V-190814-S5FI088 |  | Yes | Y | [6 empty] | 56-F-EU-V-190814-S5FIV088A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560303 | No | UBE | BXU545711 |  | 3 |  | CRP | Credit Limit Extr. BILCRE From Cust Master + AR Ledger | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 07/09/2019 | 07/17/2019 |  | 2112 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 01:37 | Joshi, Abhishek N | 56-F-EU-V-190709-S3FI155 |  | Yes | Y | [6 empty] | 56-F-EU-V-190709-S3FIV155A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560359B | No | UBE | BXU545714 |  | 5 |  | CRP | AIDA Extract balance for ECEMEA - Cognos to F56902EC | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/11/2019 | 7/11/2019 |  | 2113 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 02:11 | Joshi, Abhishek N | 56-F-EU-V-190709-S3FI153 |  | Yes | Y | [6 empty] | 56-F-EU-V-190709-S3FIV153A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560359C | No | UBE | BXU545714 |  | 5 |  | CRP | AIDA - Job Finished Date Stamp UBE | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/27/2019 | 8/26/2019 |  | 2114 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 02:12 | Joshi, Abhishek N | 56-F-EU-V-190816-S5FI105 |  | Yes | Y | [6 empty] | 56-F-EU-V-190816-S5FIV105A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5604830 | No | UBE |  |  | 999 |  | CRP | EMEA - Update Payment Instrument | Obsolete |  |  | TRUE | HNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2115 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-22 08:45 | Gilthorpe, Peter | 56-F-EU-V-190612-S2FI078 |  | Yes | Y |  |  | Email fromeSSC confirming that this object is no longer used, was only used for Baxalta payments. |  |  |  | 56-F-EU-V-190612-S2FIV078A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5609473 | No | UBE | BXU545733 |  | 2 |  | CRP | Debit/Credit T/B by Object | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 12/06/2019 | 12/06/2019 |  | 2116 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 04:33 | Joshi, Abhishek N | 56-F-EU-V-190611-S2FI021 |  | Yes | Y | [6 empty] | 56-F-EU-V-190611-S2FIV021A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5609MAC | No | UBE | BXU545734 |  | 4 |  | CRP | MILD Account Master Extract | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/8/2019 | 8/7/2019 |  | 2117 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 04:41 | Joshi, Abhishek N | 56-F-EU-V-190731-S4FI073 |  | Yes | [7 empty] | 56-F-EU-V-190731-S4FIV073A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R561201Z1I | No | UBE |  |  | 2 |  | CRP | Asset Master/Equipment Tag Inbound Processor | L3 Pass | 167 | Closed | TRUE | HNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete | L2 Testing completed after rework |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/25/2019 | 6/24/2019 |  | 2118 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-17 12:17 | Slaby, Libor | 56-F-EU-V-190617-S2FI043 | Inbound | Yes | Y | [6 empty] | 56-F-EU-V-190617-S2FIV43A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5612G95 | No | UBE |  |  | 999 |  |  | Leased Hardware Interface WISE/JDE | Obsolete |  |  | FALSE | HNE2E |  | Finance GL | Finance | Libor Slaby |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2119 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-24 02:47 | Greenard, Terry |  | Interface | [9 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R563B5005 | No | UBE | BXU545951 |  | 5 |  | CRP | A/R Statement Print Driver - As Of GEMINI (56) | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete | Calling R563B5002 /Defect 248 |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/9/2019 | 8/8/2019 |  | 2120 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-08 00:48 | Joshi, Abhishek N | 56-F-EU-V-190802-S4FI087 | Printer | Yes | Y | [6 empty] | 56-F-EU-V-190802-S4FIV087A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5674R9011 | No | UBE | BXU546727 |  | 2 |  |  | RU Analysis of Account | L3 Not Required |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Not required | No KT, test in E2E |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/28/2019 | 6/27/2019 |  | 2121 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 05:55 | Joshi, Abhishek N | 56-F-EU-V-190625-S2FI133 |  | Yes | Y |  |  |  | No KT |  |  | 56-F-EU-V-190625-S2FIV133A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56CRTZ0 | No | UBE |  |  | 999 |  |  | Concur Interface - Payment Processing | Obsolete | [5 empty] | Finance | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2122 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet |  | Interface | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56GETPD01 | No | UBE | BXU546008 |  | 1 |  | CRP | GetPaid ARCUST build programs (F56ARCUS) | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Vijey Sesha | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/3/2019 | 6/3/2019 |  | 2123 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 04:23 | Joshi, Abhishek N | 56-F-EU-V-190527-S1FI058 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190527-S1FIV58A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56GETPD14 | No | UBE |  |  | 999 |  |  | GetPaid - Build file F56ARMST, F56ARTRA, F56AREXTI (ARCASH) | Obsolete | [5 empty] | Finance AR | Finance | Francisco Alvargonzalez |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2124 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56GETPD21 | No | UBE |  |  | 999 |  |  | GetPaid ARCUST build programs (F56ARCUS) | Obsolete | [5 empty] | Finance AR | Finance | Francisco Alvargonzalez |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2125 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56GETPD23 | No | UBE | BXU545893 |  | 1 |  |  | GetPaid ARCASH build programs (F56ARCSH) | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Vijey Sesha | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/3/2019 | 6/3/2019 |  | 2126 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 04:31 | Joshi, Abhishek N | 56-F-EU-V-190521-S1FI040 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190521-S1FIV040A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56GETPD24 | No | UBE |  |  | 999 |  |  | GetPaid - Build file F56ARMST, F56ARTRA, F56AREXTI | Obsolete | [5 empty] | Finance AR | Finance | Francisco Alvargonzalez |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2127 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56GETPD41 | No | UBE |  |  | 999 |  |  | GetPaid ARCUST build programs (F56ARCUS) I/Co Only | Obsolete | [5 empty] | Finance AR | Finance | Francisco Alvargonzalez |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2128 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56GETPD44 | No | UBE |  |  | 999 |  |  | GetPaid - I/Co Only Build file F56ARMST, F56ARTRA, F56AREXTI | Obsolete | [5 empty] | Finance AR | Finance | Francisco Alvargonzalez |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2129 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R570400M1 | No | UBE | BXU555735 | BXU555629 | 999 |  |  | Print Automatic Payments - Cheques - Malta - Cust | Obsolete | [5 empty] | Finance | Finance | Luigi Amorini |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2130 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-07-24 09:45 | Singh, Sunil Kumar |  | Printer | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5704572B | No | UBE |  |  | 999 |  |  | Create A/P Bank Tape - BACS - UK | Obsolete | [5 empty] | Finance | Finance | Luigi Amorini |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2131 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5704572U | No | UBE |  |  | 999 |  |  | Create A/P Bank Tape - UK | Obsolete | [5 empty] | Finance | Finance | Luigi Amorini |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2132 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5812805 | No | UBE |  |  | 3 |  | CRP | Payments by Contract - Update CTL with RMK | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/11/2019 | 7/10/2019 |  | 2133 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-07 05:19 | GOLGE, SERAY | 56-F-EU-V-190708-S3FI144 |  | Yes | Y | [6 empty] | 56-F-EU-V-190708-S3FIV144A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58R09110Z | No | UBE | BXU545364 |  | 2 |  | CRP | Journal Entry Batch Processor - Allow Machine PST | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/12/2019 | 6/11/2019 |  | 2134 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 09:07 | Joshi, Abhishek N | 56-F-EU-V-190611-S2FI023 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190611-S2FIV23A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58RU0411S | No | UBE | BXU544981 |  | 2 |  | CRP | Export A/P Information to CSV | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Vijey Sesha | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 06/10/2019 | 06/12/2019 |  | 2135 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 09:11 | Joshi, Abhishek N | 56-F-EU-V-190610-S2FI014 | Export | Yes | Y | [6 empty] | 56-F-EU-V-190610-S2FIV014A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R0010P | OBS | UBE |  |  | 999 |  |  | Company Constants Report | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | (Blank) |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2136 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet |  | Constant / Report | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R097001 | No | UBE |  |  | 999 |  |  | Companies in Balance | Obsolete |  |  | TRUE | HNE2E |  | Finance GL | Finance | Robbin/Florencia | L2 Not required |  |  |  | Terry Greenard / Vikas Verma | VV-17/10 - As per the request from Joanne obsoleted the object as it does not have any Baxter Customizations | Bargavi |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/24/2019 | 6/24/2019 |  | 2137 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-17 05:34 | Byrne, Joanne Aileen |  |  | Yes |  |  |  | No Retrofit Required |  |  |  | 56-F-EU-V-210619-BV0129A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R31415 | No | UBE | 1257192 (27241) | 1258344 | 2 |  |  | Work Order Print | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/13/2019 | 6/12/2019 |  | 2138 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 13:02 | Singh, Sunil Kumar | 56-F-EU-V-190611-S2LO042 | Printer | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190611-S2LOV42A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R46471 | No | UBE |  |  | 999 |  |  | Task and Trip Creation | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2139 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R550018VNP | No | UBE | BXU548614 |  | 6 | 6 | CRP | Recover VAT for Vouchers (not paid) | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/18/2019 | 6/11/2019 |  | 2140 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 06:02 | Joshi, Abhishek N | 56-F-EU-V-190610-S2FI016 |  | Yes | Y |  |  | Retrofit not required |  |  |  | 56-F-EU-V-190610-S2FIV016A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R550911 | No | UBE | BXU548607 |  | 3 |  | CRP | Text Extraction of F0911 | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Ravi Thapa | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saieja |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/28/2019 | 6/27/2019 |  | 2141 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 06:09 | Joshi, Abhishek N | 56-F-EU-V-190627-S3FI028 | Text | Yes | Y |  |  | Retrofit not required |  |  |  | 56-F-EU-V-190627-S3FIV028A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R554211D | No | UBE |  |  | 999 |  |  | Toscanini Sales History extract to CSV | Obsolete |  |  |  | L |  | MDM | MDM | Tom Hoste | (Blank) |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2142 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5543121 | No | UBE | BXU549775 |  | 4 |  |  | Extract from PO receipt file | L3 Pass |  |  | TRUE | LNE2E |  | Procurement | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 08/07/2019 | 08/06/2019 |  | 2143 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 04:31 | Joshi, Abhishek N | 56-F-EU-V-190805-S4LO114 |  | Yes |  |  |  |  | KTW4 |  |  | 56-F-EU-V-190805-S4LOV114A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R554714A | No | UBE | BXU547734 |  | 6 |  | CRP | Target II - MO EDI for Vouchers | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete | R554714A is dependent on object R55470412 for which defect #271 has been raised |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/27/2019 | 8/26/2019 |  | 2144 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 06:40 | Joshi, Abhishek N | 56-F-EU-V-190819-S5FI118 |  | Yes | Y |  |  | Awaiting completion of L2 testing before data available to test this object |  |  |  | 56-F-EU-V-190819-S5FIV118A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5574R0018 | No | UBE | BXU545950 |  | 5 |  | CRP | Working with Russian Tax File | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | CIZMECI,TANKUT |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/27/2019 | 8/26/2019 |  | 2145 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 06:11 | Joshi, Abhishek N | 56-F-EU-V-190813-S5FI055 |  | Yes | Y | [6 empty] | 56-F-EU-V-190813-S5FIV055A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55AMD01 | No | UBE | BXU545220 |  | 4 |  |  | Agreement master detail | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Venkateswaran Murugesan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/2/2019 | 8/1/2019 |  | 2146 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 08:40 | Joshi, Abhishek N | 56-F-EU-V-190802-S4OM036 |  | Yes | Y | [6 empty] | 56-F-EU-V-190802-S4OMV036A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRDSO | No | UBE | BXU547669 |  | 6 |  | CRP | French DSO - Portfolio Debt Analysis | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/12/2019 | 9/11/2019 |  | 2147 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 07:15 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI065 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S6FIV065A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRGL74A | No | UBE | BXU547574 |  | 5 |  | CRP | BHSA UK VAT REPORTING | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/27/2019 | 8/20/2019 |  | 2148 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 07:41 | Joshi, Abhishek N | 56-F-EU-V-190819-S5FI115 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190819-S5FIV115A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55SCM001 | No | UBE |  |  | 999 |  |  | Toscanini Address Book Interface - UBE | Obsolete |  |  |  | H |  | MDM | MDM | Tom Hoste | (Blank) |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2149 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet |  | Interface | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55SCM002 | OBS | UBE |  |  | 999 |  |  | Cost Interfaces - Generic | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2150 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet |  | Interface | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55SCM003 | OBS | UBE |  |  | 999 |  |  | Sales Interfaces - Generic | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2151 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet |  | Interface | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55SCM004 | No | UBE |  |  | 999 |  |  | Inventory & GIT Interface - Generic | Obsolete |  |  |  | H |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2152 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet |  | Interface | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600040 | No | UBE | BXU547602 |  | 3 |  | CRP | Intercompany (CIPI) Voucher Integrity Report | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Greg Felitto | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 07/11/2019 | 07/10/2019 |  | 2153 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 03:55 | Joshi, Abhishek N | 56-F-EU-V-190708-S3FI142 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190708-S3FIV142A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600059 | Yes | UBE | 1240725 (16555) | 1241634 (16555) | 5 |  |  | Move SSCC18 Label Print | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/22/2019 | 8/21/2019 |  | 2154 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 07:03 | ANAND, S | 56-F-EU-V-190820-S5LO071 | Printer | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190820-S5LOV071A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600068 | No | UBE | 1231851 (13044) | 1231852 (13044) | 4 |  |  | Print Valorized PDF Before EDI | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/7/2019 | 8/6/2019 |  | 2155 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 07:56 | ANAND, S | 56-F-EU-V-190801-S4LO101 | Printer | Yes | Y |  |  |  | KTW4 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600070 | No | UBE | 1231851 (13044) | 1231852 (13044) | 4 |  |  | Print Valorized PDF After EDI | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/7/2019 | 8/6/2019 |  | 2156 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 08:04 | ANAND, S | 56-F-EU-V-190805-S4LO117 | Printer | Yes | Y |  |  |  | KTW5 |  |  | 56-F-EU-V-190805-S4LOV117A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600071 | Yes | UBE | 1231851 (13044) | 1231852 (13044) | 4 |  |  | Print Quantity by Lot Status After EDI | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/7/2019 | 8/6/2019 |  | 2157 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 08:06 | ANAND, S | 56-F-EU-V-190805-S4LO112 | Printer | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190805-S4LOV112A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600101 | Yes | UBE | 1248870 (21934) | 1248871 | 4 |  |  | Repost Move Ticket Commitments UBE | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/07/2019 | 8/06/2019 |  | 2158 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-05 14:06 | Singh, Sunil Kumar | 56-F-EU-V-190806-S4LO077 |  | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190806-S4LOV077A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600104 | No | UBE |  |  | 2 | 2 |  | eMail Home Patients Route Planning Report | L3 Pass |  |  | TRUE | HNE2E |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/27/2019 | 6/26/2019 |  | 2159 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:09 | Chiau, Liesbet | 56-F-EU-V-250619-S2LO136 | Report | Yes | Y |  |  |  | KTS6 |  |  | 56-F-EU-V-250619-S2LOV136A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600107 | No | UBE |  |  | 4 |  |  | Product Allocation Customer Group Creation Report | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/5/2019 | 8/2/2019 |  | 2160 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-14 04:41 | Kamatham, Deepika | 56-F-EU-V-190805-S4OM039 | Report | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190805-S4OMV039A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600109 | No | UBE |  |  | 3 | 3 |  | Load List Selection Wrapper Report | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Puneet Sharma | L2 Pass / Complete | Except email funcationality testing completed this will be tested in L3 UT., Pl. refer R5600103 comments. |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/17/2019 | 7/16/2019 |  | 2161 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-23 05:01 | Chavan, Prasad | 56-F-EU-V-190715-S3LO151 | Report | Yes | Y |  |  |  | KTT3 |  |  | 56-F-EU-V-190715-S3LOV151A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600117 | No | UBE |  |  | 4 |  |  | Automate creation of QED for Homepatients | L3 Pass |  |  | TRUE | L |  | transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 08/07/2019 | 08/06/2019 |  | 2162 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-12 03:17 | Destrebecq, Eric | 56-F-EU-V-190802-S4LO156 |  | Yes | Y |  |  |  | various2 |  |  | 56-F-EU-V-190802-S4LOV156A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600126 | No | UBE | BXU545218 |  | 4 |  |  | Hold Codes report with Statuses | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Venkateswaran Murugesan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/5/2019 | 8/2/2019 |  | 2163 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 08:38 | Joshi, Abhishek N | 56-F-EU-V-190802-S4OM035 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190802-S4OMV035A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600140 | No | UBE | 1259576 (27028) | 1259577 (27028) | 4 |  |  | Shipping Document Set - Master UBE | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/8/2019 | 8/7/2019 |  | 2164 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 08:23 | ANAND, S | 56-F-EU-V-190708-S4LO160 |  | Yes | Y |  |  |  | KTT5 |  |  | 56-F-EU-V-190708-S4LOV160A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600140S | No | UBE | 1264936 (8358) | 1263135 (8358) | 6 |  |  | Shipping Document Set - Schedule UBE | PPD Passed |  |  | TRUE | HE2E |  | Transportation | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 08/08/2019 | 08/07/2019 |  | 2165 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 08:31 | ANAND, S | 56-F-EU-V-190807-S4LO157 |  | Yes | Yes |  |  | this object is launched only when a specific version of R5600140 is launched. During test script in L2/L3, we do not call that specific version. can be put as L2 & L3 not required tested informally in UT, works | KTT5 |  |  | 56-F-EU-V-190807-S4LOV157A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600148 | No | UBE | 1276006 (23830) | 1276008 | 2 |  |  | UBE for EMEA - P4205 Plug and Play - Functions | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Reveiw E2E process exists |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/25/2019 | 6/24/2019 |  | 2166 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 08:24 | Singh, Sunil Kumar | 56-F-EU-V-190624-S2LO134 |  | Yes | Y |  |  | Blindly submitted the UBE for Unit test as the report is being called from P4205 . Confirmed the same from the functional | KTW4 | VV-24/06 Moved to Sprint 2 as per approval from Leo |  | 56-F-EU-V-190624-S2LOV134A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560018I3 | No | UBE | BXU545181, BXU545242 (16924) |  | 4 |  |  | Intrastat Extract Error Report. | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/8/2019 | 8/7/2019 |  | 2167 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-02 12:48 | Singh, Sunil Kumar | 56-F-EU-V-190801-S4LO002 | Error / Report | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190801-S4LOV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600202 | Yes | UBE | BXU544632&nbsp; 1262729 23271 | 13375, BXU545906 | 2 |  |  | EIM : Create GBL rows in F59002 when item added | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 17/06/2019 | 17/06/2019 |  | 2168 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-20 06:05 | Vishnubhatla, Mithra | 56-F-EU-V-190613-S2MD031 |  | Yes | Y | [6 empty] | 56-F-EU-V-190613-S2MDV031A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560101ZA | No | UBE | 1230484 13772 | 1225082 | 2 |  |  | Upload - Address Book Interoperability | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri |  |  |  | 2169 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-18 09:59 | Vishnubhatla, Mithra | 56-F-EU-V-190612-S2MD005 | Upload | [8 empty] | 56-F-EU-V-190612-S2MDV005A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5601025 | Yes | UBE | 1262729 1242047 | 23271, 1262755 | 2 |  |  | Baxter Customer and Contact Warm Up Consumer UBE | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 11/06/19 | 11/06/19 |  | 2170 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-18 10:06 | Vishnubhatla, Mithra | 56-F-EU-V-190611-S2MD019 |  | Yes | Y | [6 empty] | 56-F-EU-V-190611-S2MDV19A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5601VUH | No | UBE |  | BXU546897 | 4 |  |  | Vehicle Utilization by Hub Report | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 08/08/2019 | 08/07/2019 |  | 2171 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 06:02 | Joshi, Abhishek N | 56-F-EU-V-190805-S4LO121 | Report | Yes |  |  |  |  | FCA2 |  |  | 56-F-EU-V-190805-S4LOV121A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5603012D | No | UBE | 1229478 | 1233852 | 2 |  |  | Deactivation of Customer & HP | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/17/2019 | 6/17/2019 |  | 2172 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 06:58 | Joshi, Abhishek N | 56-F-EU-V-190614-S2MD035 |  | Yes | Y | [6 empty] | 56-F-EU-V-190614-S2MDV035A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5603013 | Yes | UBE |  | 1253946 | 2 |  |  | Synchronise Customer Master Companies For An Address | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/17/2019 | 6/14/2019 |  | 2173 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 06:29 | Joshi, Abhishek N | 56-F-EU-V-190610-S2MD008 |  | Yes | Y | [6 empty] | 56-F-EU-V-190610-S2MDV08A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56110ZA | No | UBE |  |  | 3 |  | CRP | Rebatch Pega Invoices for Target | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saieja |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 6/27/2019 | 6/26/2019 |  | 2174 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-09 06:56 | Gilthorpe, Peter | 56-F-EU-V-190626-S3FI027 |  | Yes | Y | [6 empty] | 56-F-EU-V-190626-S3FIV027A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5612809 | No | UBE | BXU549999 |  | 2 |  | CRP | AP Netting Extract Upload (Access) | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 06/12/2019 | 06/11/2019 |  | 2175 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 03:38 | Joshi, Abhishek N | 56-F-EU-V-190610-S2FI012 | Upload | Yes | Y | [6 empty] | 56-F-EU-V-190610-S2FIV12A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5614346 | No | UBE | BXU545950 |  | 4 |  | CRP | Weighted Avg COGS Write Off | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | CIZMECI,TANKUT |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/9/2019 | 8/8/2019 |  | 2176 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 23:59 | Joshi, Abhishek N | 56-F-EU-V-190729-S4FI055 |  | Yes | Y | [6 empty] | 56-F-EU-V-190729-S4FIV055A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5622667 | No | UBE | BXU546005 |  | 5 |  | CRP | VAT Recoverable Report for Slovakia | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/27/2019 | 8/26/2019 |  | 2177 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-08 00:21 | Joshi, Abhishek N | 56-F-EU-V-190813-S5FI062 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190813-S5FIV062A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5624052 | No | UBE | BXU546028 |  | 6 |  | CRP | Audit Counter part Report Russia | L3 Pass |  |  | TRUE | LNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 9/12/2019 | 9/11/2019 |  | 2178 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-08 00:31 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI049 | Audit / Report | Yes | Y | [6 empty] | 56-F-EU-V-190827-S6FIV049A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5625084 | No | UBE | BXU546029 |  | 4 |  | CRP | Active duplicate records finder | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Lokesh Reddy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/9/2019 | 8/8/2019 |  | 2179 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-08 00:35 | Joshi, Abhishek N | 56-F-EU-V-190806-S4FI098 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190806-S4FIV098A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R563460B | No | UBE |  | BXU546893 | 5 |  |  | Extract Actuals for Intercompany | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/22/2019 | 8/22/2019 |  | 2180 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 06:08 | Joshi, Abhishek N | 56-F-EU-V-190822-S5LO080 |  | Yes | Yes |  |  |  | KTW4 |  |  | 56-F-EU-V-190822-S5LOV080A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5640071C | No | UBE | BXU545808 |  | 4 |  |  | Customers Linked to Preference Groups | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/5/2019 | 8/2/2019 |  | 2181 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 10:02 | Joshi, Abhishek N | 56-F-EU-V-190731-S4OM027 |  | Yes | [7 empty] | 56-F-EU-V-190731-S4OMV027A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5640304U | No | UBE | BXU545798 |  | 3 |  |  | Buying Group Upload | L3 Pass | 216 |  | TRUE | L |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete | L3 testing - need access to \\DEFRE1WIN903.AWS.BAXTER.COM=> KSR000009172004; INC000001226663 (workaround) + defect # 216 |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 7/16/2019 | 7/15/2019 |  | 2182 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 01:53 | Joshi, Abhishek N | 56-F-EU-V-190715-S3OM038 | Upload | Yes | Y | [6 empty] | 56-F-EU-V-190715-S3OMV038A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56403UP | No | UBE | BXU545800 |  | 4 |  |  | Buying Group Upload Purge | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:55 | Kishi, Sayuri | 8/2/2019 | 8/1/2019 |  | 2183 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 04:19 | Joshi, Abhishek N | 56-F-EU-V-190801-S4OM031 | Upload | Yes | Y | [6 empty] | 56-F-EU-V-190801-S4OMV031A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56405 | No | UBE |  |  | 999 |  |  | TOSCANINI Item Master Interface | Obsolete |  |  |  | H |  | MDM | MDM | Tom Hoste | (Blank) |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2184 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet |  | Interface | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56406 | Yes | UBE |  |  | 999 |  |  | PMDA : Lots File update | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2185 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56407 | No | UBE |  |  | 999 |  |  |  | Obsolete | [5 empty] | Quality | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2186 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564071NH | No | UBE |  | 1262754 | 4 |  |  | Sales Authorisation Flag Extract - New Horizons | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/5/2019 | 8/2/2019 |  | 2187 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-27 10:16 | Singh, Sunil Kumar | 56-F-EU-V-190801-S4OM001 |  | Yes | [7 empty] | 56-F-EU-V-190801-S4OMV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564072 | OBS | UBE |  |  | 999 |  |  | Baxter Nikkiso Price Record ID Stamp | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2188 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564072O | No | UBE | BXU545809 |  | 4 |  |  | salesforce.com orchestrator | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | John Whalley | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 08/05/2019 | 08/02/2019 |  | 2189 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 10:00 | Joshi, Abhishek N | 56-F-EU-V-190801-S4OM029 |  | Yes | Y | [6 empty] | 56-F-EU-V-190801-S4OMV029A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564072U | No | UBE |  |  | 4 |  |  | salesforce.com upload | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | John Whalley | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/6/2019 | 8/5/2019 |  | 2190 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-23 07:44 | Whalley, John | 56-F-EU-V-190805-S4OM041 | Upload | Yes | Yes | [6 empty] | 56-F-EU-V-190805-S4OMV041A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564072UP | OBS | UBE |  |  | 999 |  |  | Flag F4072 records as Baxalta | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2191 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564074H | No | UBE |  |  | 5 |  |  | Pricing Invoice Hold Controller | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Mike Tarpey | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/6/2019 | 8/5/2019 |  | 2192 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-11 18:05 | Mike, Tarpey | 56-F-EU-V-190801-S4OM032 |  | Yes | Y | [6 empty] | 56-F-EU-V-190801-S4OMV032A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564074P | No | UBE |  |  | 5 |  |  | Eurydice Pending Prices | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Mike Tarpey | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/6/2019 | 8/5/2019 |  | 2193 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-11 18:05 | Mike, Tarpey | 56-F-EU-V-190805-S4OM045 |  | Yes | [7 empty] | 56-F-EU-V-190805-S4OMV045A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564074X | No | UBE |  |  | 999 | R6 |  | Convert VAT inclusive to exclusive | Obsolete |  |  | TRUE |  | TRUE | Finance | Finance | Piet Van Gijseghem, Lina Seputyte | L2 Not required |  |  |  | Terry Greenard / Vikas Verma | Obsolete 26/11 Felitto, Gregory, raised defect 664 for this UBE and confirmed that it is still used. changed the sprint from 999 to R4 as per aggrement with Sameer | Bargavi Durairajan |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 11/27/2019 | 11/26/2019 |  | 2194 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-09 09:38 | Greenard, Terry | 56-F-EU-V-191127-R4FI001 |  | Yes | [7 empty] | 56-F-EU-V-191127-R4FIV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641002 | Yes | UBE | 1240723 | 1241633 | 2 |  |  | WCS IG/IF PreProcessor | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 6/12/2019 | 6/12/2019 |  | 2195 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-28 22:00 | Singh, Sunil Kumar | 56-F-EU-V-190610-S2LO011 |  | Yes | Y |  |  |  | KTW6 |  |  | 56-F-EU-V-190610-S2LOV11A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641002V | No | UBE | 1229495 | 1230564 | 2 |  |  | Generate Carton Volume in F41002 from F46011 | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2196 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 08:33 | Joshi, Abhishek N | 56-F-EU-V-190610-S2MD007 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190610-S2MDV07A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641010 | Yes | UBE | 1230484 | 13772 | 2 |  |  | Branch Plant Unauthorised User Integrity Report | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | Retrofit not required | Saiteja |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 14/06/2019 | 14/06/2019 |  | 2197 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-27 09:26 | Vishnubhatla, Mithra | 56-F-EU-V-190611-S2MD022 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190611-S2MDV022A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641011 | Yes | UBE |  |  | 2 |  |  | Item Stocking Type Integrity Report | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 6/14/2019 | 6/13/2019 |  | 2198 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:09 | Chiau, Liesbet | 56-F-EU-V-190613-S2MD030 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190613-S2MDV30A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641012 | Yes | UBE |  |  | 2 |  |  | Item Branch Local Country/Company Integrity Report | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 6/14/2019 | 6/12/2019 |  | 2199 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:09 | Chiau, Liesbet | 56-F-EU-V-190610-S2MD012 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190610-S2MDV012A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641013 | Yes | UBE |  |  | 2 |  |  | F4102/SRP1 F4101/SRP4 Product Type Integrity Report | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 6/13/2019 | 6/12/2019 |  | 2200 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:09 | Chiau, Liesbet | 56-F-EU-V-190610-S2MD011 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190610-S2MDV11A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641014 | Yes | UBE |  |  | 2 |  |  | EIM Integrity report - Temp –Class-Transp. Grp | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 6/13/2019 | 6/13/2019 |  | 2201 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:09 | Chiau, Liesbet | 56-F-EU-V-190610-S2MD005 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190610-S2MDV05A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641015 | Yes | UBE |  |  | 2 |  |  | EIM Integrity report - F4102 missing CLMs | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 6/10/2019 | 6/9/2019 |  | 2202 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 06:58 | Sagar, Sanjay | 56-F-EU-V-190610-S2MD010 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190610-S2MDV010A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641018 | No | UBE | 1268367 (26174) | 1268368 (26174), BXU549397 | 4 |  |  | Customer Demand Inventory balance | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/8/2019 | 8/7/2019 |  | 2203 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 06:11 | Joshi, Abhishek N | 56-F-EU-V-190801-S4LO102 |  | Yes | Y |  |  | Under investigation | KTW4 |  |  | 56-F-EU-V-190801-S4LOV102A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641019 | No | UBE |  | BXU545108 | 4 |  |  | Customer Demand Inventory Transaction | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/8/2019 | 8/7/2019 |  | 2204 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 06:15 | Joshi, Abhishek N | 56-F-EU-V-190805-S4LO118 |  | Yes | Yes |  |  |  | KTW4 |  |  | 56-F-EU-V-190805-S4LOV118A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564101B | YES | UBE | BXU544582 | 24083, BXU545917 | 2 |  |  | Update the BOM Flag | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 6/13/2019 | 6/13/2019 |  | 2205 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 06:45 | Joshi, Abhishek N | 56-F-EU-V-190610-S2MD009 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190610-S2MDV009A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564101P1 | No | UBE | BXU544582 | BXU545917 | 5 |  |  | PDO Report - All Existing Products | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 08/27/2019 | 08/26/2019 |  | 2206 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 06:45 | Joshi, Abhishek N | 56-F-EU-V-190820-S5MD026 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190820-S5MDV026A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564101P2 | No | UBE | BXU544582 | BXU545917 | 5 |  |  | PDO Report of potential missing candidates | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/28/2019 | 8/28/2019 |  | 2207 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 06:46 | Joshi, Abhishek N | 56-F-EU-V-190820-S5MD027 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190820-S5MDV027A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564101Q2 | Yes | UBE | BXU547205 (13691), BXU547402 (15265) | BXU547443 (13691), BXU547508 (15265) | 5 |  |  | Quicklist Extraction Report | L3 Pass | 276 |  | TRUE | L |  | Quality | Logistics | Pawel Oskroba | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/22/2019 | 8/22/2019 |  | 2208 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 09:34 | ANAND, S | 56-F-EU-V-190819-S5LO066 | Report | Yes | Y |  |  |  | KTQ3 |  |  | 56-F-EU-V-190819-S5LOV066A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641021 | No | UBE |  |  | 5 |  |  | Stock Status Report | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 08/22/2019 | 08/21/2019 |  | 2209 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-28 05:14 | Mughal, Abdul | 56-F-EU-V-190820-S5LO076 | Report | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190820-S5LOV076A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641021Z | Yes | UBE | 1241409 (15519), 1255656 (26519), 1269572 (11411), BXU545449 (14060), 1241409 (15519), 1255660 (26519) | 1269575 (11411), BXU545543 (14060), 1241410 (15519), 1264218 (26519) | 5 |  |  | Load Stock Quantity details from WMS and JDE into F5641021 | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Léonard Dartois | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/22/2019 | 8/21/2019 |  | 2210 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 09:52 | ANAND, S | 56-F-EU-V-190814-S5LO044 |  | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190814-S5LOV044A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641027 | Yes | UBE | 1240512 (16342) | 1241632 | 2 |  |  | RAQA Information Detail | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Pawel Oskroba | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 6/19/2019 | 6/18/2019 |  | 2211 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-18 09:06 | ANAND, S | 56-F-EU-V-190619-S2LO113 |  | Yes | Y |  |  | Vikas - Moved from Sprint 5 to Sprint 2 as per reqest from Pawel | KTQ3 |  |  | 56-F-EU-V-190619-S2LOV113A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641028 | Yes | UBE |  | BXU545996 | 5 |  |  | WCS replication : create F59002 row | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 08/28/2019 | 08/27/2019 |  | 2212 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-27 05:44 | Singh, Sunil Kumar | 56-F-EU-V-190820-S5MD28 |  | Yes | Y | [6 empty] | 56-F-EU-V-190820-S5MDV28A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564102T | No | UBE | 1229495 | 1230564 | 2 |  |  | Extract F4102 and Fire RTE for Item BPs changes | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2213 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 08:34 | Joshi, Abhishek N |  |  | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564102V | No | UBE | BXU544681 | 1242048 | 2 |  |  | Restamp VAT Flag in Item BP Tag File | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Devi |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 6/11/2019 | 6/11/2019 |  | 2214 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 06:48 | Joshi, Abhishek N | 56-F-EU-V-190610-S2MD003 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190610-S2MDA03V | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641036 | No | UBE |  |  | 5 |  |  | Empty Location Report | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/22/2019 | 8/21/2019 |  | 2215 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-02 08:01 | De Brouwer, Peter | 56-F-EU-V-190816-S5LO060 | Report | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190816-S5LOV060A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641037 | Yes | UBE | 1255649 (25984) | BXU547001 (25984) | 2 |  |  | Whse Pobis OWC - Reprocess Open Requests | L3 Pass | 151 | Closed | TRUE | HE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 6/19/2019 | 6/18/2019 |  | 2216 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 10:11 | ANAND, S | 56-F-EU-V-190619-S2LO114 |  | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190619-S2LOV114A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641039 | Yes | UBE | 1258611 (25919) |  | 5 |  |  | JDE Stock Reconciliation Recheck | L3 Pass | 281 | Open | TRUE | L |  | Warehouse | Logistics | Leonard Dartois | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | SaiTeja |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/22/2019 | 8/22/2019 |  | 2217 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 08:42 | Singh, Sunil Kumar | 56-F-EU-V-190821-S5LO078 |  | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190821-S5LOV078A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641049 | Yes | UBE |  |  | 999 |  |  | Load Medolla Stock Rec details into F564121Z | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2218 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564104RT | Yes | UBE | BXU544781 | 1270173 | 6 | 6 |  | Send RTE to Siebel for selected F4104 records | L3 Not Required |  |  | TRUE | HNE2E |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/6/2019 | 8/5/2019 |  | 2219 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-27 06:02 | Singh, Sunil Kumar | 56-F-EU-V-190802-S4OM034 |  | Yes | Y | [6 empty] | 56-F-EU-V-190802-S4OMV034A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641050 | Yes | UBE | 1262603 (9834) | 1262604 (9834) | 5 |  |  | Broken Box Report | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/28/2019 | 8/27/2019 |  | 2220 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 10:14 | ANAND, S | 56-F-EU-V-190814-S5LO050 | Report | Yes | Y |  |  |  | KTW4 |  |  | 56-F-EU-V-190814-S5LOV050A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641082 | Yes | UBE |  |  | 999 |  |  | Update Lot Dates where on-hand date greater than Expiry Date | Obsolete | [5 empty] | Quality | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2221 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641089 | No | UBE | 1240662 (17810) | 1241641 (17810) | 2 |  |  | Synchronise Lot Master LRP2 with IMZ59SSSF from F594101 | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Pawel Oskroba | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 6/10/2019 | 6/10/2019 |  | 2222 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 10:18 | ANAND, S | 56-F-EU-V-190610-S2LO016 |  | Yes | Yes |  |  |  | KTQ4 |  |  | 56-F-EU-V-190610-S2LOV016A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564108B | Yes | UBE |  |  | 4 |  |  | Inbound Lot Shipment Flag Update | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Pawel Oskroba | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | VV-01/08 - Moved to Sprint 4 as per request from Miruna | Tankut Cizmeci |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/2/2019 | 8/1/2019 |  | 2223 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-09 04:34 | Oskroba, Pawel | 56-F-EU-V-190801-S4LO099 | Inbound | Yes | Y |  |  |  | KTQ3 |  |  | 56-F-EU-V-190801-S4LOV099A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564108E | Yes | UBE | 1230245 (13528) | 1231902 (13528) | 5 |  |  | LLM to CLM Conversion Extraction UBE | L3 Not Required |  |  | TRUE | L |  | Quality | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/26/2019 | 8/23/2019 |  | 2224 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 10:23 | ANAND, S | 56-F-EU-V-190820-S5LO074 |  | Yes | Y |  |  | On Hold N/A for EMEA | N/A |  |  | 56-F-EU-V-190820-S5LOV074A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564108F | Yes | UBE |  |  | 999 |  |  | WISE Batch File to JDE CLM Discrepancies | Obsolete | [5 empty] | Quality | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2225 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564108Q | Yes | UBE | 1244526 (20309) | 20309 1246231 | 6 |  |  | Quickcert Interface Data Extract & Lot Update | L3 Not Required | 452 | Closed | TRUE | L |  | Quality | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/5/2019 | 9/4/2019 |  | 2226 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-19 06:17 | ANAND, S | 56-F-EU-V-190827-S6LO016 | Interface | Yes | Y |  |  | Waiting to have integration before testing | KTQ4 |  |  | 56-F-EU-V-190827-S6LOV016A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641171 | No | UBE | 1229495 | 1230564 | 6 |  |  | Item Branch Plant F41171 Return Flag set up | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/5/2019 | 9/4/2019 |  | 2227 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 08:35 | Joshi, Abhishek N | 56-F-EU-V-190827-S6MD002 |  | Yes | Y | [6 empty] | 56-F-EU-V-190827-S6MDV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564121D | No | UBE |  |  | 5 |  |  | Daily Item Balances Report | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/26/19 | 8/23/19 |  | 2228 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-27 04:21 | Partanen, Aki | 56-F-EU-V-190812-S5LO011 | Report | Yes | Y |  |  |  | KTW8 |  |  | 56-F-EU-V-190812-S5LOV011A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564121M | No | UBE |  |  | 5 |  |  | Monthly Item Balances Report | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/26/2019 | 8/23/2019 |  | 2229 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-29 22:52 | Partanen, Aki | 56-F-EU-V-190816-S5LO058 | Report | Yes | Yes |  |  |  | KTW8 |  |  | 56-F-EU-V-190816-S5LOV058A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564121ZK | No | UBE | 1265844 | 10893 1265845 | 6 |  |  | KfH Stock Reconciliation against Snapshot file | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Léonard Dartois | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/5/2019 | 8/28/2019 |  | 2230 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 09:47 | Vishnubhatla, Mithra | 56-F-EU-V-190827-S6LO014 |  | Yes | Yes |  |  |  | KTW4 |  |  | 56-F-EU-V-190827-S6LOV014A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564121ZS | No | UBE | 1255076 (21228), 1255656 (26519), BXU545447, 1255660 (26519) | 1255077 (21228), 1264218 (26519) | 6 |  |  | WCS Stock Reconciliation against Snapshot file | L3 Pass | 297 |  | TRUE | L |  | Warehouse | Logistics | Léonard Dartois | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/5/2019 | 9/4/2019 |  | 2231 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-12 06:23 | ANAND, S | 56-F-EU-V-190829-S6LO026 |  | Yes | Yes |  |  |  | KTW4 |  |  | 56-F-EU-V-190829-S6LOV026A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564121ZU | Yes | UBE | 1258611 (25919) |  | 6 |  |  | WMS UK Stock Reconciliation against Snapshot file | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Léonard Dartois | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 09/05/2019 | 09/04/2019 |  | 2232 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 08:44 | Singh, Sunil Kumar | 56-F-EU-V-190828-S6LO021 |  | Yes | Yes |  |  |  | KTW5 |  |  | 56-F-EU-V-190828-S6LOV021A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564142S | No | UBE | 1249640 (22313) | 1249642 (22313) | 6 |  |  | Bollini Sesto import UBE | L3 Pass |  |  | TRUE | H |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/5/2019 | 9/4/2019 |  | 2233 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-12 06:39 | ANAND, S | 56-F-EU-V-190827-S6LO017 |  | Yes | Yes |  |  | Review for Bollini E2E process | KTW4 |  |  | 56-F-EU-V-190827-S6LOV017A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56418C1 | Yes | UBE |  |  | 999 |  |  | WISE Lot and Location Master Conversion - TC | Obsolete |  |  |  | L |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2234 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet | [7 empty] | KTW6 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642006 | Yes | UBE | 1253922 (24450) | BXU548867 24450 | 2 |  |  | APS Replenishment Orders BA and BR | L3 Pass |  |  | TRUE | HE2E |  | Procurement | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 6/19/2019 | 6/18/2019 |  | 2235 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 09:17 | Vishnubhatla, Mithra | 56-F-EU-V-190619-S2LO115 |  | Yes | Y |  |  |  | KTW5 |  |  | 56-F-EU-V-190619-S2LOV115A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642011 | No | UBE | BXU545045 (20207) | 1248395 | 6 |  |  | Master Compounding Integration Error Report | L3 Not Required |  |  | TRUE | HNE2E |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/6/2019 | 8/5/2019 |  | 2236 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 09:42 | ANAND, S | 56-F-EU-V-190806-S4OM046 | Error / Report | Yes | [7 empty] | 56-F-EU-V-190806-S4OMV046A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642012 | Yes | UBE | BXU545045 (20207) | 1248395 | 6 |  |  | Master Compounding Driver UBE | L3 Not Required |  |  | FALSE | HNE2E |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/17/2019 | 9/17/2019 |  | 2237 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 09:42 | ANAND, S | 56-F-EU-V-190805-S4OM042 |  | Yes | [7 empty] | 56-F-EU-V-190805-S4OMV042A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642016 | No | UBE | 1258803 (25961), 1240725 (16555) | 1259574 (25961) | 6 |  |  | Whse BR Messaging UBE | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | Yes | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/5/2019 | 9/4/2019 |  | 2238 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-12 07:01 | ANAND, S | 56-F-EU-V-190827-S6LO010 |  | Yes |  |  |  |  | KTW5 |  |  | 56-F-EU-V-190827-S6LOV010A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642025 | No | UBE | 1259921 (4304) | 4304 | 6 |  |  | Merlin Master Compounding Driver UBE | L3 Not Required |  |  | TRUE | HNE2E |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/4/2019 | 9/3/2019 |  | 2239 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 08:47 | ANAND, S | 56-F-EU-V-190805-S4OM037 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190805-S4OMV037A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642028 | No | UBE | 1259921 (4304) |  | 6 |  |  | Merlin Master Compounding Order Creation Report | L3 Not Required |  |  | TRUE | HNE2E |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/4/2019 | 9/3/2019 |  | 2240 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 08:47 | ANAND, S | 56-F-EU-V-190805-S4OM046 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190805-S4OMV046A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642031 | No | UBE |  |  | 4 |  |  | Customer Demand Customer Order | L3 Pass |  |  | TRUE | LE2E |  | Procurement | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/8/2019 | 8/7/2019 |  | 2241 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-20 05:28 | De Brouwer, Peter | 56-F-EU-V-190808-S4LO122 |  | Yes |  |  |  | Review E2E process exists | KTW5 |  |  | 56-F-EU-V-190808-S4LOV122A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642035 | No | UBE | 1255068 (26047) | 1255069 (26047) | 4 |  |  | Negative Sales Commitment Report | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/08/2019 | 8/07/2019 |  | 2242 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 06:19 | ANAND, S | 56-F-EU-V-190807-S4LO158 | Report | Yes | Yes |  |  |  | KTW5 |  |  | 56-F-EU-V-190807-S4LOV158A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642040 | No | UBE |  |  | 4 |  |  | CIG Number Differences Report | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/7/2019 | 8/6/2019 |  | 2243 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-08 06:13 | Kamatham, Deepika | 56-F-EU-V-190801-S4OM002 | Report | Yes | [7 empty] | 56-F-EU-V-190801-S4OMV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642051 | No | UBE | BXU545842 | BXU546788 | 4 |  |  | EDI Sales Order Transaction Originator Update | L3 Pass |  |  | TRUE | HE2E |  | EDI Order Management | eCommerce | Aidan Scally | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 08/02/2019 | 08/01/2019 |  | 2244 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 07:44 | Joshi, Abhishek N | 56-F-EU-V-190731-S4OM024 |  | Yes | Y |  |  |  | KTEDI5 |  |  | 56-F-EU-V-190731-S4OMV024A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564241 | No | UBE | BXU545793 | BXU547521 | 4 |  |  | Integrity report between Open Orders & Committed Quantity | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Venkateswaran Murugesan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 08/07/2019 | 08/06/2019 |  | 2245 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 04:33 | Joshi, Abhishek N | 56-F-EU-V-190805-S4OM040 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190805-S4OMV040A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642599M | Yes | UBE |  |  | 999 |  |  | Replenishment Notification - Medolla | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2246 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642861 | No | UBE |  |  | 4 |  |  | Convert Sales Order to Uncommitted | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Venkateswaran Murugesan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 08/08/2019 | 08/07/2019 |  | 2247 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-15 05:28 | Murugesan, Venkateswaran | 56-F-EU-V-190807-S4OM049 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190807-S4OMV049A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642900 | No | UBE | 1259579 |  | 4 |  |  | Zero Cost Price Validation | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | George Malithara | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/8/2019 | 8/7/2019 |  | 2248 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-20 10:06 | Singh, Sunil Kumar | 56-F-EU-V-190805-S4OM043 |  | Yes | Y | [6 empty] | 56-F-EU-V-190805-S4OMV043A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642950 | No | UBE |  |  | 5 |  |  | Baxter Sales Order Batch Price/Cost Update | L3 Pass | 262 | L3 testing defect Log# 262 open for UTS_R5642950 | TRUE | HNE2E |  | Order Management | OM | George Malithara | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | Due to L3 testing defect Log# 262, UT 9.2 job number 3980 done with modified Data Selection | Rishikesh |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/8/2019 | 8/7/2019 |  | 2249 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-05 02:58 | Malithara, George Manuval | 56-F-EU-V-190801-S4OM033 |  | Yes | Yes |  |  |  |  | UTS_R5642950 |  | 56-F-EU-V-190801-S4OMV033A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643002 | Yes | UBE | BXU545094 (16423), 1236462 (16423) | 1236463 (16423) | 4 |  |  | Update Lot Status on F4311 | L3 Pass |  |  | TRUE | LE2E |  | Procurement | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/8/2019 | 8/7/2019 |  | 2250 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 08:52 | ANAND, S | 56-F-EU-V-190807-S4LO159 |  | Yes | Yes |  |  |  | KTW5 |  |  | 56-F-EU-V-190807-S4LOV159A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643013 | No | UBE | 1272865 (23357) | 1272955 | 6 |  |  | Inbound Receipt Routing Errors Report | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/6/2019 | 9/6/2019 |  | 2251 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 08:52 | Singh, Sunil Kumar | 56-F-EU-V-190829-S6LO032 | Error / Inbound / Report | Yes | Y |  |  |  | KTW5 |  |  | 56-F-EU-V-190829-S6LOV032A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643092M | Yes | UBE |  |  | 999 |  |  | Receipt Routing Notification - Medolla | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2252 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643092Z | Yes | UBE | 1258017 (26923) | 1258019 (26923) | 6 |  |  | Receipt Routing Transactions Inbound Processor Great Bear | L3 Pass |  |  | TRUE | LE2E |  | Procurement | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/6/2019 | 9/5/2019 |  | 2253 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-12 07:17 | ANAND, S | 56-F-EU-V-190830-S6LO035 | Inbound | Yes | Y |  |  | Review E2E process exists | KTW5 |  |  | 56-F-EU-V-190830-S6LOV035A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643101 | No | UBE |  |  | 6 |  | CRP | Upload SPRING data to JDE Z-files | L3 Pass | 330 | Closed | TRUE | HE2E |  | Finance AP | Finance | Keith Haxton | L2 Pass / Complete | Was added to Sprint 6 as still needed |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/11/2019 | 9/12/2019 |  | 2254 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-04 07:37 | Haxton, Keith | 56-F-EU-V-190904-S6FI142 | Upload | Yes | Yes | [6 empty] | 56-F-EU-V-190904-S6FIV142A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564311R | Yes | UBE | BXU545031 (14166), 1230525 (14166) | 1233110 (14166) | 6 |  |  | Update Lot Status on F4311 for Customer Returns | L3 Pass | 290 | Open | TRUE | LE2E |  | Procurement | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/06/2019 | 9/06/2019 |  | 2255 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-12 07:27 | ANAND, S | 56-F-EU-V-190829-S6LO029 |  | Yes | Yes |  |  | Review E2E process exists | KTW5 |  |  | 56-F-EU-V-190829-S6LOV029A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564312A | No | UBE | BXU542146 |  | 6 |  |  |  | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 09/06/2019 | 09/05/2019 |  | 2256 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 01:19 | Joshi, Abhishek N | 56-F-EU-V-190905-S6LO046 |  | Yes | Y |  |  |  | KTW5 |  |  | 56-F-EU-V-190905-S6LOV046A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643510 | Yes | UBE | BXU545508 (15838), BXU545143 (20072), 1235550 (15838) | 1235568 (15838) BXU545326 20072 | 6 |  |  | Baxter Move Ticket for PO Receiving | L3 Pass | 288 | Open | TRUE | LE2E |  | Procurement | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/6/2019 | 9/5/2019 |  | 2257 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-14 05:36 | Vishnubhatla, Mithra | 56-F-EU-V-190827-S6LO011 |  | Yes | Yes |  |  | Review E2E process exists.No code change needed for Defect #288 but RD job executed successfully after the removal of 32 bit POC. Requested Oracle for 64 bit POC. | KTW5 |  |  | 56-F-EU-V-190827-S6LOV011A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643801 | No | UBE |  |  | 6 |  |  | MILD to JDE Integrity Report - POs | L3 Pass |  |  | TRUE | LNE2E |  | Procurement | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth, Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/6/2019 | 9/5/2019 |  | 2258 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-13 05:21 | Sharma, Nikit | 56-F-EU-V-190829-S6LO031 | Report | Yes |  |  |  |  | KTW5 |  |  | 56-F-EU-V-190829-S6LOV031A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647004 | No | UBE | 1251319 (21666) | 1251321 (21666) | 6 |  |  | KfH Adjustments CONIN/CONOUT PreProc | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 09/06/2019 | 09/05/2019 |  | 2259 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 10:15 | ANAND, S | 56-F-EU-V-190828-S6LO022 |  | Yes | Yes |  |  | Review E2E process exists | KTW4 |  |  | 56-F-EU-V-190828-S6LOV022A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647005 | No | UBE | 1251326 (21837) |  | 6 |  |  | KfH RECADV EDI Pre Processor | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/6/2019 | 9/5/2019 |  | 2260 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-05 13:34 | Singh, Sunil Kumar | 56-F-EU-V-190830-S6LO033 |  | Yes | Yes |  |  | Review E2E process exists | KTW4 |  |  | 56-F-EU-V-190830-S6LOV033A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647007A | No | UBE | 1258017 (26923) | 1258019 (26923) | 999 |  |  | Great Bear NDC - Inbound Receipt Text File Processor | Obsolete |  |  | TRUE | LE2E |  | Procurement | Logistics | Leonard Dartois | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | VV-19/09 Obsoleted the Object as per the request form Leo | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 09/12/2019 | 09/08/2019 |  | 2261 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-12 08:44 | ANAND, S | 56-F-EU-V-190905-S6LO044 | Text / Inbound | Yes | Yes |  |  | Review E2E process exists | KTW4 |  |  | 56-F-EU-V-190905-S6LOV044A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647007M | Yes | UBE |  |  | 999 |  |  | Medolla - Inbound Receipt Text File Processor | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2262 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet |  | Text / Inbound | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647009 | No | UBE | 1272865 (23357) | 1272955 | 6 |  |  | Inbound Product Activity Errors Report | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/9/2019 | 9/6/2019 |  | 2263 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 09:01 | Singh, Sunil Kumar | 56-F-EU-V-190903-S6LO127 | Error / Inbound / Report | Yes | Yes |  |  |  | KTW4 |  |  | 56-F-EU-V-190903-S6LOV127A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647018 | No | UBE |  |  | 6 |  |  | Process EDI TRAX Data into Inbound Intrastat table | L3 Pass |  |  | TRUE | LNE2E |  | Procurement | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth, Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/9/2019 | 9/8/2019 |  | 2264 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-13 05:21 | Sharma, Nikit | 56-F-EU-V-190827-S6LO019 | Inbound | Yes |  |  |  |  | KTW4 |  |  | 56-F-EU-V-190827-S6LOV019A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647118 | No | UBE | BXU545242 |  | 6 |  |  | Process Intrastat Inbound Transactions | L3 Pass | 303 | Closed | TRUE | L |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/9/2019 | 9/8/2019 |  | 2265 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-02 12:52 | Singh, Sunil Kumar | 56-F-EU-V-190830-S6LO034 | Inbound | Yes | Yes |  |  |  | KTW4 |  |  | 56-F-EU-V-190830-S6LOV034A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647211 | No | UBE | BXU545835 | BXU546789 | 6 |  |  | EDI Inbound Baxter/Baxalta Item Error Report | L3 Pass |  |  | TRUE | LNE2E |  |  | eCommerce |  | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 09/06/2019 | 09/05/2019 |  | 2266 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 07:34 | Joshi, Abhishek N | 56-F-EU-V-190828-S6OM005 | Error / Inbound / Report | Yes | Yes |  |  |  | NoKT |  |  | 56-F-EU-V-190828-S6OMV005A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564736 | No | UBE | BXU545095 |  | 5 |  |  | Pharmalink Consignment Letter | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Lina Seputyte | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/8/19 | 8/7/19 |  | 2267 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 09:18 | Joshi, Abhishek N | 56-F-EU-V-190708-S4OM049 |  | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56474Z1 | No | UBE | BXU545441 |  | 5 |  |  | Eurydice Buying Group Interface Report | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Mike Tarpey | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 08/08/2019 | 08/07/2019 |  | 2268 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 09:16 | Joshi, Abhishek N | 56-F-EU-V-190807-S4OM048 | Interface / Report | Yes | Yes | [6 empty] | 56-F-EU-V-190807-S4OMV048A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56474Z2 | No | UBE |  |  | 5 |  |  | Eurydice Pricing Interface Report | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Mike Tarpey | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 08/07/2019 | 08/06/2019 |  | 2269 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-30 03:26 | Mike, Tarpey | 56-F-EU-V-190807-S4OM047 | Interface / Report | Yes | Yes | [6 empty] | 56-F-EU-V-190807-S4OMV047A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56474Z3 | No | UBE |  |  | 5 |  |  | Datagon Price Upload | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Mike Tarpey | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/19/2019 | 8/16/2019 |  | 2270 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-05 08:15 | Mike, Tarpey | 56-F-EU-V-190813-S5OM009 | Upload | Yes | Y | [6 empty] | 56-F-EU-V-190813-S5OMV009A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56474Z3A | No | UBE |  |  | 5 |  |  | Datagon Preprocessor | L3 Pass |  |  | TRUE | OBS |  | Order Management | OM | Mike Tarpey | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/19/2019 | 8/16/2019 |  | 2271 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-05 08:15 | Mike, Tarpey | 56-F-EU-V-190819-S5OM016 |  | Yes | Y | [6 empty] | 56-F-EU-V-190819-S5OMV016A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56474Z3B | No | UBE |  |  | 5 |  |  | Datagon Price Upload by Batch Number | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | MIke Tarpey | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | CIZMECI,TANKUT |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 08/16/2019 | 08/14/2019 |  | 2272 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-05 08:16 | Mike, Tarpey | 56-F-EU-V-190814-S5OM013 | Upload | Yes | Y | [6 empty] | 56-F-EU-V-190814-S5OMV013A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56474Z5 | No | UBE | BXU545441 |  | 5 |  |  | Eurydice Pricing Interface Report - France & UK | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | MIke Tarpey | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/20/2019 | 8/19/2019 |  | 2273 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 08:53 | Joshi, Abhishek N | 56-F-EU-V-190819-S5OM017 | Interface / Report | Yes | Y | [6 empty] | 56-F-EU-V-190819-S5OMV017A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564750 | No | UBE |  |  | 3 | 3 |  | Inbound Load Planning Processor | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 7/11/2019 | 7/10/2019 |  | 2274 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-15 08:37 | Destrebecq, Eric | 56-F-EU-V-190709-S3LO085 | Inbound | Yes | Y |  |  |  | KTT5 |  |  | 56-F-EU-V-190709-S3LOV085A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5648001 | No | UBE | BXU546725 |  | 6 |  | CRP | WIP Report | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/12/2019 | 9/11/2019 |  | 2275 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 04:34 | Joshi, Abhishek N | 56-F-EU-V-190910-S6FI151 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190910-S6FIV151A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649004 | Yes | UBE | BXU545235 (17955), 1240668 (17955) | 1241037 (17955) | 5 |  |  | Shipment Consolidation Integrity Report | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/26/2019 | 8/23/2019 |  | 2276 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 09:46 | ANAND, S | 56-F-EU-V-190820-S5LO072 | Report | Yes | Y |  |  |  | various |  |  | 56-F-EU-V-190820-S5LOV072A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649006 | No | UBE | 1258803 (25961), 1240725 (16555) | 1259574 (25961) | 6 |  |  | WUK Shipment Feedback | PPD Passed |  |  | TRUE | HE2E |  | Transportation | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/9/2019 | 9/8/2019 |  | 2277 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 09:53 | ANAND, S | 56-F-EU-V-190827-S6LO013 |  | Yes | Y |  |  | waiting for integration to be available | KTT5 |  |  | 56-F-EU-V-190827-S6LOV013A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649009D | No | UBE | 1242055 (18384) |  | 6 |  |  | Delete zero shipment record(s) from F5649009 | L3 Pass |  |  | TRUE | HNE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete | There was no record selected as there is no record with zero shipment number |  |  | Terry Greenard / Vikas Verma | Yes | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/9/2019 | 9/8/2019 |  | 2278 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 05:54 | Singh, Sunil Kumar | 56-F-EU-V-190828-S6LO023 |  | Yes |  |  |  |  | various |  |  | 56-F-EU-V-190828-S6LOV023A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649016 | No | UBE | 1253127 (25015) | 1254401 (25015) | 4 |  |  | Update Shipment Status | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/8/2019 | 8/7/2019 |  | 2279 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 09:59 | ANAND, S | 56-F-EU-V-190801-S4LO003 |  | Yes | Y |  |  |  | FCA2 |  |  | 56-F-EU-V-190801-S4LOV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649020 | Yes | UBE | 1264174 (10180) | 1264183 (10180) | 6 |  |  | Update Temp Logger Information | L3 Pass |  |  | TRUE | HNE2E |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/9/2019 | 9/6/2019 |  | 2280 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 10:06 | ANAND, S | 56-F-EU-V-190830-S6LO036 |  | Yes | Yes |  |  |  | various2 |  |  | 56-F-EU-V-190830-S6LOV036A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649039 | No | UBE |  |  | 6 |  |  | Order Status to Load Status Integrity Report | L3 Pass |  |  | TRUE | MNE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 09/06/2019 | 09/09/2019 |  | 2281 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-05 08:58 | weber, scott | 56-F-EU-V-190829-S6LO030 | Report | Yes | Yes |  |  |  | FCA2 |  |  | 56-F-EU-V-190829-S6LOV030A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564916A | No | UBE | BXU549786 (20599) |  | 6 |  |  | Update F4941.URRF with Logistics WarehouseSystem | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/10/2019 | 9/10/2019 |  | 2282 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 07:39 | ANAND, S | 56-F-EU-V-190903-S6LO131 |  | Yes | Y |  |  |  | various |  |  | 56-F-EU-V-190903-S6LOV131A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564941 | No | UBE |  |  | 999 |  |  | Shipments not Load Confirmed | Obsolete |  |  |  | NA |  | Transportation | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2283 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564941BS | No | UBE |  |  | 3 | 3 |  | Summary Load List - Germany | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Puneet Sharma | L2 Pass / Complete | Except email funcationality testing completed this will be tested in L3 UT., Pl. refer R5600103 comments. |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 7/17/2019 | 7/16/2019 |  | 2284 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-23 05:02 | Chavan, Prasad | 56-F-EU-V-190716-S3LO152 |  | Yes | Y |  |  |  | KTT3 |  |  | 56-F-EU-V-190716-S3LOV152A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564941F | No | UBE |  |  | 4 | 4 |  | Load Summary | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 7/11/2019 | 7/10/2019 |  | 2285 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-13 10:10 | weber, scott | 56-F-EU-V-190709-S3LO050 |  | Yes | Y |  |  |  | KTT5 |  |  | 56-F-EU-V-190709-S3LOV050A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564960 | No | UBE |  |  | 6 |  |  | Order Loaded Ship Confirm | PPD Passed |  |  | TRUE | HE2E |  | Transportation | Logistics | Eric Destrebecq | L2 Not required | cannot be tested in dv 9.2 |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/10/2019 | 9/9/2019 |  | 2286 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-18 08:32 | Destrebecq, Eric | 56-F-EU-V-190904-S6LO041 |  | Yes | Yes |  |  | waiting for integration to be available | various |  |  | 56-F-EU-V-190904-S6LOV041A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649702 | No | UBE |  |  | 6 |  |  | Zero Invoice Control | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/9/2019 | 9/9/2019 |  | 2287 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-11 08:35 | Deveen, Genevive | 56-F-EU-V-190904-S6OM010 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190904-S6OMV010A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649704 | No | UBE |  |  | 6 |  |  | Delivery Date Cycle Billing Program by CSTP | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth, Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/9/2019 | 9/8/2019 |  | 2288 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-17 03:12 | Deveen, Genevive | 56-F-EU-V-190904-S6OM008 |  | Yes | [7 empty] | 56-F-EU-V-190904-S6OMV0008A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649821 | No | UBE |  |  | 6 |  |  | Batch Shipment Approval | L3 Pass |  |  | TRUE | MNE2E |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 09/10/2019 | 09/09/2019 |  | 2289 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-16 04:23 | Destrebecq, Eric | 56-F-EU-V-190905-S6LO043 |  | Yes | Yes |  |  |  | various |  |  | 56-F-EU-V-190905-S6LOV043A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564983 | No | UBE |  |  | 999 |  |  | BX Batch Load Approval | Obsolete |  |  |  | NA |  | Transportation | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2290 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56570030 | No | UBE |  |  | 4 |  | CRP | Remove BANk Type H record in F0030 & in F570030 | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/09/2019 | 8/08/2019 |  | 2291 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-16 10:09 | Touyaa, Manuel | 56-F-EU-V-190808-S4FI105 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190808-S4FIV105A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5674411 | No | UBE | BXU546723 |  | 999 |  |  | Italian Withholding Tax | Obsolete |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton |  |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 7/11/2019 | 7/10/2019 |  | 2292 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-08 03:59 | Joshi, Abhishek N | 56-F-EU-V-190709-S3FI150 |  | Yes | Y | [6 empty] | 56-F-EU-V-190709-S3FIV150A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5695600 | No | UBE |  |  | 999 |  |  | Update Effective Dates on F95600 | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2293 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5698001 | No | UBE |  |  | 6 |  |  | Send Heartbeat Requests | PPD Passed |  |  | TRUE |  |  | CNC | CNC | Rob Zande | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Saieja |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 7/3/2019 | 7/2/2019 |  | 2294 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-29 11:24 | Zande, Robert | 56-F-EU-V-190702-S3CNC001 |  | Yes | Y |  |  | To Be Tested in CRP |  |  |  | 56-F-EU-V-190702-S3CNCV001A_VER | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5698008 | Yes | UBE | BXU545036 | BXU545329 | 6 |  |  | MILD PABACO Process UBE | L3 Pass |  |  | TRUE | HE2E |  | Procurement | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 09/10/2019 | 09/09/2019 |  | 2295 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-05-12 09:17 | Singh, Sunil Kumar | 56-F-EU-V-190905-S6LO045 |  | Yes | Yes |  |  | Reivew E2E process exists | KTW4 |  |  | 56-F-EU-V-190905-S6LOV045A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5698012 | No | UBE |  |  | 6 |  |  | IXOS Print Engine | L3 Not Required |  |  | TRUE | MNE2E |  | IXOS Archive | eCommerce | Linda Kenny | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/29/2019 | 8/28/2019 |  | 2296 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-03 08:12 | Kenny, Linda | 56-F-EU-V-190820-S5EC007 | Printer | Yes | Y |  |  | To be tested in CRP | NoKT |  |  | 56-F-EU-V-190820-S5ECV007A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5698039 | No | UBE |  |  | 6 |  |  | File Purger | PPD Passed |  |  | TRUE |  |  | ARO | ARO | Terry Greenard | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma | Yes | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/5/2019 | 9/4/2019 |  | 2297 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-12-19 02:55 | Greenard, Terry | 56-F-EU-V-190827-S6CN001 |  | Yes |  |  |  | Yes, run on Scheduler 14/12/2019 |  |  |  | 56-F-EU-V-190827-S6CNV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5698040 | No | UBE |  | BXU546790 | 2 |  |  | Baxter Send E-mails | L3 Not Required |  |  | TRUE | MNE2E |  | IXOS Archive | eCommerce | Piet Van Gijseghem, Lina Seputyte | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2298 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-21 05:39 | Joshi, Abhishek N | 56-F-EU-V-190611-S2EC001 |  | Yes | Y |  |  |  | NoKT |  |  | 56-F-EU-V-190611-S2ECV001A |  |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56A0101 | No | UBE |  | 1253946 | R1 |  |  | Address Book Integrity Update Report | PPD Passed |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/26/2019 | 9/25/2019 |  | 2299 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 06:29 | Joshi, Abhishek N | 56-F-EU-V-190924-R1MD007 | Report | No | Y |  |  |  | KT unplanned |  |  | 56-F-EU-V-190924-R1MDV007A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56ARCHI3 | No | UBE |  |  | 999 |  |  | ARCHIBUS - Transaction Extract | Obsolete |  |  |  | HNE2E |  | Finance AP | Finance | Luigi Amorini |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2300 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56ARCHI4 | No | UBE |  |  | 999 |  |  | ARCHIBUS - Date Stamp of EXTRACT per Company | Obsolete |  |  |  | HNE2E |  | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2301 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56ARCHI5 | No | UBE |  |  | 999 |  |  | ARCHIBUS - Vendor Extract (F0101) AT1 =V | Obsolete |  |  |  | HNE2E |  | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2302 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:16 | Chiau, Liesbet | [14 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56BIP07 | No | UBE |  |  | 5 |  |  | IXOS Synchronize Intercompany Invoices | L3 Pass |  |  | TRUE | LNE2E |  | IXOS Archive | eCommerce | Linda Kenny | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/29/2019 | 8/28/2019 |  | 2303 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-12 05:23 | Kenny, Linda | 56-F-EU-V-190819-S5EC003 |  | Yes | Y |  |  |  | NoKT |  |  | 56-F-EU-V-190819-S5ECV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56BIP91 | No | UBE | BXU549595 | BXU546792 | 6 |  |  | IXOS Integrity - Invoices (A) JDE to BIP | L3 Pass |  |  | TRUE | MNE2E |  | IXOS Archive | eCommerce | Linda Kenny | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/26/2019 | 8/23/2019 |  | 2304 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 03:05 | Joshi, Abhishek N | 56-F-EU-V-190814-S5EC001 |  | Yes | Y |  |  |  | NoKT |  |  | 56-F-EU-V-190814-S5ECV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56BIP92 | No | UBE | BXU549595 | BXU546792 | 6 |  |  | IXOS Integrity - Invoices - (B) BIP to IXOS | L3 Pass |  |  | TRUE | MNE2E |  | IXOS Archive | eCommerce | Linda Kenny | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/27/2019 | 8/26/2019 |  | 2305 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 03:08 | Joshi, Abhishek N | 56-F-EU-V-190820-S5EC008 |  | Yes | Y |  |  |  | NoKT |  |  | 56-F-EU-V-190820-S5ECV008A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56BIP93 | No | UBE |  |  | R3 |  |  | IXOS Integrity - Delivery Notes - (C) JDE to BIP | PPD Passed |  |  | TRUE |  | TRUE | IXOS Archive | eCommerce | Linda Kenny | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma | Obsolete | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 11/21/2019 | 11/20/2019 |  | 2306 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-12-20 08:30 | Kenny, Linda | 56-F-EU-V-191114-R3EC001 |  | Yes | Yes | [6 empty] | 56-F-EU-V-191114-R3ECV01A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56BIP94 | No | UBE |  |  | R3 |  |  | IXOS Integrity - Delivery Notes - (D) BIP to IXOS | PPD Passed |  |  | TRUE |  | TRUE | IXOS Archive | eCommerce | Linda Kenny | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Thippulla Sreekanth |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 11/21/2019 | 11/20/2019 |  | 2307 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-12-20 08:30 | Kenny, Linda | 56-F-EU-V-191125-R3EC003 |  | Yes |  |  |  | Code difference not found b/w DV920 and PD812. |  |  |  | 56-F-EU-V-191125-R3ECV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56CDNCK | No | UBE | 1260383 | 18020 1260385 | 5 |  |  | Check CDN exists for Sales Order Lines | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/26/2019 | 8/26/2019 |  | 2308 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-31 09:12 | Vishnubhatla, Mithra | 56-F-EU-V-190826-S5LO081 |  | Yes | Yes |  |  | Review E2E process exists | KTW5 |  |  | 56-F-EU-V-190826-S5LOV081A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56CDNIP | No | UBE |  |  | 6 |  |  | Calculate CDN Import Price | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/10/2019 | 9/9/2019 |  | 2309 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-11 03:24 | De Brouwer, Peter | 56-F-EU-V-190903-S6LO128 |  | Yes | Yes |  |  | Review E2E process exists | KTW5 |  |  | 56-F-EU-V-190903-S6LOV128A | FALSE | FALSE | 302 | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56CDNLG | No | UBE | BXU546443 | 18022 BXU547398 | 6 |  |  | CDN Ledger Report | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/6/2019 | 9/7/2019 |  | 2310 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-31 09:08 | Vishnubhatla, Mithra | 56-F-EU-V-190828-S6LO025 | Report | Yes | Yes |  |  |  | KTW5 |  |  | 56-F-EU-V-190828-S6LOV025A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56COD02 | No | UBE |  |  | 3 |  | CRP | Concur - process the uploaded batch to F570401 | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Eileen Paula | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 7/11/2019 | 7/10/2019 |  | 2311 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-25 02:36 | Gilthorpe, Peter | 56-F-EU-V-190710-S3FI157 | Upload | Yes | Y | [6 empty] | 56-F-EU-V-190710-S3FIV157A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56COD03 | No | UBE |  |  | 3 |  | CRP | Concur Lite - select Countries to process | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Eileen Paula | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 7/11/2019 | 7/10/2019 |  | 2312 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-25 02:36 | Gilthorpe, Peter | 56-F-EU-V-190710-S3FI158 |  | Yes | Y | [6 empty] | 56-F-EU-V-190710-S3FIV158A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56CODN | No | UBE |  |  | 6 |  |  | Russian Conformity Declaration Document | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth, Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/10/2019 | 9/9/2019 |  | 2313 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-16 03:46 | De Brouwer, Peter | 56-F-EU-V-190904-S6LO042 |  | Yes | Yes |  |  | Review E2E process exists | KTW5 |  |  | 56-F-EU-V-190904-S6LOV042A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56EIMGIM | Yes | UBE |  |  | 999 |  |  | Integrity Report EIM-GIM | Obsolete |  |  |  | H |  | MDM | MDM | Tom Hoste | (Blank) |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2314 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:17 | Chiau, Liesbet |  | Report | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FB260 | No | UBE |  |  | 5 |  |  | Sales Report With TAX Id | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/14/2019 | 8/13/2019 |  | 2315 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-23 07:27 | Kamatham, Deepika | 56-F-EU-V-190812-S5OM004 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5OMV004A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FBP150 | No | UBE |  |  | 999 |  |  | CATEGORIZATION REPORT | Obsolete |  |  |  | L |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2316 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:17 | Chiau, Liesbet |  | Report | [5 empty] | NA | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FBP200 | No | UBE |  |  | 6 |  |  | Goods in Transit Report | L3 Pass |  |  | TRUE | LNE2E |  | Procurement | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth, Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/11/2019 | 9/10/2019 |  | 2317 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-13 08:47 | Partanen, Aki | 56-F-EU-V-190904-S6LO037 | Report | Yes | Yes |  |  |  | KTW4 |  |  | 56-F-EU-V-190904-S6LOV037A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FGL111A | No | UBE | BXU546726 |  | 2 |  | CRP | European Sales/Purchase Listing | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 6/11/2019 | 6/11/2019 |  | 2318 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 08:31 | Joshi, Abhishek N | 56-F-EU-V-190610-S2FI008 |  | Yes | Y | [6 empty] | 56-F-EU-V-190610-S2FIV008A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FINM1 | No | UBE | BXU544752 |  | 4 |  | CRP | Update F56FINMV with details from F0911Z1 | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 08/09/2019 | 08/08/2019 |  | 2319 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 08:33 | Joshi, Abhishek N | 56-F-EU-V-190806-S4FI008 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190806-S4FIV008A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRAP145 | No | UBE |  |  | 4 |  | CRP | KPI for p2P non-compliant vouchers | L3 Pass |  |  | TRUE | LNE2E |  | Finance AP | Finance | Saurabh Gupta | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/9/2019 | 8/8/2019 |  | 2320 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-11 03:20 | Frade Dolesor, Constanza | 56-F-EU-V-190805-S4FI095 |  | Yes | Y | [6 empty] | 56-F-EU-V-190805-S4FIV095A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56G0002 | Yes | UBE | BXU533639, BXU544639 (3409) | 3409 BXU544770 | 6 |  |  | Gambro: Inbound ASN Preprocessor | L3 Pass |  |  | TRUE | HE2E |  | Procurement | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth, Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/11/2019 | 9/11/2019 |  | 2321 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 07:08 | Singh, Sunil Kumar | 56-F-EU-V-190910-S6LO045 | Inbound | Yes | Yes |  |  | Reivew E2E process exists | KTW4 |  |  | 56-F-EU-V-190910-S6LOV045A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56G4212 | No | UBE |  |  | 6 |  |  | Gambro: Inbound Invoice Preprocessor | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/11/2019 | 9/10/2019 |  | 2322 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-17 02:44 | BILENSOY, NURI | 56-F-EU-V-190910-S6LO134 | Inbound | Yes | Yes |  |  | Review E2E process exists | KTW4 |  |  | 56-F-EU-V-190910-S6LOV134A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56G4311Z | No | UBE | 1259325 (3405) | 3405 | 6 |  |  | Gambro: Inbound PO From I2 Preprocessor | L3 Pass |  |  | TRUE | HE2E |  | Procurement | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 09/11/2019 | 09/11/2019 |  | 2323 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 07:39 | Singh, Sunil Kumar | 56-F-EU-V-190906-S6LO047 | Inbound | Yes | Yes |  |  | Review E2E process exists | KTW4 |  |  | 56-F-EU-V-190906-S6LOV047A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56G4712 | No | UBE |  |  | 999 |  |  | Gambro GFS-JDE Interface Pre-Processor Error Report | Obsolete | [5 empty] | Technical Services | Logistics | Mandy Corbett, Swetha M S, Thierry Kestens |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2324 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:17 | Chiau, Liesbet |  | Error / Interface / Report | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56G4941A | No | UBE |  |  | 6 |  |  | Gambro: LOAD LIST - Benelux | L3 Pass |  |  | TRUE | HNE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/11/2019 | 9/11/2019 |  | 2325 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-10 07:48 | weber, scott | 56-F-EU-V-190903-S6LO132 |  | Yes | Yes |  |  |  | KTT3 |  |  | 56-F-EU-V-190903-S6LOV132A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56G6105 | No | UBE |  |  | 6 |  |  | Gambro: eMail PO Technicians Report | L3 Pass | 310 | Closed | TRUE | ME2E |  | Technical Services | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/11/2019 | 9/10/2019 |  | 2326 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-11 08:17 | BILENSOY, NURI | 56-F-EU-V-190903-S6LO129 | Report | Yes | Yes |  |  | Retrofitted the Report as the Index BX Related Order in Pd812 was at 561 and in DV920 it was at 49. Hence retrofitted the object for Index change | KTTS5 |  |  | 56-F-EU-V-190903-S6LOV129A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56GB43500 | No | UBE | 1258312 |  | 6 |  |  | Baxter Purchase Order Print GB - BIPublisher output | L3 Pass |  |  | TRUE | LNE2E |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/11/2019 | 9/10/2019 |  | 2327 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-09 05:33 | Singh, Sunil Kumar | 56-F-EU-V-190829-S6LO027 | Printer | Yes | Yes |  |  |  | various |  |  | 56-F-EU-V-190829-S6LOV027A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56GRK02 | No | UBE | BXU546827, 1258235 | 25778 1258236 | 4 |  | CRP | Integrity- Conversion-Greek report | L3 Pass |  |  | TRUE | HNE2E |  | MDM | MDM | Carlos M. Barrera Pérez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/9/2019 | 8/7/2019 |  | 2328 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 06:53 | Joshi, Abhishek N | 56-F-EU-V-190731-S4FI076 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190731-S4FIV076A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56IB0014M | No | UBE |  |  | 2 | 2 |  | Pallet Labels - Zebra Printer Output - Iberia - Manual | L3 Pass |  |  | TRUE | HNE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 6/25/2019 | 6/24/2019 |  | 2329 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:09 | Chiau, Liesbet | 56-F-EU-V-240619-S2LO129 | Printer | Yes |  |  |  | Review E2E process exists | Various2 |  |  | 56-F-EU-V-240619-S2LOV129A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56IRP0Z | OBS | UBE |  |  | 999 |  |  | Upload IRP data from Z file | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2330 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:17 | Chiau, Liesbet |  | Upload | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56IRP1 | OBS | UBE |  |  | 999 |  |  | Build IRP Product Master Table | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2331 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:17 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56IRP2 | OBS | UBE |  |  | 999 |  |  | Build IRP Country Sold To Table | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2332 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:17 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56IRP3 | OBS | UBE |  |  | 999 |  |  | Extract IRP Price Data | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2333 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:17 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56IRP4 | OBS | UBE |  |  | 999 |  |  | Clear List Price for restricted Country / Item / Sales Chann | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2334 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:17 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56IRPP2 | OBS | UBE |  |  | 999 |  |  | Purge selected IRP List Price Records | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2335 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:17 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56MD118 | Yes | UBE | 1242047 18159 |  | 1 |  | CRP | Reproduce the GE Trigger in EMEA | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 5/21/2019 | 5/21/2019 |  | 2336 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-25 04:40 | Vishnubhatla, Mithra | 56-F-EU-V-190517-S1MD043 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190517-S1MDV43A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56ND535CF | No | UBE | 1241414 (17921) | 17921 | 5 |  |  | Nordics Customer Feedback Form | L3 Pass |  |  | TRUE | ME2E |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/27/2019 | 8/26/2019 |  | 2337 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-02 13:26 | Singh, Sunil Kumar | 56-F-EU-V-190819-S5LO069 |  | Yes | Y |  |  |  | KTT3 |  |  | 56-F-EU-V-190819-S5LOV069A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56O4211 | OBS | UBE |  |  | 999 |  |  | OUT-JDE Interface Service Orders Return Data | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2338 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:17 | Chiau, Liesbet |  | Interface | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56P4110A | Yes | UBE | BXU546384 16982 | 16982 BXU549475 | 5 |  | CRP | Inventory Trial Balance Reconciliation | L3 Pass | 318 |  | TRUE | HNE2E |  | Finance GL | Finance | Ravi Thapa | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | SaiTeja |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/28/2019 | 8/27/2019 |  | 2339 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-18 09:37 | Vishnubhatla, Mithra | 56-F-EU-V-190820-S5FI126 |  | Yes | Y | [6 empty] | 56-F-EU-V-190820-S5FIV126A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL0007 | No | UBE | BXU546597 |  | 5 |  |  | Receipt Document (PZ) | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/27/2019 | 8/26/2019 |  | 2340 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 04:29 | Joshi, Abhishek N | 56-F-EU-V-190821-S5LO076 |  | Yes | Yes |  |  |  | KTW5 |  |  | 56-F-EU-V-190821-S5LOV076A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL0027 | No | UBE |  |  | 5 |  |  | Home Delivery Protocol | L3 Pass | 272 |  | TRUE | HE2E |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/27/2019 | 8/27/2019 |  | 2341 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-28 08:29 | Destrebecq, Eric | 56-F-EU-V-190826-S5LO082 |  | Yes | Yes |  |  |  | FCA2 |  |  | 56-F-EU-V-190826-S5LOV082A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL0029 | Yes | UBE |  |  | 999 |  |  | Consumption Report | Obsolete |  |  |  | L |  | Order Management | OM | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2342 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:17 | Chiau, Liesbet |  | Report | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL003R | No | UBE | BXU545377, BXU545409 |  | 6 |  |  | Reprint multiple Invoices - Poland | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 09/09/2019 | 09/08/2019 |  | 2343 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 06:13 | Joshi, Abhishek N | 56-F-EU-V-190904-S6OM009 | Printer | Yes | Yes | [6 empty] | 56-F-EU-V-190904-S6OMV009A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL003S | No | UBE | BXU545409 | BXU547611 | 3 | 3 |  | Polish Invoice - Summarisation | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete | L3 - waiting for R42565 |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 07/16/2019 | 07/15/2019 |  | 2344 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 06:14 | Joshi, Abhishek N | 56-F-EU-V-190711-S3OM109 |  | Yes | [7 empty] | 56-F-EU-V-190711-S3OMV109A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL0047 | OBS | UBE |  |  | 999 |  |  | Backorders Report | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2345 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:17 | Chiau, Liesbet |  | Report | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL005 | No | UBE |  |  | 999 |  |  | Delivery Notes Print | Obsolete |  |  |  | NA |  | Transportation | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2346 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:17 | Chiau, Liesbet |  | Printer | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL0050 | No | UBE | BXU546831 |  | 5 |  | CRP | Integrity Report - GL with no Cardex Entries | L3 Pass | 283 | Closed | TRUE | LNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/28/2019 | 8/28/2019 |  | 2347 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 11:17 | Joshi, Abhishek N | 56-F-EU-V-190826-S5FI129 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190826-S5FIV129A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL0051 | No | UBE | BXU546586 |  | 5 |  | CRP | Integrity Report - Unposted Cardex Transactions | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | HNE2E | Nikit Sharma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/28/2019 | 8/27/2019 |  | 2348 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 02:57 | Joshi, Abhishek N | 56-F-EU-V-190819-S5FI119 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190819-S5FIV119A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL0052 | No | UBE | BXU546660 |  | 6 |  |  | Integrity Report - F4211/F4111 | PPD Passed |  |  | TRUE | L |  | Purge | ARO | Cosmin Mutiu | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/27/2019 | 8/26/2019 |  | 2349 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:10 | Joshi, Abhishek N | 56-F-EU-V-190814-S5LO048 | Report | Yes | Y |  |  | Yes, run on Scheduler 16/12/2019 | KTW5 |  |  | 56-F-EU-V-190814-S5LOV048A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL0053 | No | UBE |  |  | 6 |  |  | Integrity Report - F4111 with no F4211 | PPD Passed |  |  | TRUE | L |  | Purge | ARO | Cosmin Mutiu | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/27/2019 | 8/26/2019 |  | 2350 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-12-19 02:57 | Greenard, Terry | 56-F-EU-V-190819-S5LO064 | Report | Yes | Y |  |  | Yes, run on Scheduler 16/12/2019 | KTW5 |  |  | 56-F-EU-V-190819-S5LOV064A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL027 | No | UBE |  |  | 999 |  |  | Home Delivery Protocol | Obsolete |  |  | TRUE | HE2E |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | CIZMECI,TANKUT |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/28/2019 | 8/27/2019 |  | 2351 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-05-08 09:30 | Singh, Sunil Kumar | 56-F-EU-V-190813-S5LO035 |  | Yes | Y |  |  | obsolete | FCA2 |  |  | 56-F-EU-V-190813-S5LOV035A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL03R | No | UBE |  |  | 6 |  |  | Reprint multiple Invoices - Poland | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 09/10/2019 | 09/09/2019 |  | 2352 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-17 05:48 | Deveen, Genevive | 56-F-EU-V-190904-S6OM011 | Printer | Yes | Yes | [6 empty] | 56-F-EU-V-190904-S6OMV011A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PYRGL05 | No | UBE | BXU546942 |  | 1 |  | CRP | Arinso Payroll Text Conversion - UK Format | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Lokesh Reddy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 6/6/2019 | 6/6/2019 |  | 2353 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 03:15 | Joshi, Abhishek N | 56-F-EU-V-190521-S1FI039 | Text | Yes | Y | [6 empty] | 56-F-EU-V-190521-S1FIV039A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56R9011A | No | UBE | BXU545464 |  | 6 |  |  | Generate Russian Correspondence Detail Postings Table | L3 Not Required |  |  | TRUE | LNE2E |  | Localization | Finance | Keith Haxton | L2 Not required | No KT, test in E2E |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 09/18/2019 | 09/17/2019 |  | 2354 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 03:32 | Joshi, Abhishek N | 56-F-EU-V-190906-S6FI147 |  | Yes | Y |  |  |  | No KT |  |  | 56-F-EU-V-190906-S6FIV147A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56R9011C | No | UBE | BXU545463 |  | 4 |  |  | Extract Detail Correspondence to CSV | L3 Not Required |  |  | TRUE | LNE2E |  | Localization | Finance | Keith Haxton | L2 Not required | No KT, test in E2E |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/9/2019 | 8/8/2019 |  | 2355 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 03:33 | Joshi, Abhishek N | 56-F-EU-V-190807-S4FI102 |  | Yes | Y |  |  |  | No KT |  |  | 56-F-EU-V-190807-S4FIV102A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56SA42535 | No | UBE | 1242570 (17425) | 1242571 (17425) | 5 |  |  | Delivery Notes Print SAUDI | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/28/2019 | 8/21/2019 |  | 2356 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-07-27 02:53 | Singh, Sunil Kumar | 56-F-EU-V-190819-S5LO070 | Printer | Yes | Y |  |  |  | KTT3 |  |  | 56-F-EU-V-190819-S5LOV070A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56TC3012Z | Yes | UBE |  | 1248414 | 2 |  |  | Load F03012Z1 from csv | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 06/10/2019 | 06/11/2019 |  | 2357 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 04:31 | Joshi, Abhishek N | 56-F-EU-V-190610-S2MD001 |  | Yes | Y | [6 empty] | 56-F-EU-V-190610-S2MDV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56TCRECIC | No | UBE |  |  | 999 |  |  | RECIC100 File Table Converter | Obsolete | [5 empty] | Finance | Finance | Luigi Amorini |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2358 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:17 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56TN42565 | No | UBE |  | BXU547576 | 4 |  |  | Print Invoices Tunisia | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/9/19 | 8/8/19 |  | 2359 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-16 07:10 | Joshi, Abhishek N | 56-F-EU-V-190708-S4OM050 | Printer | Yes | Yes | [6 empty] | 56-F-EU-V-190708-S4OMV050A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56TRGII01 | No | UBE |  |  | 999 |  |  | Target Extracts - Vendor Master | Obsolete | [5 empty] | Finance AP | Finance | Luigi Amorini |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2360 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:17 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56X0001 | No | UBE |  |  | 2 |  | CRP | Bio: Supplier Remark Update for Transfer Orders | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 6/17/2019 | 6/11/2019 |  | 2361 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-17 05:45 | Touyaa, Manuel | 56-F-EU-V-190611-S2FI004 |  | Yes | Y | [6 empty] | 56-F-EU-V-190611-S2FIV004A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56X4202 | Yes | UBE | 1267340 (12614) | 12614 | 6 |  |  | Local Release Status Integrity Report | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Pawel Oskroba | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/12/2019 | 9/12/2019 |  | 2362 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-01 06:16 | Singh, Sunil Kumar | 56-F-EU-V-190904-S6LO038 | Report | Yes | Yes |  |  |  | KTQ3 |  |  | 56-F-EU-V-190904-S6LOV038A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5700092 | No | UBE | BXU546589 |  | 5 |  | CRP | List Leased Hardware Thresholds | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Joanne Byrne | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/28/2019 | 8/27/2019 |  | 2363 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 04:50 | Joshi, Abhishek N | 56-F-EU-V-190813-S5FI063 |  | Yes | Y | [6 empty] | 56-F-EU-V-190813-S5FIV063A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5703B575 | No | UBE | BXU546015 |  | 4 |  |  | Process Automatic Debits - EMEA SEPA | L3 Pass | 177 | Open | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete | L2 Tested after Rework |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 6/11/2019 | 6/11/2019 |  | 2364 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 05:06 | Joshi, Abhishek N | 56-F-EU-V-190610-S2FI013 |  | Yes | Y | [6 empty] | 56-F-EU-V-190610-S2FI013A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R57093S | No | UBE | BXU546695 |  | 5 |  | CRP | Registro Riepilogativo IVA | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Ravi Thapa | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 08/28/2019 | 08/27/2019 |  | 2365 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 03:35 | Joshi, Abhishek N | 56-F-EU-V-190628-S3FI048 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190628-S3FIV048A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R57R0111 | Yes | UBE | BXU546558 (12961) | BXU548866 (12961) | 6 |  |  | Excessive F41021 Records | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/12/2019 | 9/12/2019 |  | 2366 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 08:05 | ANAND, S | 56-F-EU-V-190910-S6LO046 |  | Yes | Yes |  |  |  | KTW5 |  |  | 56-F-EU-V-190910-S6LOV046A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R57RECICRP | No | UBE |  |  | 999 |  |  | RECIC100 UBE for Entity output CSV | Obsolete | [5 empty] | Finance | Finance | Luigi Amorini |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2367 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:17 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R57TCFIP | No | UBE | BXU546945 |  | 3 |  | CRP | TC for Entities from FIPARM | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 7/12/2019 | 7/11/2019 |  | 2368 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 03:39 | Joshi, Abhishek N | 56-F-EU-V-190710-S3FI159 |  | Yes | Y |  |  | Table conversion object unable to find the FIPARM table in DV920 and PD812. |  |  |  | 56-F-EU-V-190710-S3FIV159A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R57TCREC | No | UBE |  |  | 999 |  |  | TC for RECIC100 | Obsolete | [5 empty] | Finance | Finance | Luigi Amorini |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2369 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:17 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R580018CV | No | UBE | BXU546822 |  | 5 |  | CRP | Czech VAT Report @ CBR Rate - CSV | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Lokesh Reddy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  | 8/8/2019 | 8/9/2019 | 2370 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 03:41 | Joshi, Abhishek N | 56-F-EU-V-190807-S4FI103 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190807-S4FIV103A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5814109 | No | UBE | BXU545269, BXU545398 | BXU547484 | 5 |  |  | New Sales Report With Carrier Number | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/14/2019 | 8/13/2019 |  | 2371 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 05:08 | Joshi, Abhishek N | 56-F-EU-V-190813-S5OM008 | Report | Yes | Yes | [6 empty] | 56-F-EU-V-190813-S5OMV008A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5841112C | No | UBE | BXU549970 |  | 5 |  | CRP | LOCOM Report - CSV Extract | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/9/2019 | 8/8/2019 |  | 2372 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 03:54 | Joshi, Abhishek N | 56-F-EU-V-190801-S4FI005 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190801-S4FIV005A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5843501 | No | UBE |  |  | 999 |  |  | Purchase Order Print Output - Russia | Obsolete |  |  |  | OBS |  | Procurement | Logistics | [5 empty] | Terry Greenard / Vikas Verma | Obsolete |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2373 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:17 | Chiau, Liesbet |  | Printer | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5874R3033 | No | UBE | BXU550681 |  | 4 |  |  | Russian Delivery Note Summarisation | L3 Pass | 227 | Close | TRUE | HE2E |  | Transportation | Logistics | Puneet Sharma | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 7/23/2019 | 7/22/2019 |  | 2374 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-20 06:35 | Joshi, Abhishek N | 56-F-EU-V-190722-S4LO026 |  | Yes | Y |  |  |  | various2 |  |  | 56-F-EU-V-190722-S4LOV026A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5895004 | Yes | UBE | BXU546668 (12878) | BXU547462 (12878) | 6 |  |  | 21CFR Report - A4072 | PPD Passed |  |  | TRUE | L |  | Purge | ARO | Cosmin Mutiu / Terry Greenard | L2 Not required | No KT, as Tested by user only in ICT |  |  | Terry Greenard / Vikas Verma |  | Sreekanth, Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/16/2019 | 9/16/2019 |  | 2375 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-14 08:03 | ANAND, S | 56-F-EU-V-190906-S6AR004 | 21CFR / Report | Yes | Yes |  |  | Yes, run on Scheduler 02/12/2019 |  |  |  | 56-F-EU-V-190906-S6ARV004A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58AU005I | No | UBE | BXU550485 |  | 5 |  |  | Manual Price Override Audit Report | L3 Pass |  |  | TRUE | L |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 08/12/2019 | 08/09/2019 |  | 2376 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 03:19 | Joshi, Abhishek N | 56-F-EU-V-190812-S5OM002 | Audit / Report | Yes | Yes | [6 empty] | 56-F-EU-V-190812-S5OMV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58CDNPRG | No | UBE |  |  | 6 |  |  | Purge CDN Print information for Cancelled Orders | PPD Passed |  |  | TRUE | L |  | Purge | ARO | Cosmin Mutiu / Terry Greenard | L2 Not required | No KT, as Tested by user only in ICT |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/17/2019 | 9/16/2019 |  | 2377 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-12-23 03:49 | Greenard, Terry | 56-F-EU-V-190909-S6AR001 | Printer | Yes | Yes |  |  | Works in PPD, no records processed - Report Saved |  |  |  | 56-F-EU-V-190909-S6ARV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58CLR01 | No | UBE |  |  | 5 |  |  | Customer List Report | L3 Pass |  |  | TRUE | L |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma |  | CIZMECI,TANKUT |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/29/2019 | 8/28/2019 |  | 2378 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-04 08:08 | Barrera Perez, Carlos Manuel | 56-F-EU-V-190813-S5MD016 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190813-S5MDV016A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58CLR01C | No | UBE | BXU550992 |  | 5 |  |  | Customer List Report - CSV Format | L3 Pass |  |  | TRUE | L |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/29/2019 | 8/20/2019 |  | 2379 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-27 06:26 | Joshi, Abhishek N | 56-F-EU-V-190819-S5MD024 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190819-S5MDV024A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58CZ010S | No | UBE | BXU549676 |  | 4 |  |  | CZ: Invoice Baxter Czech Summarisation | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Devi Krishnan |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 07/24/2019 | 07/23/2019 |  | 2380 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 02:30 | Joshi, Abhishek N | 56-F-EU-V-190722-S4OM003 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190722-S4OMV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58FB0050 | No | UBE |  |  | 6 |  |  | Purchase Process tracing report by details of orders | L3 Pass |  |  | TRUE | L |  | Procurement | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/12/2019 | 9/12/2019 |  | 2381 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-12 03:06 | De Brouwer, Peter | 56-F-EU-V-190904-S6LO040 | Report | Yes | Yes |  |  |  | KTW5 |  |  | 56-F-EU-V-190904-S6LOV040A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58FB0060 | Yes | UBE | 1230246 (13692) | 13692 | 6 |  |  | QA Report | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Douglas Roussel | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 09/12/2019 | 09/11/2019 |  | 2382 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 11:31 | Singh, Sunil Kumar | 56-F-EU-V-190905-S6LO047 | Report | Yes | Yes |  |  |  | KTQ4 |  |  | 56-F-EU-V-190905-S6LOV0047A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58FBP060 | Yes | UBE | BXU547204 (13602) | 13602 | 6 |  |  | Item Branch Lot Status Code | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Douglas Roussel | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/12/2019 | 9/11/2019 |  | 2383 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-23 22:56 | Singh, Sunil Kumar | 56-F-EU-V-190903-S6LO130 |  | Yes | Yes |  |  |  | KTQ3 |  |  | 56-F-EU-V-190903-S6LOV130A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58FBP230 | No | UBE | BXU550720 |  | 6 |  |  | Open Purchase Order Report | L3 Pass |  |  | TRUE | L |  | Procurement | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/12/2019 | 9/11/2019 |  | 2384 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-20 06:34 | Joshi, Abhishek N | 56-F-EU-V-190829-S6LO028 | Report | Yes | Yes |  |  |  | KTW5 |  |  | 56-F-EU-V-190829-S6LOV028A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58IC300S | No | UBE | BXU545523 |  | 5 |  | CRP | PII report IC300 - Summary | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Libor Slaby | L2 Pass / Complete | As discussed in GL scrum call, changed Fiscal year to 2018 in processing option |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/28/19 | 8/27/19 |  | 2385 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 08:59 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI023 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190812-S5FIV023A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58PL001 | No | UBE |  |  | 999 |  |  | Plasma Update | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2386 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:17 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58PL010 | Yes | UBE |  |  | 999 |  |  | Out of Expiry Warning Report | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2387 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:17 | Chiau, Liesbet |  | Report | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58PL015 | No | UBE |  |  | 999 |  |  | Discount Report | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2388 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:17 | Chiau, Liesbet |  | Report | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58PL024 | No | UBE |  |  | 999 |  |  | Shipments Matching Invoices | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2389 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:17 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58R9801 | No | UBE | BXU545459 |  | 5 |  |  | New Correspondance UBE- RUS - 09 - 74R | L3 Not Required |  |  | TRUE | LNE2E |  | Localization | Finance | Keith Haxton | L2 Not required | No KT, test in E2E |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/29/2019 | 8/28/2019 |  | 2390 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 04:03 | Joshi, Abhishek N | 56-F-EU-V-190813-S5FI064 |  | Yes | Y |  |  |  | No KT |  |  | 56-F-EU-V-190813-S5FIV064A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58SCM001 | No | UBE |  |  | 2 |  |  | List of Material Class Discrepancies | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 6/12/2019 | 6/12/2019 |  | 2391 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 03:50 | Mohammed, Saleem | 56-F-EU-V-190610-S2MD006 |  | Yes | Y | [6 empty] | 56-F-EU-V-190610-S2MDV006A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58SCM008 | No, linked to RU (CR 12484) | UBE |  |  | 2 |  |  | Restamp Cat Code 28 with Country Code | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 06/10/2019 | 06/10/2019 |  | 2392 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-12-05 07:37 | Singh, Sunil Kumar | 56-F-EU-V-190610-S2MD002 |  | Yes | Y | [6 empty] | 56-F-EU-V-190610-S2MDV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59040 | No | UBE | BXU546671 |  | 3 | 3 |  | ECC: Download Cost Integrity Report errors to csv | L3 Pass |  |  | TRUE |  |  | ECC | ARO | Ravi / Cosmin | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 7/18/2019 | 7/18/2019 |  | 2393 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:19 | Joshi, Abhishek N | 56-F-EU-V-190611-S2AR003 | Error / Download / Report | Yes | Y | [6 empty] | 56-F-EU-V-190611-S2ARV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59041 | No | UBE | BXU546671 |  | 4 |  |  | ECC:Generate Missing Budget based on Toscanini sales | L3 Pass |  |  | TRUE |  |  | ECC | ARO | Ravi / Cosmin | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 7/24/2019 | 7/23/2019 |  | 2394 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:32 | Joshi, Abhishek N | 56-F-EU-V-190625-S2AR014 |  | Yes | [7 empty] | 56-F-EU-V-190625-S2ARV014A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59043 | No | UBE | BXU546671 |  | 4 |  |  | ECC: Download Budget Integrity Report errors to csv | L3 Pass |  |  | TRUE |  |  | ECC | ARO | Ravi / Cosmin | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 7/25/2019 | 7/24/2019 |  | 2395 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:29 | Joshi, Abhishek N | 56-F-EU-V-190620-S2AR006 | Error / Download / Report | Yes | [7 empty] | 56-F-EU-V-190620-S2ARV006A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59045 | No | UBE | BXU546671 |  | 3 |  |  | ECC:Generate Missing costs based Toscanini sales | L3 Pass |  |  | TRUE |  |  | ECC | ARO | Ravi / Cosmin | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 7/18/2019 | 7/17/2019 |  | 2396 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:19 | Joshi, Abhishek N | 56-F-EU-V-190628-S2AR001 |  | Yes | Y | [6 empty] | 56-F-EU-V-190628-S2ARV01A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59047 | No | UBE | BXU546671 |  | 3 |  |  | ECC XL file of Missing Costs / Budgets for Toscanini/EUROPOD | L3 Pass |  |  | TRUE |  |  | ECC | ARO | Ravi / Cosmin | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 6/27/2019 | 6/27/2019 |  | 2397 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:18 | Joshi, Abhishek N | 56- F-EU-V-190620-S2AR010 |  | Yes | Y | [6 empty] | 56- F-EU-V-190620-S2ARV010A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59050 | No | UBE | BXU546671 |  | 4 |  |  | Download Multiple Budget Costs into csv | L3 Pass |  |  | TRUE |  |  | ECC | ARO | Ravi / Cosmin | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 7/25/2019 | 7/24/2019 |  | 2398 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:25 | Joshi, Abhishek N | 56-F-EU-V-250619-S2AR013 | Download | Yes | Y |  |  | As discuss with Prashant (Functional) pass this object without data.Please find attached mail for more information.. |  |  |  | 56-F-EU-V-250619-S2ARV013A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59051 | No | UBE | BXU546671 |  | 3 |  |  | ECC extract Multiple MFG Costs to F55TC01 | L3 Pass |  |  | TRUE |  |  | ECC | ARO | Ravi / Cosmin | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saiteja |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 6/27/2019 | 6/25/2019 |  | 2399 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:17 | Joshi, Abhishek N | 56-F-EU-V-190619-S2AR005 |  | Yes | Y |  |  | Retrofit not required |  |  |  | 56-F-EU-V-190619-S2ARV005A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59052 | No | UBE | BXU546671 |  | 3 |  |  | Download Multiple Mfg Costs into csv | L3 Pass |  |  | TRUE |  |  | ECC | ARO | Ravi / Cosmin | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 07/18/2019 | 07/17/2019 |  | 2400 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:17 | Joshi, Abhishek N | 56-F-EU-V-190628-S3AR029 | Download | Yes | Y | [6 empty] | 56-F-EU-V-190628-S3ARV029A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59053 | No | UBE | BXU546671 |  | 4 |  |  | ECC:Generate Missing Budget based on Europot Inventory | L3 Pass |  |  | TRUE |  |  | ECC | ARO | Ravi / Cosmin | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 7/22/2019 | 7/21/2019 |  | 2401 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:24 | Joshi, Abhishek N | 56- F-EU-V-190620-S2AR009 |  | Yes | Y | [6 empty] | 56- F-EU-V-190620-S2ARV009A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59054 | No | UBE | BXU546671 |  | 3 |  |  | ECC:Generate Missing Costs based on Europot Inventory | L3 Pass |  |  | TRUE |  |  | ECC | ARO | Ravi / Cosmin | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 6/26/2019 | 6/25/2019 |  | 2402 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:16 | Joshi, Abhishek N | 56-F-EU-V-250619-S2AR012 |  | Yes | Y | [6 empty] | 56-F-EU-V-250619-S2ARV012A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59055 | No | UBE | BXU546671 |  | 4 |  |  | Extract Multiple Budgeted Costs | L3 Pass |  |  | TRUE |  |  | ECC | ARO | Ravi / Cosmin | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 6/26/2019 | 6/25/2019 |  | 2403 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:23 | Joshi, Abhishek N | 56-F-EU-V-190625-S2AR009 |  | Yes | [7 empty] | 56-F-EU-V-190625-S2ARV09A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59058 | No | UBE | BXU546671 |  | 4 |  |  | ECC: Download Cost/budget missing EIM parts to csv | L3 Pass |  |  | TRUE |  |  | ECC | ARO | Ravi / Cosmin | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 7/26/2019 | 7/25/2019 |  | 2404 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:22 | Joshi, Abhishek N | 56-F-EU-V-190723-S4AR008 | Download | Yes | Y | [6 empty] | 56-F-EU-V-190723-S4ARV008A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59063 | No | UBE | BXU546671 |  | 4 |  |  | ECC Download UOM changed / Mfg costs-Budget(.csv) | L3 Pass |  |  | TRUE |  |  | ECC | ARO | Ravi / Cosmin | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 7/26/2019 | 7/25/2019 |  | 2405 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:22 | Joshi, Abhishek N | 56-F-EU-V-190619-S2AR002 | Download | Yes | [7 empty] | 56-F-EU-V-190619-S2ARV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59064 | No | UBE | BXU546671 |  | 4 |  |  | ECC Download Mfg costs to be approved(.csv) | L3 Pass |  |  | TRUE |  |  | ECC | ARO | Ravi / Cosmin | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 06/25/2019 | 06/24/2019 |  | 2406 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:21 | Joshi, Abhishek N | 56-F-EU-V-190624-S2AR002 | Download | Yes | Y |  |  | Retrofitted under sprint2 |  |  |  | 56-F-EU-V-190624-S2ARV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59094 | Yes | UBE | BXU544636 | 22290, BXU545907 | 2 |  |  | EIM : Create GR : KG F41002 rows | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 6/12/2019 | 6/11/2019 |  | 2407 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 05:41 | Joshi, Abhishek N | 56-F-EU-V-190611-S2MD012 |  | Yes | Y | [6 empty] | 56-F-EU-V-190611-S2MDV012A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5947031 | No | UBE |  |  | 6 |  |  | Preprocessor of EDI Shipping Notice Edit/Create | L3 Pass |  |  | TRUE | HE2E |  | Procurement | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 09/12/2019 | 09/12/2019 |  | 2408 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-13 10:17 | Partanen, Aki | 56-F-EU-V-190906-S6LO048 |  | Yes | Yes |  |  |  | KTW3 |  |  | 56-F-EU-V-190906-S6LOV048A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59600 | No | UBE | 1258235 |  | 2 |  |  | Extract EIM Changes done on EBX products | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 6/12/2019 | 6/12/2019 |  | 2409 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-09 05:38 | Singh, Sunil Kumar | 56-F-EU-V-190612-S2MD001 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190612-S2MD001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59603P | Yes | UBE | 1272955 | 53579 | 3 |  |  | EBX : Print errors generated by R59603 | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | No KT needed. Global object not modified in EMEA |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 7/12/2019 | 7/12/2019 |  | 2410 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-27 09:15 | Vishnubhatla, Mithra | 56-F-EU-V-190710-S3MD039 | Error / Printer | Yes | Y | [6 empty] | 56-F-EU-V-190710-S3MDV039A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0016 | Yes | UBE | 1248867 (16629) | BXU548826 (590016) | 2 |  |  | QTS Z-File Processor | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Pawel Oskroba | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 19/06/21 | 19/06/20 |  | 2411 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 08:10 | ANAND, S | 56- F-EU-V-190620-S2LO121 |  | Yes |  |  |  |  | KTQ4 |  |  | 56- F-EU-V-190620-S2LOV121A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0017 | Yes | UBE | NA-FS-EU-R-21735 | 21735 BXU548639 | 2 |  |  | Item Restrictions Data Upload | L3 Pass |  |  | TRUE | H |  | Quality | Logistics | Pawel Oskroba | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 6/21/2019 | 6/11/2019 |  | 2412 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-31 06:55 | Vishnubhatla, Mithra | 56-F-EU-V-190611-S2MD015 | Upload | Yes | Y |  |  |  | KTQ4 |  |  | 56-F-EU-V-190611-S2MDV015A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0039 | No | UBE |  |  | 3 | 3 |  | Cross Reference Batch Update | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 7/16/2019 | 7/15/2019 |  | 2413 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-17 09:25 | BILENSOY, NURI | 56-F-EU-V-190715-S3LO098 | Cross Refer | Yes | Y |  |  |  | KTTS5 |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0068 | No | UBE |  |  | 2 | 3 |  | Customer List for FCA Report | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 6/18/2019 | 6/18/2019 |  | 2414 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 04:10 | Chiau, Liesbet | 56-F-EU-V-190618-S2LO099 | Report | Yes | Y |  |  |  | KTTS3 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0073 | Yes | UBE |  |  | 4 |  |  | Lot Master Creation for Inbound Transaction Set 856 | L3 Pass |  |  | TRUE | HE2E |  | Procurement | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/9/2019 | 8/8/2019 |  | 2415 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-14 05:29 | Mughal, Abdul | 56-F-EU-V-190801-S4LO103 | Inbound | Yes | Y |  |  |  | KTW5 |  |  | 56-F-EU-V-190801-S4LOV103A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0080 | No | UBE |  |  | 4 |  |  | Serial Number List for Specific Product Report | L3 Not Required |  |  | TRUE | L |  | Technical Services | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/9/2019 | 8/8/2019 |  | 2416 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-09 07:25 | Corbett, Mandy | 56-F-EU-V-190805-S4LO119 | Report | Yes | Y |  |  | On Hold N/A for EMEA |  |  |  | 56-F-EU-V-190805-S4LOV119A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0100 | No | UBE |  |  | 4 |  |  | HT Returned Device Report | L3 Not Required |  |  | TRUE |  |  | Technical Services | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/9/2019 | 8/8/2019 |  | 2417 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 08:39 | Javadi, Vinod | 56-F-EU-V-190808-S4LO123 | Report |  | Y |  |  | On Hold N/A for EMEA |  |  |  | 56-F-EU-V-190808-S4LOV123A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0112 | On Hold | UBE |  |  | 4 |  |  | Customer Owned and Leased Product List Specification | L3 Not Required |  |  | TRUE |  |  | Technical Services | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/09/2019 | 8/08/2019 |  | 2418 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-12 02:35 | Corbett, Mandy | 56-F-EU-V-190808-S4LO160 |  | Yes | Y |  |  | On Hold N/A for EMEA |  |  |  | 56-F-EU-V-190808-S4LOV160A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0177 | No | UBE |  |  | 4 |  |  | In-Transit System UBE Update of PO# on ASN | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 08/09/2019 | 08/08/2019 |  | 2419 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-16 16:27 | Mughal, Abdul | 56-F-EU-V-190808-S4LO001 |  | Yes |  |  |  | Review E2E process exists | KTW5 |  |  | 56-F-EU-V-190808-S4LOV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0178 | No | UBE |  |  | 4 |  |  | Update of Receipt status on EDI ASN -InTransit | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/9/2019 | 8/8/2019 |  | 2420 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-14 04:57 | Mughal, Abdul | 56-F-EU-V-190805-S4LO116 |  | Yes | Yes |  |  | Review E2E process exists | KTW5 |  |  | 56-F-EU-V-190805-S4LOV116A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0183 | Yes | UBE |  |  | 4 |  |  | In-Transit UBE for EDI and Z files | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/9/2019 | 8/8/2019 |  | 2421 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-22 05:19 | Mughal, Abdul | 56-F-EU-V-190805-S4LO120 |  | Yes | Y |  |  | Review E2E process exists | KTW5 |  |  | 56-F-EU-V-190805-S4LOV120A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0231 | No | UBE | BXU548337 |  | 3 |  | CRP | Cost Data - Change Flag Reset | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 7/12/2019 | 7/12/2019 |  | 2422 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 10:21 | Joshi, Abhishek N | 56-F-EU-V-190611-S2FI018 |  | Yes | Y |  |  | Object moved to Sprint 3. |  |  |  | 56-F-EU-V-190611-S2FIV018A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0312 | Yes | UBE |  |  | 999 |  |  | Print APRE Cache Message | Obsolete |  |  |  | H |  | MDM | MDM | Tom Hoste | (Blank) |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2423 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:17 | Chiau, Liesbet |  | Printer | [5 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59TC0300 | No | UBE | BXU546671 |  | 6 |  |  | Transfer ECC Actual Mfg Cost into CST010/B8 | L3 Not Required |  |  | TRUE |  | TRUE | ECC | ARO | Ravi / Cosmin | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 07/26/2019 | 07/25/2019 |  | 2424 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:40 | Joshi, Abhishek N | 56-F-EU-V-190624-S2AR006 |  | Yes | Y |  |  | To be tested in CRP |  |  |  | 56-F-EU-V-190624-S2ARV006A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59TC0309 | No | UBE | BXU546671 |  | 6 |  |  | Upload EUROPOT Inventory Current year Into ECC F59011 | L3 Not Required | 223 | Later Testing CRP. Defect closed | TRUE |  | TRUE | ECC | ARO | Ravi / Cosmin | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Nikit |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 7/16/2019 | 7/16/2019 |  | 2425 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 01:37 | Joshi, Abhishek N | 56-F-EU-V-190704-S3AR001 | Upload | Yes | Y |  |  | To be tested in CRP |  |  |  | 56-F-EU-V-190704-S3ARV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59TC0314 | No | UBE |  |  | 6 | 6 |  | ECC : upload XL of Mfg Costs into ECC | PPD Passed |  |  | TRUE | L | FALSE | ECC | ARO | Krista Vansever | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 24/06/2019 | 24/06/2019 |  | 2426 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-12-02 07:32 | Thapa, Ravi Pratap | 56-F-EU-V-190624-S2AR005 | Upload | Yes | Y |  |  | To be tested in CRP |  |  |  | 56-F-EU-V-190624-S2ARV005A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59TC0315 | No | UBE |  |  | 6 | 6 |  | ECC Upload XL file of Budget Costs for 3rd Party | PPD Passed |  |  | TRUE | L | FALSE | ECC | ARO | Krista Vansever | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 6/24/2019 | 6/21/2019 |  | 2427 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-12-02 07:32 | Thapa, Ravi Pratap | 56-F-EU-V-190624-S2AR007 | Upload | Yes | Y |  |  | To be tested in CRP |  |  |  | 56-F-EU-V-190624-S2ARV07A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59TC0416 | No | UBE |  | 1230568 | 999 |  |  | Generate WISE Missing parts from PRTEUR in F594116 | Obsolete |  |  | TRUE | LNE2E |  | MDM | MDM | Joanne Byrne |  |  |  |  | Terry Greenard / Vikas Verma | VV-13/09 -Obsoleted as per advise from Carlos | Nikit Sharma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 8/28/2019 | 8/27/2019 |  | 2428 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 09:59 | Joshi, Abhishek N | 56-F-EU-V-190814-S5FI089 |  | Yes | Y |  |  | L1 testing not done as its TC object and foreign tables are not present in DV920 .Hence checkedout/checkedin the report |  |  |  | 56-F-EU-V-190814-S5FIV089A |  |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R60A4006 | No | UBE |  |  | 3 |  | CRP | Sales Commission To Pay By Company | L3 Not Required |  |  | TRUE | HNE2E |  | Finance External | Finance | Izaskun Ajuria | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 7/17/2019 | 7/16/2019 |  | 2429 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-06 09:06 | Ajuria, Izaskun | 56-F-EU-V-190716-S3FI164 |  | Yes | Y |  |  |  | NoKT |  |  | 56-F-EU-V-190716-S3FIV164A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R60A4007 | No | UBE |  |  | 3 |  | CRP | Open Commissions (CSV) | L3 Not Required |  |  | TRUE | HNE2E |  | Finance External | Finance | Izaskun Ajuria | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 7/18/2019 | 7/18/2019 |  | 2430 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-06 09:07 | Ajuria, Izaskun | 56-F-EU-V-190715-S3FI162 |  | Yes | Y |  |  |  | NoKT |  |  | 56-F-EU-V-190715-S3FIV162A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R60A4BX001 | No | UBE |  |  | 3 |  |  | Assign Commissions to SO - Baxter Italy | L3 Not Required |  |  | TRUE | HNE2E |  | Finance External | Finance | Luigi Amorini | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 7/18/2019 | 7/16/2019 |  | 2431 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-30 03:30 | Amorini, Luigi | 56-F-EU-V-190716-S3FI163 |  | Yes | Y |  |  | Retrofit not required | NoKT |  |  | 56-F-EU-V-190716-S3FIV163A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600061 | No | UBE | BXU547571 |  | R1 |  | CRP | Clear RCND on F0911 | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/26/2019 | 9/25/2019 |  | 2432 | Custom | 0 |  |  |  | 2020-03-10 04:09 | Joshi, Abhishek N | 56-F-EU-V-190923-R1FI006 |  | Yes | Y | [6 empty] | 56-F-EU-V-190923-R1FIV006A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5639120 | No | UBE | BXU546031 |  | R1 |  | CRP | Weighted Average Simulation | L3 Pass |  |  | TRUE | LNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/26/2019 | 9/25/2019 |  | 2433 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 03:30 | Joshi, Abhishek N | 56-F-EU-V-190925-R1FI011 |  | Yes | Y | [6 empty] | 56-F-EU-V-190925-R1FIV011A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59074 | No | UBE | BXU550551 |  | R1 |  |  | ECC:Budget Rollover#3:Archive-Remove Budget,clear draft budg | PPD Passed |  |  | TRUE |  |  | ECC | ARO | Ravi / Cosmin | L2 Not required | Object not working in 8.12, Confirmed by Terry, L2 not required |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/26/2019 | 9/25/2019 |  | 2434 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 02:36 | Joshi, Abhishek N | 56-F-EU-V-190920-R1EC001 |  | Yes | Y | [6 empty] | 56-F-EU-V-190920-R1ECV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5601MX1 | OBS | UBE |  |  | 999 |  |  | MX1- Report | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2435 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:17 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5601MX3 | OBS | UBE |  |  | 999 |  |  | MX3- Report | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2436 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:17 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5617610 | OBS | UBE |  |  | 999 |  |  | Printing of stock count | Obsolete |  |  |  | OBS |  | Warehouse | Logistics | [5 empty] | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2437 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:17 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600192 | Yes | UBE | 1260749 (6343) | 6343, 1260786 | R1 |  |  | Mass Generic Update Supplemental Data table | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 09/24/2019 | 09/24/2019 |  | 2438 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-20 06:10 | ANAND, S | 56-F-EU-V-190923-R1MD005 |  | Yes | Y |  |  |  | R1 Script created |  |  | 56-F-EU-V-190923-R1MDV005A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600193 | No | UBE | 1263246 | 1263247 | R1 |  |  | Refresh F4101H X-Level From GE F59XLVLS | L3 Pass | 365 | Closed | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 09/26/2019 | 09/26/2019 |  | 2439 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 09:03 | Vishnubhatla, Mithra | 56-F-EU-V-190925-R1MD011 |  | Yes | Y |  |  |  | DEFECT ID: 365 |  |  | 56-F-EU-V-190925-R1MDV011A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641005 | Yes | UBE |  |  | 999 |  |  | Copy Item UOM F41002 between branch plants | Obsolete |  |  |  | H |  | MDM | MDM | Tom Hoste | (Blank) |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2440 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 03:06 | Greenard, Terry | [6 empty] | Carlos, Objects to Obsolete | KT unplanned | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641006 | No | UBE |  |  | 999 |  |  | Copy UOM Defn F46011 from one BP to another | Obsolete |  |  |  | H |  | MDM | MDM | Tom Hoste | (Blank) |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2441 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 03:06 | Greenard, Terry | [6 empty] | Carlos, Objects to Obsolete | KT unplanned | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56EQL01 | Yes | UBE | BXU531848 | 148540 BXU532520 | 6 |  |  | Expired Quantity List | L3 Pass | 323 | Closed | TRUE | L |  | Quality | Logistics | Miruna Danes | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth, Thippulla |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/9/2019 | 9/9/2019 |  | 2442 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-31 08:42 | Vishnubhatla, Mithra | 56-F-EU-V-190903-S6LO133 |  | Yes | Yes |  |  |  | KTQ3 |  |  | 56-F-EU-V-190903-S6LOV133A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5895001 | No | UBE | BXU544636 12878 |  | R1 |  |  | 21CFR Report AB set | PPD Passed |  |  | TRUE | L |  | 21CFR | ARO | Cosmin Mutiu / Terry Greenard | L2 Not required | No KT, as Tested by user only in ICT |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/24/2019 | 9/24/2019 |  | 2443 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-20 02:59 | Vishnubhatla, Mithra | 56-F-EU-V-190924-R1AR006 |  | Yes | Y |  |  | Yes, run on Scheduler 02/12/2019 |  |  |  | 56-F-EU-V-190924-R1ARV06A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5895002 | No | UBE |  |  | R1 |  |  | CFR21 Bank Reporting - ESSC - Vendors | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/26/2019 | 9/25/2019 |  | 2444 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-07 05:13 | Barrera Perez, Carlos Manuel | 56-F-EU-V-190923-R1MD006 |  | Yes | Y |  |  |  | R1 Script created |  |  | 56-F-EU-V-190923-R1MDV006A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5895003 | No | UBE |  |  | R1 |  |  | 21CFR Report Lots for | PPD Passed |  |  | TRUE | L |  | 21CFR | ARO | Terry Greenard | L2 Not required | No KT, as Tested by user only in ICT |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/26/2019 | 9/26/2019 |  | 2445 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-12-19 02:59 | Greenard, Terry | 56-F-EU-V-190924-R1ARO001 |  | Yes | Y |  |  | Yes, run on Scheduler 04/12/2019 |  |  |  | 56-F-EU-V-190924-R1AROV001A, 56-F-EU-V-190924-R1AROV001B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59TC0044 | Yes | UBE |  |  | R1 |  |  | Check F4101 with X2 level code existing in UDC 41/6 | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/26/2019 | 9/26/2019 |  | 2446 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:32 | Mohammed, Saleem | 56-F-EU-V-190923-R1MD004 |  | Yes | Y |  |  |  | R1 Script Created |  |  | 56-F-EU-V-190923-R1MDV004A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59TC0314A | No | UBE |  |  | R1 |  |  | ECC : Input fromCosts XLS File front-end | PPD Passed |  |  | TRUE |  |  | ECC | ARO | Ravi / Cosmin | L2 Not required | Object not working in 8.12, Confirmed by Terry, L2 not required |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/26/2019 | 9/25/2019 |  | 2447 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-31 03:18 | Thapa, Ravi Pratap | 56-F-EU-V-190923-R1AR001 |  | Yes | Y | [6 empty] | 56-F-EU-V-190923-R1ARV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59TC0315A | No | UBE |  |  | R1 |  |  | ECC : Input from Budget XLS File front-end | PPD Passed |  |  | TRUE |  |  | ECC | ARO | Ravi / Cosmin | L2 Not required | Object not working in 8.12, Confirmed by Terry, L2 not required |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/26/2019 | 9/25/2019 |  | 2448 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-31 03:19 | Thapa, Ravi Pratap | 56-F-EU-V-190923-R1AR003 |  | Yes | Y |  |  | No Retrofit required but the object and versions were present in DV92064 OL |  |  |  | 56-F-EU-V-190923-R1ARV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59TC0316 | No | UBE |  |  | R1 |  |  | ECC:Upload WISECOST/B2 into actual MFg Cost | PPD Passed |  |  | TRUE |  |  | ECC | ARO | Ravi / Cosmin | L2 Not required | Object not working in 8.12, Confirmed by Terry, L2 not required |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/26/2019 | 9/25/2019 |  | 2449 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-07 04:51 | Thapa, Ravi Pratap | 56-F-EU-V-190919-R1AR001 |  | Yes | Y |  |  | No L2 & L2 testing will be required for this object. |  |  |  | 56-F-EU-V-190926-R1ARV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59TC0324 | No | UBE |  |  | R1 |  |  | ECC : Write to Budget Table from WISECOST | PPD Passed |  |  | TRUE |  |  | ECC | ARO | Ravi / Cosmin | L2 Not required | Object not working in 8.12, Confirmed by Terry, L2 not required |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/25/2019 | 9/24/2019 |  | 2450 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-07 04:34 | Thapa, Ravi Pratap | 56-F-EU-V-190924-R1EC004 |  | Yes | Y |  |  | L2 not required as per attached vikas mail. error while open design this TC object. |  |  |  | 56-F-EU-V-190924-R1ECV004A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R555120 | No | UBE | BXU550471 |  | R1 |  | CRP | Fixed Assets Act of Disposal - OC-4 | L3 Pass | 408 | Closed | TRUE | HNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/26/2019 | 9/26/2019 |  | 2451 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 09:13 | Joshi, Abhishek N | 56-F-EU-V-190925-R1FI006 |  | Yes | Y | [6 empty] | 56-F-EU-V-190925-R1FIV006A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FREX16B | No | UBE | BXU547571 |  | R1 |  | CRP | Inactive BUs used by Variable Allocations | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 09/26/2019 | 09/25/2019 |  | 2452 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 07:20 | Joshi, Abhishek N | 56-F-EU-V-190925-R1FI001 |  | Yes | Y | [6 empty] | 56-F-EU-V-190925-R1FIV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55GL001 | No | UBE | BXU547597 |  | R1 |  | CRP | Grant Header Report-F55GL001 | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Robbin/Florencia | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/26/2019 | 9/26/2019 |  | 2453 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 02:59 | Joshi, Abhishek N | 56-F-EU-V-190925-R1FI010 |  | Yes | Y | [6 empty] | 56-F-EU-V-190925-R1FIV010A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600021 | No | UBE | BXU545613 |  | R1 |  | CRP | Integrity Report - Cardex/GL | L3 Pass | 374 |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/26/2019 | 9/25/2019 |  | 2454 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 03:48 | Joshi, Abhishek N | 56-F-EU-V-190924-R1FI011 |  | Yes | Y | [6 empty] | 56-F-EU-V-190924-R1FIV011A , 56-F-EU-V-190924-R1FIV011B ,56-F-EU-V-190924-R1FIV011C | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560901 | No | UBE | BXU544659 |  | R1 |  | CRP | NOMAP Accrual - CSV | L3 Pass |  |  | TRUE | LNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/26/2019 | 9/25/2019 |  | 2455 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 03:10 | Joshi, Abhishek N | 56-F-EU-V-190920-R1FI003 |  | Yes | Y | [6 empty] | 56-F-EU-V-190920-R1FIV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564572NCI | No | UBE |  |  | R1 |  | CRP | Deutsche Bank - Nordic Print Pgm (Charges) +IBAN | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/26/2019 | 9/25/2019 |  | 2456 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-07 12:11 | Gilthorpe, Peter | 56-F-EU-V-190924-R1FI008 |  | Yes | Y | [6 empty] | 56-F-EU-V-190924-R1FIV008A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647071P | No | UBE |  |  | 999 |  |  | Ariba Receipts - Poland -Final | Obsolete | [5 empty] | Finance AP | Finance | Peter Gilthorpe |  |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2457 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:17 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560041 | OBS | UBE |  |  | 999 |  |  | Deliveries by Customer / Item (Vaccinet Report) | Obsolete |  |  |  | OBS |  | Order Management | Order Management | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2458 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-05-13 09:02 | Verma, Vikas | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58E4211 | OBS | UBE |  |  | 999 |  |  | CZ csv extract F4211 | Obsolete |  |  |  | OBS |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte |  |  |  |  | Terry Greenard / Vikas Verma |  | Obsolete |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri |  |  |  | 2459 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-08 02:17 | Chiau, Liesbet | [7 empty] | Obsolete | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58FB0040 | No | UBE | BXU545815 |  | 6 |  | CRP | Sales Process Tracing by Customer | L3 Pass |  |  | TRUE | LNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/18/2019 | 9/17/2019 |  | 2460 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 08:55 | Joshi, Abhishek N | 56-F-EU-V-190903-S6FI042 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190903-S6FIV042A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58FBP270 | No | UBE | BXU546590 |  | R1 |  | CRP | Inventory Transaction History Logistic Report | L3 Pass | 375 |  | TRUE | HNE2E |  | Finance GL | Finance | Cedric Rasselet | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/26/2019 | 9/25/2019 |  | 2461 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 08:57 | Joshi, Abhishek N | 56-F-EU-V-190923-R1FI007 |  | Yes | Y | [6 empty] | 56-F-EU-V-190923-R1FIV007A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58IN010G | No | UBE |  |  | R1 |  |  | Edelivery - Universal | L3 Pass | 386 | Closed | TRUE | HE2E |  | transportation | logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/26/2019 | 9/24/2019 |  | 2462 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-31 04:50 | Destrebecq, Eric | 56-F-EU-V-190925-R1LO015 |  | Yes | Y |  |  |  | various2 |  |  | 56-F-EU-V-190925-R1LOV015A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R04110ZA | No | UBE | BXU548622 |  | 6 |  | CRP | Batch Voucher Processor Report | L3 Pass |  |  | TRUE | HE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete | Defect 362 |  |  | Terry Greenard/Vikas Verma |  | CIZMECI,TANKUT |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 7/29/2019 | 7/26/2019 |  | 2463 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 05:36 | Joshi, Abhishek N | 56-F-EU-V-190729-S4FI057 |  | Yes | Y |  |  | VV-25/07 - Moved from Sprint R1 to 4 as per agreement with Baxter and BSL |  |  |  | 56-F-EU-V-190729-S4FIV057A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R7430030 | No | UBE | BXU548340 |  | R3 |  | CRP | Legal Document Print Process | L3 Pass |  |  | TRUE | HNE2E | TRUE | Localization | Finance | Keith Haxton | L2 Pass / Complete | Issue has been fixed in 8.12 as well as in 9.2 DV |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 9/26/2019 | 9/25/2019 |  | 2464 | Custom | 0 | Sandhya / Sameer |  |  | 2020-03-12 07:50 | Joshi, Abhishek N | 56-F-EU-V-190923-R1FI005 |  | Yes | Y | [6 empty] | 56-F-EU-V-190923-R1FIV005A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56474Z4 | No | UBE | BXU545441 |  | R1 |  |  | Process EUDC Mass Upload Batch | L3 Not Required |  |  | TRUE | HNE2E |  | Order Management | OM | Piet Van Gijseghem / Lina Seputyte | L2 Not required |  |  |  | Terry Greenard/Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 09/26/2019 | 09/23/2019 |  | 2465 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 08:53 | Joshi, Abhishek N | 56-F-EU-V-190923-R1OM006 |  | Yes | Y | [6 empty] | 56-F-EU-V-190923-R1OMV006A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56474Z6 | No | UBE | BXU545441 |  | R1 |  |  | Process EUDC Mass Upload Batch | L3 Not Required |  |  | TRUE | HNE2E |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-02 12:56 | Kishi, Sayuri | 09/26/2019 | 09/26/2019 |  | 2466 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 08:53 | Joshi, Abhishek N | 56-F-EU-V-190925-R1OM014 |  | Yes | Y | [6 empty] | 56-F-EU-V-190925-R1OMV014A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P560018P | No | APPL |  | BXU544916 | R1 |  |  | Maintain Port Types | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-03 06:39 | Greenard, Terry | 9/23/2019 | 9/23/2019 |  | 2467 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-21 08:16 | Joshi, Abhishek N | 56-F-EU-V-190923-R1LO011 |  | Yes | Y |  |  | PAR file restored. | various2 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5643005 | Yes | APPL |  | 1242775 (15521) | R1 |  |  | Logistics Warehouse Integration Receipt Forms | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Leonard Dartois | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-08 08:49 | Greenard, Terry | 9/23/2019 | 9/22/2019 |  | 2468 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 07:56 | ANAND, S | 56-F-EU-V-230905-R1LO001 |  | Yes |  |  |  | Review E2E process exists | KTW3 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56BIP01 | No | APPL |  | BXU546795 | R1 |  |  | BI Publisher Output distribution - UBE/versions to archive | L3 Pass |  |  | TRUE | HNE2E |  | IXOS Archive | eCommerce | Linda Kenny | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard/Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-08 08:51 | Greenard, Terry | 9/23/2019 | 9/23/2019 |  | 2469 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-21 05:55 | Joshi, Abhishek N | 56-F-EU-V-190920-R1EC002 |  | Yes | Y |  |  |  | NoKT |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56HWT00 | No | UBE | 1278647 (82802) | 82802 | 4 | 4 |  | HWT Clean Up - Driver for SQL Updates | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Rishikesh |  | Item |  | 2019-05-10 01:54 | BILENSOY, NURI | 8/9/2019 | 8/8/2019 |  | 2470 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 03:14 | Singh, Sunil Kumar | 56-F-EU-V-190802-S4LO152 |  | Yes |  |  |  |  | KTTS4 |  |  | 56-F-EU-V-190802-S4LOV152A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56121IRVC | No | UBE | BXU550357 |  | R1 |  | CRP | AP Vchr Match - IRV Calculation Russia – CSV | L3 Pass |  |  | TRUE | HNE2E | FALSE | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-10 08:01 | GOLGE, SERAY | 9/24/2019 | 9/24/2019 |  | 2471 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 06:02 | Joshi, Abhishek N | 56-F-EU-V-190924-R1FN007 |  | Yes | Y | [6 empty] | 56-F-EU-V-190924-R1FNV07A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0340 | No | UBE |  |  | R1 |  |  | UBE PeopleSoft Interface to JDE Security User File | PPD Passed |  |  | TRUE | L |  | Security | Security | Karol | L2 Not required | No KT, testing to be done in UAT |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-15 07:08 | Greenard, Terry | 09/25/2019 | 09/25/2019 |  | 2472 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-31 11:24 | Bodin, Fatiha | 56-F-EU-V-190923-R1OM007 | Security | Yes | Y |  |  |  | NoKT |  |  | 56-F-EU-V-190923-R1OMV007A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FRTNT | No | UBE | 1252013 (21980) |  | R1 |  |  | Freight Routing Flat File Import UBE - TNT | L3 Pass |  |  | TRUE | L |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-16 03:01 | BILENSOY, NURI | 9/26/2019 | 9/25/2019 |  | 2478 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:24 | Singh, Sunil Kumar | 56-F-EU-V-190923-R1LO013 | Upload | Yes | Y |  |  |  | FCAOUT |  |  | 56-F-EU-V-190923-R1LOV013A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59TC0313 | No | UBE |  |  | 999 |  |  | Write F59013 with Counter of CST010 records created | Obsolete |  |  | TRUE | L |  | ECC | ARO | Krista Vansever/Claire Mitchell | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard/Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-17 01:30 | Greenard, Terry | 9/26/2019 | 9/26/2019 |  | 2479 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-08 07:48 | Greenard, Terry | 56-F-EU-V-190924-R1ARO002 | ECC | Yes | Y |  |  | Retrofitted. As per Vikas's mail mark L2 not required, it should be tested in L3. | NoKT |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74LI5IMP | No | UBE | 1266483 |  | 6 | 6 |  | Import SAFT Transport Documents | L3 Not Required |  |  | TRUE | HE2E |  | Transportation | Logistics |  | L2 Not required | 07/05 RK: As per Eric mail, marked L2 Not required: As Scott advised during the KT session, there is no integration with Portuguese authorities web portal in DV or UT. Step 14 & 15 cannot be tested.objects related to saft except R74LI5IMP: L2 not requir |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-05-22 05:28 | Greenard, Terry | 6/26/2019 | 6/26/2019 |  | 2487 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-20 05:12 | Singh, Sunil Kumar | 56-F-EU-V-190626-S2LO001 | [5 empty] | requiring integration. will be tested in PPD CRP | various |  |  | 56-F-EU-V-190626-S2LOV01A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
T5947021 | No | DSTR |  |  | 1 |  |  | EDI 855/860 Custom Inbound Processor PO | Baxter Code Review Complete |  |  | TRUE | HE2E |  | Warehouse | Logistics | Piet Van Gijseghem, Lina Seputyte | (Blank) |  |  |  | Terry Greenard / Vikas Verma |  | Vikas |  | Item |  | 2019-05-23 08:35 | Prasad, Sindhu | 5/31/2019 | 5/30/2019 |  | 2490 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:56 | Chiau, Liesbet | 56-F-EU-V-190515-S1OM024 |  | Yes | Yes |  |  |  | NA | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
T56PL0005 | No | DSTR |  |  | 1 |  |  | Delivery Notes Print | Baxter Code Review Complete |  |  | TRUE | HE2E |  | Transportation | Logistics |  | (Blank) |  |  |  | Terry Greenard / Vikas Verma |  | Vikas |  | Item |  | 2019-05-23 08:50 | Bastawade, Sushant | 5/24/2019 | 5/24/2019 |  | 2491 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:56 | Chiau, Liesbet | 56-F-EU-V-190514-S1LO021 | Printer | Yes | Yes |  |  | done | KTT3 | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
T5642024 | No | DSTR |  |  | 1 |  |  | Reset Rebate Summary by MSD | Baxter Code Review Complete |  |  | TRUE | L |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte | (Blank) |  |  |  | Terry Greenard / Vikas Verma |  | Vikas |  | Item |  | 2019-05-23 08:56 | Bastawade, Sushant | 5/23/2019 | 5/23/2019 |  | 2492 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:56 | Chiau, Liesbet | 56-F-EU-V-190514-S1OM023 |  | Yes | Yes |  |  | done | [7 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
T56PL011 |  | DSTR |  |  | 1 |  |  |  | Baxter Code Review Complete |  |  | TRUE | L |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte | (Blank) |  |  |  | Terry Greenard / Vikas Verma |  | Vikas |  | Item |  | 2019-05-23 23:18 | Pandya, Krupa | 5/23/2019 | 5/23/2019 |  | 2493 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:56 | Chiau, Liesbet | 56-F-EU-V-190517-S1OM030 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190517-S1OMV030A |  |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
T564184 |  | DSTR |  |  | 1 |  |  |  | Baxter Code Review Complete |  |  | TRUE |  |  | MDM | MDM | Tom Hoste | (Blank) |  |  |  | Terry Greenard / Vikas Verma |  | Vikas |  | Item |  | 2019-05-23 23:20 | Pandya, Krupa | 5/21/2019 | 5/21/2019 |  | 2494 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:56 | Chiau, Liesbet | 56-F-EU-V-190517-S1MD038 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190517-S1MDV038A |  |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
T5641003 | Yes | DSTR |  |  | 1 |  |  |  | Baxter Code Review Complete |  |  | TRUE |  |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler | (Blank) |  |  |  | Terry Greenard / Vikas Verma |  | Vikas |  | Item |  | 2019-05-24 04:08 | Pandya, Krupa | 5/24/2019 | 5/24/2019 |  | 2495 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:56 | Chiau, Liesbet | 56-F-EU-V-190517-S1LO050 |  | Yes | Yes |  |  |  | NA |  |  | 56-F-EU-V-190517-S1LOV050A |  |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
T56MD118 |  | DSTR |  |  | 1 |  |  | Reproduce the GE Trigger in EMEA | Baxter Code Review Complete |  |  | TRUE |  |  | MDM | MDM |  | (Blank) | [5 empty] | Vikas |  | Item |  | 2019-05-24 05:39 | Chalawadi, Geeta | 5/21/2019 | 5/21/2019 |  | 2496 | Custom | 0 |  |  |  | 2019-07-05 03:56 | Chiau, Liesbet | 56-F-EU-V-190517-S1MD043 |  | Yes | Yes | [10 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
T4116 |  | DSTR |  |  | 1 |  |  | Item Reclassifications | Baxter Code Review Complete |  |  | TRUE |  |  | Warehouse | Logistics |  | (Blank) | [5 empty] | Vikas |  | Item |  | 2019-05-24 05:52 | Chalawadi, Geeta | 5/22/2019 | 5/23/2019 |  | 2498 | Standard | 0 |  |  |  | 2019-07-05 03:56 | Chiau, Liesbet | 56-F-EU-V-190517-S1MD043 |  | Yes | Yes |  |  |  | NA | [6 empty] | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
T56GB42535 |  | DSTR |  |  | 1 |  |  | Delivery Note - UK and Belfast | Baxter Code Review Complete |  |  | TRUE |  |  | Transportation | Logistics |  | L2 In progress | [5 empty] | Vikas |  | Item |  | 2019-05-27 03:22 | Chalawadi, Geeta | 5/24/2019 | 5/24/2019 |  | 2499 | Custom | 0 |  |  |  | 2019-07-05 03:56 | Chiau, Liesbet | 56-F-EU-V-190521-S1LO074 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190521-S1LOV74A |  |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
T594108A | Yes | DSTR |  |  | 1 |  |  |  | Baxter Code Review Complete |  |  | TRUE |  |  | Quality | Logistics |  | (Blank) |  |  |  | Terry Greenard / Vikas Verma |  | Vikas |  | Item |  | 2019-05-27 06:06 | Pandya, Krupa | 5/27/2019 | 5/27/2019 |  | 2500 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:56 | Chiau, Liesbet | 56-F-EU-V-190521-S1LO086 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190521-S1LOV086A |  |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
T5643214 |  | DSTR |  |  | 1 |  |  |  | Baxter Code Review Complete |  |  | TRUE |  |  | Warehouse | Logistics | Léonard Dartois, Peter De Brouwer, Rajesh TK, Abdul Mughal, Grant Butler | (Blank) |  |  |  | Terry Greenard / Vikas Verma |  | Vikas |  | Item |  | 2019-05-27 06:10 | Pandya, Krupa | 5/27/2019 | 5/27/2019 |  | 2501 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:56 | Chiau, Liesbet | 56-F-EU-V-190521-S1LO087 |  | Yes | Yes |  |  |  | NA |  |  | 56-F-EU-V-190521-S1LOV087A |  |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
T59R41083 |  | DSTR |  |  | 1 |  |  | Update Effective Lots - Lot Status Synchronization | Baxter Code Review Complete |  |  | TRUE |  |  | Quality | Logistics |  | L2 In progress | [5 empty] | Vikas |  | Item |  | 2019-05-27 06:57 | Chalawadi, Geeta | 5/27/2019 | 5/27/2019 |  | 2502 | Custom | 0 |  |  |  | 2019-07-05 03:56 | Chiau, Liesbet | 56-F-EU-V-190521-S1LO081 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190521-S1LOV81A |  |  |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59034 | No | UBE |  |  | R1 |  |  | ECC integrate F59012 into Srce Plant item F40306 | PPD Passed |  |  | TRUE | L |  | ECC | ARO | Ravi / Cosmin | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-29 02:38 | Greenard, Terry | 9/27/2019 | 9/27/2019 |  | 2503 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-28 10:18 | Thapa, Ravi Pratap | 56-F-EU-V-190923-R1EC003 | ECC | Yes | Y | [6 empty] | 56-F-EU-V-190923-R1ECV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R57002C | No | UBE | BXU550543 |  | 999 |  |  | Inbound Flat File Conversion | Obsolete |  |  | TRUE | HNE2E |  | ECC | ARO | Krista Vansever/Claire Mitchell | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-05-29 02:39 | Greenard, Terry | 9/27/2019 | 9/26/2019 |  | 2504 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 01:09 | Joshi, Abhishek N | 56-F-EU-V-190923-R1AR002 | ECC |  | Y |  |  | VV:11/12 this was obsoleted by mistake in tracker. PG: Note this UBE is also used by the ICO Team SSC for processing payments for Intercompany Netting. Testing should include the ICO team when ready |  |  |  | 56-F-EU-V-190923-R1ARV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59048 | No | UBE | BXU550551 |  | R1 |  |  | ECC Purge of Historical MFG costs from F59048 | PPD Passed |  |  | TRUE | L |  | ECC | ARO | Thapa, Ravi Pratap | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-29 02:39 | Greenard, Terry | 9/27/2019 | 9/26/2019 |  | 2505 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 02:31 | Joshi, Abhishek N | 56-F-EU-V-190923-R1AR004 | ECC | Yes | Y |  |  | No Retrofit required but the object and versions were present in DV92064 OL |  |  |  | 56-F-EU-V-190923-R1ARV004A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59049 | No | UBE | BXU550551 |  | R1 |  |  | ECC Purge of Historical Budget Mfg Cost | PPD Passed |  |  | TRUE | L |  | ECC | ARO | Thapa, Ravi Pratap | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-29 02:40 | Greenard, Terry | 9/27/2019 | 9/26/2019 |  | 2506 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-16 02:29 | Joshi, Abhishek N | 56-F-EU-V-190923-R1AR005 | ECC | Yes | Y | [6 empty] | 56-F-EU-V-190923-R1ARV005A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59071 | No | UBE | 1247143 (12817) |  | R1 |  |  | Integration Log Report | PPD Passed |  |  | TRUE | L |  | ECC | ARO | Thapa, Ravi Pratap | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-29 02:41 | Greenard, Terry | 9/27/2019 | 9/26/2019 |  | 2507 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-19 07:21 | ANAND, S | 56-F-EU-V-190925-R1AR007 | ECC | Yes | Y | [6 empty] | 56-F-EU-V-190925-R1ARV007A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59TC0134A | No | UBE | BXU550551 |  | R1 |  |  | ECC : Input to F59012 XLS File front-end | PPD Passed | 575 | Open | TRUE | L |  | ECC | ARO | Ravi / Cosmin | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-29 02:42 | Greenard, Terry | 9/27/2019 | 9/26/2019 |  | 2508 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 07:19 | Joshi, Abhishek N | 56-F-EU-V-190925-R1AR001 | ECC | Yes | Y | [6 empty] | 56-F-EU-V-190925-R1ARV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59TC0305 | No | UBE |  |  | 999 |  |  | Import TOSCANINI Sales Products=X7A1 into ECC(F59010) | Obsolete |  |  |  | L |  | ECC | ARO | Ravi / Cosmin | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-29 02:43 | Greenard, Terry |  |  |  | 2509 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 03:07 | Greenard, Terry |  | ECC |  |  |  |  | Carlos, Objects to Obsolete |  |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59TC0306 | No | UBE |  |  | 999 |  |  | Import TOSCANINI Sales Products=X7A4 into ECC (F59010) | Obsolete |  |  |  | L |  | ECC | ARO | Ravi / Cosmin | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-29 02:44 | Greenard, Terry |  |  |  | 2510 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 03:08 | Greenard, Terry |  | ECC |  |  |  |  | Carlos, Objects to Obsolete |  |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59TC0307 | No | UBE |  |  | 999 |  |  | Import TOSCANINI Sales Products=X7C1 into ECC (F59010) | Obsolete |  |  |  | L |  | ECC | ARO | Ravi / Cosmin | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-29 02:44 | Greenard, Terry |  |  |  | 2511 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 03:08 | Greenard, Terry |  | ECC |  |  |  |  | Carlos, Objects to Obsolete |  |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59TC0308 | No | UBE |  |  | 999 |  |  | Import TOSCANINI Sales Products=X7C4 into ECC (F59010) | Obsolete |  |  |  | L |  | ECC | ARO | Ravi / Cosmin | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-29 02:45 | Greenard, Terry |  |  |  | 2512 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 03:09 | Greenard, Terry |  | ECC |  |  |  |  | Carlos, Objects to Obsolete |  |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59TC0311 | No | UBE |  |  | 999 |  |  | Import TOSCANINI Sales Products=X7E1 into ECC (F59010) | Obsolete |  |  |  | L |  | ECC | ARO | Ravi / Cosmin | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-05-29 02:46 | Greenard, Terry |  |  |  | 2513 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-08-06 03:09 | Greenard, Terry |  | ECC |  |  |  |  | Carlos, Objects to Obsolete |  |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59TC0317 | No | UBE |  |  | 999 |  |  | Retrieval BEC CSTADD/EUCON1 into ECC Mfg Costs | Obsolete |  |  | TRUE | L |  | ECC | ARO | Ravi / Cosmin | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-05-29 02:46 | Greenard, Terry | 09/27/2019 | 09/26/2019 |  | 2514 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-25 11:25 | Greenard, Terry | 56-F-EU-V-190925-R1ARO001 | ECC | Yes | Y |  |  | Obsoleted by Claire/Krista |  |  |  | 56-F-EU-V-190925-R1AROV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0005 | No | UBE |  |  | 1 |  |  | Advanced Preference Upload UBE | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-05-29 04:35 | Greenard, Terry | 5/22/2019 | 5/22/2019 |  | 2515 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-07-05 03:56 | Chiau, Liesbet | 56-F-EU-V-190529-S1OM045 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190529-S1OMV45A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74LI5I | No | UBE | 1266483 |  | 2 | 2 |  | Upload Transport Document | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete | No integration with Portuguese authorities web portal in DV or UT. Step 14 & 15 cannot be tested. |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-06-04 10:24 | Greenard, Terry | 6/24/2019 | 6/26/2019 |  | 2519 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-20 05:10 | Singh, Sunil Kumar | 56-F-EU-V-190701-S2LO001 |  | Yes | Y |  |  |  | various |  |  | 56-F-EU-V-190701-S2LOV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P594116 | No | APPL |  | 1230568 | 2 |  |  | WISE missing parts in EIM Inquiry | L3 Not Required |  |  | TRUE | LNE2E |  | MDM | MDM | Tom Hoste | L2 Not required | No KT/Object to Secure |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-06-06 08:37 | Greenard, Terry | 6/12/2019 | 6/12/2019 |  | 2521 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 09:59 | Joshi, Abhishek N | 56-F-EU-V-190612-S2FI029 | SECURE | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0492 | No | UBE |  |  | 1 |  | CRP | Workday JDE Integration - Bank Info | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Sriram Natarajan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Saieja |  | Item |  | 2019-06-10 04:43 | Greenard, Terry | 6/3/2019 | 6/2/2019 |  | 2522 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-12-05 07:12 | Singh, Sunil Kumar | 56-F-EU-V-190530-S1FI016 |  | Yes | Y |  |  | BD3N0003 (DSI object) missing in DV920. it's obsolete as per Oracle support comment. Find attached screen shot. |  |  |  | 56-F-EU-V-190530-S1FIV016A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P55FRDSX | No | APPL | BXU548833 |  | 2 |  | CRP | Maintain Company DSO settings | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-06-12 07:22 | Greenard, Terry | 06/18/2019 | 06/17/2019 |  | 2523 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-13 03:52 | Joshi, Abhishek N | 56-F-EU-V-190614-S2FI042 |  | Yes | Y | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900095 | No | APPL | 1257164 (27203) |  | 2 |  |  | Related Address Book Search | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-06-12 07:23 | Greenard, Terry | 6/18/2019 | 6/18/2019 |  | 2524 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-20 06:20 | ANAND, S | 56-F-EU-V-190617-S2MD036 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900097 | No | APPL | 1278730 (93271) |  | 2 |  |  | Address Number Search By Bank Account | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-06-12 07:24 | Greenard, Terry | 6/18/2019 | 6/17/2019 |  | 2525 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-19 07:29 | ANAND, S | 56-F-EU-V-190614-S2MD033 |  | Yes | [7 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900098 | No | APPL | 1278730 (93271) |  | 2 |  |  | Address Number Search By Shipto Xref | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-06-12 07:25 | Greenard, Terry | 6/18/2019 | 6/17/2019 |  | 2526 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-19 07:30 | ANAND, S | 56-F-EU-V-190614-S2MD036 |  | Yes | Y | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5603016 | Yes | APPL | 1256164 | 27203, 1257368 | 2 |  |  | Special Delivery Instructions Revision | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-06-12 07:26 | Greenard, Terry | 6/18/2019 |  |  | 2527 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-03 06:43 | Joshi, Abhishek N | 56-F-EU-V-190614-S2MD034 |  | Yes | Y | [6 empty] | 56-F-EU-V-190614-S2MDV34A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56EIM01 | No | APPL | BXU550751 |  | 6 |  |  | EIM : Error Recovery App | L3 Pass |  |  | TRUE |  |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-06-13 03:58 | Greenard, Terry | 9/5/2019 | 9/4/2019 |  | 2528 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-24 04:58 | Joshi, Abhishek N | 56-F-EU-V-190827-S6MD004 |  | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0152 | Obsolete | UBE |  |  | 999 |  |  | Order and Basket Level Pricing | Obsolete |  |  | FALSE | HNE2E |  | Order Management | OM | Van Gijseghem, Piet; Seputyte, Lina | (Blank) |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-06-13 04:25 | Greenard, Terry |  |  |  | 2529 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-12-05 07:03 | Singh, Sunil Kumar | [6 empty] | VV-24/06 -Obsoleted as per the request from Lina |  |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5603B702 | No | UBE | BXU545723 |  | 2 |  | CRP | A/R to G/L Receipts Integrity by Batch | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-06-28 02:48 | Verma, Vikas | 06/25/2019 | 06/24/2019 |  | 2530 | A/R to G/L Receipts Integrity by Batch | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 03:03 | Joshi, Abhishek N | 56-F-EU-V-190624-S2FI128 |  | Yes | Y |  |  | Cloned from R03B702 From 8.12 and Restored PAR | 2 |  |  | 56-F-EU-V-190624-S2FIV128A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5674ZD13 | No | UBE | BXU548584 |  | 2 |  |  | Stock Document Print | L3 Pass |  |  | TRUE | L |  | Quality | Logistics | Miruna Danes | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-07-05 02:50 | Greenard, Terry | 7/9/2019 | 6/24/2019 |  | 2531 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 04:34 | Joshi, Abhishek N | 56-F-EU-V-190624-S2LO130 | Printer | Yes | Y |  |  | Clone created for this Std object as R74ZD013 | KTQ3 |  |  | 56-F-EU-V-190624-S2LOV130A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600103 | No | UBE |  |  | 3 |  |  | eMail LoadList Report | L3 Pass | 203 | Closed | TRUE | HE2E |  | Transportation | Logistics | Puneet Sharma | L2 Not required | 07/23 RK: As per attached mail, marked as L2 not Required. |  |  | Terry Greenard/Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-07-05 09:03 | Greenard, Terry | 7/9/2019 | 7/9/2019 |  | 2545 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-12-05 06:36 | Singh, Sunil Kumar | 56-F-EU-V-190708-S3LO047 |  | Yes | Y |  |  | The object has same behaviour in DV812 & DV920. Unable to test it in both environments DV920 & DV812 |  |  |  | 56-F-EU-V-190708-S3LOV47A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74LI01B | No | UBE |  |  | 3 |  |  | Get SAF-T Data - General Ledger | L3 Not Required |  |  | FALSE | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-07-09 04:03 | Greenard, Terry | 7/10/2019 | 7/09/2019 |  | 2548 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-12-05 07:12 | Singh, Sunil Kumar | 56-F-EU-V-190709-S3FI152 | [6 empty] | No KT |  |  | 56-F-EU-V-190709-S3FIV152A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74LI01B1 | No | UBE |  |  | 3 |  |  | Get SAF-T Data - General Ledger | L3 Not Required |  |  | FALSE | HNE2E |  | Finance External | Finance | Keith Haxton | L2 Not required | No KT, as Tested by user only in ITC |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-07-09 04:03 | Greenard, Terry |  |  |  | 2549 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-12-05 07:12 | Singh, Sunil Kumar | [7 empty] | No KT |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R561015K | Yes | UBE | 1230268 (12888) | 12888 BXU547800 | 6 |  |  | Baxter Sales Order Manager Asynch Commit | L3 Not Required |  |  | TRUE | L |  | Order Management | OM | Piet Van Gijseghem, Lina Seputyte | L2 Not required | 09/18 RK: As per attached mail, marked as L2 Not required. |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-07-10 04:53 | Greenard, Terry | 9/10/2019 | 9/9/2019 |  | 2552 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-18 06:47 | ANAND, S | 56-F-EU-V-190620-S2OM040 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190620-S2OMV040A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5609200 | No | APPL | BXU547426 |  | 3 | 3 | CRP | Account Ledger Inquiry - Job Capitalisation | L3 Pass |  |  | TRUE |  |  | Finance GL | Finance | Robbin/Florencia | L2 Pass / Complete |  |  |  | Terry Greenard/Vikas Verma |  | Vikas Verma |  | Item |  | 2019-07-10 07:49 | Greenard, Terry | 7/11/2019 | 7/10/2019 |  | 2553 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 10:17 | Joshi, Abhishek N | 56-F-EU-V-190710-S3FI126 |  | Yes | Y | [6 empty] | 56-F-EU-V-190710-S3FIV126A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R7404500 | Obsolete | UBE |  |  | 999 |  |  | Withholding Tax Payments | Obsolete |  |  | FALSE | HNE2E |  | Localization | Finance | Keith Haxton | (Blank) |  |  |  | Terry Greenard / Vikas Verma | VV-30/08 - As there are no Baxter customization on the this standard object it will come from Pristine. |  |  | Item |  | 2019-07-10 10:54 | Greenard, Terry |  |  |  | 2554 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-12-05 07:03 | Singh, Sunil Kumar | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R7404530 | Obsolete | UBE |  |  | 999 |  |  | Distribute W/T Amount Report | Obsolete |  |  | FALSE | HNE2E |  | Localization | Finance | Keith Haxton | (Blank) |  |  |  | Terry Greenard / Vikas Verma | VV-30/08 - As there are no Baxter customization on the this standard object it will come from Pristine. |  |  | Item |  | 2019-07-10 10:55 | Greenard, Terry |  |  |  | 2555 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-12-05 07:03 | Singh, Sunil Kumar | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74099C | Obsolete | UBE | BXU545400 |  | 999 |  |  | Sequential Number Report -A/R | Obsolete |  |  | FALSE | HNE2E |  | Localization | Finance | Keith Haxton | (Blank) |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-07-10 10:56 | Greenard, Terry | 9/12/2019 | 9/5/2019 |  | 2556 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 07:42 | Joshi, Abhishek N |  |  | Yes | [7 empty] | 56-F-EU-V-190626-BV0310A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74L09POB | No | UBE | BXU549969 |  | 6 |  |  | Create Parent Accounts | L3 Not Required |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Not required | L2 Not Reqd, test in E2E |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-07-10 10:56 | Greenard, Terry | 9/12/2019 | 9/11/2019 |  | 2557 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 07:54 | Joshi, Abhishek N | 56-F-EU-V-190903-S6FI130 |  | Yes | Yes |  |  |  | No KT |  |  | 56-F-EU-V-190903-S6FIV130A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74P0018I | Obsolete | UBE |  |  | 999 |  |  | INTRASTAT Poland | Obsolete |  |  | FALSE |  |  |  | Logistics |  | (Blank) | [7 empty] | Item |  | 2019-07-10 10:57 | Greenard, Terry |  |  |  | 2558 | Standard | 0 |  |  |  | 2020-01-09 07:59 | Bodin, Fatiha | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74P1050 | Obsolete | UBE | BXU545722 |  | 999 |  |  | VAT Sales Register F4211/F42119 - Poland | Obsolete |  |  | FALSE | HNE2E |  | Localization | Finance | Keith Haxton | (Blank) |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-07-10 10:58 | Greenard, Terry | 09/11/2019 | 09/12/2019 |  | 2559 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 06:11 | Joshi, Abhishek N | 56-F-EU-V-190904-S6FI146 | [9 empty] | 56-F-EU-V-190904-S6FIV146A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74P1110 | No | UBE | BXU545458 |  | 6 |  | CRP | Statement Print | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-07-10 10:59 | Greenard, Terry | 9/12/2019 | 9/11/2019 |  | 2560 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 07:57 | Joshi, Abhishek N | 56-F-EU-V-190912-S6FI156 |  | Yes | Y |  |  | Object not availble in DV920 OL , PAR File restored from PD812. |  |  |  | 56-F-EU-V-190912-S6FIV156A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74P3B1T | No | UBE | BXU545457 |  | 6 |  | CRP | Conversion Process - Tax Liability Date - POL | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-07-10 11:00 | Greenard, Terry | 9/12/2019 | 9/10/2019 |  | 2561 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 07:58 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI066 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190626-BV0318A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74R3018 | No | UBE | BXU551101 |  | 6 |  | CRP | Russian Tax File Maintenance A/R - RUS | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth, Thippulla |  | Item |  | 2019-07-10 11:01 | Greenard, Terry | 9/12/2019 | 9/11/2019 |  | 2562 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-04-02 06:55 | Joshi, Abhishek N | 56-F-EU-V-190904-S6FI143 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190626-BV0319A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74R4018 | No | UBE | BXU551102 |  | 6 |  | CRP | Russian Tax File Maintenance - RUS | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-07-10 11:01 | Greenard, Terry | 9/12/2019 | 9/11/2019 |  | 2563 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-04-02 06:56 | Joshi, Abhishek N | 56-F-EU-V-190911-S6FI152 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190626-BV0320A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74R41003 | No | UBE | BXU545453 |  | 6 |  | CRP | Item Transfer Note - RUS | L3 Pass |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-07-10 11:02 | Greenard, Terry | 9/12/2019 | 9/12/2019 |  | 2564 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 08:07 | Joshi, Abhishek N | NA |  | Yes | No OMW Project. |  |  | No code difference between E812 and E920.Retrofit Not required |  |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74R9801 | No | UBE | BXU548341 |  | 6 |  |  | Generate Correspondance - RUS | L3 Not Required |  |  | TRUE | HNE2E |  | Localization | Finance | Keith Haxton | L2 Not required | L2 Not req, test in E2E |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-07-10 11:03 | Greenard, Terry | 9/12/2019 | 9/12/2019 |  | 2565 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 08:09 | Joshi, Abhishek N | 56-F-EU-V-190904-S6FI141 |  | Yes | Y |  |  |  | No KT |  |  | 56-F-EU-V-190626-BV0322A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74Y015 | No | UBE |  |  | 999 |  |  | Yearly List Information - ITA | Obsolete |  |  | FALSE | HNE2E |  | Localization | Finance | Keith Haxton | (Blank) |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-07-10 11:03 | Greenard, Terry |  |  |  | 2566 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-12-05 07:11 | Singh, Sunil Kumar | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74Y050 | No | UBE | BXU545358 |  | 999 |  |  | Generate Black List Information - IT | Obsolete |  |  | FALSE | HNE2E |  | Localization | Finance | Keith Haxton | (Blank) |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-07-10 11:04 | Greenard, Terry |  |  |  | 2567 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 06:22 | Joshi, Abhishek N | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58ICR01C | No | UBE | BXU546244 |  | 999 |  |  | Item Cross Reference Print - CSV | Obsolete |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Asha |  | Item |  | 2019-07-15 07:10 | Greenard, Terry | 7/17/2019 | 7/16/2019 |  | 2569 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 04:51 | Joshi, Abhishek N | 56-F-EU-V-190715-S3LO054 | Cross Ref / Printer | Yes | Y | [6 empty] | 56-F-EU-V-190715-S3LOV054A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900061 | Yes | APPL |  |  | 3 |  |  | Potency Calculator | L3 Not Required |  |  | TRUE | L |  | Order Management | OM | John Whalley | L2 Not required | Functionally obsolete - only required for P42101 to execute |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-07-17 01:48 | Greenard, Terry | 7/18/2019 | 7/17/2019 |  | 2570 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:00 | Mohammed, Saleem | 56-F-EU-V-190717-S3OM111 |  | Yes | Y |  |  | There was a spec diff b/w PD812 and DV920 as the 'VA frm_mnPotencyRequiredFlag' feild mapping in BSFN B4201610_D4201610 was pointing to 'cConsignedBillingLineTYpe' feild as in DV920 instead of 'cPotentunitsdefault' feild as in PD812. Hence retrofitted |  |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56VESR | No | APPL | BXU550733 |  | 3 |  | CRP | VESR Scanning Applications | L3 Pass |  |  | TRUE |  |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete | L2 pass after call 22/07 |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-07-17 10:25 | Greenard, Terry | 7/18/2019 | 7/18/2019 |  | 2571 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-23 02:36 | Joshi, Abhishek N | 56-F-EU-V-190718-S3FI165 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600103NT | No | UBE | BXU550487 |  | 3 |  |  | Email Report Output_only for NT Jobs | L3 Pass |  |  | TRUE | LE2E |  | Warehouse | Logistics | Léonard Dartois | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-07-18 06:25 | Greenard, Terry | 7/19/2019 | 7/18/2019 |  | 2572 | Custom | 0 |  |  |  | 2020-03-14 01:22 | Joshi, Abhishek N | 56-F-EU-V-190718-S3LO055 |  | Yes | Y |  |  | waiting for integration to be available |  |  |  | 56-F-EU-V-190718-S3LOV055A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P55GL01S | No | APPL | BXU550734 |  | 4 |  | CRP | Grants - Search and Select | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-07-23 08:22 | Greenard, Terry | 7/24/2019 | 7/24/2019 |  | 2573 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-23 02:38 | Joshi, Abhishek N | 56-F-EU-V-190724-S4FI029 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R57AR003A | No | UBE | BXU545819 |  | 3 |  | CRP | Summary list - Receipt Sweep Com to Prin (F0911Z1) | L3 Pass |  |  | TRUE |  |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-07-24 04:44 | Verma, Vikas | 7/25/2019 | 7/25/2019 |  | 2574 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 08:38 | Joshi, Abhishek N | 56-F-EU-V-190725-S4FI002 |  | Yes | [7 empty] | 56-F-EU-V-190725-S4FIV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564572RUC | No | UBE | BXU550735 |  | 6 | 5 | CRP | Deutche Bank - Russian Payment Check for any Errors in Batch | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete | Defect 287 is in process |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-08-06 01:58 | Greenard, Terry | 8/28/2019 | 8/27/2019 |  | 2576 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-23 02:39 | Joshi, Abhishek N | 56-F-EU-V-190827-S5FI130 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S5FIV130A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564572CZC | No | UBE | BXU550358 |  | 5 |  | CRP | Deutche Bank - Czech Payment Check for any Errors in Batch | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-06 01:58 | Greenard, Terry | 8/29/2019 | 8/22/2019 |  | 2577 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 06:03 | Joshi, Abhishek N | 56-F-EU-V-190820-S5FI123 |  | Yes | Y | [6 empty] | 56-F-EU-V-190820-S5FIV123A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564572PLC | No | UBE | BXU550736 |  | 5 |  | CRP | Deutche Bank - Poland Payment Check for any Errors in Batch | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-08-06 01:59 | Greenard, Terry | 8/29/2019 | 8/28/2019 |  | 2578 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-23 02:41 | Joshi, Abhishek N | 56-F-EU-V-190827-S5FI131 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190827-S5FIV131A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642023X | No | UBE | BXU546733 |  | 6 |  | CRP | SOX Pricing Exceptions | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Libor Slaby | L2 Pass / Complete | As discussed in the todays scrum call R5642023O UTS has also been attached for R5642023X |  |  | Terry Greenard / Vikas Verma |  | CIZMECI,TANKUT |  | Item |  | 2019-08-09 04:37 | Greenard, Terry | 8/29/2019 | 8/28/2019 |  | 2579 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 00:28 | Joshi, Abhishek N | 56-F-EU-V-190813-S5FI066 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190813-S5FIV066A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649010 | Obsolete | UBE |  |  | 999 |  |  | Batch Report to upload Print Message Information in F5649010 | Obsolete |  |  | TRUE |  |  | Transportation | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-08-12 06:54 | Verma, Vikas |  |  |  | 2580 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:38 | Mohammed, Saleem | 56-F-EU-V-190812-S5LO025 | [5 empty] | obsolete, linked with Alabau carrier which is not in used anymore |  |  |  | 56-F-EU-V-190812-S5LOV025A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56IB0014Z | Obsolete | UBE |  |  | 999 |  |  | Pallet Labels - Zebra Printer Output - Iberia | Obsolete |  |  | TRUE |  |  | Transportation | Logistics |  | L2 Not required | [5 empty] | Vikas Verma |  | Item |  | 2019-08-12 06:56 | Verma, Vikas |  |  |  | 2581 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:38 | Mohammed, Saleem | [6 empty] | obsolete, not required in EMEA |  |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5603B22 | No | UBE | BXU545718 |  | 5 |  |  | Late Interest Invoice Generati | L3 Pass |  |  | TRUE |  |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi |  | Item |  | 2019-08-13 03:12 | Greenard, Terry | 8/14/19 | 8/13/19 |  | 2583 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 02:44 | Joshi, Abhishek N | 56-F-EU-V-190814-S5FI077 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190814-S5FIV077A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5603B2R | No | UBE | BXU545719 |  | 5 |  |  | Reconcile Late Interests | L3 Pass |  |  | TRUE |  |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth |  | Item |  | 2019-08-13 03:13 | Greenard, Terry | 08/14/2019 | 08/13/2019 |  | 2584 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 02:48 | Joshi, Abhishek N | 56-F-EU-V-190813-S5FI068 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190813-S5FIV068A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4210 | Yes | APPL | BXU545444 (60558), 1222473 (11402) | 1276496 (60558),1263371 (4099), BXU545241 (11402) | R1 |  |  | Sales Order Entry | PPD Passed |  |  | TRUE | HE2E |  | Order Management | OM | Seputyte Lina | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-15 02:08 | Greenard, Terry | 09/20/2019 | 09/16/2019 |  | 2585 | Standard | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-07-24 05:36 | Singh, Sunil Kumar | 56-F-EU-V-190522-S1OM042 |  | Yes | Y |  |  | Changes in Production after Cut-Off |  |  |  | 56-F-EU-V-190522-S1OM042A-R,56-F-EU-V-190522-S1OM042T-Z, 56-F-EU-V-190522-S1OM042AA - AD | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P42117 | Yes | APPL | BXU545444 (60558), 1270935 (Global Document) | 1276496 (60558), 1255648 (Global Document) | R1 |  |  | Backorder Release | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Meltem Cetinkus | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 02:09 | Greenard, Terry | 09/20/19 | 09/19/19 |  | 2586 | Standard | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-06-09 05:35 | Singh, Sunil Kumar | 56-F-EU-V-190513-S2OM001 |  | Yes | Y |  |  | Changes in Production after Cut-Off |  |  |  | 56-F-EU-V-190513-S2OMV01A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5601101 | No | APPL |  | 1253946 | R1 |  |  | Company in Commercial Category | L3 Pass |  |  | TRUE |  |  | MDM | MDM | Carlos | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 02:09 | Greenard, Terry | 9/23/2019 | 9/20/2019 |  | 2587 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-04 09:05 | Javadi, Vinod | 56-F-EU-V-190920-R1MD003 |  | Yes | Y |  |  | Changes in Production after Cut-Off. PAR restored from PD812. But in DV920 the Company field was shrinked .Hence increased the company field width in W5601101A form | R1 Script created |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5603012 | Yes | APPL |  | 1253946 | R1 |  |  | Patient/Ship To Maintenance | PPD Passed |  |  | TRUE | H |  | MDM | MDM | Carlos | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-15 02:10 | Greenard, Terry | 9/23/2019 | 9/20/2019 |  | 2588 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-04 06:27 | Joshi, Abhishek N | 56-F-EU-V-190611-S2MD017 | Maintenance | Yes | Y |  |  | Changes in Production after Cut-Off | R1 Script created |  |  | 56-F-EU-V-190611-S2MDV17A,56-F-EU-V-190919-R1MDV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5603014 | No | APPL |  | 1253946 | R1 |  |  | Basis/Bill To Maintenance | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Carlos | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-15 02:10 | Greenard, Terry | 9/23/2019 | 9/20/2019 |  | 2589 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-04 06:27 | Joshi, Abhishek N | 56-F-EU-V-190620-S2MD047 | Maintenance | Yes | Y |  |  | Changes in Production after Cut-Off | R1 Script created |  |  | 56-F-EU-V-190620-S2MDV047A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642211 | Yes | APPL | BXU540989 (158122) | BXU545874 (158122) | R1 |  |  | Pharmacy Label Print | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Albert VIla | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-15 02:11 | Greenard, Terry | 9/20/2019 | 9/19/2019 |  | 2590 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-06 07:34 | ANAND, S | 56-F-EU-V-190920-R1LO005 |  | Yes | Y |  |  | Move to CRP |  |  |  | 56-F-EU-V-190920-R1LOV005A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642212 | Yes | APPL | BXU540989 (158122), BXU546572 (158122) | BXU545874 (158122) | R1 |  |  | Box Label Print | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Albert VIla | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-15 02:11 | Greenard, Terry | 9/20/2019 | 9/20/2019 |  | 2591 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-10 13:46 | Singh, Sunil Kumar | 56-F-EU-V-190923-R1LO007 |  | Yes | Y |  |  | Move to CRP |  |  |  | 56-F-EU-V-190923-R1LOV007A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5643070 | Yes | APPL | BXU532396 (148542) | BXU532399 (148542) | R1 |  |  | Line Level Held Order Release | L3 Pass |  |  | TRUE | H |  | Quality | Logistics | Pawel Oskroba | L2 Not required | Retrofit Not required |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-15 02:17 | Greenard, Terry | 9/23/2019 | 9/23/2019 |  | 2592 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-06 08:11 | ANAND, S | 56-F-EU-V-190610-S2LO032 |  | Yes |  |  |  | Changes in Production after Cut-Off. <9/24> No R1 changes. |  |  |  | 56-F-EU-V-190610-S2LOV32A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5643129 | No | APPL | 1258017 (26923) | 1258019 (26923) | R1 |  |  | Receipt Routing Mass Update | PPD Passed | 441 | Open | TRUE | LE2E |  | Procurement | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 02:18 | Greenard, Terry | 09/25/2019 | 09/23/2019 |  | 2593 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-06 08:25 | ANAND, S | 56-F-EU-V-230905-R1LO002 |  | Yes | Y |  |  | Move to CRP |  |  |  | 56-F-EU-V-190517-S1LOV55A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5645550 | No | APPL | BXU545286 | BXU547673 | R1 |  |  | F4072 Global Update Engine | PPD Passed |  |  | TRUE | HNE2E |  | Order Management | OM | John Whalley | L2 Pass / Complete | JW 4/11/19 General functional testing completed in UT920; CRQ162117 Record Lock testing completed in UT920 and PPD920 |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 02:18 | Greenard, Terry | 9/23/2019 | 9/23/2019 |  | 2594 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-03-14 05:51 | Joshi, Abhishek N | 56-F-EU-V-190722-S4OM011 |  | Yes | Y |  |  | Changes in Production after Cut-Off |  |  |  | 56-F-EU-V-190722-S4OMV011A, 56-F-EU-V-190722-S4OMV011B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564638 | Yes | APPL | 1238862 (14849) | 1241629 (14849) | R1 |  |  | Maintain Hazardous Shipping Information | L3 Not Required |  |  | TRUE | HE2E |  | transportation | Logistics | Eric Destrebecq | L2 Not required | 10/09 RK: As per Eric's mail, marked as L2 Not required. This will be L3 Testing only. "please drop testing in L2 as it requires a lot of setup. The setup will be done in UT and we’ll do L3 testing. " |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-15 02:19 | Greenard, Terry | 9/23/2019 | 9/22/2019 |  | 2595 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-07 06:52 | ANAND, S | 56-F-EU-V-190923-R1LO009 |  | Yes | Y |  |  | Changes in Production after Cut-Off |  |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5647019 | No | APPL |  |  | R1 |  |  | Sales Order Error | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-15 02:19 | Greenard, Terry |  |  |  | 2596 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2019-10-21 04:26 | Kamatham, Deepika | 56-F-EU-V-190617-S2OM034 |  | Yes | Y |  |  | Changes in Production after Cut-Off |  |  |  | 56-F-EU-V-190617-S2OMV034A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564736 | No | APPL | BXU546232 (19778), 1235782 (14853) | 1235723 (14853) | R1 |  |  | Maintain/Send Freight Forwarder EDI Data | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Puneet Sharma | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-15 02:20 | Greenard, Terry | 9/24/2019 | 9/23/2019 |  | 2597 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-06 10:16 | ANAND, S | 56-F-EU-V-190717-S3LO153 |  | Yes | Y |  |  | Changes in Production after Cut-Off |  |  |  | 56-F-EU-V-190717-S3LOV153A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649018 | No | APPL |  |  | R1 |  |  | Packing List Entry | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-15 02:20 | Greenard, Terry | 9/23/2019 | 9/22/2019 |  | 2598 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2019-10-08 08:02 | weber, scott | 56-F-EU-V-190523-S1LO104 |  | Yes | Y |  |  | Changes in Production after Cut-Off |  |  |  | 56-F-EU-V-190523-S1LOV104A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564901G | No | APPL | BXU513247 (104668) | BXU512852 (104668) | R1 |  |  | Packing List Entry - GLAB | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-15 02:21 | Greenard, Terry | 9/23/2019 | 9/20/2019 |  | 2599 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-07 07:12 | ANAND, S | 56-F-EU-V-190613-S2LO082 |  | Yes | Y |  |  | Changes in Production after Cut-Off |  |  |  | 56-F-EU-V-190613-S2LOV082A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5690701 | No | APPL | BXU542147 (160199) | BXU542148 (160199) | R1 |  |  | Container and Single RTE Relationship | PPD Passed |  |  | TRUE | HE2E |  | warehouse | Logistics | Leonard Dartois | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 02:21 | Greenard, Terry | 9/23/2019 | 9/22/2019 |  | 2600 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-07 10:28 | ANAND, S | 56-F-EU-V-190918-R1WD001 |  | Yes | Y |  |  | Move to CRP |  |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5695400 | No | APPL | BXU542147 (160199) | BXU542148 (160199) | R1 |  |  | Consumer Service Key for Warehouse | PPD Passed |  |  | TRUE | HE2E |  | warehouse | Logistics | Leonard Dartois | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-15 02:22 | Greenard, Terry | 09/24/2019 | 09/20/2019 |  | 2601 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-07 10:23 | ANAND, S | 56-F-EU-V-190918-R1LO001 |  | Yes | Y |  |  | Move to CRP |  |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56SLOG1 | No | APPL | BXU548587 (133080A) | BXU547397 (133080B) | R1 |  |  | Serialised Log Maintenance | PPD Passed |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 02:22 | Greenard, Terry | 09/23/2019 | 09/23/2019 |  | 2602 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-05-26 08:25 | Singh, Sunil Kumar | 56-F-EU-V-190621-S2LO001 |  | Yes | Y |  |  | Move to CRP |  |  |  | 56-F-EU-V-190621-S2LOV01A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900054 | No | APPL |  |  | R1 |  |  | Transaction Detail Inquiry | L3 Pass |  |  | TRUE | L |  | Technical Services | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-15 02:23 | Greenard, Terry | 9/23/2019 | 9/23/2019 |  | 2603 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2019-10-08 07:17 | BILENSOY, NURI | 56-F-EU-V-260619-S2LO148 |  | Yes | Y |  |  | Changes in Production after Cut-Off |  |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900090 | No | APPL | BXU547240 |  | R1 |  | CRP | Override Currency Rules | L3 Pass | 500 | Closed | TRUE | HNE2E |  | Finance GL | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 02:24 | Greenard, Terry | 9/23/2019 | 9/20/2019 |  | 2604 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-03-06 05:08 | Joshi, Abhishek N | 56-F-EU-V-190725-S4FI038 |  | Yes | Y |  |  | Changes in Production after Cut-Off |  |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5943250 | Yes | APPL |  |  | R1 |  |  | Movement and Disposition By Load Number | PPD Passed |  |  | TRUE | HE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-15 02:24 | Greenard, Terry | 9/23/2019 | 9/23/2019 |  | 2605 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2019-10-10 08:28 | Corbett, Mandy | 56-F-EU-V-190527-S1LO115 |  | Yes | Y |  |  | Move to CRP |  |  |  | 56-F-EU-V-190527-S1LOV115A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55JDRCP1 | No | UBE | BXU547856 |  | R1 |  | CRP | MILD - Receipts to JDE - JDRCPT/POJDE to Z files | L3 Pass |  |  | TRUE | HE2E |  | Finance AP | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-08-15 02:32 | Greenard, Terry | 9/24/2019 | 9/23/2019 |  | 2606 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-03-10 03:02 | Joshi, Abhishek N | 56-F-EU-V-190723-S4FI026 |  | Yes |  |  |  | Changes in Production after Cut-Off |  |  |  | 56-F-EU-V-190723-S4FIV026A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55NSIIB | No | UBE |  |  | R1 |  | CRP | SII Generacion de XML B | L3 Pass |  |  | TRUE |  |  | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-15 02:33 | Greenard, Terry | 9/24/2019 | 9/23/2019 |  | 2607 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2019-10-28 09:19 | Ajuria, Izaskun | 56-F-EU-V-190910-S6FI125 |  | Yes | Y |  |  | Changes in Production after Cut-Off |  |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600074 | No | UBE | BXU547134 |  | R1 |  | CRP | F4211 Adjust Sales Line UBE | L3 Pass |  |  | TRUE | HE2E |  | Finance GL | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 02:33 | Greenard, Terry | 9/24/2019 | 9/23/2019 |  | 2608 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-03-05 06:44 | Joshi, Abhishek N | 56- F-EU-V-190625-S3FI025 |  | Yes | Y |  |  | Changes in Production after Cut-Off |  |  |  | 56- F-EU-V-190625-S3FIV025A,56- F-EU-V-190625-S3FIV025B,56- F-EU-V-190625-S3FIV025C,56- F-EU-V-190625-S3FIV025D | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600075 | No | UBE | BXU547134 |  | R1 |  | CRP | 10/10 - Tested successfully the following scenarios: Buyer (FG and FGH) UK to Ppal Seller (SP) UK to Ppal 14/10 Override currency. Can not be test it at the moment as P4210 is on hold. 24/10 FA - Test it successfully the last scenario | L3 Pass |  |  | TRUE | HE2E |  | Finance GL | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 02:34 | Greenard, Terry | 9/24/2019 | 9/23/2019 |  | 2609 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-03-05 06:47 | Joshi, Abhishek N | 56-F-EU-V-190701-S3FI069 |  | Yes | Y |  |  | Changes in Production after Cut-Off |  |  |  | 56-F-EU-V-190701-S3FIV69A,56-F-EU-V-190701-S3FIV69B,56-F-EU-V-190701-S3FIV69C | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560018IB | No | UBE | BXU544776 (18535) |  | R1 |  |  | Statutory Intrastat Reporting Belgium | L3 Pass |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Rakesh Kumar | L2 Pass / Complete | Necessary Data needed to test. |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-15 02:34 | Greenard, Terry | 9/24/2019 | 9/22/2019 |  | 2610 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-06 10:20 | Singh, Sunil Kumar | 56-F-EU-V-190812-S5LO007 |  | Yes | Y |  |  | Move to CRP |  |  |  | 56-F-EU-V-190812-S5LOV007A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560018X2 | No | UBE |  |  | R1 |  |  | Generate XML file for Customs Declaration | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 02:35 | Greenard, Terry | 9/24/2019 | 9/23/2019 |  | 2611 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2019-10-22 04:34 | Bordignon, Veronique | 56-F-EU-V-190705-S3LO040 |  | Yes | Y |  |  | Changes in Production after Cut-Off |  |  |  | 56-F-EU-V-190705-S3LOV040A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5624053 | No | UBE | BXU546028 |  | R1 |  | CRP | Audit Counter part Report Russia | L3 Pass |  |  | TRUE | LNE2E |  | Localisations | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-15 02:35 | Greenard, Terry | 09/24/2019 | 09/24/2019 |  | 2612 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-03-08 00:34 | Joshi, Abhishek N | 56-F-EU-V-190919-R1FI001 |  | Yes | Y |  |  | Changes in Production after Cut-Off |  |  |  | 56-F-EU-V-190919-R1FIV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641024 | No | UBE | BXU545027 | BXU537485 | R2 |  |  | JDE to JDE – Interco Return (Credit Order) | PPD Passed | 485 | Closed | TRUE | HE2E | TRUE | Order Management | OM | Rafal Molas | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 02:36 | Greenard, Terry | 09/24/2019 | 09/24/2019 |  | 2613 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-03-12 10:06 | Joshi, Abhishek N | 56-F-EU-V-190729-S4OM022 |  | Yes | Y |  |  | Changes in Production after Cut-Off. Moved from R1 to R2 as testing is delayed |  |  |  | 56-F-EU-V-190729-S4OMV022A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641201X | No | UBE |  |  | R1 |  |  | Inventory Audit Report for FR | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Rakesh Kumar | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-15 02:36 | Greenard, Terry | 9/23/2019 | 9/23/2019 |  | 2614 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2019-12-12 03:55 | Singh, Sunil Kumar | 56-F-EU-V-190923-R1LO010 |  | Yes | Y |  |  | Move to CRP |  |  |  | 56-F-EU-V-190923-R1LOV10A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642032 | No | UBE | BXU546245 |  | R1 |  |  | UK Compounding Stuck Order details from F4211 | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Rakesh Kumar | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 02:37 | Greenard, Terry | 9/24/2019 | 9/23/2019 |  | 2615 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-03-09 04:55 | Joshi, Abhishek N | 56-F-EU-V-190923-R1LO008 |  | Yes | Y |  |  | Move to CRP |  |  |  | 56-F-EU-V-190923-R1LOV008A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642033 | No | UBE | BXU546245 |  | R1 |  |  | UK Compounding Stuck Order details from Item Locat | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Rakesh Kumar | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 02:37 | Greenard, Terry | 9/24/2019 | 9/24/2019 |  | 2616 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-03-09 05:00 | Joshi, Abhishek N | 56-F-EU-V-190923-R1LO012 |  | Yes | Y |  |  | Move to CRP |  |  |  | 56-F-EU-V-190923-R1LOV012B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642055 | Yes | UBE | 1277534 (80724) |  | R1 |  |  | MILD Process Second Stage Order Creation | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 02:38 | Greenard, Terry | 9/25/2019 | 9/25/2019 |  | 2617 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-17 10:03 | ANAND, S | 56-F-EU-V-190724-S4OM018 |  | Yes | Y |  |  | Changes in Production after Cut-Off |  |  |  | 56-F-EU-V-190724-S4OMV018A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642055G | Yes | UBE | BXU513247 (104668) | BXU512852 (104668) | R1 |  |  | GLAB Process Second Stage Order Creation | PPD Passed | 550 | WIP | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 02:38 | Greenard, Terry | 9/25/2019 | 9/24/2019 |  | 2618 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-11 06:28 | ANAND, S | 56-F-EU-V-190611-S2LO045 |  | Yes | Y |  |  | Move to CRP |  |  |  | 56-F-EU-V-190611-S2LOV045A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564211B | Yes | UBE | BXU545508, 1241776 (17980), 1249046 (22088), BXU546685 (23866), BXU546688 (20127), 1249046 (22088) | BXU537484, BXU546927 (20127), 1249047 (22088), BXU546931 (23866), BXU547619 (25431) | R1 |  |  | Populate EDI from Sales Order Dispatches | PPD Passed |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-15 02:39 | Greenard, Terry | 9/25/2019 | 9/24/2019 |  | 2620 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-11 06:57 | ANAND, S | 56-F-EU-V-190724-S4LO049 |  | Yes | Y |  |  | Move to CRP |  |  |  | 56-F-EU-V-190724-S4LOV049A, 56-F-EU-V-190724-S4LOV049B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564211SA | Yes | UBE | BXU532056 (139511) | BXU532059 (139511) | R1 |  |  | Export Compliance and Sales Authorization check | PPD Passed |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete | Data needed for 2 scenarios. |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 02:40 | Greenard, Terry | 9/25/2019 | 9/24/2019 |  | 2621 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-11 07:10 | ANAND, S | 56-F-EU-V-190702-S3LO026 |  | Yes | Y |  |  | Move to CRP |  |  |  | 56-F-EU-V-190702-S3LOV026A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642520D | Yes | UBE | BXU546242 | BXU542143 162784 | R1 |  |  | Manual Warehouse Picklist GB AP 11/10/2019 - Test passed PPD without issues. | PPD Passed |  |  | TRUE | HE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 02:40 | Greenard, Terry | 9/25/2019 | 9/25/2019 |  | 2622 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-13 10:26 | Vishnubhatla, Mithra | 56-F-EU-V-190924-R1LO003 |  | Yes | Y |  |  | Move to CRP |  |  |  | 56-F-EU-V-190924-R1LOV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643018 | No | UBE | BXU547013 |  | R1 |  | CRP | Output Analysis for Saudi New VAT Returns | L3 Pass |  |  | TRUE | HNE2E |  | Localisations | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 02:42 | Greenard, Terry | 09/25/2019 | 09/24/2019 |  | 2623 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-03-08 01:40 | Joshi, Abhishek N | 56-F-EU-V-190924-R1FI001 |  | Yes | Y |  |  | Changes in Production after Cut-Off |  |  |  | 56-F-EU-V-190924-R1FIV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643019 | No | UBE |  |  | R1 |  | CRP | Concur Expense Analysis for Saudi New VAT Returns | L3 Pass |  |  | TRUE | HNE2E |  | Localisations | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 02:42 | Greenard, Terry | 9/25/2019 | 9/25/2019 |  | 2624 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2019-12-05 07:12 | Singh, Sunil Kumar | 56-F-EU-V-190924-R1FI006 |  | Yes | Y |  |  | Changes in Production after Cut-Off |  |  |  | 56-F-EU-V-190924-R1FNV006A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643020 | No | UBE | BXU547013 |  | R1 |  | CRP | GL Voucher Analysis for Saudi New VAT Returns | L3 Pass |  |  | TRUE | HNE2E |  | Localisations | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 02:43 | Greenard, Terry | 9/25/2019 | 9/24/2019 |  | 2625 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-03-08 03:38 | Joshi, Abhishek N | 56-F-EU-V-190924-R1FI009 |  | Yes | Y |  |  | Changes in Production after Cut-Off |  |  |  | 56-F-EU-V-190924-R1FIV009A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643092 | Yes | UBE | 1258017 (26923) | 1258019 (26923) | R1 |  |  | Receipt Routing Notification - Great Bear | PPD Passed |  |  | TRUE | LE2E |  | Procurement | Logistics | Abdul Mughal/TK | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-15 02:43 | Greenard, Terry | 09/24/2019 | 09/23/2019 |  | 2626 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-12 07:07 | ANAND, S | 56-F-EU-V-190611-S2LO044 |  | Yes | Y |  |  | Move to CRP |  |  |  | 56-F-EU-V-190611-S2LOV044A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647341 | Yes | UBE | 1253922 (24450), 1255649 (25984) | 1254243 (24450), BXU547001 (25984) | R1 |  |  | EMEA APS UBE | PPD Passed |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 02:44 | Greenard, Terry | 9/26/2019 | 9/26/2019 |  | 2627 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-13 08:17 | ANAND, S | 56-F-EU-V-190517-S1LO056 |  | Yes | Y |  |  | Move to CRP |  |  |  | 56-F-EU-V-190517-S1LOV56A, 56-F-EU-V-190517-S1LOV56B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649003 | No | UBE | 1240721 | 16249 1240744 | R1 |  |  | Print Packing List | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 02:45 | Greenard, Terry | 9/25/2019 | 9/24/2019 |  | 2628 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-01-31 08:36 | Vishnubhatla, Mithra | 56-F-EU-V-190523-S1LO105 |  | Yes | Y |  |  | Changes in Production after Cut-Off |  |  |  | 56-F-EU-V-190523-S1LOV105A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649003G | No | UBE |  |  | R1 |  |  | Print Packing List - GLAB | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 02:45 | Greenard, Terry | 9/25/2019 | 9/23/2019 |  | 2629 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2019-10-08 05:06 | weber, scott | 56-F-EU-V-190725-S4LO055 |  | Yes | Y |  |  | Changes in Production after Cut-Off |  |  |  | 56-F-EU-V-190725-S4LOV055A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649044G | Yes | UBE |  |  | R1 |  |  | GLAB Ship Confirm Processor | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Rakesh Kumar | L2 Pass / Complete | Data needed to test this object |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-15 02:46 | Greenard, Terry | 9/25/2019 | 9/24/2019 |  | 2630 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2019-10-22 03:44 | Dartois, Léonard | 56-F-EU-V-190731-S4LO089 |  | Yes | Y |  |  | Move to CRP |  |  |  | 56-F-EU-V-190731-S4LOV089A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56BH42535 | No | UBE | BXU531854 (133080B), BXU546242 (162784),BXU547134 | BXU542143 (162784) | R1 |  |  | Delivery Note -BH | L3 Not Required |  |  | TRUE | ME2E |  | transportation | Logistics | Eric Destrebecq | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-08-15 02:46 | Greenard, Terry | 09/23/2019 | 09/25/2019 |  | 2631 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-03-05 06:47 | Joshi, Abhishek N | 56-F-EU-V-190920-R1LO006 |  | Yes |  |  |  | Changes in Production after Cut-Off => move to PPD |  |  |  | 56-F-EU-V-190920-R1LOV006A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56DE42535 | No | UBE | 1251956 | 1251989 22040 | R1 |  |  | Delivery Note Germany | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 03:06 | Greenard, Terry | 09/25/2019 | 09/25/2019 |  | 2632 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-24 06:05 | ANAND, S | 56-F-EU-V-190621-S1LO126 |  | Yes | Y |  |  | Changes in Production after Cut-Off |  |  |  | 56-F-EU-V-190621-S1LOV126A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56E4211 | No | UBE |  |  | R1 |  |  | CZ csv extract F4211 | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Lina Seputyte | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-15 03:06 | Greenard, Terry | 9/23/2019 | 9/22/2019 |  | 2633 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2019-10-15 08:52 | Seputyte, Lina | 56-F-EU-V-190611-S2OM002 |  | Yes | Y |  |  | Changes in Production after Cut-Off |  |  |  | 56-F-EU-V-190611-S2OMV002A, 56-F-EU-V-190923-R1OMV02A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FR42535 | No | UBE | 1256041 (25586) | 25586 1256042 | R1 |  |  | Delivery Note France | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 03:07 | Greenard, Terry | 9/25/2019 | 9/24/2019 |  | 2634 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-07 10:28 | Singh, Sunil Kumar | 56-F-EU-V-190710-S3LO088 |  | Yes | Y |  |  | Changes in Production after Cut-Off |  |  |  | 56-F-EU-V-190710-S3LOV088A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56G0001 | Yes | UBE | 1278730 (93271) | 93271, 1278732 | R1 |  |  | GSP Address Book Number Extract | L3 Pass |  |  | TRUE |  |  |  | MDM |  | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 03:07 | Greenard, Terry | 9/25/2019 | 9/25/2019 |  | 2635 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-18 07:08 | ANAND, S | 56-F-EU-V-190923-R1MDM001 |  | Yes | Y |  |  | Changes in Production after Cut-Off | R1 Script Created |  |  | 56-F-EU-V-190923-R1MDMV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56G101Z | Yes | UBE | 1278350 89975 | 89975, 1278738 | R1 |  |  | GSP: Address Book Batch Upload | PPD Passed |  |  | TRUE | H |  | MDM | MDM | Carlos | L2 Not required | Retrofit Not required |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-15 03:08 | Greenard, Terry | 9/25/2019 | 9/25/2019 |  | 2636 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-24 06:35 | ANAND, S | 56-F-EU-V-190612-S2MD027 |  | Yes |  |  |  | Changes in Production after Cut-Off | R1 Script created |  |  | 56-F-EU-V-190612-S2MDV027A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56GETPD54 | No | UBE | BXU545888 |  | R1 |  |  | GetPaid - Build file F56ARMST, F56ARTRA, F56AREXTI | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Vijey Sesha | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-15 03:08 | Greenard, Terry | 9/26/2019 | 9/25/2019 |  | 2637 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-03-10 04:39 | Joshi, Abhishek N | 56-F-EU-V-190530-S1FI020 |  | Yes | Y |  |  | Changes in Production after Cut-Off |  |  |  | 56-F-EU-V-190530-S1FI020A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56MJI01 | No | UBE |  |  | R1 |  | CRP | MILD JDE Integration RECON | L3 Pass |  |  | TRUE |  |  | Finance AP | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-15 03:09 | Greenard, Terry | 9/25/2019 | 9/24/2019 |  | 2638 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2019-12-05 07:12 | Singh, Sunil Kumar | 56-F-EU-V-190919-R1FI002 |  | Yes | Y |  |  | Changes in Production after Cut-Off |  |  |  | 56-F-EU-V-190919-R1FIV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56P03B1 | No | UBE | BXU545763 |  | R1 |  | CRP | VAT Sales Register - POL - 56 | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Ravi Thapa | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-15 03:17 | Greenard, Terry | 9/25/2019 | 9/24/2019 |  | 2639 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-03-11 11:01 | Joshi, Abhishek N | 56-F-EU-V-190813-S5FI050 |  | Yes | Y |  |  | Changes in Production after Cut-Off |  |  |  | 56-F-EU-V-190813-S5FIV050A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56SAB104X | No | UBE | BXU545417 | BXU547215 | R1 |  |  | SAB104 Shipped Not Invoiced OrderLines (FINANCE) - | L3 Pass |  |  | TRUE |  |  |  | OM | Rafal Molas | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-15 03:18 | Greenard, Terry | 9/24/2019 | 9/23/2019 |  | 2640 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-03-14 03:13 | Joshi, Abhishek N | 56-F-EU-V-190919-R1OM002 |  | Yes | Y |  |  | Changes in Production after Cut-Off |  |  |  | 56-F-EU-V-190919-R1OMV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56SLOG2 | Yes | UBE | BXU531854 (133080B) | BXU547397(133080B) | R1 |  |  | Serialisation Log Processor | PPD Passed |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Peter De Brouwer | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 03:20 | Greenard, Terry | 9/25/2019 | 9/25/2019 |  | 2641 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-05-26 07:50 | Singh, Sunil Kumar | 56-F-EU-V-190710-S3LO051 |  | Yes | Y |  |  | Move to CRP |  |  |  | 56-F-EU-V-190710-S3LOV051A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56SLOGE | No | UBE | BXU531854 (133080B) |  | R1 |  |  | Serialised Log Error Reporting | PPD Passed |  |  | TRUE | LNE2E |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 03:21 | Greenard, Terry | 9/25/2019 | 9/24/2019 |  | 2642 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-12 12:12 | Singh, Sunil Kumar | 56-F-EU-V-190924-R1LO001 |  | Yes | Y |  |  | Move to CRP |  |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56SLOGR | No | UBE | BXU531854 (133080B) | 133080B | R1 |  |  | Serialized UI Reporting | PPD Passed |  |  | TRUE | L |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 03:22 | Greenard, Terry | 9/25/2019 | 9/25/2019 |  | 2643 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-09 06:19 | Singh, Sunil Kumar | 56-F-EU-V-190924-R1LO002 |  | Yes | Y |  |  | Move to CRP |  |  |  | 56-F-EU-V-190924-R1LOV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56SLOGT | No | UBE | BXU531854 (133080B) | 133080B | 999 |  |  | Serialized UI Reporting | Obsolete |  |  | FALSE | L |  | Warehouse | Logistics |  | (Blank) |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-08-15 03:23 | Greenard, Terry |  |  |  | 2644 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-10 13:11 | Singh, Sunil Kumar | [6 empty] | Changes in Production after Cut-Off |  |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R57004051 | No | UBE | BXU546189 |  | R1 |  |  | A/R - A/P IVA Tax Report - Italy - Cust | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Lokesh Reddy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 03:23 | Greenard, Terry | 9/25/2019 | 9/24/2019 |  | 2645 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-03-10 04:54 | Joshi, Abhishek N | 56-F-EU-V-190723-S4FI020 |  | Yes | Y |  |  | Changes in Production after Cut-Off |  |  |  | 56-F-EU-V-190723-S4FIV020A,56-F-EU-V-190723-S4FIV020B,56-F-EU-V-190723-S4FIV020C,56-F-EU-V-190723-S4FIV020D | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5842520 | No | UBE | 1260383 (18020) |  | R1 |  |  | Print Pick Slips - Russia | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Rakesh Kumar | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 03:24 | Greenard, Terry | 9/25/2019 | 9/24/2019 |  | 2646 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-03 05:04 | Singh, Sunil Kumar | 56-F-EU-V-190612-S2LO079 |  | Yes | Y |  |  | Move to CRP |  |  |  | 56-F-EU-V-190612-S2LOV079A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5874R3030 | No | UBE | 1260383 (18020), BXU545276, BXU545805 |  | R1 |  |  | Print Invoice - Russia - SOP/AR | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Genevieve Deveen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 03:24 | Greenard, Terry | 9/25/2019 | 9/24/2019 |  | 2647 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-03-12 10:31 | Joshi, Abhishek N | 56-F-EU-V-190715-S3OM110 |  | Yes | Y |  |  | Changes in Production after Cut-Off |  |  |  | 56-F-EU-V-190715-S3OMV110A , 56-F-EU-V-190924-R1OMV008A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5874R3032 | No | UBE |  |  | R1 |  |  | Stock Delivery Note - Russia - SOP | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Puneet Sharma | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-15 03:25 | Greenard, Terry | 9/25/2019 | 9/24/2019 |  | 2648 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2019-10-16 04:28 | Destrebecq, Eric | 56-F-EU-V-190722-S4LO003 |  | Yes | Y |  |  | Changes in Production after Cut-Off |  |  |  | 56-F-EU-V-190722-S4LOV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R47031 | No | UBE |  |  | R1 |  |  | EDI Shipping Notice Edit/Create | PPD Passed |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-15 03:27 | Greenard, Terry | 9/23/2019 | 9/23/2019 |  | 2652 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2019-10-14 08:26 | Mughal, Abdul | 56-F-EU-V-190725-S4LO064 |  | Yes | Y |  |  | Move to CRP |  |  |  | 56-F-EU-V-190725-S4LOV064A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59RMCU4 | No | UBE |  |  | R1 |  |  | Sourcing - Advance Planning Systems (APS) Demantra | L3 Not Required |  |  | TRUE |  |  | Warehouse | Logistics |  | L2 Not required | 10/01 RK: As L3 not required, as per mail marked as L2 Not Required. |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-15 03:27 | Greenard, Terry | 9/25/2019 | 9/24/2019 |  | 2653 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2019-10-16 05:51 | Thippulla, sreekanth | 56-F-EU-V-190827-S5LO083 |  | Yes | Y |  |  | Changes in Production after Cut-Off NA for EMEA |  |  |  | N/A | TRUE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRAR24 | No | UBE | BXU548346 |  | R1 |  | CRP | Swiss VAT Reporting - Accounts Receivable | L3 Pass |  |  | TRUE | HNE2E |  | Finance GL | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-28 02:57 | Greenard, Terry | 9/24/2019 | 9/23/2019 |  | 2655 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 07:12 | Joshi, Abhishek N | 56-F-EU-V-190827-S6FI020 | Report | Yes | Y | [6 empty] | 56-F-EU-V-190827-S6FIV020A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649042C | No | UBE | BXU514348 (108075F) |  | R1 |  |  | 3PL Send Order | PPD Passed | 489 | closed | TRUE | HE2E |  | Warehouse | Logistics | TK | L2 Not required | 09/26 RK: As per todays mail " Retrofit Not Required" |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-28 02:57 | Greenard, Terry | 9/24/2019 | 9/24/2019 |  | 2656 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 04:31 | Singh, Sunil Kumar | 56-F-EU-V-190723-S4LO011 |  | Yes |  |  |  | Move to CRP |  |  |  | 56-F-EU-V-190723-S4LOV011A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649043C | No | UBE | BXU514348 (108075F) | BXU514437 (108075) | R1 |  |  | 3PL Outbound Order Processor | PPD Passed | 489 | closed | TRUE | HE2E |  | Warehouse | Logistics | TK | L2 Not required | 09/26 RK: As per todays mail " Retrofit Not Required" |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-28 02:58 | Greenard, Terry | 09/25/2019 | 09/23/2019 |  | 2657 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-05-26 08:43 | Singh, Sunil Kumar | 56-F-EU-V-190729-S4LO069 | Outbound | Yes |  |  |  | Move to CRP |  |  |  | 56-F-EU-V-190729-S4LOV069A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649044C | Yes | UBE | BXU514348 (108075F) |  | R1 |  |  | 3PL Ship Confirm Processor | PPD Passed | 489 | closed | TRUE | HE2E |  | Warehouse | Logistics | TK | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-28 02:58 | Greenard, Terry | 09/24/2019 | 09/23/2019 |  | 2658 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 04:34 | Singh, Sunil Kumar | 56-F-EU-V-190731-S4LO056 |  | Yes | Y |  |  | Move to CRP |  |  |  | 56-F-EU-V-190731-S4LOV056A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641030 | Yes | UBE | 1270145 |  | R1 |  |  | CLM Whse Receipt Processing | PPD Passed | 427 | WIP | TRUE | LE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-28 02:59 | Greenard, Terry | 9/27/2019 | 9/27/2019 |  | 2659 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-07 02:32 | Singh, Sunil Kumar | 56-F-EU-V-190520-S1LO060 |  | Yes | Y |  |  | Move to CRP |  |  |  | 56-F-EU-V-190520-S1LOV60A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564915 | Yes | APPL | BXU543060, 1247267 (20730), 1264519 (12127), 1240720 (15526) | 1241564 (12127), 1241121 (15526), 1250551 (20730) | R1 |  |  | Delete Order from Warehouse | L3 Pass | 383 | open | TRUE | MNE2E |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-28 02:59 | Greenard, Terry | 20/09/2019 | 19/09/2019 |  | 2660 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 08:38 | ANAND, S | 56-F-EU-V-190521-S1LO035 |  | Yes | Y |  |  | Retrofit Completed. |  |  |  | 56-F-EU-V-190521-S1LOV35A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564915A | Yes | APPL | 1240719 (16244), BXU546752 (21933), 1251776 (23552) BXU545847 | 1264176, 1241778 (16244), BXU531175 (21933), 1251777 (23552), BXU547514 (25713) 27071 | R1 |  |  | Work with Shipments - Baxter EMEA | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-28 03:00 | Greenard, Terry | 09/20/2019 | 09/19/2019 |  | 2661 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 06:31 | Vishnubhatla, Mithra | 56-F-EU-V-190515-S1LO012 |  | Yes | Y | [6 empty] | 56-F-EU-V-190515-S1LOV12A , 56-F-EU-V-190515-S1LOV12B,56-F-EU-V-190923-R1LOV012A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P41280 | Yes | APPL |  |  | CC64 |  |  | Lot Master Availability | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | John Whalley | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-28 12:12 | Greenard, Terry |  |  |  | 2664 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-19 06:05 | Whalley, John |  |  |  | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P38010 | No | APPL | BXU545418 | BXU547085, BXU547090 | CC64 |  |  | Agreement Master | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | John Whalley | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-28 12:17 | Greenard, Terry |  |  |  | 2665 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 03:09 | Joshi, Abhishek N |  |  |  | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P43214 | Yes | APPL |  |  | CC64 |  |  | Purchase Receipts Inquiry | L3 Pass |  |  | TRUE | H |  | Procurement | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-28 12:18 | Greenard, Terry | 9/4/2019 | 9/3/2019 |  | 2666 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-17 11:44 | Mughal, Abdul | 56-F-EU-V-190612-S2LO073 |  | Yes | Y | [6 empty] | 56-F-EU-V-190612-S2LO073A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P38011 | No | APPL | BXU545418 | BXU547085 | CC64 |  |  | Agreement Quantities | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Rafal Molas | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-28 12:18 | Greenard, Terry |  |  |  | 2667 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 03:09 | Joshi, Abhishek N |  |  |  | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P41024 | Yes | APPL | 1264895 | BXU548196 | CC64 |  |  | Location Revisions | L3 Pass |  |  | TRUE | H |  | Quality | Logistics | Pawel Oskroba | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-28 12:19 | Greenard, Terry | 9/4/2019 | 9/4/2019 |  | 2668 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-27 02:07 | Singh, Sunil Kumar | 56-F-EU-V-190514-S1LO002 |  | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P43253 | Yes | APPL |  | BXU537484, 1242970, BXU549773 (18513) | CC64 |  |  | Routing Disposition | L3 Pass |  |  | TRUE | L |  | Procurement | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-28 12:19 | Greenard, Terry | 9/4/2019 | 9/3/2019 |  | 2669 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 07:30 | Singh, Sunil Kumar | 56-F-EU-V-190701-S3LO011 |  | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P41026 | Yes | APPL | BXU544673 | BXU547541, 1241362 (16342) | CC64 |  |  | Item Branch | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | Baxter Customisations not retrofitted in DV92064 as in UT920 | Tankut Cizmeci |  | Item |  | 2019-08-28 12:20 | Greenard, Terry | 9/4/2019 | 9/3/2019 |  | 2670 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-29 23:58 | Singh, Sunil Kumar | 56-F-EU-V-190510-S1MD005 |  | Yes | Y | [6 empty] | 56-F-EU-V-190510-S1MDV005A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4114 | Yes | APPL |  |  | CC64 |  |  | Inventory Adjustments | L3 Pass |  |  | TRUE | H |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | DV92064 has code discrepancies with UT920 and DV920 | Nikit Sharma |  | Item |  | 2019-08-28 12:20 | Greenard, Terry | 9/2/2019 | 9/1/2019 |  | 2671 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-17 11:27 | Mughal, Abdul | 56-F-EU-V-190514-S1WD001 |  | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4113 | Yes | APPL |  |  | CC64 |  |  | Inventory Transfers | L3 Pass |  |  | TRUE | H |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-28 12:21 | Greenard, Terry | 9/3/2019 | 9/2/2019 |  | 2672 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-17 11:12 | Mughal, Abdul | 56-F-EU-V-190514-S1LO009 |  | Yes | Y | [6 empty] | 56-F-EU-V-190514-S1LOV09A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4112 | Yes | APPL |  |  | CC64 |  |  | Inventory Issues | L3 Pass |  |  | TRUE | H |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Tankut Cizmeci |  | Item |  | 2019-08-28 12:21 | Greenard, Terry | 9/3/2019 | 9/3/2019 |  | 2673 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-19 05:50 | Mughal, Abdul | 56-F-EU-V-190510-S1LO001 |  | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P03B102 | No | APPL | BXU547057 |  | CC64 |  |  | Standard Receipt Entry | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | DV92064 has code discrepancies with UT920 and DV920 | Nikit Sharma |  | Item |  | 2019-08-28 12:22 | Greenard, Terry | 9/5/2019 | 9/3/2019 |  | 2674 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 08:47 | Joshi, Abhishek N | 56-F-EU-V-190612-S2FI001 |  | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P31114 | Yes | APPL | 1260283 | 1268370 | CC64 |  |  | Work Order Completions | L3 Pass | 340 | Closed | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-28 12:22 | Greenard, Terry | 9/5/2019 | 9/4/2019 |  | 2675 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-24 04:31 | Singh, Sunil Kumar | 56-F-EU-V-190611-S2LO062 |  | Yes | Y | [6 empty] | 56-F-EU-V-190611-S2LOV062A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P03013 | Yes | APPL | 1255078 (24459), BXU544578 (21524) | 1255083 (24459), BXU545131 | CC64 |  |  | Customer Master | L3 Pass |  |  | TRUE | H |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-28 12:25 | Greenard, Terry | 9/2/2019 | 8/30/2019 |  | 2676 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-12 13:51 | Singh, Sunil Kumar | 56-F-EU-V-190517-S1MD037 |  | Yes | Y | [6 empty] | 56-F-EU-V-190517-S1MDV037A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P03B571 | No | APPL | BXU547417 |  | CC64 |  |  | Automatic Debit Batches | L3 Not Required |  |  | TRUE | HNE2E |  | Finance AR | Finance | Francisco Alvargonzalez | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | VV-01/10 - Object will be tested in CRP as per the confirmation from Luigi and Francisco | Nikit Sharma |  | Item |  | 2019-08-28 12:26 | Greenard, Terry |  |  |  | 2677 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 08:52 | Joshi, Abhishek N | 56-F-EU-V-190617-S2FI046 |  | Yes | Y |  |  | To be tested in CRP |  |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P400511 | Yes | APPL |  | BXU544710 | CC64 |  |  | Return Material Authorization Revisions | L3 Not Required |  |  | TRUE |  |  | Warehouse | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma | DV92064 has code discrepancies with UT920 and DV920 | Nikit Sharma |  | Item |  | 2019-08-28 12:26 | Greenard, Terry | 9/5/2019 | 9/3/2019 |  | 2678 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-09 06:10 | Singh, Sunil Kumar | 56-F-EU-V-190708-S3LO042 |  | Yes | Y |  |  | On Hold N/A for EMEA |  |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4205 | Yes | APPL | 1235608 | 1235888, 1276008 | CC64 |  |  |  | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-28 12:27 | Greenard, Terry | 9/5/2019 | 9/5/2019 |  | 2679 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-27 02:11 | Singh, Sunil Kumar | 56-F-EU-V-190612-S2LO074 |  | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P43070 | Yes | APPL | BXU545405 (9876) | 25921, BXU546472, BXU546469, BXU547849 | CC64 |  |  | Held Order Release | L3 Pass |  |  | TRUE | HNE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-28 12:27 | Greenard, Terry | 9/5/2019 | 9/4/2019 |  | 2680 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-18 07:04 | ANAND, S | 56-F-EU-V-190618-S2OM037 |  | Yes | Y | [6 empty] | 56-F-EU-V-190618-S2OMV037A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P42101 | Yes | APPL |  |  | CC64 |  |  | Sales Order Entry | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-28 12:28 | Greenard, Terry |  |  |  | 2681 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-10-04 01:36 | Kamatham, Deepika |  |  |  | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P421007 | No | APPL |  |  | CC64 |  |  | Sales Order Header Reusable Subform | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Jaisingh Jaiswar | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | UT920 and DV92064 BSFN Parameter Mismatch | Nikit Sharma |  | Item |  | 2019-08-28 12:28 | Greenard, Terry | 9/10/2019 | 9/9/2019 |  | 2682 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-26 08:11 | Jaiswar, Jaisingh | 56-F-EU-V-190612-S2OM024 |  | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P421002 | Yes | APPL |  |  | CC64 |  |  | Sales Order Detail Reusable Subform | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Jaisingh Jaiswar | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | DV92064 has code discrepancies with UT920 and DV920 | Nikit Sharma |  | Item |  | 2019-08-28 12:29 | Greenard, Terry | 9/10/2019 | 9/8/2019 |  | 2683 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-26 08:12 | Jaiswar, Jaisingh | 56-F-EU-V-190531-S2OM001 |  | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4210 | Yes | APPL | BXU545444 (60558), 1222473 (11402) | 1276496 (60558),1263371 (4099), BXU545241 (11402) | CC64 |  |  | Sales Order Entry | L3 Pass |  |  | TRUE | HE2E |  | Order Management | OM | Seputyte Lina | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-28 12:29 | Greenard, Terry | 9/9/2019 | 9/7/2019 |  | 2684 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-07-24 05:36 | Singh, Sunil Kumar | 56-F-EU-V-190522-S1OM042 |  | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P03B121 | No | APPL | BXU547222 |  | CC64 |  | CRP | Work With Electronic Receipts Input | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-28 12:30 | Greenard, Terry | 9/11/2019 | 9/8/2019 |  | 2685 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-04-01 04:36 | Joshi, Abhishek N | 56-F-EU-V-190613-S2FI039 |  | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P47070 | Yes | APPL | 1267636 (19294), BXU545170 (20682) | 1267640, BXU544769 | CC64 |  |  | Inbound EDI Receiving Advice Inquiry | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-28 12:30 | Greenard, Terry |  |  |  | 2686 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 07:37 | Singh, Sunil Kumar | 56-F-EU-V-190612-S2LO001 |  | Yes | Y | [6 empty] | 56-F-EU-V-190612-S2LO001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P43250 | Yes | APPL |  | BXU545767, 1235851 | CC64 |  |  | Receipt Routing Movement and Disposition | L3 Pass | 331 | Open | TRUE | HE2E |  | Procurement | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-28 12:31 | Greenard, Terry | 9/9/2019 | 9/9/2019 |  | 2687 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-05 02:59 | Joshi, Abhishek N | 56- F-EU-V-190618-S2LO109 |  | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4314 | No | APPL |  |  | CC64 |  | CRP | Voucher Match | L3 Pass | 357 | Closed | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete | Defect 357 has been raised and Technical team is working on the same |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-28 12:31 | Greenard, Terry |  |  |  | 2688 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-09 02:28 | Bodin, Fatiha | 56-F-EU-V-190508-S2FI001 |  | Yes | Y | [6 empty] | 56-F-EU-V-190508-S2FIV01A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4312 | No | APPL | BXU545508 | BXU537484 | CC64 |  |  | PO Receipts | L3 Pass |  |  | TRUE | HE2E |  | Procurement | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-28 12:32 | Greenard, Terry | 9/9/2019 | 9/9/2019 |  | 2689 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-27 03:03 | Singh, Sunil Kumar | 56-F-EU-V-190614-S2LO090 |  | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P42053 | Yes | APPL |  |  | CC64 |  |  | Select Multiple Locations | L3 Pass |  |  | TRUE | L |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-28 12:32 | Greenard, Terry |  |  |  | 2690 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-17 06:57 | Mughal, Abdul |  |  |  | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4310 | Yes | APPL |  |  | CC64 |  |  | Purchase Orders Defect 338: Errors when adding a line level details. 26.09 - Defect fixed and re-test passed. | L3 Pass | 338 | Open | TRUE | HE2E |  | Procurement | Logistics | Aki Partanen | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | DV92064 has code discrepancies with UT920 and DV920 | Nikit Sharma |  | Item |  | 2019-08-28 12:33 | Greenard, Terry | 9/11/2019 | 9/11/2019 |  | 2691 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-26 03:40 | Partanen, Aki | 56-F-EU-V-190605-S2LO001 |  | Yes | Y | [6 empty] | 56-F-EU-V-190605-S2LO001A, 56-F-EU-V-190605-S2LO001B, 56-F-EU-V-190605-S2LO001C, 56-F-EU-V-190605-S2LO001D | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4915 | Yes | APPL |  |  | CC64 |  |  | Work with Shipments | L3 Pass |  |  | TRUE | HE2E |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-28 12:33 | Greenard, Terry |  |  |  | 2692 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-16 05:01 | Destrebecq, Eric |  |  |  | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R4311Z1I | Yes | UBE | 1260788 (3411), BXU544569 (RE83933) | BXU546900 (83933) | CC64 |  |  | PO Unedited Transaction Inbound Processor | L3 Pass |  |  | TRUE | HE2E |  | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | DV92064 has code discrepancies with UT920 and DV920 | Nikit Sharma |  | Item |  | 2019-08-28 12:34 | Greenard, Terry | 9/12/2019 | 9/10/2019 |  | 2693 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 06:15 | ANAND, S | 56-F-EU-V-190701-S4LO038 |  | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R12800 | No | UBE | BXU551113 |  | CC64 |  | CRP | Post G/L Entries to Assets | L3 Pass |  |  | TRUE | HNE2E |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-28 12:34 | Greenard, Terry | 9/12/2019 | 9/12/2019 |  | 2694 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-04-02 05:53 | Joshi, Abhishek N | 56-F-EU-V-190624-S2FI129 |  | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R04570 | No | UBE | BXU547238 |  | CC64 |  | CRP | Create Payment Control Groups | L3 Pass |  |  | TRUE | HNE2E |  | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-28 12:35 | Greenard, Terry | 9/12/2019 | 9/11/2019 |  | 2695 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-06 05:52 | Joshi, Abhishek N | 56-F-EU-V-190624-S3FI004 |  | Yes | Y | [6 empty] | 56-F-EU-V-190624-S3FIV04A,56-F-EU-V-190624-S3FIV04B,56-F-EU-V-190624-S3FIV04C,56-F-EU-V-190624-S3FIV04D,56-F-EU-V-190624-S3FIV04E | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R42565 | No | UBE |  |  | CC64 |  |  | Print Invoices | L3 Pass | 324 | Fixed 17 Sept in UT 64, works OK now | TRUE | HE2E |  | Order Management | OM | Rafal Molas | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-28 12:35 | Greenard, Terry | 9/12/2019 | 9/11/2019 |  | 2696 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-09-17 10:34 | MOLAS, RAFAL | 56-F-EU-V-190709-S3OM032 |  | Yes | Y | [6 empty] | 6-F-EU-V-190709-S3OMV32A to 56-F-EU-V-190709-S3OMV32Z,56-F-EU-V-190709-S3OMV32AA to 56-F-EU-V-190709-S3OMV32AZ and 56-F-EU-V-190709-S3OMV32BA to 56-F-EU-V-190709-S3OMV32BN | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R03B551 | No | UBE | BXU548273 |  | CC64 |  | CRP | Update Receipts Header | L3 Pass |  |  | TRUE | HNE2E |  | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-28 12:36 | Greenard, Terry | 9/6/2019 | 9/6/2019 |  | 2697 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-05 06:19 | Joshi, Abhishek N | 56-F-EU-V-190617-S2FI045 |  | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R11414A | no | UBE | BXU547045 |  | R3 |  |  | Currency Restatement Compute and Print | L3 Pass |  |  | TRUE | HNE2E | TRUE | Finance GL | Finance | Joanne Byrne | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-08-28 12:36 | Greenard, Terry | 23/10/2019 | 23/10/2019 |  | 2698 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-05 06:22 | Joshi, Abhishek N | 56-F-EU-V-190617-S2FI048_01 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R47071 | No | UBE | BXU544569 (83933) | BXU547743 | CC64 |  |  | EDI Receiving Advice Edit/Create - Purchasing | L3 Pass | 333 | Closed | TRUE | HE2E |  | Procurement | Logistics | Mandy Corbett | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-08-28 12:37 | Greenard, Terry | 9/6/2019 | 9/3/2019 |  | 2699 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-07-24 03:34 | Singh, Sunil Kumar | 56-F-EU-V-190515-S1LO030 |  | Yes | Y | [6 empty] | 56-F-EU-V-190515-S1LOV30A, 56-F-EU-V-190515-S1LOV30B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P560000T | No | APPL | BXU545283 | BXU547532 | 6 |  |  | Launch iframe Applications | L3 Not Required |  |  | TRUE |  |  | Order Management | OM |  | L2 Not required | 09/11 RK: As per attached mail, marked L2 Not Required |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-09-03 05:45 | Verma, Vikas | 9/5/2019 | 9/3/2019 |  | 2700 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 04:47 | Joshi, Abhishek N | 56-F-EU-V-190903-S6OM007 |  | Yes | Y | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5748014 | No | APPL |  |  | 999 |  |  | Project Task Details 57 | Obsolete |  |  | TRUE |  | FALSE | Finance FA | Finance | Libor Slaby | L2 Not required | Waiting for test script |  |  | Terry Greenard / Vikas Verma | VV-23/09 - Obsoleted as per Joanne's request | Bargavi |  | Item |  | 2019-09-06 01:55 | Verma, Vikas | 9/11/2019 | 9/10/2019 |  | 2701 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 21:13 | Waishampayan, Meghanad | 56-F-EU-V-190910-S6FI154 |  | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P560411 | No | APPL |  |  | 999 |  |  | Baxter Specific P0411 A/P Standard Voucher Entry called by P560411A | Obsolete | 349 | Open | TRUE | MNE2E |  | Finance AP | Finance | Seray Golge | L2 Pass / Complete |  |  |  | Terry Greenard/Vikas Verma | PG 10/10: This application was retrofitted to 9.2 and promoted to PPD. However the users have now confirmed that it is not used and not required in production. | Tankut Cizmeci |  | Item |  | 2019-09-09 05:06 | Gilthorpe, Peter | 9/11/2019 | 9/10/2019 |  | 2702 |  | 0 |  |  |  | 2019-10-10 02:36 | Gilthorpe, Peter | 56-F-EU-V-190909-S6FI148 |  | Yes | Y |  |  | Object called by P560411A and has validation erros same like DV812 |  |  |  | 56-F-EU-V-190909-S6FI148A,56-F-EU-V-190909-S6FI148B | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0249 | Obsolete | UBE |  |  | 999 |  |  | Distributor Credit Price Calc UBE | Obsolete |  |  | TRUE |  |  |  | Logistics |  | (Blank) |  |  |  | Terry Greenard / Vikas Verma | VV-12/09 - Obsoleted the object as it not used in 812 | Sreekanth Thippulla |  | Item |  | 2019-09-11 00:30 | Verma, Vikas | 9/12/2019 | 9/11/2019 |  | 2703 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:38 | Mohammed, Saleem | 56-F-EU-V-190911-S6OM014 |  | Yes | Yes |  |  | 9/12 KP:As a part of 64bit retrofit object failed to validate due to BLC BSFN hence rewrite the BSFN code. |  |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5612006 | No | UBE | BXU547428 |  | R1 |  | CRP | Asset revaluation indexes Application | L3 Pass |  |  | TRUE |  |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-09-15 23:57 | Verma, Vikas | 9/23/2019 | 9/23/2019 |  | 2705 |  | 0 |  |  |  | 2020-03-06 23:27 | Joshi, Abhishek N | 56-F-EU-V-190814-S5FI074 |  | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5612006R | No | UBE | BXU545942 |  | R1 |  | CRP | Asset Revaluation insurance extract Report | L3 Pass |  |  | TRUE |  |  | Finance FA | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-09-16 00:01 | Verma, Vikas | 9/27/2019 | 9/26/2019 |  | 2706 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 04:51 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI027 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5641005 | Yes | APPL | 1250897 (22485) | 1250898, 1258829, 1242681, 1266997 (11226), 1244875 (19727) | R1 |  |  | Inventory Transaction Processor | L3 Not Required |  |  | TRUE |  |  | Warehouse | Logistics | Leonard Dartois | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-09-16 00:03 | Verma, Vikas | 23/09/2019 | 20/09/2019 |  | 2707 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 08:27 | Singh, Sunil Kumar | 56-F-EU-V-190523-S1LO099 |  | Yes | Y |  |  | Move to CRP |  |  |  | 56-F-EU-V-190523-S1LOV99A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643008CR | No | UBE | BXU550203 |  | R1 |  |  | Count Sheet - Customer Returns | L3 Not Required |  |  | TRUE |  |  | Warehouse | Logistics | Aki Partanen/Swetha | L2 Not required | 10/15 RK: As L3 Not required, L2 also not required decided in todays scrum call & Aki's mail" as there are changes pending for it in PROD." |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-09-16 00:08 | Verma, Vikas | 9/27/2019 | 9/26/2019 |  | 2708 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-04-16 07:27 | Greenard, Terry | 56-F-EU-V-190919-R1LO004 |  | Yes | Y |  |  | to be tested in R3 sprint |  |  |  | 56-F-EU-V-190919-R1LOV004A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R47011 | No | UBE |  |  | R1 |  |  | EDI Inbound Purchase Order Edit/Create | L3 Not Required |  |  | TRUE |  |  | EDI Order Management | eCommerce | Aidan Scally | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-09-16 00:10 | Verma, Vikas | 9/27/2019 | 9/26/2019 |  | 2709 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:03 | Mohammed, Saleem | 56-F-EU-V-190516-S1ED002 |  | Yes | Y |  |  | Testing to be done in CRP / UAT / OQ |  |  |  | 56-F-EU-V-190516-S1EDV02A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL42535 | No | UBE | 1267798 (26162 |  | R1 |  |  | Delivery Note - Poland | L3 Pass |  |  | TRUE |  |  | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-09-16 00:15 | Verma, Vikas | 9/26/2019 | 9/25/2019 |  | 2710 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 06:13 | Singh, Sunil Kumar | 56-F-EU-V-190725-S4LO060 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56ND42535 | No | UBE | 1241414 (17921 |  | R1 |  |  | Delivery Note Nordics | L3 Pass |  |  | TRUE |  |  | Transportation | Logistics | Eric Destrebecq | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-09-16 00:18 | Verma, Vikas | 9/27/2019 | 9/26/2019 |  | 2711 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-02 13:25 | Singh, Sunil Kumar | 56-F-EU-V-190731-S4LO087 |  | Yes | Y | [6 empty] | 56-F-EU-V-190731-S4LOV087A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R74R9018 | No | UBE | BXU551103 |  | 6 |  | CRP | Russian Tax File Maintenance G/L - RUS - 09 - 74R | L3 Pass |  |  | TRUE |  |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-09-16 03:07 | Verma, Vikas | 9/17/2019 | 9/16/2019 |  | 2712 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-04-02 06:58 | Joshi, Abhishek N | 56-F-EU-V-190916-S6FI157 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5640ITM | Obsolete | APPL |  |  | 999 |  |  | Item Search Returns Quantity | Obsolete |  |  | FALSE |  |  | Warehouse | Logistics | Abdul Mughal | L2 Not required | 10/04 RK: As yesterday this object marked as Retrofit Not Required, marking as L2 Not Required. |  |  | Terry Greenard / Vikas Verma | VV-08/10 - Obsoleted the object as it was already included in Sprint1 and has not code changes | Nikit Sharma |  | Item |  | 2019-09-20 05:03 | Verma, Vikas | 9/27/2019 | 9/26/2019 |  | 2713 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:38 | Mohammed, Saleem | 56-F-EU-V-190515-S1LO033 |  | Yes |  |  |  | Move to CRP |  |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R590401 | No | UBE |  |  | R1 |  |  | MILD Vendor Interface | PPD Passed |  |  | TRUE |  |  | MDM | MDM | Tom Hoste | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-09-20 05:06 | Verma, Vikas | 09/27/2019 | 09/26/2019 |  | 2714 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-04-16 07:26 | Greenard, Terry | 56-F-EU-V-190625-S2MD001 |  | Yes | Y | [6 empty] | 56-F-EU-V-190625-S2MDV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642047 | Obsolete | UBE | BXU549678 |  | 999 |  |  | OWC Item & Costs Integrity Report | Obsolete |  |  | FALSE |  |  | Order Management | OM | John Whalley | L2 Not required | JW - 03/10/19: Object Tracker entry obsolete because a duplicate of Tracker ID 1463Object not working in 8.12, Confirmed by Terry, L2 not required |  |  | Terry Greenard / Vikas Verma |  | Nikit Sharma |  | Item |  | 2019-09-20 05:08 | Verma, Vikas | 9/27/2019 | 9/27/2019 |  | 2715 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 02:13 | Joshi, Abhishek N | 56-F-EU-V-190711-S3AR120 |  | Yes | [7 empty] | 56-F-EU-V-190711-S3ARV120A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649019 | No | UBE |  |  | R1 |  |  | FCA Freight Expense Report | L3 Pass |  |  | TRUE |  |  | Transportation | Logistics | Puneet Sharma | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-09-20 05:12 | Verma, Vikas | 9/27/2019 | 9/26/2019 |  | 2716 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:04 | Mohammed, Saleem | 56-F-EU-V-190725-S4LO053 |  | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P74R0018 | No | APPL | BXU551104 |  | 6 |  | CRP | Working with Russian Tax File - 74R | L3 Pass |  |  | TRUE |  |  | Localization | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-09-27 05:05 | Verma, Vikas | 9/27/2019 | 9/27/2019 |  | 2717 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-04-02 07:01 | Joshi, Abhishek N | 56-F-EU-V-190926-S6FI001 |  | Yes | [7 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900122 | No | APPL |  |  | R1 |  |  | S29 Compliance Information | L3 Not Required |  |  | TRUE |  |  | Order Management | OM |  | L2 Not required | 10/04 RK: As per Piets mail, marked as L2 Not Required. |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-10-02 03:36 | Greenard, Terry | 10/4/2019 | 10/3/2019 |  | 2718 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:04 | Mohammed, Saleem | 56-F-EU-V-191004-R1OM018 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5709200 | No | APPL | BXU551579 |  | R1 |  | CRP | Account Ledger Inquiry | L3 Pass |  |  | TRUE |  |  | Finance GL | Finance | Greg Felitto | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-10-11 08:35 | Verma, Vikas | 10/14/2019 | 10/14/2019 |  | 2719 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-04-06 09:02 | Joshi, Abhishek N | 56-F-EU-V-191014-R1FI012 |  | Yes | [7 empty] | 56-F-EU-V-191014-R1FIV012A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P58MSQ02 | No | APPL |  |  | R1 |  |  | Selling / Purchasing Quantity(S) - E812 | L3 Not Required |  |  | TRUE |  |  | Order Management | OM | Deepika | L2 Not required | 10/16 RK: As per Vikas mail, marked as L2 not required & willbe tested in CRP. |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-10-15 10:47 | Verma, Vikas |  |  |  | 2720 |  | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-04 09:05 | Javadi, Vinod | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641081 | Obsolete | UBE |  |  | 999 |  |  | Move Ticket for Lot Status Change | Obsolete |  |  | FALSE |  |  | Warehouse | Logistics |  | (Blank) |  |  |  | Terry Greenard / Vikas Verma | VV-30/10 Obsoleted as it was found in PD full build log as dependency. It was agreed with Terry and BSL that these objects will be obsoleted and call to these will be commented in calling objects |  |  | Item |  | 2019-10-16 06:38 | Verma, Vikas |  |  |  | 2721 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:39 | Mohammed, Saleem | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642020 | Obsolete | UBE |  |  | 999 |  |  | Sample Order Creation Driver UBE | Obsolete |  |  | FALSE |  |  | Order Management | OM |  | (Blank) |  |  |  | Terry Greenard / Vikas Verma | VV-30/10 Obsoleted as it was found in PD full build log as dependency. It was agreed with Terry and BSL that these objects will be obsoleted and call to these will be commented in calling objects |  |  | Item |  | 2019-10-16 06:39 | Verma, Vikas |  |  |  | 2722 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:39 | Mohammed, Saleem | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58IN010F | Obsolete | UBE |  |  | 999 |  |  | Edelivery - Medico | Obsolete |  |  | FALSE |  |  | Warehouse | Logistics |  | (Blank) |  |  |  | Terry Greenard / Vikas Verma | VV:03/11 Obsoleted the object as per confirmation from Leo |  |  | Item |  | 2019-10-16 06:39 | Verma, Vikas |  |  |  | 2723 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:39 | Mohammed, Saleem | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649011 | Obsolete | UBE |  |  | 999 |  |  | Buytrago Label Print File UBE | Obsolete |  |  | FALSE |  |  | Warehouse | Logistics |  | (Blank) |  |  |  | Terry Greenard / Vikas Verma | VV-30/10 Obsoleted as it was found in PD full build log as dependency. It was agreed with Terry and BSL that these objects will be obsoleted and call to these will be commented in calling objects |  |  | Item |  | 2019-10-16 06:39 | Verma, Vikas |  |  |  | 2724 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:39 | Mohammed, Saleem | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58IN010E | Obsolete | UBE |  |  | 999 |  |  | Edelivery - Defis | Obsolete |  |  | FALSE |  |  | Warehouse | Logistics |  | (Blank) |  |  |  | Terry Greenard / Vikas Verma | VV:03/11 Obsoleted the object as per confirmation from Leo |  |  | Item |  | 2019-10-16 06:39 | Verma, Vikas |  |  |  | 2725 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:39 | Mohammed, Saleem | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58IN010D | Obsolete | UBE |  |  | 999 |  |  | Edelivery - Pharmdata | Obsolete |  |  | FALSE |  |  | Warehouse | Logistics |  | (Blank) |  |  |  | Terry Greenard / Vikas Verma | VV:03/11 Obsoleted the object as per confirmation from Leo |  |  | Item |  | 2019-10-16 06:40 | Verma, Vikas |  |  |  | 2726 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:39 | Mohammed, Saleem | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58IN010C | Obsolete | UBE |  |  | 999 |  |  | Edelivery - Lekis | Obsolete |  |  | FALSE |  |  | Warehouse | Logistics |  | (Blank) |  |  |  | Terry Greenard / Vikas Verma | VV:03/11 Obsoleted the object as per confirmation from Leo |  |  | Item |  | 2019-10-16 06:40 | Verma, Vikas |  |  |  | 2727 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:39 | Mohammed, Saleem | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58IN010B | Obsolete | UBE |  |  | 999 |  |  | Edelivery - Pentenium | Obsolete |  |  | FALSE |  |  | Warehouse | Logistics |  | (Blank) |  |  |  | Terry Greenard / Vikas Verma | VV:03/11 Obsoleted the object as per confirmation from Leo |  |  | Item |  | 2019-10-16 06:40 | Verma, Vikas |  |  |  | 2728 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:39 | Mohammed, Saleem | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58IN010A | Obsolete | UBE |  |  | 999 |  |  | Edelivery - Mediox | Obsolete |  |  | FALSE |  |  | Warehouse | Logistics |  | (Blank) |  |  |  | Terry Greenard / Vikas Verma | VV:03/11 Obsoleted the object as per confirmation from Leo |  |  | Item |  | 2019-10-16 06:40 | Verma, Vikas |  |  |  | 2729 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:39 | Mohammed, Saleem | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0185 | Obsolete | UBE |  |  | 999 |  |  | Transport Expiration and Time Limit | Obsolete |  |  | FALSE |  |  | Warehouse | Logistics |  | (Blank) |  |  |  | Terry Greenard / Vikas Verma | VV-30/10 Obsoleted as it was found in PD full build log as dependency. It was agreed with Terry and BSL that these objects will be obsoleted and call to these will be commented in calling objects |  |  | Item |  | 2019-10-16 06:40 | Verma, Vikas |  |  |  | 2730 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:39 | Mohammed, Saleem | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5942521B | Obsolete | UBE |  |  | 999 |  |  | Print Pick/Pack Slip by Shipment | Obsolete |  |  | FALSE |  |  | Warehouse | Logistics |  | (Blank) |  |  |  | Terry Greenard / Vikas Verma | VV-30/10 Obsoleted as it was found in PD full build log as dependency. It was agreed with Terry and BSL that these objects will be obsoleted and call to these will be commented in calling objects |  |  | Item |  | 2019-10-16 06:40 | Verma, Vikas |  |  |  | 2731 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:39 | Mohammed, Saleem | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5949140 | Obsolete | UBE |  |  | 999 |  |  | Print Shipping/ASN Labels | Obsolete |  |  | FALSE |  |  | Warehouse | Logistics |  | (Blank) |  |  |  | Terry Greenard / Vikas Verma | VV-30/10 Obsoleted as it was found in PD full build log as dependency. It was agreed with Terry and BSL that these objects will be obsoleted and call to these will be commented in calling objects |  |  | Item |  | 2019-10-16 06:40 | Verma, Vikas | 10/29/2019 | 10/29/2019 |  | 2732 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:39 | Mohammed, Saleem | 56-F-EU-V-191024-R2LO009 | [9 empty] | 56-F-EU-V-191024-R2LOV009A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564121Z2 | Obsolete | UBE |  |  | 999 |  |  | Load Stock Quantity details from WCS and JDE into F5641021 | Obsolete |  |  | FALSE |  |  | Warehouse | Logistics |  | (Blank) |  |  |  | Terry Greenard / Vikas Verma | VV-30/10 Obsoleted as it was found in PD full build log as dependency. It was agreed with Terry and BSL that these objects will be obsoleted and call to these will be commented in calling objects |  |  | Item |  | 2019-10-16 06:40 | Verma, Vikas |  |  |  | 2733 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:39 | Mohammed, Saleem | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5712G87 | No | UBE |  |  | 999 |  |  | Batch Update of Fixed Asset Category Codes | Obsolete |  |  | FALSE |  |  | Fixed Assets | Finance | Libor Slaby | (Blank) |  |  |  | Terry Greenard / Vikas Verma |  | VV-30/10 Obsoleted as it was found in PD full build log as dependency. It was agreed with Terry and BSL that these objects will be obsoleted and call to these will be commented in calling objects |  | Item |  | 2019-10-16 06:40 | Verma, Vikas |  |  |  | 2735 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-12-05 07:12 | Singh, Sunil Kumar | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55PMIZ1I | Yes | UBE | 1240716 12821 | 12821 BXU548882 | 999 |  |  | QTS Interface Z-File Upload | Obsolete |  |  | TRUE |  | TRUE | QTS | Logistics |  | L2 Not required | 18/11 MW - confirmed by Fatiha email 18 Nov |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-10-16 06:41 | Verma, Vikas | 01/11/2019 | 31/10/2019 |  | 2737 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 08:38 | Vishnubhatla, Mithra | 56-F-EU-V-191101-R2LO012 |  | Yes | Yes | [6 empty] | 56-F-EU-V-191101-R2LOV012A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58IC300 | No | UBE | BXU545523 |  | R2 |  | CRP | PII report IC300 - Load from JDE to hyperion | L3 Pass | 637 | Closed | TRUE |  | TRUE | Finance GL | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | VV:08/11 Object moved to R2 from R3, As per request from Sandhya | Sreekanth Thippulla |  | Item |  | 2019-10-19 21:04 | Verma, Vikas | 9/25/2019 | 9/25/2019 |  | 2738 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 04:02 | Joshi, Abhishek N | 56-F-EU-V-190725-S4FI039_R2 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190725-S4FIV039A_R2 | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58IC300S | No | UBE | BXU545523 |  | R2 |  | CRP | PII report IC300 - Summary | L3 Pass |  |  | TRUE |  | TRUE | Finance GL | Finance | Libor Slaby | L2 Pass / Complete | R58IC300 calls object R58IC300S |  |  | Terry Greenard / Vikas Verma | VV:08/11 Object moved to R2 from R3, As per request from Sandhya | Sreekanth Thippulla |  | Item |  | 2019-10-19 21:04 | Verma, Vikas | 30/10/2019 | 29/10/2019 |  | 2739 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 08:59 | Joshi, Abhishek N | 56-F-EU-V-190812-S5FI023_R2 |  | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564217M | No | APPL |  |  | R2 |  |  | Uncommitted Order Release_Multiple Records | L3 Not Required |  |  | TRUE |  | TRUE | Order Management | OM | Venkateswaran Murugesan | L2 Not required | 10/25 RK: As L3 Not Required & mail confirmation, marking as L2 Not Required. |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-10-19 21:04 | Verma, Vikas |  |  |  | 2740 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:05 | Mohammed, Saleem |  |  |  | Yes |  |  | DK: No changes in PD812 and DV920 code. no retrofit required in R2 |  |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560018X2 | No | UBE |  |  | R2 |  |  | Generate XML file for Customs Declaration | PPD Passed |  |  | TRUE |  | TRUE | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-10-19 21:05 | Verma, Vikas | 10/25/2019 | 10/24/2019 |  | 2741 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-12-02 05:19 | Singh, Sunil Kumar | 56-F-EU-V-190705-S3LO040_R2 |  | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560018Z1 | No | UBE |  |  | R2 |  |  | Generate Customs Data for Sales | PPD Passed |  |  | TRUE |  | TRUE | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-10-19 21:05 | Verma, Vikas | 10/31/2019 | 10/25/2019 |  | 2742 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:05 | Mohammed, Saleem | 56-F-EU-V-190709-S3LO084_R2 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190709-S3LOV084A_R2 | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564941C | No | UBE |  |  | R2 |  |  | LOAD LIST | L3 Not Required |  |  | TRUE |  | TRUE | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | L3 not required as object also in R3 | Sreekanth Thippulla |  | Item |  | 2019-10-19 21:05 | Verma, Vikas | 19/10/25 | 19/10/24 |  | 2743 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:05 | Mohammed, Saleem | 56-F-EU-V-190704-S3LO039_R2 |  | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564941H | No | UBE |  |  | R2 |  |  | LOAD LIST CSV | PPD Passed |  |  | TRUE |  | TRUE | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-10-19 21:05 | Verma, Vikas | 10/26/2019 | 10/25/2019 |  | 2744 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:06 | Mohammed, Saleem | 56-F-EU-V-191024-R2LO007 |  | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564915A | Yes | APPL | 1240719 (16244), BXU546752 (21933), 1251776 (23552) | 1264176, 1241778 (16244), BXU531175 (21933), 1251777 (23552), BXU547514 (25713) | R2 |  |  | Work with Shipments - Baxter EMEA | L3 Not Required |  |  | TRUE |  | TRUE | Transportation | Logistics | Albert Vila | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | L3 not required as object also in R3 | Sreekanth Thippulla |  | Item |  | 2019-10-19 21:05 | Verma, Vikas | 10/30/2019 | 10/29/2019 |  | 2745 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 09:31 | ANAND, S | 56-F-EU-V-190515-S1LO012_R2 |  | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5698167 | No | APPL | BXU550204 |  | R3 |  |  | Custom Printer Application | PPD Passed |  |  | TRUE |  | TRUE | Warehouse | Logistics | Albert Vila Léonard Dartois | L2 Pass / Complete | 11/08 RK: Waiting for input for L1. |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-10-19 21:05 | Verma, Vikas | 11/20/2019 | 11/19/2019 |  | 2746 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 02:08 | Joshi, Abhishek N | 56-F-EU-V-191030-R2LO036 |  | Yes | [7 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5645014 | No | UBE | BXU549674 |  | R2 |  |  | Service Billing with High VAT Rate | L3 Not Required |  |  | TRUE |  | TRUE | Order Management | OM | Venkateswaran Murugesan | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-10-19 21:05 | Verma, Vikas | 10/29/2019 | 10/25/2019 |  | 2748 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 02:34 | Joshi, Abhishek N | 56-F-EU-V-191024-R2OM002 |  | Yes | Yes | [6 empty] | 56-F-EU-V-191024-R2OMV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56SLOG2 | Yes | UBE | BXU531854 (133080B) | BXU547397(133080B) | R3 |  |  | Serialisation Log Processor | PPD Passed |  |  | TRUE |  | TRUE | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete | 11/08 RK: Waiting for input for L1. |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-10-19 21:05 | Verma, Vikas | 11/21/2019 | 11/21/2019 |  | 2749 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-05-26 07:50 | Singh, Sunil Kumar | 56-F-EU-V-190710-S3LO051_R2 |  | Yes | [8 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642520D | Yes | UBE | BXU546242 |  | R3 |  |  | Manual Warehouse Picklist GB | PPD Passed |  |  | TRUE |  | TRUE | Warehouse | Logistics | Albert Vila | L2 Pass / Complete | 11/08 RK: Waiting for input for L1 |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-10-19 21:05 | Verma, Vikas |  |  |  | 2750 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 05:21 | Joshi, Abhishek N | [10 empty] | 56-F-EU-V-190924-R1LOV003A_R3 | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56BH42535 | No | UBE | BXU531854 (133080B), BXU546242 (162784) | BXU542143 (162784) | R2 |  |  | Delivery Note -BH | PPD Passed |  |  | TRUE |  | TRUE | Transportation | Logistics | Albert Vila | L2 Not required | 11/05 RK: As per eric's mail, marked as L2 Not required. |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-10-19 21:06 | Verma, Vikas | 10/30/2019 | 10/28/2019 |  | 2751 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-13 07:36 | ANAND, S | 56-F-EU-V-190920-R1LO006_R2 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190920-R1LOV006A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5698003 | No | APPL | P5698003 |  | R3 |  |  | Integration User Profile Selection - Maintenance | PPD Passed |  |  | TRUE |  | TRUE | Procurement | Logistics | TK, Rajesh | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | VV:08/11 Object moved to R2 from R3, As per request from Sandhya | Sreekanth Thippulla |  | Item |  | 2019-10-21 10:39 | Verma, Vikas | 10/31/2019 | 10/30/2019 |  | 2752 |  | 0 |  |  |  | 2020-03-17 01:51 | Joshi, Abhishek N | 56-F-EU-V-191029-R2LO034 |  | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59TC0134 | No | UBE |  |  | R3 |  |  | Upload XLS Preferred Source plant in F59012 | PPD Passed |  |  | TRUE |  | TRUE | ECC | ARO | Ravi / Cosmin | L2 Not required | As per mail confirmation by Baxter SME, these object does not required L2 Testing |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-10-31 04:39 | Verma, Vikas | 11/21/19 | 11/20/19 |  | 2753 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-04 08:57 | Javadi, Vinod | 56-F-EU-V-191101-R3AR001 |  | Yes | [8 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5949645 | No | APPL |  |  | R3 |  |  | Transportation Shipment Confirmation | PPD Passed |  |  | TRUE |  | TRUE | Transportation | Logistics | Eric Destrebecq, Puneet Sharma, Scott Weber | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | VV:31/10 Object added to R3 as it was in sprint 1 but marked as "On Hold NA for EMEA", Albert confirmed that its needed in 9.2 | Sreekanth Thippulla |  | Item |  | 2019-10-31 09:14 | Verma, Vikas | 11/21/2019 | 11/20/2019 |  | 2754 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:08 | Mohammed, Saleem | 56-F-EU-V-190626-S2LO147_02 |  | Yes | Yes |  |  | Related to defect fix #580 commented the calls to P594915 and P594980 Applications |  |  |  | 56-F-EU-V-191101-R3LOV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R6213G09 | No | UBE |  |  | R3 |  | CRP | Supplemental Account Integrity Report by MCU | L3 Not Required |  |  | TRUE | HNE2E | TRUE | Finance GL | Finance | Libor Slaby | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-11-06 03:51 | Verma, Vikas |  |  |  | 2755 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-12-05 07:13 | Singh, Sunil Kumar | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564101S | No | APPL |  |  | R3 |  |  | Item iFrame for Siebel | L3 Not Required |  |  | TRUE |  | TRUE | Order Management | OM | Geneveive, Deveen | L2 Not required | 5/12 Bharat waiting for scripts |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-11-06 08:04 | Verma, Vikas | 22/11/2019 | 21/11/2019 |  | 2756 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:08 | Mohammed, Saleem | 56-F-EU-V-191107-R3MD001 |  | Yes |  |  |  | No change. Taken care in defect 611 |  |  |  | 56-F-EU-V-191107-R3MDV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600074 | No | UBE | BXU547134 |  | R3 |  | CRP | F4211 Adjust Sales Line UBE | L3 Pass |  |  | TRUE |  | TRUE | Finance GL | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-11-07 06:47 | Verma, Vikas | 11/18/2019 | 11/15/2019 |  | 2757 |  | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-03-05 06:44 | Joshi, Abhishek N | 56-F-EU-V-191120-R3FI006 |  | Yes | [7 empty] | 56- F-EU-V-190625-S3FIV025B_R3 | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56B42J3 | No | APPL |  |  | R3 |  | CRP | Management Entity Data | L3 Pass |  |  | TRUE |  | TRUE | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-11-07 06:48 | Verma, Vikas | 11/18/2019 | 11/18/2019 |  | 2758 |  | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2019-12-17 12:11 | BAYINDIR, AYSE | 56-F-EU-V-191114-R3FI007 |  | Yes | Yes |  |  | Restored PAR from PD812 |  |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5603B421J | No | UBE | BXU545721 |  | R3 |  | CRP | A/R Details with Aging - Country and Region | L3 Pass |  |  | TRUE |  | TRUE | Finance AR | Finance | Ayse Bayindir | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-11-07 06:48 | Verma, Vikas | 11/18/2019 | 11/15/2019 |  | 2759 |  | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-03-07 02:58 | Joshi, Abhishek N | 56-F-EU-V-190527-S1FI062_R3 |  | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R60EFAT01 | No | UBE |  |  | R3 |  |  | Estrazione Fattura Elettronica PA | L3 Not Required |  |  | TRUE |  | TRUE | Finance External | Finance |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-11-07 07:12 | Sinha, Rishikesh |  |  |  | 2760 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-12-05 07:13 | Singh, Sunil Kumar | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56414B | No | UBE | BXU546734 |  | R3 |  | CRP | Generate Profit Allocation Journal - RMF | L3 Pass |  |  | TRUE |  | TRUE | Finance GL | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-11-07 07:36 | Sinha, Rishikesh | 11/18/19 | 11/18/19 |  | 2761 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-11 00:25 | Joshi, Abhishek N | 56-F-EU-V-191113-R3FN005 |  | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5609100 | No | UBE | BXU545731 |  | R3 |  | CRP | Leased Hardware Profit Allocations | L3 Pass |  |  | TRUE |  | TRUE | Finance GL | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-11-07 07:43 | Sinha, Rishikesh | 11/18/2019 | 11/15/2019 |  | 2762 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-07 03:24 | Joshi, Abhishek N | 56-F-EU-V-190702-S3FI140_R3 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0503 | No | UBE |  |  | R3 |  | CRP | As Of VAT on Open AP Vouchers | L3 Pass |  |  | TRUE |  | TRUE | Finance GL | Finance | Sriram Krithivasan | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-11-07 08:00 | Sinha, Rishikesh | 11/19/2019 | 11/18/2019 |  | 2763 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-12-16 10:41 | Krithivasan Natarajan, Sriram | 56-F-EU-V-191118-R3FI004 |  | Yes | Y | [6 empty] | 56-F-EU-V-191118-R3FIV004A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R563002Z1 | No | UBE |  |  | R3 |  |  | Import CSV file to F3002Z1 | PPD Passed |  |  | TRUE |  | TRUE | MDM | MDM |  | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-11-07 08:00 | Sinha, Rishikesh | 11/19/2019 | 11/18/2019 |  | 2764 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:09 | Mohammed, Saleem | 56-F-EU-V-191114-R3MD004 |  | Yes | [7 empty] | 56-F-EU-V-191114-R3MDV004A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564101Y1 | No | UBE |  |  | R3 |  |  | Import CSV file to F4101Y | PPD Passed |  |  | TRUE |  | TRUE | MDM | MDM |  | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-11-07 08:00 | Sinha, Rishikesh | 11/18/2019 | 11/18/2019 |  | 2765 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:09 | Mohammed, Saleem | 56-F-EU-V-191114-R3MD008 |  | Yes | Y | [6 empty] | 56-F-EU-V-191114-R3MDV008A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564101ZIM | No | UBE |  |  | R3 |  |  | Import CSV file to F564101Z | PPD Passed |  |  | TRUE |  | TRUE | MDM | MDM |  | L2 Pass / Complete | L2 Completed |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-11-07 08:03 | Sinha, Rishikesh | 11/19/2019 | 11/18/2019 |  | 2766 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:09 | Mohammed, Saleem | 56-F-EU-V-191115-R3MD011 |  | Yes | Y | [6 empty] | 56-F-EU-V-191115-R3MDV011A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564101ZP | No | UBE |  |  | R3 |  |  | Import Packaging Data from WISE | PPD Passed |  |  | TRUE |  | TRUE | MDM | MDM |  | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-11-07 08:03 | Sinha, Rishikesh | 11/18/2019 | 11/19/2019 |  | 2767 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:09 | Mohammed, Saleem | 56-F-EU-V-191114-R3MD009 |  | Yes | Y | [6 empty] | 56-F-EU-V-191114-R3MDV009A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56594101Y | No | UBE |  |  | R3 |  |  | Import CSV file to F594101Y | PPD Passed |  |  | TRUE |  | TRUE | MDM | MDM |  | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-11-07 08:03 | Sinha, Rishikesh | 11/19/2019 | 11/18/2019 |  | 2768 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:10 | Mohammed, Saleem | 56-F-EU-V-191113-R3MD003 |  | Yes | Y | [6 empty] | 56-F-EU-V-191113-R3MDV03A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600123 | No | UBE |  |  | R3 |  |  | Report for HWT Sales Data | L3 Pass |  |  | TRUE |  | TRUE | Technical Services | Logistics | Douglas Roussel | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi Durairajan |  | Item |  | 2019-11-07 08:03 | Sinha, Rishikesh | 11/16/2019 | 11/15/2019 |  | 2769 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:10 | Mohammed, Saleem | 56-F-EU-V-191115-R3LO011 |  | Yes | [7 empty] | 56-F-EU-V-191115-R3LOV011A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649042E | No | UBE |  |  | R3 |  |  | GME Send Order | PPD Passed |  |  | TRUE |  | TRUE | Warehouse | Logistics | Miruna Danes | L2 Not required | 11/21 RK: As discussed, setup will take more time in DV, to be test in PPD so L2 Not Required |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-11-07 08:03 | Sinha, Rishikesh | 11/19/2019 | 11/18/2019 |  | 2770 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:10 | Mohammed, Saleem | 56-F-EU-V-191120-R3LO012 |  | Yes | [7 empty] | 56-F-EU-V-191120-R3LOV012A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649043E | Yes | UBE |  | 159373 BXU549264 BXU549263 | R3 |  |  | GME Outbound Order Processor | PPD Passed |  |  | TRUE |  | TRUE | Warehouse | Logistics | Miruna Danes | L2 Not required | 11/21 RK: As discussed, setup will take more time in DV, to be test in PPD so L2 Not Required |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-11-07 08:03 | Sinha, Rishikesh | 11/21/2019 | 11/21/2019 |  | 2771 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 09:35 | Vishnubhatla, Mithra | 56-F-EU-V-191114-R3LO011 |  | Yes | Yes | [6 empty] | 56-F-EU-V-191114-R3LOV011A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564734H | Yes | UBE |  | 159373 BXU549165 | R3 |  |  | EMEA GME UBE | L3 Not Required |  |  | TRUE |  | TRUE | Warehouse | Logistics | Miruna Danes | L2 Not required | 11/21 RK: As discussed, setup will take more time in DV, to be test in PPD so L2 Not Required |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-11-07 08:04 | Sinha, Rishikesh | 11/19/2019 | 11/18/2019 |  | 2772 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-25 05:10 | Vishnubhatla, Mithra | 56-F-EU-V-191114-R3LO007 |  | Yes | Y |  |  | won't be tested in R3. as also part of R5. will be tested end to end during CL5 |  |  |  | 56-F-EU-V-191114-R3LOV07A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564900H | No | UBE |  |  | R3 |  |  | GME Shipment Feedback | PPD Passed |  |  | TRUE |  | TRUE | Warehouse | Logistics | Miruna Danes | L2 Not required | 11/20 RK: As discussed in todays scrum call, marked as L2 Not Required. |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-11-07 08:04 | Sinha, Rishikesh | 11/20/2019 | 11/19/2019 |  | 2773 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:11 | Mohammed, Saleem | 56-F-EU-V-191114-R3LO003 |  | Yes | Yes | [6 empty] | 56-F-EU-V-191114-R3LOV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642030 | No | UBE | 1240722 (15527) | 1241039 (15527) | R3 |  |  | WCS Ship Note UBE | PPD Passed |  |  | TRUE |  | TRUE | Transportation | Logistics | Eric Destrebecq | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-11-07 08:04 | Sinha, Rishikesh | 11/19/2019 | 11/19/2019 |  | 2774 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 06:16 | ANAND, S | 56-F-EU-V-191118-R3LO001 |  | Yes | Y | [6 empty] | 56-F-EU-V-191118-R3LOV001 | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FR42535 | No | UBE | 1256041 (25586) |  | R3 |  |  | Delivery Note France | PPD Passed |  |  | TRUE |  | TRUE | Transportation | Logistics | Eric Destrebecq | L2 Not required | setup is not present in DV |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-11-07 08:04 | Sinha, Rishikesh | 11/19/2019 | 11/18/2019 |  | 2775 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 10:28 | Singh, Sunil Kumar | 56-F-EU-V-190710-S3LO088_R3 |  | Yes | [7 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56DE42565 | No | UBE |  |  | R3 |  |  | Print Invoices Germany - It was tested in Halle for 9.2 UAT's | L3 Pass |  |  | TRUE |  | TRUE | Order Management | OM | Piet Van Gijseghem, Lina Seputyte | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-11-07 08:04 | Sinha, Rishikesh | 11/19/2019 | 11/18/2019 |  | 2776 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:12 | Mohammed, Saleem | 56-F-EU-V-190712-S3OM001 |  | Yes | [8 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649003G | No | UBE |  |  | R3 |  |  | Print Packing List - GLAB | PPD Passed |  |  | TRUE |  | TRUE | Transportation | Logistics | Puneet Sharma | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-11-07 08:04 | Sinha, Rishikesh | 11/19/2019 | 11/20/2019 |  | 2777 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:12 | Mohammed, Saleem | 56-F-EU-V-191113-R3LO005 |  | Yes | Y | [6 empty] | 56-F-EU-V-191113-R3LOV005A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56U242565 | No | UBE | BXU545297 |  | R3 |  |  | BHSA Intercompany Invoices / Credits / Debits note - It was tested in Hechingen for 9.2 UAT's | L3 Pass |  |  | TRUE |  | TRUE | Order Management | OM | Piet Van Gijseghem, Lina Seputyte | L2 Not required | Kaustubh:11/26 :To tests new enhancement on packing list we need integration.As there is no integration in DV, we can’t test it. |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-11-07 08:08 | Sinha, Rishikesh | 20/11/2019 | 19/11/2019 |  | 2778 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 10:14 | Joshi, Abhishek N | 56-F-EU-V-191114-R3OM009 |  | Yes | [8 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56R0049B | No | UBE |  |  | R3 |  |  | BSM Vendor Create Request - EMEA | PPD Passed |  |  | TRUE |  | TRUE | MDM | MDM | Jean-Luc | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi Durairajan |  | Item |  | 2019-11-07 08:08 | Sinha, Rishikesh | 20/20/2019 | 19/20/2019 |  | 2779 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:13 | Mohammed, Saleem | 56- F-EU-V-190612-S2MD030_R3 |  | Yes | [8 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56R0049N | No | UBE |  |  | R3 |  |  | Process Vendor Branch Plants - EMEA | PPD Passed |  |  | TRUE |  | TRUE | MDM | MDM | Carlos Barrera | L2 Pass / Complete | 5/12 Bharat: waiting for scripts |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thppulla |  | Item |  | 2019-11-07 08:08 | Sinha, Rishikesh | 11/20/2019 | 11/19/2019 |  | 2780 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:13 | Mohammed, Saleem | 56-F-EU-V-191114-R3MD010 |  | Yes | [7 empty] | 56-F-EU-V-191114-R3MDV10A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R42565 | No | UBE |  |  | R3 |  |  | Print Invoices | L3 Pass |  |  | TRUE |  | TRUE | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-11-07 08:08 | Sinha, Rishikesh | 11/20/2019 | 11/19/2019 |  | 2781 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:14 | Mohammed, Saleem | 56-F-EU-V-190709-S3OM032_R3 |  | Yes | [8 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647042 | No | UBE |  |  | R3 |  |  | eInvoice Tag File Insert Report | PPD Passed |  |  | TRUE |  | TRUE | eCommerce | eCommerce | Aidan | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Thippulla Sreekanth |  | Item |  | 2019-11-07 08:09 | Sinha, Rishikesh | 11/20/2019 | 11/19/2019 |  | 2782 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-05-18 08:34 | Greenard, Terry | 56-F-EU-V-191113-R3OM005 |  | Yes | [7 empty] | 56-F-EU-V-191113-R3OMV005A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56NO42001 | No | UBE | 1242579 (17919) |  | R3 |  |  | Proforma Invoice Nordics | PPD Passed |  |  | TRUE |  | TRUE | Transportation | Logistics | Destrebecq, Eric | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-11-07 08:09 | Sinha, Rishikesh | 11/19/2019 | 11/20/2019 |  | 2783 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-20 06:38 | ANAND, S | 56-F-EU-V-190710-S3OM034_R3 |  | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564941C | No | UBE |  |  | R3 |  |  | LOAD LIST | PPD Passed |  |  | TRUE |  | TRUE | Transportation | Logistics | Scott Weber | L2 Not required | setup is not present in DV |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-11-07 08:09 | Sinha, Rishikesh |  |  |  | 2784 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:06 | Mohammed, Saleem |  |  | Yes |  |  |  | Was retofitted in R2 - No Retrofit required for R3 |  |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56SB42565 | No | UBE | BXU545438 |  | R3 |  |  | Saudi Arabia Invoice with VAT | L3 Not Required |  |  | TRUE |  | TRUE | Order Management | OM | Venkateswaran Murugesan | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-11-07 08:09 | Sinha, Rishikesh | 11/20/2019 | 11/19/2019 |  | 2785 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 06:06 | Joshi, Abhishek N | 56-F-EU-V-190704-S3OM026_R3 |  | Yes | [8 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56IT42535 | No | UBE | 1248392 (21265 |  | R3 |  |  | Delivery Note Italy | PPD Passed | 637 | Open | TRUE |  | TRUE | Transportation | Logistics | Puneet Sharma | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item | Italy | 2019-11-07 08:09 | Sinha, Rishikesh | 11/20/2019 | 11/19/2019 |  | 2786 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-05 13:24 | Singh, Sunil Kumar | 56-F-EU-V-190725-S4LO059 |  | Yes | [8 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643008CR | No | UBE | BXU550203 |  | R3 |  |  | Count Sheet - Customer Returns | PPD Passed |  |  | TRUE |  | TRUE | Warehouse | Logistics | Swetha MS | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-11-07 08:09 | Sinha, Rishikesh | 11/20/2019 | 11/19/2019 |  | 2787 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-04-16 07:27 | Greenard, Terry | 56-F-EU-V-190919-R1LO004_R3 |  | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56CZMOH | No | UBE |  |  | R3 |  |  | DIS13 - REG | PPD Passed |  |  | TRUE |  | TRUE | Warehouse | Logistics | TK, Rajesh | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-11-07 08:09 | Sinha, Rishikesh | 11/20/2019 | 11/21/2019 |  | 2788 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-28 07:55 | TK, Rajesh | 56-F-EU-V-191024-R2OM004 |  | Yes | Y | [6 empty] | 56-F-EU-V-191024-R2OMV004A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56CZMOH1 | No | UBE |  |  | R3 |  |  | DIS13 - NREG | PPD Passed |  |  | TRUE |  | TRUE | Warehouse | Logistics | TK, Rajesh | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-11-07 08:09 | Sinha, Rishikesh | 11/21/2019 | 11/19/2019 |  | 2789 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-28 07:55 | TK, Rajesh | 56-F-EU-V-191024-R2OM008 |  | Yes | [7 empty] | 56-F-EU-V-191024-R2OMV008A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56CZMOH2 | No | UBE |  |  | R3 |  |  | MAH | PPD Passed |  |  | TRUE |  | TRUE | Warehouse | Logistics | TK, Rajesh | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-11-07 08:09 | Sinha, Rishikesh | 11/21/2019 | 11/20/2019 |  | 2790 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-28 07:56 | TK, Rajesh | 56-F-EU-V-191118-R3OM007 |  | Yes | Y | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56CZMOHE | No | UBE |  |  | R3 |  |  | DIS - Error | PPD Passed |  |  | TRUE |  | TRUE | Warehouse | Logistics | TK, Rajesh | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-11-07 08:14 | Sinha, Rishikesh | 11/25/2019 | 11/24/2019 |  | 2791 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-28 07:56 | TK, Rajesh | 56-F-EU-V-191106-R2OM010 |  | Yes | Y | [6 empty] | 56-F-EU-V-191106-R2OMV010A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56REG13 | No | UBE |  |  | R3 |  |  | REG13 | PPD Passed |  |  | TRUE |  | TRUE | Warehouse | Logistics | TK, Rajesh | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-11-07 08:14 | Sinha, Rishikesh | 11/20/2019 | 11/18/2019 |  | 2792 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-28 07:57 | TK, Rajesh | 56-F-EU-V-191107-R2OM011 |  | Yes | Y | [6 empty] | 56-F-EU-V-191107-R2OMV011A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56E0001 | No | UBE | BXU516652 (109164) | 109164 | R3 |  |  | GLAB - Update E1 to E1 ASN information | PPD Passed |  |  | TRUE |  | TRUE | Warehouse | Logistics | Albert Vila | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-11-07 08:14 | Sinha, Rishikesh | 11/20/2019 | 11/18/2019 |  | 2793 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-08 05:20 | Singh, Sunil Kumar | 56-F-EU-V-190628-S3LO004_R3 |  | Yes | Y | [6 empty] | 56-F-EU-V-190628-S3LOV004A_R3 | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5645014 | No | UBE | BXU549674 |  | R3 |  |  | Service Billing with High VAT Rate | L3 Not Required |  |  | TRUE |  | TRUE | Order Management | OM | Venkateswaran Murugesan | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-11-07 08:14 | Sinha, Rishikesh | 11/20/2019 | 11/20/2019 |  | 2794 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-17 02:34 | Joshi, Abhishek N | 56-F-EU-V-191024-R2OM002 |  | Yes | Y | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560411P | No | UBE |  |  | R3 |  |  | Invalid Pay status report | L3 Pass |  |  | TRUE |  | TRUE | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-11-07 08:14 | Sinha, Rishikesh | 11/20/2019 | 11/19/2019 |  | 2795 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-12-16 09:40 | GOLGE, SERAY | 56-F-EU-V-191120-R3FI010 |  | Yes | [7 empty] | 56-F-EU-V-191120-R3FIV010A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564572FGB | No | UBE |  |  | R4 |  | CRP | Deutche Bank - Foreign Print Program GB+ IBAN | L3 Pass |  |  | TRUE |  | TRUE | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete | HR 13/12 Sent back to ARO for correction Peter.G will confirm once it is available for testing |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-11-07 08:14 | Sinha, Rishikesh | 12/13/2019 | 12/12/2019 |  | 2796 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-07 04:17 | Gilthorpe, Peter | 56-F-EU-V-191114-R3FI001A |  | Yes | [7 empty] | 56- F-EU-V-191218-R5FIV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55NSIIB | No | UBE |  |  | R3 |  |  | SII Generacion de XML B | L3 Not Required |  |  | TRUE |  | TRUE | Finance External | Finance | Joanne Byrne | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-11-07 08:14 | Sinha, Rishikesh | 11/20/2019 | 11/20/2019 |  | 2797 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-09 08:07 | Bodin, Fatiha | 56-F-EU-V-191120-R3FI001 |  | Yes | [7 empty] | 56-F-EU-V-190910-S6FIV125A_R3 | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R57004052 | No | UBE |  |  | R3 |  |  | A/R - A/P European Tax Report - Cust | L3 Pass |  |  | TRUE |  | TRUE | Finance GL | Finance | Lokesh Reddy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-11-07 08:14 | Sinha, Rishikesh | 11/20/2019 | 11/19/2019 |  | 2798 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-12-12 06:16 | Reddy, Lokeswar | 56-F-EU-V-191118-R3FI003 |  | Yes | Y |  |  | 11/20/2019 |  |  |  | 56-F-EU-V-191118-R3FIV003A,56-F-EU-V-191118-R3FIV003B,56-F-EU-V-191118-R3FIV003C,56-F-EU-V-191118-R3FIV003D | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5603010 | No | UBE |  |  | R3 |  |  | Active Customer Report | PPD Passed |  |  | TRUE |  | TRUE | ARO | ARO | Rakesh | L2 Not required | Bharat : Email confirmation from Rakesh dated - 12/12/2019; Prashant 4/12: Waiting for script |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-11-07 08:14 | Sinha, Rishikesh | 11/19/2019 | 11/20/2019 |  | 2799 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:15 | Mohammed, Saleem | 56-F-EU-V-191118-R3AR007 |  | Yes | Y | [6 empty] | 56-F-EU-V-191118-R3ARV007A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56BO01 | No | UBE |  |  | R3 |  |  | AI SO Analysis Report | PPD Passed |  |  | TRUE |  | TRUE | ARO | ARO | Rakesh Kumar | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-11-07 08:14 | Sinha, Rishikesh | 11/27/2019 | 11/21/2019 |  | 2800 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:15 | Mohammed, Saleem | 56-F-EU-V-191118-R3AR008 |  | Yes | [7 empty] | 56-F-EU-V-191118-R3ARV008A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56BO02 | No | UBE |  |  | R3 |  |  | Process CTI Table Records. | PPD Passed |  |  | TRUE |  | TRUE | ARO | ARO | Rakesh Kumar | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-11-07 08:15 | Sinha, Rishikesh | 11/22/2019 | 11/21/2019 |  | 2801 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:16 | Mohammed, Saleem | 56-F-EU-V-191114-R3AR003 |  | Yes | [7 empty] | 56-F-EU-V-191114-R3ARV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56BO03 | No | UBE |  |  | R3 |  |  | AI SO Purge Batch | PPD Passed |  |  | TRUE |  | TRUE | ARO | ARO | Rakesh Kumar | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-11-07 08:15 | Sinha, Rishikesh | 11/20/2019 | 11/21/2019 |  | 2802 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:16 | Mohammed, Saleem | 56-F-EU-V-191114-R3AR001 |  | Yes | [7 empty] | 56-F-EU-V-191114-R3ARV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56BO04 | No | UBE |  |  | R3 |  |  | AI Service Request Report | PPD Passed |  |  | TRUE |  | TRUE | ARO | ARO | Rakesh Kumar | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-11-07 08:15 | Sinha, Rishikesh | 11/21/2019 | 11/20/2019 |  | 2803 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:16 | Mohammed, Saleem | 56-F-EU-V-191114-R3AR002 |  | Yes | [7 empty] | 56-F-EU-V-191114-R3ARV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56BO05 | No | UBE |  |  | R3 |  |  | AI SO Purge Temp File | PPD Passed |  |  | TRUE |  | TRUE | ARO | ARO | Rakesh Kumar | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-11-07 08:15 | Sinha, Rishikesh | 11/21/2019 | 11/20/2019 |  | 2804 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:16 | Mohammed, Saleem | 56-F-EU-V-191115-R3AR006 |  | Yes | [7 empty] | 56-F-EU-V-191115-R3ARV006A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R57R0110 | Yes | UBE | BXU531264 39268 | BXU547463 (12961) | R3 |  |  | F4111 / F41021 Integrity | PPD Passed |  |  | TRUE |  | TRUE | ARO | ARO | Rakesh Kumar | L2 Not required | Bharat : Email confirmation from Rakesh, dated - 12/12/2019; Prashant 4/12: Waiting for script |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-11-07 08:15 | Sinha, Rishikesh | 11/21/19 | 11/21/19 |  | 2805 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-20 08:16 | Vishnubhatla, Mithra | 56-F-EU-V-191113-R3LO001 |  | Yes | [8 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0269 | No | UBE |  |  | R3 |  |  | Repost - Failed WO Commitments | PPD Passed |  |  | TRUE |  | TRUE | Warehouse | Logistics | Rakesh Kumar | L2 Not required | 11/19 RK: As discussed & decided in todays call, only data selection has changed so marked as L2 Not Required |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-11-07 08:15 | Sinha, Rishikesh | 11/21/2019 | 11/21/2019 |  | 2806 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:17 | Mohammed, Saleem | 56-F-EU-V-190715-S3LO095_R3 |  | Yes | [8 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649012 | No | UBE |  |  | R3 |  |  | FCA Freight Expense Accrual Report | PPD Passed |  |  | TRUE |  | TRUE | Transportation | Logistics | Rakesh Kumar | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Thippulla Sreekanth |  | Item |  | 2019-11-07 08:15 | Sinha, Rishikesh | 11/20/2019 | 11/21/2019 |  | 2807 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:17 | Mohammed, Saleem | 56-F-EU-V-191120-R3LO013 |  | Yes | [7 empty] | 56-F-EU-V-190731-S4LOV081A_R3 | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649019 | No | UBE |  |  | R3 |  |  | FCA Freight Expense Report | PPD Passed |  |  | TRUE |  | TRUE | Transportation | Logistics | Rakesh Kumar | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-11-07 08:15 | Sinha, Rishikesh | 11/20/2019 | 11/20/2019 |  | 2808 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:04 | Mohammed, Saleem | 56-F-EU-V-191114-R3LO010 |  | Yes | [8 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56414C | No | APPL |  |  | R3 |  | CRP | Profit allocation history data interfaced from RMF | L3 Pass |  |  | TRUE |  | TRUE | Finance GL | Finance | Libor Slaby | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-11-07 08:22 | Sinha, Rishikesh | 12/18/2019 | 11/18/2019 |  | 2809 |  | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2019-12-10 10:23 | Slaby, Libor | 56-F-EU-V-191114-R3FI002 |  | Yes |  |  |  |  | R3 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564101 | Yes | APPL | 1263246 | 1271288, 1263247 | R3 |  |  | Item Master XE EMEA Version | PPD Passed |  |  | TRUE |  | TRUE | MDM | MDM |  | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-11-07 08:22 | Sinha, Rishikesh | 11/19/2019 | 11/18/2019 |  | 2811 |  | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-04 03:20 | Joshi, Abhishek N | 56-F-EU-V-190515-S1MD023_R3 |  | Yes | [7 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5600123 | No | APPL |  |  | R3 |  |  | HWT Sales Application | L3 Pass |  |  | TRUE |  | TRUE | Technical Services | Logistics | Douglas Roussel | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi Durairajan |  | Item |  | 2019-11-07 08:23 | Sinha, Rishikesh | 11/19/2019 | 11/18/2019 |  | 2813 |  | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-06 04:18 | Mohammed, Saleem | 56-F-EU-V-191115-R3LO008 |  | Yes |  |  |  | Restored PAR file from PD812. |  |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P57PMEX | No | APPL |  |  | R3 |  |  | Exceptional Mark For Preferential Origin | L3 Pass |  |  | TRUE |  | TRUE | Order Management | OM | Piet Van Gijseghem, Lina Seputyte | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-11-07 08:23 | Sinha, Rishikesh | 11/20/2019 | 11/18/2019 |  | 2814 |  | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-04 08:49 | Javadi, Vinod | 56-F-EU-V-191115-R3OM006 |  | Yes | [7 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642053 | Yes | APPL | 1253299 (22471) | 1253300 22471 | R3 |  |  | EMEA Locate Goods - Manual Branch | PPD Passed |  |  | TRUE |  | TRUE | Warehouse | Logistics | Albert Vila | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-11-07 08:23 | Sinha, Rishikesh | 11/20/2019 | 11/19/2019 |  | 2815 |  | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-06-09 06:10 | Singh, Sunil Kumar | 56-F-EU-V-190617-S2LO097_R3 |  | Yes | [8 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5603013 | No | APPL |  |  | R3 |  |  | Account Information Iframe | L3 Not Required |  |  | TRUE |  | TRUE | Order management | OM | Venkateswaran Murugesan | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-11-07 08:23 | Sinha, Rishikesh | 11/20/2019 | 11/19/2019 |  | 2816 |  | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2019-12-20 10:22 | Murugesan, Venkateswaran | 56-F-EU-V-191120-R3OM008 |  | Yes | [7 empty] | 56-F-EU-V-191120-R3OMV008A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5603014 | No | APPL |  | 1253946 | R3 |  |  | Basis/Bill To Maintenance | L3 Not Required |  |  | TRUE |  | TRUE | Order Management | OM | Venkateswaran Murugesan | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-11-07 08:23 | Sinha, Rishikesh | 11/20/2019 | 11/19/2019 |  | 2817 |  | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-04 06:27 | Joshi, Abhishek N | 56-F-EU-V-190620-S2MD047_R3 | [9 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4210 | Yes | APPL | BXU545444 (60558), 1222473 (11402) | 1276496 (60558),1263371 (4099), BXU545241 (11402) | R3 |  |  | Sales Order Entry | PPD Passed |  |  | TRUE |  | TRUE | Order Management | OM | Kamatham Deepika | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-11-07 08:23 | Sinha, Rishikesh | 11/21/2019 | 11/22/2019 |  | 2818 |  | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-07-24 05:36 | Singh, Sunil Kumar | 56-F-EU-V-191113-R3OM003 |  | Yes | [7 empty] | 56-F-EU-V-191113-R3OMV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564915A | Yes | APPL | 1240719 (16244), BXU546752 (21933), 1251776 (23552) | 1264176, 1241778 (16244), BXU531175 (21933), 1251777 (23552), BXU547514 (25713) | R3 |  |  | Work with Shipments - Baxter EMEA | PPD Passed |  |  | TRUE |  | TRUE | Transportation | Logistics | Albert vila | L2 Not required | requiring integrations |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-11-07 08:23 | Sinha, Rishikesh |  |  |  | 2819 |  | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-07 09:32 | ANAND, S | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5943250 | Yes | APPL |  |  | R3 |  |  | Movement and Disposition By Load Number | PPD Passed |  |  | TRUE |  | TRUE | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-11-07 08:23 | Sinha, Rishikesh | 11/20/2019 | 11/19/2019 |  | 2820 |  | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-06 04:19 | Mohammed, Saleem | 56-F-EU-V-190527-S1LO115_R3 |  | Yes | [7 empty] | N/a | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900054 | No | APPL |  |  | R3 |  |  | Transaction Detail Inquiry | L3 Pass |  |  | TRUE |  | TRUE | Technical Services | Logistics | Nuri Bilensoy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-11-07 08:24 | Sinha, Rishikesh | 11/20/2019 | 11/19/2019 |  | 2821 |  | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-06 04:19 | Mohammed, Saleem | 56-F-EU-V-191113-R3LO002 |  | Yes | [7 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P55NSII3 | No | APPL |  |  | R3 |  |  | SII - Tipo de Identificación | L3 Not Required |  |  | TRUE |  | TRUE | Finance External | Finance |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-11-07 08:24 | Sinha, Rishikesh | 11/20/2019 | 11/19/2019 |  | 2822 |  | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2019-12-05 07:13 | Singh, Sunil Kumar | 56-F-EU-V-191115-R3FI008 |  | Yes | [7 empty] | 56-F-EU-V-191115-R3FIV008A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56BOT01 | No | APPL |  |  | R3 |  |  | AI Process, Validation & Message Rules Applicatio | PPD Passed |  |  | TRUE |  | TRUE | ARO | ARO | Rakesh Kumar | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-11-07 08:24 | Sinha, Rishikesh | 11/21/2019 | 11/20/2019 |  | 2823 |  | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-06 04:19 | Mohammed, Saleem | 56-F-EU-V-191114-R3AR004 |  | Yes | [7 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56BOT02 | No | APPL |  |  | R3 |  |  | AI Analysis Work and Tag File | PPD Passed |  |  | TRUE |  | TRUE | ARO | ARO | Rakesh Kumar | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Bargavi Durairajan |  | Item |  | 2019-11-07 08:24 | Sinha, Rishikesh | 11/21/2019 | 11/20/2019 |  | 2824 |  | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-06 04:20 | Mohammed, Saleem | 56-F-EU-V-191120-R3AR009 |  | Yes | [7 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56BOT03 | No | APPL |  |  | R3 |  |  | AI SO Analysis Specical Instruction Application | PPD Passed |  |  | TRUE |  | TRUE | ARO | ARO | Rakesh Kumar | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-11-07 08:24 | Sinha, Rishikesh | 11/21/2019 | 11/21/2019 |  | 2825 |  | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-06 04:20 | Mohammed, Saleem | 56-F-EU-V-191114-R3AR012 |  | Yes | [8 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564915 | Yes | APPL | BXU543060, 1247267 (20730), 1264519 (12127), 1240720 (15526) | 1241564 (12127), 1241121 (15526), 1250551 (20730) | R3 |  |  |  | PPD Passed |  |  | TRUE |  | TRUE | Transportation | Logistics | Albert vila | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-11-07 08:28 | Sinha, Rishikesh | 11/21/2019 | 11/20/2019 |  | 2826 |  | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-07 08:38 | ANAND, S | 56-F-EU-V-190521-S1LO035_R3 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190521-S1LOV35A_R3 | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642016 | No | APPL | 1248691 (22032) | 1250559 | R3 |  |  | Batch Reservations Inquiry | PPD Passed |  |  | TRUE |  | TRUE | Warehouse | Logistics | Rakesh Kumar | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | TANKUT, CIZMECI |  | Item |  | 2019-11-07 08:28 | Sinha, Rishikesh | 11/20/2019 | 11/19/2019 |  | 2827 |  | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-06 05:40 | Singh, Sunil Kumar | 56-F-EU-V-190625-S2LO145_R3 |  | Yes | [7 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5647012 | Yes | APPL |  | BXU549161 167051 | R3 |  |  | Audit Data A47012 Validation | PPD Passed |  |  | TRUE |  | TRUE | Warehouse | Logistics | Rakesh Kumar | L2 Not required | 12/03 RK: Waiting for input from baxter SME |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-11-07 08:28 | Sinha, Rishikesh | 11/20/2019 | 11/19/2019 |  | 2828 |  | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-17 10:00 | Vishnubhatla, Mithra | 56-F-EU-V-191113-R3LO006 |  | Yes |  |  |  |  | AUDIT EDI |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56R0110 | Yes | APPL |  | 168769 BXU549178 | R3 |  |  | F4111/F41021 Integrity | PPD Passed |  |  | TRUE |  | TRUE | ARO | ARO | Albert Vila | L2 Not required | 4/12: TG - Albert to test in PPD Prashant 4/12: Waiting for script |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-11-07 08:28 | Sinha, Rishikesh | 11/19/2019 | 11/18/2019 |  | 2829 |  | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-02-17 10:04 | Vishnubhatla, Mithra | 56-F-EU-V-191121-R3AR013 |  | Yes | [7 empty] | 56-F-EU-V-191121-R3ARV013A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56CZMOH | No | APPL |  |  | R2 |  |  |  | PPD Passed |  |  | TRUE |  | TRUE | Warehouse | Logistics | TK, Rajesh | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-11-07 21:16 | Verma, Vikas | 10/24/19 | 10/25/19 |  | 2835 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2019-11-28 08:03 | TK, Rajesh | 56-F-EU-V-191024-R2OM001 |  | Yes | [8 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5674R01 | No | APPL |  |  | R3 |  | CRP | Russian Localisation - Proc Opts BAX | L3 Pass |  |  | TRUE |  | TRUE | Finance Localisations | Finance | Keith Haxton | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma | 14/11 TG - Missing Object | TANKUT, CIZMECI |  | Item |  | 2019-11-13 22:24 | Greenard, Terry | 11/25/2019 | 11/24/2019 |  | 2836 |  | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2019-12-05 07:13 | Singh, Sunil Kumar | 56-F-EU-V-191119-R3FI005 |  | Yes |  |  |  | Restored PAR from PD812. |  |  |  | 56-F-EU-V-191119-R3FIV005A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56VND01 | No | UBE |  |  | R3 |  |  | WISE Vendor Interface | PPD Passed |  |  | TRUE |  | TRUE | MDM | MDM | Carlos | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2019-11-13 22:24 | Verma, Vikas | 20/11/2019 | 19/11/2019 |  | 2837 |  | 0 |  |  |  | 2020-02-06 04:21 | Mohammed, Saleem | 56-F-EU-V-191120-R3MD012 |  | Yes | [7 empty] | 56-F-EU-V-191120-R3MDV012A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56SLOGS | No | APPL |  |  | R4 |  |  | Serialised Log Maintenance | PPD Passed |  |  | TRUE |  | TRUE | Warehouse | Logistics | Abdul Mughal | L2 Not required | 12/12 RK: As discussed in scrum call,marked as L2 Not Required |  |  | Léonard Dartois |  |  |  | Item |  | 2019-11-25 05:58 | Verma, Vikas | 12/04/2019 | 12/04/2019 |  | 2838 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:21 | Mohammed, Saleem | 56-F-EU-V-191203-R4LO001 |  | Yes | Yes | [6 empty] | 56-F-EU-V-191203-R4LOV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56SLOGS | No | UBE |  |  | R4 |  |  | Serialised Items Exceptions | PPD Passed |  |  | TRUE |  | TRUE | Warehouse | Logistics | Abdul Mughal | L2 Not required | 12/12 RK: As discussed in scrum call,marked as L2 Not Required |  |  | Léonard Dartois |  |  |  | Item |  | 2019-11-25 05:58 | Verma, Vikas | 12/04/2019 | 12/04/2019 |  | 2839 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:22 | Mohammed, Saleem | 56-F-EU-V-191203-R4LO002 |  | Yes | Yes | [6 empty] | 56-F-EU-V-191203-R4LOV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564211F | No | UBE |  |  | R4 |  |  | SK OWC DVAN Post-Processor UBE | PPD Passed |  |  | TRUE |  | TRUE | Warehouse | Logistics | Abdul Mughal | L2 Not required | 12/12 RK: As discussed in scrum call,marked as L2 Not Required |  |  | Léonard Dartois |  |  |  | Item |  | 2019-11-25 05:58 | Verma, Vikas | 12/05/2019 | 12/04/2019 |  | 2840 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:22 | Mohammed, Saleem | 56-F-EU-V-191203-R4LO003 |  | Yes | Yes | [6 empty] | 56-F-EU-V-191203-R4LOV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56DE42565 | No | UBE |  |  | R4 |  |  | Print Invoices Germany | L3 Not Required |  |  | TRUE |  | TRUE | Order Management | OM |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-11-25 05:58 | Verma, Vikas | 12/5/19 | 12/4/19 |  | 2841 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:12 | Mohammed, Saleem | 56-F-EU-V-190712-S3OM001_R4 |  | Yes | [7 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600150 | Yes | UBE | 1263246 | 1263247 16923 BXU549048 | R4 |  |  | MDM Replication - Batch Re-processor | PPD Passed |  |  | TRUE |  | TRUE |  | MDM |  | L2 Pass / Complete | 19/12/2019 Bharat : Waiting for Script from SME. Email already sent. |  |  | Terry Greenard / Vikas Verma |  | Bargavi Durairajan |  | Item |  | 2019-11-26 08:45 | Verma, Vikas | 11/27/2019 | 11/27/2019 |  | 2842 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 10:10 | Vishnubhatla, Mithra | 56-F-EU-V-191127-R4MD001 |  | Yes | [7 empty] | 56-F-EU-V-191127-R4MDV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56470371 | No | UBE |  |  | R4 |  |  | RU Serialization-Enrich F470371 | PPD Passed |  |  | TRUE |  | TRUE | Warehouse | Logistics | Abdul Mughal | L2 Not required | 12/12 RK: As discussed in scrum call,marked as L2 Not Required |  |  | Léonard Dartois |  | Sreekanth Thippulla |  | Item |  | 2019-11-29 01:12 | Verma, Vikas | 12/5/2019 | 12/4/2019 |  | 2843 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:22 | Mohammed, Saleem | 56-F-EU-V-191203-R4LO004 |  | Yes | [7 empty] | 56-F-EU-V-191203-R4LOV004A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649042F | No | UBE |  |  | R4 |  |  | Send Order - RU | L3 Not Required |  |  | TRUE |  | TRUE | Warehouse | Logistics | Abdul Mughal | L2 Not required | 12/12 RK: As discussed in scrum call,marked as L2 Not Required |  |  | Léonard Dartois |  | Sreekanth Thippulla |  | Item |  | 2019-11-29 01:12 | Verma, Vikas | 12/5/19 | 12/4/19 |  | 2844 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:23 | Mohammed, Saleem | 56-F-EU-V-191203-R4LO005 |  | Yes | [7 empty] | 56-F-EU-V-191203-R4LO005A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649043F | No | UBE |  |  | R4 |  |  | 3PL OutBound Order Processor | PPD Passed |  |  | TRUE |  | TRUE | Warehouse | Logistics | Abdul Mughal | L2 Not required | 12/12 RK: As discussed in scrum call,marked as L2 Not Required |  |  | Léonard Dartois |  | Sreekanth Thippulla |  | Item |  | 2019-11-29 01:12 | Verma, Vikas | 12/6/19 | 12/5/19 |  | 2845 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:23 | Mohammed, Saleem | 56-F-EU-V-191203-R4LO006 |  | Yes | [7 empty] | 56-F-EU-V-191203-R4LO006A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600010 | Yes | UBE | 1222666 |  | R4 |  |  | JDE WMS Receiving Label Print | PPD Passed | 774 | Closed | TRUE |  | TRUE | Warehouse | Logistics | Abdul Mughal | L2 Not required | 12/12 RK: As discussed in scrum call,marked as L2 Not Required |  |  | Léonard Dartois |  |  |  | Item |  | 2019-11-29 01:12 | Verma, Vikas | 12/4/2019 | 12/3/2019 |  | 2846 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-25 04:59 | Vishnubhatla, Mithra | 56-F-EU-V-191008-R1LO032_R4 |  | Yes | Yes | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642565A | No | UBE | BXU545271 |  | R4 |  |  | Order Acknowledgement Report | L3 Not Required |  |  | TRUE |  | TRUE | Order Management | OM | George Manuval Malithara | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-11-29 01:13 | Verma, Vikas | 12/6/2019 | 12/5/2019 |  | 2847 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 03:11 | Joshi, Abhishek N | 56-F-EU-V-190611-S2OM023_R4 |  | Yes | Yes | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P0911 | No | APPL |  |  | R4 |  |  | Journal Entries | L3 Pass |  |  | TRUE |  | TRUE | Finance GL | Finance | Joanne Byrne | L2 Pass / Complete | AD 20/12 ; Waiting for Test Script from Joanne |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-11-29 02:23 | Verma, Vikas | 12/03/2019 | 12/03/2019 |  | 2848 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-01-17 16:44 | Byrne, Joanne Aileen | 56-F-EU-V-191118-R3FI009 |  | Yes | Yes | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600097 | No | UBE |  |  | R4 |  |  | Therapy Billing Check Report | L3 Not Required |  |  | TRUE |  | TRUE | OM | OM | Rafal Molas | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-12-05 03:22 | Verma, Vikas | 12/6/2019 | 12/5/2019 |  | 2849 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:24 | Mohammed, Saleem | 56-F-EU-V-191205-R4OM001 |  | Yes | [7 empty] | 56-F-EU-V-191205-R4OMV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55PDDST | Obsolete | UBE |  |  | 999 |  |  | ProDart Source D.S. Values (T.C.) | Obsolete |  |  | FALSE |  | FALSE |  | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-12-09 05:24 | Verma, Vikas |  |  |  | 2851 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:39 | Mohammed, Saleem | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55PDREP | Obsolete | UBE |  |  | 999 |  |  | ProDart Source P.O. Values Repository | Obsolete |  |  | FALSE |  | FALSE |  | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-12-09 05:24 | Verma, Vikas |  |  |  | 2852 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:39 | Mohammed, Saleem | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R42950 | No | UBE |  |  | R5 |  |  | Sales Order Batch Price/Cost Update | L3 Pass |  |  | TRUE |  | TRUE | Finance | Finance | Francisco Alvargonzalez | L2 Pass / Complete | 12/27 RK: Need KT/Updated test script/data. waiting for the reply. 01/14 AD - Francisco requested to prepare fresh data and confirm result, Data creation and testing is in progress |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-12-09 05:24 | Verma, Vikas | 12/19/2019 | 12/19/2019 |  | 2853 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:24 | Mohammed, Saleem | 56-F-EU-V-191219-FI002 |  | Yes | [8 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560015E | No | UBE |  |  | R5 |  |  | F0015 Exchange Rate Extract UBE | PPD Passed |  |  | TRUE |  | TRUE | Finance | Finance | Joanne Byrne | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-12-09 05:25 | Verma, Vikas | 19/12/2019 | 18/12/2019 |  | 2854 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:24 | Mohammed, Saleem | 56- F-EU-V-191218-R5FI001_01 |  | Yes | [7 empty] | 56- F-EU-V-191218-R5FIV001A_01 | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564734H | Yes | UBE |  | 159373 BXU549165 | R5 |  |  | EMEA GME UBE | PPD Passed | 787 |  | TRUE |  | TRUE | Warehouse | Logistics | Miruna Danes | L2 Not required | 12/23 RK: As per confirmation mail, marked as L2 Not Required. |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2019-12-09 05:25 | Verma, Vikas | 12/18/2019 | 12/18/2019 |  | 2855 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-25 05:10 | Vishnubhatla, Mithra | 56-F-EU-V-191114-R3LO007_R5 |  | Yes | [7 empty] | 56-F-EU-V-191114-R3LOV07A_R5 | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56470371 | No | UBE |  |  | R5 |  |  | RU Serialization-Enrich F470371 | PPD Passed |  |  | TRUE |  | TRUE | Logistics | Logistics | Abdul Mughal | L2 Not required | 12/23 RK: As per confirmation mail, marked as L2 Not Required |  |  | Léonard Dartois |  |  |  | Item |  | 2019-12-09 05:25 | Verma, Vikas | 12/18/2019 | 12/18/2019 |  | 2856 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:22 | Mohammed, Saleem | 56-F-EU-V-191203-R4LO004_R5 |  | Yes | [8 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649043F | No | UBE |  |  | R5 |  |  | 3PL OutBound Order Processor | PPD Passed |  |  | TRUE |  | TRUE | Logistics | Logistics | Abdul Mughal | L2 Not required | 12/23 RK: As per confirmation mail, marked as L2 Not Required |  |  | Léonard Dartois |  | Sreekanth Thippulla |  | Item |  | 2019-12-09 05:25 | Verma, Vikas | 12/18/2019 | 12/17/2019 |  | 2857 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:23 | Mohammed, Saleem | 56-F-EU-V-191217-R5LO001 |  | Yes | [8 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55NSIIB | No | UBE |  |  | R5 |  |  | SII Generacion de XML B | PPD Passed |  |  | TRUE |  | TRUE | Finance | Finance | Izaskun Ajuria | L2 Not required | 30/12: This object is marked as L2 not required in earlier sprint, waiting for input from Joanne 03/01: As per the confirmation from Joanne marking this object as "L2 Not Required" |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-12-09 05:25 | Verma, Vikas | 12/18/2019 | 12/17/2019 |  | 2858 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:25 | Mohammed, Saleem | 56-F-EU-V-191120-R3FI001_R5 |  | Yes | [8 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564740 | No | UBE | 1238862 (14849) |  | R5 |  |  | Post Picking EDI FFA Generation | PPD Passed |  |  | TRUE |  | TRUE | Transportation | Logistics |  | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-12-09 05:25 | Verma, Vikas | 12/18/2019 | 12/17/2019 |  | 2859 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-01 07:01 | Singh, Sunil Kumar | 56-F-EU-V-191218-R5FI003 |  | Yes | Y | [6 empty] | 56-F-EU-V-190725-S4LOV054A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56BO02 | No | UBE |  |  | R5 |  |  | Process CTI Table Records. | PPD Passed |  |  | TRUE |  | TRUE | ARO | ARO | Rakesh Kumar | L2 Not required | 12/22 Bharat : Waiting for input, email sent by Prashant. 12/26 Prashant : L2 not required as mail confirmation by rakesh Kumar |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-12-09 05:25 | Verma, Vikas | 12/178/2019 | 12/18/2019 |  | 2860 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:16 | Mohammed, Saleem | 56-F-EU-V-191217-R5AR001 |  | Yes | [7 empty] | 56-F-EU-V-191217-R5ARV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56SLOGS | No | APPL |  |  | R5 |  |  | Serialised Log Maintenance | PPD Passed |  |  | TRUE |  | TRUE | Logistics | Logistics | Abdul Mughal | L2 Not required | 12/23 RK: As per confirmation mail, marked as L2 Not Required |  |  | Léonard Dartois |  | Sreekanth Thippulla |  | Item |  | 2019-12-09 07:30 | Verma, Vikas | 12/18/2019 | 12/18/2019 |  | 2862 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:21 | Mohammed, Saleem | 56-F-EU-V-191203-R4LO001_R5 |  | Yes | [8 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56BOT02 | No | APPL |  |  | R5 |  |  | AI Analysis Work and Tag File | PPD Passed |  |  | TRUE |  | TRUE | ARO | ARO | Rakesh Kumar | L2 Not required | 12/22 Bharat : Waiting for input, email sent by Prashant. 12/26 Prashant : L2 not required as mail confirmation by rakesh Kumar |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2019-12-09 07:30 | Verma, Vikas | 12/18/2019 | 12/17/2019 |  | 2863 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:20 | Mohammed, Saleem | 56-F-EU-V-191217-R5AR002 |  | Yes | [7 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56QACTR | Yes | UBE |  |  | R6 |  |  | Movement of QA controlled objects | L3 Pass |  |  | TRUE |  | TRUE | Validation | Validation | Vinod Javadi | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-01-17 08:17 | Verma, Vikas | 1/23/2020 | 1/23/2020 |  | 2865 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 22:25 | Naik, Prashant | 56-F-EU-V-200121-R6VA001 |  | Yes | [7 empty] | 56-F-EU-V-200121-R6VAV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56QACOM | Yes | UBE |  | 29753 BXU549253 | R6 |  |  | UDC and Version Tracking | L3 Pass |  |  | TRUE |  | TRUE | Validation | Validation | Vinod Javadi | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-01-17 08:19 | Verma, Vikas |  |  |  | 2866 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 10:14 | Vishnubhatla, Mithra | 56-F-EU-V-200121-R6VA002 |  | Yes |  |  |  |  | R6 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56QASNP | Yes | UBE |  | 30415 BXU549071 | R6 |  |  | PO Snapshot Report QA | L3 Pass |  |  | TRUE |  | TRUE | Validation | Validation | Vinod Javadi | L2 Pass / Complete | Kindly provide test data |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-01-17 08:21 | Verma, Vikas | 1/23/2020 | 1/23/2020 |  | 2867 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-17 10:29 | Vishnubhatla, Mithra | 56-F-EU-V-200121-R6VA004 |  | Yes | [7 empty] | 56-F-EU-V-200121-R6VAV004A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56QAPOC | Yes | UBE |  |  | R6 |  |  | PO Compare Report for QA | L3 Pass |  |  | TRUE |  | TRUE | Validation | Validation | Vinod Javadi | L2 Pass / Complete | Kindly provide test data |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-01-17 08:22 | Verma, Vikas | 1/23/2020 | 1/23/2020 |  | 2868 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 06:18 | Javadi, Vinod | 56-F-EU-V-200121-R6VAV003A |  | Yes | [7 empty] | 56-F-EU-V-200121-R6VAV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560015E | No | UBE |  |  | R6 |  |  | F0015 Exchange Rate Extract UBE | PPD Passed |  |  | TRUE |  | TRUE | Finance | Finance | Joanne Byrne | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-01-20 02:02 | Verma, Vikas | 22/01/2020 | 21/01/2020 |  | 2869 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-14 06:06 | Byrne, Joanne Aileen | 56- F-EU-V-200121-R6FI001 |  | Yes | [7 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R60A41Z1E | No | UBE |  |  | R6 |  |  | Input Batch from SOP - Sales Commissions | PPD Passed |  |  | TRUE |  | TRUE | Finance External | Finance | Izaskun Ajuria | L2 Not required | Marked "L2 not required" as per the mail confirmation from Keith and Luigi |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-01-20 02:02 | Verma, Vikas | 1/24/2020 | 1/23/2020 |  | 2870 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 02:47 | Ajuria, Izaskun | 56-F-EU-V-200123-R6FI006 |  | Yes | [7 empty] | 56-F-EU-V-200123-R6FIV06A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R60A4BX002 | No | UBE |  |  | R6 |  |  | Commission Credit Note X-ref update | PPD Passed |  |  | TRUE |  | TRUE | Finance External | Finance | Izaskun Ajuria | L2 Not required | Marked "L2 not required" as per the mail confirmation from Keith and Luigi |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-01-20 02:02 | Verma, Vikas | 1/24/2020 | 1/23/2020 |  | 2871 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-07 02:46 | Ajuria, Izaskun | 56-F-EU-V-200123-R6FI007 |  | Yes | [8 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56SLOGS | No | APPL |  |  | R6 |  |  | Serialised Log Maintenance | L3 Pass |  |  | TRUE |  | TRUE | Logistics | Logistics | Peter De Brouwer | L2 Not required | 01/23 RK: As per mail confirmationmarked as L2 Not Required. |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-01-20 02:02 | Verma, Vikas | 01/23/2020 | 01/22/2020 |  | 2872 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 04:45 | De Brouwer, Peter | 56-F-EU-V-191203-R4LO001_R6 |  | Yes | [7 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FEC014 | No | UBE |  |  | R6 |  |  | FEC - Sequential Number Generation Process V3 | L3 Pass |  |  | TRUE |  | TRUE | Finance External | Finance | Keith Haxton | L2 Not required | Marked "L2 not required" as per the mail confirmation from Keith and Luigi |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-01-20 02:02 | Verma, Vikas | 1/24/2020 | 1/23/2020 |  | 2873 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-27 04:00 | Gerth, Felix | 56-F-EU-V-200121-R6FI004 |  | Yes | [7 empty] | 56-F-EU-V-200121-R6FIV004A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FEC03 | No | UBE |  |  | R6 |  |  | ASOF Report for Customer/Supplier | L3 Pass |  |  | TRUE |  | TRUE | Finance External | Finance | Keith Haxton | L2 Not required | Marked "L2 not required" as per the mail confirmation from Keith and Luigi |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-01-20 02:02 | Verma, Vikas | 01/22/2020 | 01/21/2020 |  | 2874 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-27 03:44 | Gerth, Felix | 56-F-EU-V-200121-R6FI005 |  | Yes | [7 empty] | 56-F-EU-V-200121-R6FIV005A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FEC034 | No | UBE |  |  | R6 |  |  | FEC - Extractor CSV Statutory Accounting Audit Fil | L3 Pass |  |  | TRUE |  | TRUE | Finance External | Finance | Keith Haxton | L2 Not required | Marked "L2 not required" as per the mail confirmation from Keith and Luigi |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-01-20 02:02 | Verma, Vikas | 02/22/2020 | 01/22/2020 |  | 2875 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-27 04:09 | Gerth, Felix | 56-F-EU-V-190912-S6FI115_R6 |  | Yes | [7 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FEC04 | No | UBE |  |  | R6 |  |  | Report based on F55FEC04 | L3 Pass |  |  | TRUE |  | TRUE | Finance External | Finance | Keith Haxton | L2 Not required | Marked "L2 not required" as per the mail confirmation from Keith and Luigi |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-01-20 02:02 | Verma, Vikas | 1/24/2020 | 01/23/2020 |  | 2876 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-27 03:45 | Gerth, Felix | 56-F-EU-V-200121-R6FI006 |  | Yes | [7 empty] | 56-F-EU-V-200121-R6FIV006A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560401 | No | UBE |  |  | R6 |  |  | CONCUR GLAP Interface - EMEA Region | L3 Not Required |  |  | TRUE |  | TRUE | Finance AP | Finance | Eileen Paula | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-01-20 02:02 | Verma, Vikas | 1/24/2020 | 1/23/2020 |  | 2877 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-06 04:28 | Mohammed, Saleem | 56- F-EU-V-200121-R6FI002 |  | Yes |  |  |  | Will be tested in R7 when bug is fixed |  |  |  | 56- F-EU-V-200121-R6FI002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R57004051 | No | UBE | BXU546189 |  | R6 |  |  | A/R - A/P IVA Tax Report - Italy - Cust | L3 Pass |  |  | TRUE |  | TRUE | Finance GL | Finance | Lokesh Reddy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-01-20 02:02 | Verma, Vikas | 1/23/2020 | 1/22/2020 |  | 2878 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-10 04:55 | Joshi, Abhishek N | 56-F-EU-V-190723-S4FI020_R6 |  | Yes | [8 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R57004052 | No | UBE |  |  | R6 |  |  | A/R - A/P European Tax Report - Cust | L3 Pass |  |  | TRUE |  | TRUE | Finance GL | Finance | Lokesh Reddy | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-01-20 02:02 | Verma, Vikas | 01/21/2020 | 01/21/2020 |  | 2879 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-10 05:48 | Reddy, Lokeswar | 56-F-EU-V-191118-R3FI003_R6 |  | Yes | [8 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL0007P | No | UBE | BXU546597 |  | R6 |  |  | Receipt Document (PZ) | L3 Pass |  |  | TRUE |  | TRUE | ARO | Logistics | Rakesh Kumar | L2 Pass / Complete | 31/01 Prashant Naik : Please provide test script and data. |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-01-20 02:02 | Verma, Vikas | 01/24/2020 | 01/23/2020 |  | 2880 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-09 04:31 | Joshi, Abhishek N | 56-F-EU-V-190517-S1LO049_R6 |  | Yes |  |  |  |  | R6 |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564211Q | No | UBE | BXU545274, BXU545801, BXU545827 |  | R6 |  |  | Price Protocol for Russia | PPD Passed | 800 | BSL to apply new template on JDE 9.2 | TRUE |  | TRUE | Order Management | OM | Jaisingh Jaiswar | L2 Not required | 01/23 RK: As per mail confirmation,marked as L2 Not required |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-01-20 02:02 | Verma, Vikas | 01/24/2020 | 01/23/2020 |  | 2881 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-14 01:39 | Joshi, Abhishek N | 56-F-EU-V-190516-S1OM025_R6 |  | Yes | [8 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5603010 | No | UBE |  |  | R6 |  |  | Active Customer Report | L3 Pass |  |  | TRUE |  | TRUE | ARO | ARO | Rakesh | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-01-20 02:02 | Verma, Vikas | 01/24/2020 | 01/23/2020 |  | 2882 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-24 04:23 | Kumar, Rakesh | 56-F-EU-V-200121-R6AR001 |  | Yes | [7 empty] | 56-F-EU-V-191118-R3ARV007A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5600926 | Yes | APPL |  |  | R6 |  |  | Role Sequence Table | PPD Passed |  |  | TRUE |  | TRUE | JDE Security | Security | Karol | L2 Not required | 28/ 01 MW: Mail from Terry and Vikas 27 Jan |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-01-27 04:29 | Verma, Vikas | 1/28/2020 | 1/27/2020 |  | 2883 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 05:26 | Maglewski, Karol | 56-F-EU-V-200127-R6SEC001 |  | Yes | [7 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5600927 | Yes | APPL |  |  | R6 |  |  | Role Sequencing Ranges | PPD Passed |  |  | TRUE |  | TRUE | JDE Security | Security | Karol | L2 Not required | 28/ 01 MW: Mail from Terry and Vikas 27 Jan |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-01-27 04:29 | Verma, Vikas | 01/28/2020 | 01/27/2020 |  | 2884 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-02-11 05:27 | Maglewski, Karol | 56-F-EU-V-200127-R6SEC002 |  | Yes | [8 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560401 |  | UBE |  |  | R7 |  |  | CONCUR GLAP Interface - EMEA Region | PPD Passed |  |  | TRUE |  | TRUE | Finance | Finance | Eileen Paula | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-02-10 04:43 | Verma, Vikas | 2/12/2020 | 2/11/2020 |  | 2885 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-02 10:54 | Paula, Eileen Annette | 56-F-EU-V-190624-S3FI010_R7 |  | Yes |  |  |  | Testing successful |  |  |  |  | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642565CO |  | UBE | BXU545794 |  | R7 |  |  | BAXTER Invoice Consolidation Pre-Processor | L3 Pass |  |  | TRUE |  | TRUE | ARO | ARO | Rakesh Kumar | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-02-10 04:43 | Verma, Vikas | 2/12/2020 | 2/11/2020 |  | 2886 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-03-12 10:58 | Joshi, Abhishek N | 56-F-EU-V-190710-S3OM106_R7 |  | Yes | [7 empty] | 56- F-EU-V-200212-R7OMV003A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642565CO | No | UBE | BXU545794 |  | R9 |  |  | BAXTER Invoice Consolidation Pre-Processor | L3 Pass | 950 | Closed | TRUE |  | TRUE |  | ARO | Rakesh Kumar / Rafal Molas | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item | Belgium | 2020-03-09 04:47 | Verma, Vikas |  |  |  | 2887 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-04-30 02:22 | Seputyte, Lina | 56-F-EU-V-200309-R9ARO001 |  | Yes | [7 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56BX42565 | No | UBE |  |  | R9 |  |  | Print Invoices BeNeLux | L3 Pass |  |  | TRUE |  | TRUE | Order Management | OM | Rafal Molas | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-03-09 05:05 | Verma, Vikas |  |  |  | 2888 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-05-07 08:31 | MOLAS, RAFAL | 56-F-EU-V-200309-R9OM001 |  | Yes | [7 empty] | 56-F-EU-V-190710-S3OMV033A_R9,56-F-EU-V-190710-S3OMV033B_R9 | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P46011 |  | APPL |  |  | R9 |  |  | Item Unit of Measure Definition | L3 Pass |  |  | TRUE |  | TRUE | MDM | MDM | Carlos M. Barrera | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-03-10 09:35 | Verma, Vikas |  |  |  | 2889 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-05-05 03:58 | Nebreda Martinez, Aser | 56-F-EU-V-190310-R9MD0001 |  | Yes | [7 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56EUV15 | No | APPL | BXU547432 |  | R10 |  | Initiatives | Maintain Vat Tax Rate | L3 Pass |  |  | TRUE | HNE2E | TRUE | Finance GL | Finance | Izaskun Ajuria | L2 Pass / Complete | AD - 09/04 - Access to application P56EUV15 is not available, requested for access |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2020-04-06 01:45 | Greenard, Terry |  |  |  | 2890 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-04-27 07:20 | Verma, Vikas | 56-F-EU-V-190515-S1FI009_R10 | Maintenance | Yes | Yes | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R60A4310 | No | UBE |  |  | R10 |  | Initiatives | Proforma Invoice (OA) | L3 Not Required |  |  | TRUE | HNE2E | TRUE | Finance External | Finance | Izaskun Ajuria | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2020-04-06 01:49 | Greenard, Terry |  |  |  | 2891 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-04-27 07:20 | Verma, Vikas | CNC_R60A4310_R10 |  | Yes | Yes |  |  |  | NoKT |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5709215 | No | APPL | BXU549745 |  | R10 |  | Initiatives | Trail Balance by Subledger | L3 Pass |  |  | TRUE | LNE2E | TRUE | Finance GL | Finance | Greg Felitto | L2 Pass / Complete | AD - 09/04 - Waiting for KT and Script for the changes done |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2020-04-06 05:08 | Greenard, Terry | 04/09/2020 | 04/08/2020 |  | 2893 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-04-27 07:20 | Verma, Vikas | 56-F-EU-V-190827-S6FI063_R10 |  | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600212 | No | UBE |  |  | R10 |  |  | Drug Shortage Report CSV | L3 Pass |  |  | TRUE |  | TRUE | Transportation | Logistics | Scott Weber | L2 Pass / Complete |  |  |  | Vikas Verma |  | Vikas Verma |  | Item |  | 2020-04-14 03:01 | Greenard, Terry | 04/17/2020 | 04/17/2020 |  | 2894 | Custom | 0 | Sameer Tawde |  |  | 2020-04-30 05:16 | Bodin, Fatiha | 56-F-EU-V-200414-R10LO002 |  | Yes | Yes |  |  | Retrofitted. |  |  |  | 56-F-EU-V-200414-R10LOV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900010 | No | APPL |  |  | R10 |  |  | Product Allocation Standard Preference Upload | L3 Pass |  |  | TRUE | HNE2E | TRUE | Order Management | OM | John Whalley | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2020-04-14 03:01 | Greenard, Terry | 4/15/2020 | 4/14/2020 |  | 2895 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-04-27 07:20 | Verma, Vikas | 56-F-EU-V-190611-S2OM016_R10 |  | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641421 | No | UBE | 1248389 (21264) | 1249499 (21264) | R11 |  |  | Bollini Extract from F4211 | L3 Pass |  |  | TRUE | LE2E | TRUE | Warehouse | Logistics | Nuri Bilensoy | L2 Pass / Complete | 05/18 RK: L2 Passed 05/15 RK: waiting for updated Test script/data |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-04-14 09:05 | Greenard, Terry | 14/05/2020 | 11/05/2020 |  | 2896 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-03 04:37 | BILENSOY, NURI | 56-F-EU-V-190708-S3LO080_R11 |  | Yes | [7 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R590401 | No | UBE |  |  | R10 |  |  | MILD Vendor Interface | L3 Pass |  |  | TRUE | H | TRUE | MDM | MDM | Carlos | L2 Pass / Complete | 17/04 PN: Waiting for script and test data. |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2020-04-16 07:23 | Greenard, Terry | 17/04/2020 | 17/04/2020 |  | 2897 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-04-27 10:15 | Nebreda Martinez, Aser | 56-F-EU-V-190625-S2MD001_R10 |  | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5643008CR | No | UBE | BXU550203 |  | R10 |  |  | L3 test completed. Count Sheet - Customer Returns | L3 Pass |  |  | TRUE |  | TRUE | Warehouse | Logistics | Swetha MS | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2020-04-16 07:25 | Greenard, Terry | 17/04/2020 | 17/04/2020 |  | 2898 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-04-27 07:21 | Verma, Vikas | 56-F-EU-V-190919-R1LO004_R10 |  | Yes | Yes | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5839902 | No | UBE | BXU545360 |  | R11 |  | CRP | Stock Valuation File Purge | L3 Pass |  |  | TRUE | LNE2E | TRUE | Localization | Finance | Constanza Frade | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Vikas Verma |  | Item |  | 2020-04-20 02:33 | Greenard, Terry | 22/4/2020 | 22/4/2020 |  | 2899 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-01 07:25 | Frade Dolesor, Constanza | 56-F-EU-V-190604-S1FI077_R11 |  | Yes | Yes | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5643070 | Yes | APPL | BXU532396 (148542) | BXU532399 (148542) | R11 |  |  | Line Level Held Order Release | L3 Pass |  |  | TRUE |  | TRUE | Quality | Logistics | Abdul | L2 Pass / Complete | 21/5 PN : L2 Pass, Query search for “Item number” and “Ship to “is not working in 8.11 and 9.2 |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-04-27 12:42 | Greenard, Terry |  |  |  | 2900 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-06-01 02:18 | Verma, Vikas | 56-F-EU-V-190610-S2LO032_R11 |  | Yes | Yes | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647010 | No | UBE | BXU519115 (99566) | BXU519116 (99566) | R11 |  |  | JDE Inbound PO Pre Processor | L3 Pass |  |  | TRUE | HE2E | TRUE | Warehouse | Logistics | Abdul | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-04-29 07:13 | Greenard, Terry |  |  |  | 2901 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-01 02:18 | Verma, Vikas | 56-F-EU-V-190611-S2LO070_R11 |  | Yes | Yes | [6 empty] | 56-F-EU-V-190611-S2LOV070A_R11 | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647010E | No | UBE |  |  | R11 |  |  | JDE Inbound PO Pre Processor Email | L3 Pass |  |  | TRUE |  | TRUE | Warehouse | Logistics | Abdul | L2 Pass / Complete | [5 empty] | Sreekanth Thippulla |  | Item |  | 2020-04-29 07:14 | Greenard, Terry |  |  |  | 2902 | Custom | 0 |  |  |  | 2020-06-01 02:18 | Verma, Vikas | 56-F-EU-V-200430-R11LO001 |  | Yes | Yes |  |  | Special Instructions: F564701E-Table generation required (New Table)) |  |  |  | 56-F-EU-V-200430-R11LOV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R04110ZA | No | UBE | BXU548622 |  | R11 |  |  | Batch Voucher Processor Report | PPD Passed |  |  | TRUE |  | TRUE | Finance AP | Finance | Gregory | L2 Pass / Complete |  |  |  | Terry Greenard/Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-04-30 04:05 | Greenard, Terry | 04/30/2020 | 05/04/2020 |  | 2903 | Standard | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-16 10:14 | Felitto, Gregory | 56-F-EU-V-190729-S4FI057_R11 |  | Yes | Yes | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRAP21 | No | UBE | BXU548811 |  | R11 |  |  | A/P Unrealized Gain/Loss Report | PPD Passed |  |  | TRUE | LNE2E | TRUE | Finance AP | Finance | Gregory | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-04-30 04:06 | Greenard, Terry | 05/13/20 | 05/12/20 |  | 2904 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-05 05:18 | Felitto, Gregory | 56-F-EU-V-190827-S6FI030_R11 | Report |  | Yes | [6 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55FRAR21 | No | UBE | BXU549450 |  | R11 |  |  | A/R Gains/Losses Report | PPD Passed |  |  | TRUE | HNE2E | TRUE | Finance GL | Finance | Gregory | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-04-30 04:06 | Greenard, Terry | 05/13/20 | 05/12/20 |  | 2905 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-04 09:22 | Felitto, Gregory | 56-F-EU-V-190827-S6FI041_R11 |  | Yes | Yes | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642520A | Yes | UBE |  |  | R11 |  |  | Manual Warehouse Picklist UBE | PPD Passed |  |  | TRUE |  | TRUE | Warehouse | Logistics | Daniel Clark | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-05-05 04:43 | Verma, Vikas | 5/6/2020 | 5/5/2020 |  | 2906 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-11 02:18 | Ollier, Sébastien | 56- F-EU-V-190618-S2LO108_R11 |  | Yes | Yes | [7 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56GB42565 | No | UBE | BXU545825 |  | R11 |  |  | Print Trade Invoices GB/IE | L3 Pass |  |  | TRUE | HE2E | TRUE | Order Management | OM | Rafal Molas | L2 Pass / Complete | 05/27 RK: L2 Pass 05/13 RK: Waiting for Updated Test Script /Data |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item | UK IE NI | 2020-05-12 05:38 | Greenard, Terry | 05/13/2020 | 05/12/2020 |  | 2907 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-11 08:45 | MOLAS, RAFAL | 56-F-EU-V-190711-S3OM108_R11 | Printer | Yes | [7 empty] | 56-F-EU-V-190711-S3OMV108A_R11,56-F-EU-V-200518-R11OMV005A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56BX42535 | No | UBE | 1263916 | 11215&nbsp; 1264408 | R11 |  |  | Delivery Note BeNeLux | L3 Pass |  |  | TRUE | HE2E | TRUE | Transportation | Logistics | Scott Weber | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-05-12 05:53 | Greenard, Terry |  |  |  | 2908 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-01 02:19 | Verma, Vikas | 56-F-EU-V-190710-S3LO086_R11 |  | Yes | [7 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56ES42535 | No | UBE | 1235432 (15031) | 1235890 (15031) | R11 |  |  | Delivery Notes Print Spain | L3 Pass |  |  | TRUE | HE2E | TRUE | Transportation | Logistics | Scott Weber | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-05-12 05:54 | Greenard, Terry |  |  |  | 2909 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-07-24 03:35 | Singh, Sunil Kumar | 56-F-EU-V-190701-S3LO005_R11 | Printer | Yes | [7 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564142R | No | UBE | 1248389 (21264) | 1249499 (21264) | R11 |  |  | Reprocess F5641020 records for xref errors | L3 Pass |  |  | TRUE | LE2E | TRUE | Warehouse | Logistics | Nuri Bilensoy | L2 Pass / Complete | 05/18 RK: L2 Pass 05/15 RK:Waiting for Updated Test Script/data |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-05-13 03:11 | Greenard, Terry | 14/05/2020 | 11/05/2020 |  | 2911 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-01 02:19 | Verma, Vikas | 56-F-EU-V-190610-S2LO025_R11 |  | Yes | [7 empty] | 56-F-EU-V-190610-S2LOV25A_R11 | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560041 | No | UBE |  |  | R11 |  |  | Deliveries by Customer / Item (Vaccinet Report) | PPD Passed |  |  | TRUE |  | TRUE | Order Management | OM | John Whalley | L2 Pass / Complete | Pass |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-05-13 09:02 | Verma, Vikas | 14/05/2020 | 14/05/2020 |  | 2912 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-05-27 10:16 | Malithara, George Manuval | 56-F-EU-V-200514-R11OM002 |  | Yes | [7 empty] | 56-F-EU-V-200514-R11OMV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56G0006 | Yes | UBE | 1268529 (23928) | 1268530 (23928) | R11 |  |  | Gambro: Lot Alignment UBE | L3 Pass |  |  | TRUE |  | TRUE | Warehouse | Logistics | Abdul Mughal | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-05-13 10:34 | Greenard, Terry | 05/14/2020 | 05/14/2020 |  | 2913 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-01 02:19 | Verma, Vikas | 56-F-EU-V-190731-S4LO090_R11 |  | Yes | [7 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564211Q | No | UBE | BXU545274, BXU545801, BXU545827 |  | R11 |  |  | Price Protocol for Russia | PPD Passed |  |  | TRUE |  | TRUE | Order Management | OM | Jaisingh Jaiswar | L2 Pass / Complete | 05/29 RK: L2 Passed 05/15 RK: Waiting for Updated Test Script /data |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-05-15 02:26 | Greenard, Terry | 05/15/2020 | 05/15/2020 |  | 2914 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-08 12:18 | Jaiswar, Jaisingh | 56-F-EU-V-190516-S1OM025_R11 |  | Yes | Yes | [6 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560411IT | No | UBE |  |  | R11 |  |  | Italian XML Invoices Processed | PPD Passed |  |  | TRUE |  | TRUE | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete | [5 empty] | Sreekanth Thippulla |  | Item |  | 2020-05-15 02:44 | Greenard, Terry |  |  |  | 2915 | Custom | 0 |  |  |  | 2020-06-09 02:32 | Gilthorpe, Peter | 56-F-EU-V-200515-R11FI002 |  | Yes | [7 empty] | 56-F-EU-V-200515-R11FIV002A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R560401CN | No | UBE |  |  | R11 |  |  | JDE Supplier Master to Canon Capture New | PPD Passed |  |  | TRUE |  | TRUE | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete | [5 empty] | Sreekanth Thippulla |  | Item |  | 2020-05-15 03:58 | Greenard, Terry | 05/15/2020 | 05/15/2020 |  | 2916 | Custom | 0 | Sameer Tawde/Sandhya Agrawal |  |  | 2020-06-04 04:52 | Gilthorpe, Peter | 56-F-EU-V-200515-R11FI001 |  | Yes | Yes |  |  | Special Instruction: UBEs to run on NT Server |  |  |  | 56-F-EU-V-200515-R11FIV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5900315 | No | APPL |  |  | R11 |  |  | Multi Company Journal Entries | PPD Passed |  |  | TRUE |  | TRUE | Finance GL | Finance | Krithivasan Natarajan, Sriram <sriram_krithivasan_natarajan@baxter.com> | L2 Pass / Complete | [5 empty] | Sreekanth Thippulla |  | Item |  | 2020-05-15 04:00 | Greenard, Terry | 18/05/2020 | 18/05/2020 |  | 2917 | Custom | 0 |  |  |  | 2020-06-08 10:16 | Krithivasan Natarajan, Sriram | 56-F-EU-V-200515-R11FI008 |  | Yes | [7 empty] | 56-F-EU-V-200515-R11FIV008A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55470412 | No | UBE | BXU547734 |  | R11 |  |  | EDI Inbound Invoice/Match to P.O. - Target II | PPD Passed |  |  | TRUE | HNE2E | TRUE | Finance AP | Finance | Peter Gilthorpe | L2 Pass / Complete |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-05-15 07:34 | Greenard, Terry | 5/18/2020 | 5/15/2020 |  | 2918 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-05 09:27 | Gilthorpe, Peter | 56-F-EU-V-190726-S4FI001_R11 |  | Yes | [8 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5603012 | Yes | APPL |  | 1253946 | R11 |  |  | Patient/Ship To Maintenance | L3 Pass |  |  | TRUE |  | TRUE | MDM | MDM | Carlos | L2 Pass / Complete | 20/5 PN: could you please confirm step4 and step8 in 8.12 |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-05-15 09:11 | Greenard, Terry | 5/18/2020 | 5/15/2020 |  | 2919 | Custom | 0 | Sandhya Agarwal / Sameer Tawde |  |  | 2020-06-01 02:19 | Verma, Vikas | 56-F-EU-V-190611-S2MD017_R11 |  | Yes | [8 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642520C | Yes | UBE | BXU545779 (104749) | BXU549568 (104749) | R11 |  |  | APL Hard Commitment Pickslip | PPD Passed |  |  | TRUE |  | TRUE | Warehouse | Logistics | Daniel Clark | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-05-18 05:01 | Verma, Vikas | 5/18/2020 | 5/18/2020 |  | 2920 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-11 02:17 | Ollier, Sébastien | 56-F-EU-V-190611-S2LO039_R11 |  | Yes | [7 empty] | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647042 | No | UBE |  |  | R11 |  |  | eInvoice Tag File Insert Report | PPD Passed |  |  | TRUE |  | TRUE | eCommerce | eCommerce | Linda | L2 Not required | No KT, testing to be done in CRP / UAT / OQ |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-05-18 08:33 | Greenard, Terry |  |  |  | 2921 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-11 04:37 | Greenard, Terry | 56-F-EU-V-191113-R3OM005_R11 |  | Yes | [7 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5612LHW1 | No | UBE | BXU545944, BXU545949 |  | R11 |  |  | Extract F4211 Leased Hardware Moves | L3 Not Required |  |  | TRUE | HE2E | TRUE | Finance FA | Finance | Amit | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-05-19 05:55 | Greenard, Terry |  |  |  | 2922 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-19 05:43 | Prabhu, Varsha | 56- F-EU-V-190618-S2FI049_R11 |  | Yes | [7 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FR42535 | No | UBE | 1256041 (25586) | 25586 1256042 | R11 |  |  | Delivery Note France | PPD Passed |  |  | TRUE | HE2E | TRUE | Transportation | Logistics | Jaisingh | L2 Not required | 06/01 RK: As per attached mail, L2 Not required 05/20 RK: Waiting for updated test script/data |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-05-19 12:13 | Greenard, Terry |  |  |  | 2923 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-12 05:25 | Jaiswar, Jaisingh | 56-F-EU-V-190710-S3LO088_R11 |  | Yes | [7 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647006 | No | UBE |  |  | R11 |  |  | KfH CONPCK Preprocessor Report | PPD Passed |  |  | TRUE | L | TRUE | Warehouse | Logistics | Jaisingh | L2 Pass / Complete | 05/28 RK: L2 Passed 05/20 RK: Waiting for updated test script/data |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-05-19 12:14 | Greenard, Terry | 5/20/2020 | 5/20/2020 |  | 2924 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-12 05:25 | Jaiswar, Jaisingh | 56- F-EU-V-190618-S2LO106_R11 |  | Yes |  |  |  |  | KTW6 |  |  | NA | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0503 | No | UBE |  |  | R11 |  |  | As Of VAT on Open AP Vouchers | PPD Passed |  |  | TRUE |  | TRUE | Finance GL | Finance | Sriram Krithivasan | L2 Pass / Complete | [7 empty] | Item |  | 2020-05-20 09:25 | Greenard, Terry |  |  |  | 2925 | Custom | 0 |  |  |  | 2020-06-08 09:27 | Krithivasan Natarajan, Sriram | 56-F-EU-V-191118-R3FI004_R11 |  | Yes | [7 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56744002 | No | UBE |  |  | R11 |  |  | SEPA XML Credit Transfer - COMM - 04 - EMEA | PPD Passed |  |  | TRUE | HNE2E | TRUE | Finance AP | Finance | Felix Gerth | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-05-21 05:01 | Greenard, Terry |  |  |  | 2926 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-07-03 03:24 | Bodin, Fatiha | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600113 |  | UBE |  |  | R12 |  |  |  | L3 Pass | 980 | Closed | TRUE |  | TRUE | Finance GL | Finance | Libor Slaby | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-05-29 02:51 | Verma, Vikas | 6/1/2020 |  |  | 2927 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-08 02:55 | Verma, Vikas | 56-F-EU-V-200529-R12FI001 |  | Yes | [7 empty] | 56-F-EU-V-200529-R12FIV001A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5612LHW1 | No | UBE | BXU545944, BXU545949 |  | R12 |  |  | Extract F4211 Leased Hardware Moves | L3 Pass |  |  | TRUE | HE2E | TRUE | Finance FA | Finance | Felix | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-06-17 10:54 | Greenard, Terry |  |  |  | 2928 | Custom | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-06-23 09:19 | Slaby, Libor | 56- F-EU-V-190618-S2FI049_R12 |  | Yes | [7 empty] | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56SAB104L |  | UBE |  |  | R812 |  |  | SAB104 Shipped Not Invoiced OrderLines-Logistics (CSV) | Baxter Code Review Complete |  |  | FALSE |  | FALSE | ARO |  | Jaisingh | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-06-24 03:52 | Verma, Vikas |  |  |  | 2929 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-08-11 05:09 | Chiau, Liesbet | PSSCM163193 |  | Yes |  |  |  | PAR restored from DV812 to DV920 |  |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564074I |  | UBE |  |  | R812 |  |  | Price Adjustment integrity report | Baxter Code Review Complete |  |  | FALSE |  | FALSE | Finance |  | Francisco | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-06-24 03:53 | Verma, Vikas |  |  |  | 2930 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-08-11 05:09 | Chiau, Liesbet | EUFIN160951A |  | Yes |  |  |  | PAR restored from DV812 to DV920 |  |  |  | N/A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56BO01 |  | UBE |  |  | R812 |  |  | AI SO Analysis Report | L3 Pass |  |  | FALSE |  | FALSE | ARO |  | Mayur | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-06-24 03:53 | Verma, Vikas |  |  |  | 2931 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-08-11 09:01 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56BO04 |  | UBE |  |  | R812 |  |  | AI Service Request Report | L3 In Progress |  |  | FALSE |  | FALSE | ARO |  | Mayur | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-06-24 03:53 | Verma, Vikas |  |  |  | 2932 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-08-11 09:01 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56BO06 |  | UBE |  |  | R812 |  |  | AI PO Bot Analysis Report | L3 In Progress |  |  | FALSE |  | FALSE | ARO |  | Mayur | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-06-24 03:53 | Verma, Vikas |  |  |  | 2933 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-08-11 09:01 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56BO07 |  | UBE |  |  | R812 |  |  | AI Send Email Batch Job | L3 In Progress |  |  | FALSE |  | FALSE | ARO |  | Mayur | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-06-24 03:53 | Verma, Vikas |  |  |  | 2934 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-08-11 09:01 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56BO09 |  | UBE |  |  | R812 |  |  | SR aReport | L3 In Progress |  |  | FALSE |  | FALSE | ARO |  | Mayur | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-06-24 03:53 | Verma, Vikas |  |  |  | 2935 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-08-11 09:01 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P560011 |  | APPL |  |  | R812 |  |  | Work with Batches in Error | Baxter Code Review Complete |  |  | FALSE |  | FALSE | Finance |  | Felix | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-06-24 03:55 | Verma, Vikas | 26/6/2020 | 26/6/2020 |  | 2936 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-08-11 05:09 | Chiau, Liesbet | PSFINSP27748 |  | Yes | [8 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P560911 |  | APPL |  |  | R812 |  |  | Approve F0911 Transactions | Baxter Code Review Complete |  |  | FALSE |  | FALSE | Finance |  | Felix | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-06-24 03:55 | Verma, Vikas | 26/6/2020 | 26/6/2020 |  | 2937 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-08-11 05:09 | Chiau, Liesbet | PSFINSP27748 |  | Yes | [8 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P560911B |  | APPL |  |  | R812 |  |  | View F0911 Approver | Baxter Code Review Complete |  |  | FALSE |  | FALSE | Finance |  | Felix | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-06-24 03:55 | Verma, Vikas | 26/6/2020 | 26/6/2020 |  | 2938 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-08-11 05:09 | Chiau, Liesbet | PSFINSP27748 |  | Yes | [8 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P560911C |  | APPL |  |  | R812 |  |  | Update Transaction Status in F560911A | Baxter Code Review Complete |  |  | FALSE |  | FALSE | Finance |  | Felix | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-06-24 03:55 | Verma, Vikas | 26/6/2020 | 26/6/2020 |  | 2939 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-08-11 05:09 | Chiau, Liesbet | PSFINSP27748 |  | Yes | [8 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56BO06A |  | APPL |  |  | R812 |  |  | SR BOT Results | L3 In Progress |  |  | FALSE |  | FALSE | ARO |  | Mayur | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-06-24 03:55 | Verma, Vikas |  |  |  | 2940 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-08-11 09:01 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56BOT01 |  | APPL |  |  | R812 |  |  | AI Process, Validation & Message Rules Application | L3 Pass |  |  | FALSE |  | FALSE | ARO |  | Mayur | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-06-24 03:55 | Verma, Vikas |  |  |  | 2941 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-08-11 09:00 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56BOT02 |  | APPL |  |  | R812 |  |  | AI Analysis Work and Tag File | L3 Pass |  |  | FALSE |  | FALSE | ARO |  | Mayur | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-06-24 03:55 | Verma, Vikas |  |  |  | 2942 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-08-11 09:00 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56BOT03 |  | APPL |  |  | R812 |  |  | AI SO Analysis Specical Instruction Application | L3 Pass |  |  | FALSE |  | FALSE | ARO |  | Mayur | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-06-24 03:55 | Verma, Vikas |  |  |  | 2943 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-08-11 09:01 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56BOT04 |  | APPL |  |  | R812 |  |  | AI Mailing Rule Edit Application | L3 In Progress |  |  | FALSE |  | FALSE | ARO |  | Mayur | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-06-24 03:55 | Verma, Vikas |  |  |  | 2944 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-08-11 09:01 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56BOT05 |  | APPL |  |  | R812 |  |  | EMail / Speed Status Change | L3 In Progress |  |  | FALSE |  | FALSE | ARO |  | Mayur | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-06-24 03:55 | Verma, Vikas |  |  |  | 2945 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-08-11 09:01 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P56BOT06 |  | APPL |  |  | R812 |  |  | AI SR Analysis Application | L3 In Progress |  |  | FALSE |  | FALSE | ARO |  | Mayur | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-06-24 03:55 | Verma, Vikas |  |  |  | 2946 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-08-11 09:01 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564916 |  | APPL |  |  | R812 |  |  | Air Freight Pallet Height | Baxter Code Review Complete |  |  | FALSE |  | FALSE | Logistics |  | Grant Wallis | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-07-03 01:43 | Verma, Vikas | 07/06/2020 | 07/06/2020 |  | 2947 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-08-11 05:09 | Chiau, Liesbet | EUSCM167700A |  | Yes | [8 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649611 |  | APPL |  |  | R812 |  |  | Witron4 Order SHSP Recovery | Baxter Code Review Complete |  |  | FALSE |  | FALSE | Logistics |  | Grant Wallis | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-07-03 01:43 | Verma, Vikas | 06/07/2020 | 06/07/2020 |  | 2948 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-08-11 05:09 | Chiau, Liesbet | EUSCM167700A |  | Yes | [7 empty] | EUSCM167700A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5642060 |  | APPL |  |  | R812 |  |  | Witron4 Message Recovery - Picking | Baxter Code Review Complete |  |  | TRUE |  | FALSE | Logistics |  | Grant Wallis | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-07-03 01:43 | Verma, Vikas | 6/7/2020 | 6/7/2020 |  | 2949 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-08-11 05:09 | Chiau, Liesbet | EUSCM167802A |  | Yes | [7 empty] | EUSCM167802A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564121ZW |  | UBE |  |  | R812 |  |  | WCS Stock Reconciliation | Baxter Code Review Complete |  |  | TRUE |  | FALSE | Logistics |  | Grant Wallis | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-07-03 01:43 | Verma, Vikas | 6/7/2020 | 6/7/2020 |  | 2950 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-08-11 05:09 | Chiau, Liesbet | EUSCM167701A |  | Yes | [7 empty] | EUSCM167701A | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5843501 |  | UBE |  |  | R812 |  |  | Purchase Order Print Output - Russia | Baxter Code Review Complete |  |  | TRUE |  | FALSE | ARO |  | Rakesh Kumar | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-07-28 01:53 | Verma, Vikas | 7/28/2020 | 7/28/2020 |  | 2951 |  | 0 | Sandhya Agarwal/Sameer Tawde |  |  | 2020-08-11 05:09 | Chiau, Liesbet | EULOAF28009 |  | Yes | [7 empty] | EULOAF28009 | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649013 |  | APPL |  |  | R812 |  |  | QED Maintenance Program | Development Complete |  |  | FALSE |  | FALSE | Logistics |  | Grant Wallis | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-08-11 05:14 | Verma, Vikas |  |  |  | 2952 |  | 0 |  |  |  | 2020-08-11 06:35 | Verma, Vikas | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564915A |  | APPL |  |  | R812 |  |  | Work with Shipments - Baxter EMEA |  |  |  | FALSE |  | FALSE | Logistics |  | Grant Wallis | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-08-11 05:14 | Verma, Vikas |  |  |  | 2953 |  | 0 |  |  |  | 2020-08-11 05:21 | Verma, Vikas | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5641005 |  | APPL |  |  | R812 |  |  | Inventory Transaction Processor | Development Complete |  |  | FALSE |  | FALSE | Logistics |  | Grant Wallis | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-08-11 05:14 | Verma, Vikas |  |  |  | 2954 |  | 0 |  |  |  | 2020-08-11 06:35 | Verma, Vikas | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564215Z |  | APPL |  |  | R812 |  |  | Single Transportation Screen - Inquiry | Development Complete |  |  | FALSE |  | FALSE | Logistics |  | Grant Wallis | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-08-11 05:14 | Verma, Vikas |  |  |  | 2955 |  | 0 |  |  |  | 2020-08-11 06:35 | Verma, Vikas | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5642034 |  | UBE |  |  | R812 |  |  | Pallet Tails Report - WCS | Development Complete |  |  | FALSE |  | FALSE | Logistics |  | Grant Wallis | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-08-11 05:18 | Verma, Vikas |  |  |  | 2956 |  | 0 |  |  |  | 2020-08-11 06:35 | Verma, Vikas | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649603A |  | UBE |  |  | R812 |  |  | Direct Shipments WCS Send SH SP | Development Complete |  |  | FALSE |  | FALSE | Logistics |  | Grant Wallis | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-08-11 05:18 | Verma, Vikas |  |  |  | 2957 |  | 0 |  |  |  | 2020-08-11 06:35 | Verma, Vikas | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564736A |  | UBE |  |  | R812 |  |  | Freight Forwarder EDI Table Generation UBE | Development Complete |  |  | FALSE |  | FALSE | Logistics |  | Grant Wallis | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-08-11 05:18 | Verma, Vikas |  |  |  | 2958 |  | 0 |  |  |  | 2020-08-11 06:35 | Verma, Vikas | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649001 |  | UBE |  |  | R812 |  |  | Extract Shipping Repository Data | Development Complete |  |  | FALSE |  | FALSE | Logistics |  | Grant Wallis | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-08-11 05:18 | Verma, Vikas |  |  |  | 2959 |  | 0 |  |  |  | 2020-08-11 06:35 | Verma, Vikas | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649015 |  | UBE |  |  | R812 |  |  | FCA Extraction Report | Development Complete |  |  | FALSE |  | FALSE | Logistics |  | Grant Wallis | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-08-11 05:18 | Verma, Vikas |  |  |  | 2960 |  | 0 |  |  |  | 2020-08-11 06:35 | Verma, Vikas | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649015G |  | UBE |  |  | R812 |  |  | FCA Extraction Report with G/L Date | Development Complete |  |  | FALSE |  | FALSE | Logistics |  | Grant Wallis | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-08-11 05:18 | Verma, Vikas |  |  |  | 2961 |  | 0 |  |  |  | 2020-08-11 06:35 | Verma, Vikas | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649019 |  | UBE |  |  | R812 |  |  | FCA Freight Expense Report | Development Complete |  |  | FALSE |  | FALSE | Logistics |  | Grant Wallis | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-08-11 05:18 | Verma, Vikas |  |  |  | 2962 |  | 0 |  |  |  | 2020-08-11 06:35 | Verma, Vikas | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564941B |  | UBE |  |  | R812 |  |  | LOAD LIST - Germany | Development Complete |  |  | FALSE |  | FALSE | Logistics |  | Grant Wallis | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-08-11 05:18 | Verma, Vikas |  |  |  | 2963 |  | 0 |  |  |  | 2020-08-11 06:35 | Verma, Vikas | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564941G |  | UBE |  |  | R812 |  |  | LOAD LIST - Austria | Development Complete |  |  | FALSE |  | FALSE | Logistics |  | Grant Wallis | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-08-11 05:18 | Verma, Vikas |  |  |  | 2964 |  | 0 |  |  |  | 2020-08-11 06:35 | Verma, Vikas | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647071 |  | UBE |  |  | R812 |  |  | EDI Receiving Advice Edit/Create - Purchasing - Poland | Development Complete |  |  | FALSE |  | FALSE | Logistics |  | Grant Wallis | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-08-11 05:18 | Verma, Vikas |  |  |  | 2965 |  | 0 |  |  |  | 2020-08-11 06:35 | Verma, Vikas | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564941E |  | UBE |  |  | R812 |  |  | LOAD LIST - France | Development Complete |  |  | FALSE |  | FALSE | Logistics |  | Grant Wallis | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-08-11 05:18 | Verma, Vikas |  |  |  | 2966 |  | 0 |  |  |  | 2020-08-11 06:35 | Verma, Vikas | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R564941F |  | UBE |  |  | R812 |  |  | Load Summary | Development Complete |  |  | FALSE |  | FALSE | Logistics |  | Grant Wallis | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-08-11 05:18 | Verma, Vikas |  |  |  | 2967 |  | 0 |  |  |  | 2020-08-11 06:35 | Verma, Vikas | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56G4941A |  | UBE |  |  | R812 |  |  | Gambro: LOAD LIST - Benelux | Development Complete |  |  | FALSE |  | FALSE | Logistics |  | Grant Wallis | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-08-11 05:18 | Verma, Vikas |  |  |  | 2968 |  | 0 |  |  |  | 2020-08-11 06:35 | Verma, Vikas | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P42117 |  | APPL |  |  | R812 |  |  | Backorder Release | Development Complete |  |  | TRUE |  | FALSE | Order Management | OM |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:57 | Verma, Vikas |  |  |  | 2969 |  | 0 |  |  |  | 2020-08-11 09:15 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5645002 |  | APPL |  |  | R812 |  |  | Additional Charges - Orders to be repriced | Development Complete |  |  | TRUE |  | FALSE | Order Management | OM |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:57 | Verma, Vikas |  |  |  | 2970 |  | 0 |  |  |  | 2020-08-11 09:15 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P564217B |  | APPL |  |  | R812 |  |  | Backorder Release | Development Complete |  |  | TRUE |  | FALSE | Order Management | OM |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:57 | Verma, Vikas |  |  |  | 2971 |  | 0 |  |  |  | 2020-08-11 09:15 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5647010 |  | APPL |  |  | R812 |  |  | Inbound EDI Order Inquiry - SFDC | Development Complete |  |  | TRUE |  | FALSE | eCommerce | eCommerce |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:57 | Verma, Vikas |  |  |  | 2972 |  | 0 |  |  |  | 2020-08-11 09:18 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5647019 |  | APPL |  |  | R812 |  |  | Sales Order Error | Development Complete |  |  | TRUE |  | FALSE | eCommerce | eCommerce |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:57 | Verma, Vikas |  |  |  | 2973 |  | 0 |  |  |  | 2020-08-11 09:18 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P4210 |  | APPL |  |  | R812 |  |  | Sales Order Entry | Development Complete |  |  | TRUE |  | FALSE | Order Management | OM |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:57 | Verma, Vikas |  |  |  | 2974 |  | 0 |  |  |  | 2020-08-11 09:15 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5643003 |  | APPL |  |  | R812 |  |  | Invoice File Upload - Inbound | Development Complete |  |  | FALSE |  | FALSE | Order Management | OM |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:57 | Verma, Vikas |  |  |  | 2975 |  | 0 |  |  |  | 2020-08-11 09:15 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649003 |  | APPL |  |  | R812 |  |  | Manual Invoice Entry | Development Complete |  |  | FALSE |  | FALSE | Order Management | OM |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  |  |  | Item |  | 2020-08-11 05:57 | Verma, Vikas |  |  |  | 2976 |  | 0 |  |  |  | 2020-08-11 09:15 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
P5649005 |  | APPL |  |  | R812 |  |  | Invoice File Upload - Outbound | Development Complete |  |  | FALSE |  | FALSE | Order Management | OM |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:57 | Verma, Vikas |  |  |  | 2977 |  | 0 |  |  |  | 2020-08-11 09:15 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5641001 |  | UBE |  |  | R812 |  |  | T01B Fix Populate Lot Grade | Development Complete |  |  | TRUE |  | FALSE | Logistics | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:58 | Verma, Vikas |  |  |  | 2978 |  | 0 |  |  |  | 2020-08-11 09:18 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R42565 |  | UBE |  |  | R812 |  |  | Print Invoices | Development Complete |  |  | FALSE |  | FALSE | Order Management | OM |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:58 | Verma, Vikas |  |  |  | 2979 |  | 0 |  |  |  | 2020-08-11 09:15 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600212 |  | UBE |  |  | R812 |  |  | Drug Shortage Report CSV | Development Complete |  |  | TRUE |  | FALSE | Logistics | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:58 | Verma, Vikas |  |  |  | 2980 |  | 0 |  |  |  | 2020-08-11 09:19 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56CZMOH |  | UBE |  |  | R812 |  |  | DIS13 - REG | Development Complete |  |  | TRUE |  | FALSE | Logistics | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:58 | Verma, Vikas |  |  |  | 2981 |  | 0 |  |  |  | 2020-08-11 09:19 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56CZMOH1 |  | UBE |  |  | R812 |  |  | DIS13 - NREG | Development Complete |  |  | TRUE |  | FALSE | Logistics | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:58 | Verma, Vikas |  |  |  | 2982 |  | 0 |  |  |  | 2020-08-11 09:19 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56CZMOH2 |  | UBE |  |  | R812 |  |  | MAH | Development Complete |  |  | TRUE |  | FALSE | Logistics | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:58 | Verma, Vikas |  |  |  | 2983 |  | 0 |  |  |  | 2020-08-11 09:19 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56REG13 |  | UBE |  |  | R812 |  |  | REG13 | Development Complete |  |  | TRUE |  | FALSE | Logistics | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:58 | Verma, Vikas |  |  |  | 2984 |  | 0 |  |  |  | 2020-08-11 09:24 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0058C |  | UBE |  |  | R812 |  |  | COUPA Purchase Order Request | Development Complete |  |  | FALSE |  | FALSE | Finance | Finance |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:58 | Verma, Vikas |  |  |  | 2985 |  | 0 |  |  |  | 2020-08-11 09:16 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600034 |  | UBE |  |  | R812 |  |  | Backorder Report - CSV | Development Complete |  |  | TRUE |  | FALSE | Order Management | OM |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:58 | Verma, Vikas |  |  |  | 2986 |  | 0 |  |  |  | 2020-08-11 09:15 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5600021 |  | UBE |  |  | R812 |  |  | Integrity Report - Cardex/GL | Development Complete |  |  | FALSE |  | FALSE | Logistics | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:58 | Verma, Vikas |  |  |  | 2987 |  | 0 |  |  |  | 2020-08-11 09:18 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55NSIIB |  | UBE |  |  | R812 |  |  | SII Generacion de XML B | Development Complete |  |  | FALSE |  | FALSE | Logistics | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:58 | Verma, Vikas |  |  |  | 2988 |  | 0 |  |  |  | 2020-08-11 09:18 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647121C |  | UBE |  |  | R812 |  |  | EDI Product Activity Data Edit/Create - Extended | Development Complete |  |  | FALSE |  | FALSE | eCommerce | eCommerce |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:58 | Verma, Vikas |  |  |  | 2989 |  | 0 |  |  |  | 2020-08-11 09:18 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R47031 |  | UBE |  |  | R812 |  |  | EDI Shipping Notice Edit/Create | Development Complete |  |  | FALSE |  | FALSE | eCommerce | eCommerce |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:58 | Verma, Vikas |  |  |  | 2990 |  | 0 |  |  |  | 2020-08-11 09:18 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5947031 |  | UBE |  |  | R812 |  |  | Preprocessor of EDI Shipping Notice Edit/Create | Development Complete |  |  | FALSE |  | FALSE | eCommerce | eCommerce |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:58 | Verma, Vikas |  |  |  | 2991 |  | 0 |  |  |  | 2020-08-11 09:18 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58R43Z1I |  | UBE |  |  | R812 |  |  | Demand Solutions to JDE - Create Purchase Orders | Development Complete |  |  | FALSE |  | FALSE | Logistics | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:58 | Verma, Vikas |  |  |  | 2992 |  | 0 |  |  |  | 2020-08-11 09:17 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R47042 |  | UBE |  |  | R812 |  |  | EDI Invoice Extraction | Development Complete |  |  | TRUE |  | FALSE | Order Management | OM |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:58 | Verma, Vikas |  |  |  | 2993 |  | 0 |  |  |  | 2020-08-11 09:15 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56BH42535 |  | UBE |  |  | R812 |  |  | Delivery Note -BH | Development Complete |  |  | FALSE |  | FALSE | Logistics | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:58 | Verma, Vikas |  |  |  | 2994 |  | 0 |  |  |  | 2020-08-11 09:17 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R58R0094 |  | UBE |  |  | R812 |  |  | EDI Product Activity Data Edit/Create | Development Complete |  |  | FALSE |  | FALSE | eCommerce | eCommerce |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:58 | Verma, Vikas |  |  |  | 2995 |  | 0 |  |  |  | 2020-08-11 09:18 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649043E |  | UBE |  |  | R812 |  |  | GME Outbound Order Processor | Development Complete |  |  | FALSE |  | FALSE | Logistics | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:58 | Verma, Vikas |  |  |  | 2996 |  | 0 |  |  |  | 2020-08-11 09:17 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649042E |  | UBE |  |  | R812 |  |  | GME Send Order | Development Complete |  |  | FALSE |  | FALSE | Logistics | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:58 | Verma, Vikas |  |  |  | 2997 |  | 0 |  |  |  | 2020-08-11 09:17 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56AT42535 |  | UBE |  |  | R812 |  |  | Delivery Note Austria | Development Complete |  |  | TRUE |  | FALSE | Logistics | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:58 | Verma, Vikas |  |  |  | 2998 |  | 0 |  |  |  | 2020-08-11 09:17 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56BX42535 |  | UBE |  |  | R812 |  |  | Delivery Note BeNeLux | Development Complete |  |  | TRUE |  | FALSE | Logistics | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:58 | Verma, Vikas |  |  |  | 2999 |  | 0 |  |  |  | 2020-08-11 09:24 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56CH42535 |  | UBE |  |  | R812 |  |  | Delivery Note Switzerland | Development Complete |  |  | TRUE |  | FALSE | Logistics | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:58 | Verma, Vikas |  |  |  | 3000 |  | 0 |  |  |  | 2020-08-11 09:24 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56DE42535 |  | UBE |  |  | R812 |  |  | Delivery Note Germany | Development Complete |  |  | TRUE |  | FALSE | Logistics | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:58 | Verma, Vikas |  |  |  | 3001 |  | 0 |  |  |  | 2020-08-11 09:24 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56ES42535 |  | UBE |  |  | R812 |  |  | Delivery Notes Print Spain | Development Complete |  |  | TRUE |  | FALSE | Logistics | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:58 | Verma, Vikas |  |  |  | 3002 |  | 0 |  |  |  | 2020-08-11 09:24 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56FR42535 |  | UBE |  |  | R812 |  |  | Delivery Note France | Development Complete |  |  | TRUE |  | FALSE | Logistics | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:58 | Verma, Vikas |  |  |  | 3003 |  | 0 |  |  |  | 2020-08-11 09:24 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56IE42535 |  | UBE |  |  | R812 |  |  | Delivery Note - IE | Development Complete |  |  | TRUE |  | FALSE | Logistics | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:58 | Verma, Vikas |  |  |  | 3004 |  | 0 |  |  |  | 2020-08-11 09:24 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56IT42535 |  | UBE |  |  | R812 |  |  | Delivery Note Italy | Development Complete |  |  | TRUE |  | FALSE | Logistics | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:59 | Verma, Vikas |  |  |  | 3005 |  | 0 |  |  |  | 2020-08-11 09:24 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56ND42535 |  | UBE |  |  | R812 |  |  | Delivery Note Nordics | Development Complete |  |  | TRUE |  | FALSE | Logistics | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:59 | Verma, Vikas |  |  |  | 3006 |  | 0 |  |  |  | 2020-08-11 09:24 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PL42535 |  | UBE |  |  | R812 |  |  | Delivery Note - Poland | Development Complete |  |  | TRUE |  | FALSE | Logistics | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:59 | Verma, Vikas |  |  |  | 3007 |  | 0 |  |  |  | 2020-08-11 09:24 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56PT42535 |  | UBE |  |  | R812 |  |  | Delivery Notes Print | Development Complete |  |  | TRUE |  | FALSE | Logistics | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:59 | Verma, Vikas |  |  |  | 3008 |  | 0 |  |  |  | 2020-08-11 09:24 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R55470412 |  | UBE |  |  | R812 |  |  | EDI Inbound Invoice/Match to P.O. - Target II | Development Complete |  |  | FALSE |  | FALSE | Logistics | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:59 | Verma, Vikas |  |  |  | 3009 |  | 0 |  |  |  | 2020-08-11 09:24 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56CH42565 |  | UBE |  |  | R812 |  |  | Print Invoices Switzerland | Development Complete |  |  | TRUE |  | FALSE | Logistics | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:59 | Verma, Vikas |  |  |  | 3010 |  | 0 |  |  |  | 2020-08-11 09:24 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649005A |  | UBE |  |  | R812 |  |  | Invoice File Upload | Development Complete |  |  | FALSE |  | FALSE | Logistics | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:59 | Verma, Vikas |  |  |  | 3011 |  | 0 |  |  |  | 2020-08-11 09:24 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5649005B |  | UBE |  |  | R812 |  |  | FCA - XML Invoice Upload | Development Complete |  |  | FALSE |  | FALSE | Logistics | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:59 | Verma, Vikas |  |  |  | 3012 |  | 0 |  |  |  | 2020-08-11 09:24 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R59R0431 |  | UBE |  |  | R812 |  |  | FCA-XML Inbound Upload Report | Development Complete |  |  | FALSE |  | FALSE | Logistics | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:59 | Verma, Vikas |  |  |  | 3013 |  | 0 |  |  |  | 2020-08-11 09:24 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R56MJI01 |  | UBE |  |  | R812 |  |  | MILD JDE Integration RECON | Development Complete |  |  | FALSE |  | FALSE | Logistics | Logistics |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:59 | Verma, Vikas |  |  |  | 3014 |  | 0 |  |  |  | 2020-08-11 09:25 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R47071 |  | UBE |  |  | R812 |  |  | EDI Receiving Advice Edit/Create - Purchasing | Development Complete |  |  | FALSE |  | FALSE | eCommerce | eCommerce |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:59 | Verma, Vikas |  |  |  | 3015 |  | 0 |  |  |  | 2020-08-11 09:25 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker
R5647071P |  | UBE |  |  | R812 |  |  | EDI Receiving Advice Edit/Create - ARIBA Poland | Development Complete |  |  | FALSE |  | FALSE | eCommerce | eCommerce |  | L2 Not required |  |  |  | Terry Greenard / Vikas Verma |  | Sreekanth Thippulla |  | Item |  | 2020-08-11 05:59 | Verma, Vikas |  |  |  | 3016 |  | 0 |  |  |  | 2020-08-11 09:25 | Chiau, Liesbet | [11 empty] | FALSE | FALSE |  | Item | sites/erp92upgrade/erp92emea/Lists/EMEA Retrofit Object Lifecycle Tracker